## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : Orchard Amritaya
Task Name : Orchard Amritaya
Page 1 of 1
Total Records: 4508 Records 1 to 4508
Sr_No | Task | Completion_Per | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | Estimated Qty of Completed Work | Estimated Rate of Completed Work | Estimated Cost of Completed Work | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | SITE DEVELOPMENT - Unskilled Labor for Misc. Tasks | 0 |  | Labour | (L)UNSKILLED MAN - HRS (12 HRS) | NOS | 1890 | 525 | 992250 | 0 | 0 | 0 | 1890 | 525 | 992250 | 1890 | 525 | 992250 | 1885.08 | 525 | 989667 | 0 | 4.92 | 0 | 2583
2 | SITE DEVELOPMENT - JCB Hydra Roller Rental | 100 |  | Labour | (L)8 TON ROD ROLLER FIELD LEVELLING FOR INAUGARATION | DAYS | 3 | 5000 | 15000 | 0 | 0 | 0 | 3 | 5000 | 15000 | 3 | 5900 | 17700 | 3 | 5900 | 17700 | 0 | 0 | 0 | -2700
3 | SITE DEVELOPMENT - JCB Hydra Roller Rental | 100 |  | Labour | (L)BOX HYDRA FOR RUSTOMJEE PARSE ROAD TILES PAINT | DAYS | 6 | 5000 | 30000 | 0 | 0 | 0 | 6 | 5000 | 30000 | 6 | 5900 | 35400 | 6 | 5900 | 35400 | 0 | 0 | 0 | -5400
4 | SITE DEVELOPMENT - JCB Hydra Roller Rental | 100 |  | Labour | (L)HYDRA (FOR 4 HOURS) | DAYS | 7 | 3700 | 25900 | 0 | 0 | 0 | 7 | 3700 | 25900 | 7 | 3700 | 25900 | 7 | 3700 | 25900 | 0 | 0 | 0 | 0
5 | SITE DEVELOPMENT - JCB Hydra Roller Rental | 100 |  | Labour | (L)HYDRA (FOR 8 HOURS) | DAYS | 15 | 4500 | 67500 | 0 | 0 | 0 | 15 | 4500 | 67500 | 13 | 5123.08 | 66600 | 11 | 5089.09 | 55980 | 0 | 4 | 0 | 11520
6 | SITE DEVELOPMENT - JCB Hydra Roller Rental | 100 |  | Labour | (L)JCB OPERATOR CHARGE FOR 8 HRS | HRS | 485 | 50 | 24250 | 0 | 0 | 0 | 485 | 50 | 24250 | 485 | 59 | 28615 | 483.75 | 59 | 28541.26 | 0 | 1.25 | 0 | -4291.26
7 | SITE DEVELOPMENT - JCB Hydra Roller Rental | 100 |  | Labour | (L)SUPPLYING OF JCB ON DAILY (8 HRS) HIRE CHARGE BASIS | HRS | 485 | 800 | 388000 | 0 | 0 | 0 | 485 | 800 | 388000 | 485 | 944 | 457840 | 483.75 | 944 | 456660 | 0 | 1.25 | 0 | -68660
8 | SITE DEVELOPMENT - Labour Hutment Work | 100 |  | Labour | (L)EXTRA LABOUR FOR HUTMENT WORK | JOB | 1 | 16000 | 16000 | 0 | 0 | 0 | 1 | 16000 | 16000 | 1 | 16000 | 16000 | 1 | 16000 | 16000 | 0 | 0 | 0 | 0
9 | SITE DEVELOPMENT - Labour Hutment Work | 100 |  | Labour | (L)HUTMENT WIDE 16' (FEET) & LENGTH 60' (FEET) | NOS | 960 | 70 | 67200 | 0 | 0 | 0 | 960 | 70 | 67200 | 960 | 70 | 67200 | 960 | 70 | 67200 | 0 | 0 | 0 | 0
10 | SITE DEVELOPMENT - Labour Hutment Work | 100 |  | Labour | (L)HUTMENT WIDE 16'(FEET) & LENGTH 30' (FEET) | NOS | 960 | 70 | 67200 | 0 | 0 | 0 | 960 | 70 | 67200 | 960 | 70 | 67200 | 480 | 70 | 33600 | 0 | 480 | 0 | 33600
11 | SITE DEVELOPMENT - Labour Hutment Work | 100 |  | Labour | (L)HUTMENT WIDE 16'(FEET) & LENGTH 50' (FEET) | NOS | 800 | 65 | 52000 | 0 | 0 | 0 | 800 | 65 | 52000 | 800 | 65 | 52000 | 800 | 65 | 52000 | 0 | 0 | 0 | 0
12 | SITE DEVELOPMENT - Labour Hutment Work | 100 |  | Labour | (L)OFFICE SHED WIDE 10' FEET & LENGTH 20' FEET | NOS | 200 | 70.8 | 14160 | 0 | 0 | 0 | 200 | 70.8 | 14160 | 200 | 60 | 12000 | 200 | 60 | 12000 | 0 | 0 | 0 | 2160
13 | SITE DEVELOPMENT - Labour Hutment Work | 100 |  | Material | (M)BAMBOO | PICS | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 200 | 3999.96 | 0 | 0 | 0 | -3999.96
14 | SITE DEVELOPMENT - UC Ballah Piling Work | 0 |  | Labour | (L)6" DIA 20' LONG UCALYPTUS BALLAH DRIVING INCLUDING 2 COATS | NOS | 1000 | 700 | 700000 | 0 | 0 | 0 | 1000 | 700 | 700000 | 528 | 700 | 369600 | 528 | 700 | 369600 | 0 | 472 | 0 | 330400
15 | SITE DEVELOPMENT - UC Ballah Piling Work | 0 |  | Labour | (L)DRUM SHEET SUPPLYING & FIXING INCLUDING BITUMINOUS PAINT. | NOS | 500 | 500 | 250000 | 0 | 0 | 0 | 500 | 500 | 250000 | 189 | 500 | 94500 | 189 | 500 | 94500 | 0 | 311 | 0 | 155500
16 | SITE DEVELOPMENT - UC Ballah Piling Work | 0 |  | Labour | (L)LABOUR CHARGES FOR DRIVING 6" DIA 20'0" LONG UC BALLAH. | NOS | 1000 | 300 | 300000 | 0 | 0 | 0 | 1000 | 300 | 300000 | 528 | 1200 | 633600 | 528 | 1200 | 633600 | 0 | 472 | 0 | -333600
17 | SITE DEVELOPMENT - UC Ballah Piling Work | 0 |  | Labour | (L)SUPPLYING & INSTALLATION OF UC BALLAH 5" DIA (TOP) AND 16'0" | NOS | 300 | 900 | 270000 | 0 | 0 | 0 | 300 | 900 | 270000 | 108 | 900 | 97200 | 108 | 900 | 97200 | 0 | 192 | 0 | 172800
18 | SITE DEVELOPMENT - UC Ballah Piling Work | 0 |  | Material | (M)5" NAIL | KG | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 84.02 | 420.08 | 0 | 0 | 0 | -420.08
19 | SITE DEVELOPMENT - UC Ballah Piling Work | 0 |  | Material | (M)6" DIA 20FT LONG UCALYPTUS BALLAH | PICS | 400 | 914.5 | 365800 | 400 | 914.5 | 365800 | 400 | 914.5 | 365800 | 400 | 944 | 377600 | 0 | 0 | 0 | 0 | 400 | 0 | 365800
20 | SITE DEVELOPMENT - Razor Wire Installation | 100 |  | Labour | (L)50 X 50X 6 MM MS ANGLE POST | NOS | 33 | 95 | 3135 | 0 | 0 | 0 | 33 | 95 | 3135 | 33 | 112.1 | 3699.3 | 0 | 0 | 0 | 0 | 33 | 0 | 3135
21 | SITE DEVELOPMENT - Razor Wire Installation | 100 |  | Labour | (L)DELIVERY CHARGES | NOS | 1 | 1200 | 1200 | 0 | 0 | 0 | 1 | 1200 | 1200 | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1 | 0 | 1200
22 | SITE DEVELOPMENT - Razor Wire Installation | 100 |  | Labour | (L)NUT BOLT & CLIP | NOS | 1 | 944 | 944 | 0 | 0 | 0 | 1 | 944 | 944 | 1 | 944 | 944 | 0 | 0 | 0 | 0 | 1 | 0 | 944
23 | SITE DEVELOPMENT - Razor Wire Installation | 100 |  | Labour | (L)RAZOR WIRE | RFT | 160 | 50 | 8000 | 0 | 0 | 0 | 160 | 50 | 8000 | 160 | 59 | 9440 | 0 | 0 | 0 | 0 | 160 | 0 | 8000
24 | SITE DEVELOPMENT - KMC Water Line Work | 100 |  | Labour | (L)KMC WATER SUPPLY LINE FROM KMC MAIN LINE TO RESERVOIR LINE | NOS | 1 | 30000 | 30000 | 0 | 0 | 0 | 1 | 30000 | 30000 | 1 | 354000 | 354000 | 1 | 354000 | 354000 | 0 | 0 | 0 | -324000
25 | SITE DEVELOPMENT - BP and SILO Paint Work | 100 |  | Labour | (L)PAINT WORK | NOS | 10000 | 14.5 | 145000 | 0 | 0 | 0 | 10000 | 14.5 | 145000 | 10000 | 17.11 | 171100 | 4961.96 | 17.11 | 84899.14 | 0 | 5038.04 | 0 | 60100.86
26 | SITE DEVELOPMENT - Hydra Rental for BP Relocation | 100 |  | Labour | (L)BATCHING PLANT SHIFTING | NOS | 1 | 7500 | 7500 | 0 | 0 | 0 | 1 | 7500 | 7500 | 1 | 7500 | 7500 | 1 | 7500 | 7500 | 0 | 0 | 0 | 0
27 | SITE DEVELOPMENT - Shera Board Work | 100 |  | Labour | (L)Approximate quantity of Shera board repairing and fixing | NOS | 3140.61 | 35 | 109921.35 | 0 | 0 | 0 | 3141 | 35 | 109935 | 0 | 0 | 0 | 0 | 0 | 0 | -0.39 | 3140.61 | -13.65 | 109921.35
28 | SITE DEVELOPMENT - Shera Board Work | 100 |  | Labour | (L)SHERA BOARD OIL PAINTING (BOTH SIDE) | NOS | 349.08 | 98 | 34209.84 | 0 | 0 | 0 | 349 | 98 | 34202 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 349.08 | 7.84 | 34209.84
29 | SITE DEVELOPMENT - Shera Board Work | 100 |  | Labour | (L)SHERA BORAD OIL PAINT (SINGLE SIDE) INCLUDING PAINT, LACQUE | NOS | 3901.13 | 50 | 195056.5 | 0 | 0 | 0 | 3901 | 50 | 195050 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 3901.13 | 6.5 | 195056.5
30 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Labour | (L)OUTSIDE SCRUBBING OF PORTA CABIN BY SAND PAPER BEFORE | NOS | 1266.66 | 44 | 55733.04 | 0 | 0 | 0 | 1267 | 44 | 55748 | 0 | 0 | 0 | 0 | 0 | 0 | -0.34 | 1266.66 | -14.96 | 55733.04
31 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Labour | (L)SCRUBBING, REMOVING OF RUST, SMOOTHENING OF SURFACE BEFORE | RFT | 2948.117 | 10 | 29481.17 | 0 | 0 | 0 | 2948 | 10 | 29480 | 0 | 0 | 0 | 0 | 0 | 0 | 0.117 | 2948.117 | 1.17 | 29481.17
32 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)1 TON AC | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 31441.5 | 62883 | 0 | 0 | 0 | -62883
33 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)BUNK BED . | PAIR | 4 | 11210 | 44840 | 0 | 0 | 0 | 4 | 11210 | 44840 | 0 | 0 | 0 | 4 | 11210 | 44840 | 0 | 0 | 0 | 0
34 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)GLASS WINDOW | NOS | 1 | 4130 | 4130 | 0 | 0 | 0 | 1 | 4130 | 4130 | 0 | 0 | 0 | 1 | 4130 | 4130 | 0 | 0 | 0 | 0
35 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)HALF ROUND BIT | RFT | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 320 | 7.93 | 2538.11 | 0 | -319 | 0 | -2538.11
36 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)KONA BIT | RFT | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 136 | 9.76 | 1327.62 | 0 | -135 | 0 | -1327.62
37 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)MS DOOR | NOS | 1 | 5310 | 5310 | 0 | 0 | 0 | 1 | 5310 | 5310 | 0 | 0 | 0 | 1 | 5310 | 5310 | 0 | 0 | 0 | 0
38 | SITE DEVELOPMENT - Porta Cabin Repairing Work | 0 |  | Material | (M)SWING DOOR | NOS | 1 | 15930 | 15930 | 0 | 0 | 0 | 1 | 15930 | 15930 | 0 | 0 | 0 | 1 | 15930 | 15930 | 0 | 0 | 0 | 0
39 | SITE DEVELOPMENT - Kerb Stone Fill Work | 100 |  | Material | (M)SILVER SAND | CFT | 1427 | 25 | 35675 | 1427 | 25 | 35675 | 1427 | 25 | 35675 | 1427 | 30 | 42810 | 800 | 29 | 23200 | 0 | 627 | 0 | 12475
40 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)ARECA PALM 5' - 6' | NOS | 6 | 380 | 2280 | 0 | 0 | 0 | 6 | 380 | 2280 | 6 | 380 | 2280 | 6 | 380 | 2280 | 0 | 0 | 0 | 0
41 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)BUDDHA BELLY BAMBOO PLANT 3' | NOS | 60 | 1850 | 111000 | 0 | 0 | 0 | 60 | 1850 | 111000 | 60 | 110 | 6600 | 50 | 110 | 5500 | 0 | 10 | 0 | 105500
42 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)CLERODENDRUM INERME 1.5' | NOS | 320 | 26 | 8320 | 0 | 0 | 0 | 320 | 26 | 8320 | 320 | 26 | 8320 | 320 | 26 | 8320 | 0 | 0 | 0 | 0
43 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)CORDYLINE RED PLANT 2' | NOS | 80 | 45 | 3600 | 0 | 0 | 0 | 80 | 45 | 3600 | 80 | 45 | 3600 | 80 | 45 | 3600 | 0 | 0 | 0 | 0
44 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)COSTUS SHARBS PLANT 1.5' | NOS | 550 | 46 | 25300 | 0 | 0 | 0 | 550 | 46 | 25300 | 550 | 46 | 25300 | 0 | 0 | 0 | 0 | 550 | 0 | 25300
45 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)FICUS BANJAMINA 2' -2.5' TWO COLOR | NOS | 110 | 120 | 13200 | 0 | 0 | 0 | 110 | 120 | 13200 | 110 | 120 | 13200 | 110 | 120 | 13200 | 0 | 0 | 0 | 0
46 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)FOXTAIL PALM PLANT 8' -10' | NOS | 5 | 1850 | 9250 | 0 | 0 | 0 | 5 | 1850 | 9250 | 5 | 1850 | 9250 | 5 | 1850 | 9250 | 0 | 0 | 0 | 0
47 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)GREEN BECHIA PALM 6' - 7' | NOS | 3 | 2150 | 6450 | 0 | 0 | 0 | 3 | 2150 | 6450 | 3 | 2150 | 6450 | 3 | 2150 | 6450 | 0 | 0 | 0 | 0
48 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)HELICONIA | NOS | 950 | 36 | 34200 | 0 | 0 | 0 | 950 | 36 | 34200 | 950 | 36 | 34200 | 950 | 36 | 34200 | 0 | 0 | 0 | 0
49 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)MANIURE FOR ALL PLANTS | LS | 1 | 5000 | 5000 | 0 | 0 | 0 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 0 | 0 | 0 | 0
50 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)MAXICAN GRASS CARPET | NOS | 2000 | 14 | 28000 | 0 | 0 | 0 | 2000 | 14 | 28000 | 2000 | 14 | 28000 | 900 | 14 | 12600 | 0 | 1100 | 0 | 15400
51 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)PLANTATION MAIL CHARGE FOR ABOVE PLANTS | LS | 1 | 10000 | 10000 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 0
52 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)PLANTER PVC WHITE RECTRANGULAR 24" | NOS | 18 | 420 | 7560 | 0 | 0 | 0 | 18 | 420 | 7560 | 18 | 420 | 7560 | 18 | 420 | 7560 | 0 | 0 | 0 | 0
53 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)PLANTER PVC WHITE ROUND 10" | NOS | 6 | 280 | 1680 | 0 | 0 | 0 | 6 | 280 | 1680 | 6 | 280 | 1680 | 6 | 280 | 1680 | 0 | 0 | 0 | 0
54 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)PLANTER PVC WHITE ROUND 19" | NOS | 3 | 820 | 2460 | 0 | 0 | 0 | 3 | 820 | 2460 | 3 | 820 | 2460 | 3 | 820 | 2460 | 0 | 0 | 0 | 0
55 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)RHAPIS EXCELSA 2.5' - 3' | NOS | 36 | 160 | 5760 | 0 | 0 | 0 | 36 | 160 | 5760 | 36 | 160 | 5760 | 36 | 160 | 5760 | 0 | 0 | 0 | 0
56 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)RHOEO PURPLE PLANT 6" | NOS | 300 | 45 | 13500 | 0 | 0 | 0 | 300 | 45 | 13500 | 300 | 45 | 13500 | 300 | 45 | 13500 | 0 | 0 | 0 | 0
57 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)SELECTION GRASS CARPET | NOS | 1000 | 9.5 | 9500 | 0 | 0 | 0 | 1000 | 9.5 | 9500 | 1000 | 9.5 | 9500 | 0 | 0 | 0 | 0 | 1000 | 0 | 9500
58 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)SPIDER LILY 1.5 ' | NOS | 450 | 28 | 12600 | 0 | 0 | 0 | 450 | 28 | 12600 | 450 | 28 | 12600 | 450 | 28 | 12600 | 0 | 0 | 0 | 0
59 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)SUPPLYING WHITE PABBLES | NOS | 150 | 36 | 5400 | 0 | 0 | 0 | 150 | 36 | 5400 | 150 | 36 | 5400 | 0 | 0 | 0 | 0 | 150 | 0 | 5400
60 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)SYZYGIUM 3' | NOS | 3 | 550 | 1650 | 0 | 0 | 0 | 3 | 550 | 1650 | 3 | 550 | 1650 | 3 | 550 | 1650 | 0 | 0 | 0 | 0
61 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)TOPIARY PLANT 6' | NOS | 1 | 3500 | 3500 | 0 | 0 | 0 | 1 | 3500 | 3500 | 1 | 3500 | 3500 | 1 | 3500 | 3500 | 0 | 0 | 0 | 0
62 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)WEDELIA TRILOBATA PLANT 6" | NOS | 1400 | 15 | 21000 | 0 | 0 | 0 | 1400 | 15 | 21000 | 1400 | 15 | 21000 | 800 | 15 | 12000 | 0 | 600 | 0 | 9000
63 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Labour | (L)ZEPHYRANTHES LILY PLANT 6" | NOS | 450 | 22 | 9900 | 0 | 0 | 0 | 450 | 22 | 9900 | 450 | 22 | 9900 | 450 | 22 | 9900 | 0 | 0 | 0 | 0
64 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Material | (M)1" GARDEN PIPE | MTR | 300 | 70.8 | 21240 | 0 | 0 | 0 | 300 | 70.8 | 21240 | 0 | 0 | 0 | 300 | 77.09 | 23128.01 | 0 | 0 | 0 | -1888.01
65 | SITE DEVELOPMENT - Tree Planting Work | 100 |  | Material | (M)RUELIA | NOS | 40 | 40 | 1600 | 0 | 0 | 0 | 40 | 40 | 1600 | 0 | 0 | 0 | 40 | 41.2 | 1648.16 | 0 | 0 | 0 | -48.16
66 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)L/C for Pile Driving | MTR | 4339.82 | 920.4 | 3994370.33 | 0 | 0 | 0 | 434 | 920.4 | 399453.6 | 4339.82 | 920.4 | 3994370.32 | 4047.5 | 920.4 | 3725319 | 3905.82 | 292.32 | 3594916.728 | 269051.328
67 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)L/C for Pile Driving incl. RCC pouring & Reinf. lowering | MTR | 1298.58 | 908.6 | 1179889.79 | 0 | 0 | 0 | 130 | 908.6 | 118118 | 1298.58 | 908.6 | 1179889.78 | 1298.58 | 908.6 | 1179889.78 | 1168.58 | 0 | 1061771.788 | 0.008
68 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)L/C for Reinforcement Work -12mm Dia | MT | 32.37 | 4720 | 152786.4 | 0 | 0 | 0 | 3 | 4720 | 14160 | 31.51 | 4720 | 148727.2 | 28.06 | 4720 | 132443.2 | 29.37 | 4.31 | 138626.4 | 20343.2
69 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)L/C for Reinforcement Work -6mm Dia | MT | 6.45 | 4720 | 30444 | 0 | 0 | 0 | 1 | 4720 | 4720 | 6.45 | 4720 | 30444 | 5.591 | 4720 | 26389.52 | 5.45 | 0.859 | 25724 | 4054.48
70 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (12MM) | MT | 8.998 | 4130 | 37161.74 | 0 | 0 | 0 | 1 | 4130 | 4130 | 8.998 | 4484 | 40347.04 | 8.998 | 4484 | 40347.02 | 7.998 | 0 | 33031.74 | -3185.28
71 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (6MM DIA MILD STEEL) | MT | 1.793 | 5192 | 9309.26 | 0 | 0 | 0 | 0 | 5192 | 0 | 1.793 | 4484 | 8039.82 | 1.793 | 4484 | 8039.82 | 1.793 | 0 | 9309.256 | 1269.436
72 | PILING : URVI - Pile Work | 10 | Started | Labour | (L)ROUTINE VERTICAL LOAD TEST (235 MT) | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | PILING : URVI - Pile Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 15.224 | 1402.91 | 21357.83 | 1 | -14.224 | 1770 | -19587.83
74 | PILING : URVI - Pile Work | 10 | Started | Material | (M)12 MM DIA TMT | MT | 40.984 | 54500 | 2233628 | 40.984 | 54500 | 2233628 | 4 | 54500 | 218000 | 40.984 | 55236.67 | 2263819.5574 | 39.014 | 54656.65 | 2132374.48 | 36.984 | 1.97 | 2015628 | 101253.52
75 | PILING : URVI - Pile Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 1 | 1750 | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 3.822 | 2022.48 | 7729.93 | 1 | -2.822 | 1750 | -5979.93
76 | PILING : URVI - Pile Work | 10 | Started | Material | (M)3" DIA CANVAS PIPE | ROLL | 8 | 2301 | 18408 | 8 | 2301 | 18408 | 1 | 2301 | 2301 | 8 | 2490.75 | 19926 | 4 | 2450.97 | 9803.87 | 7 | 4 | 16107 | 8604.13
77 | PILING : URVI - Pile Work | 10 | Started | Material | (M)6 MM MILD STEEL | MT | 8.57 | 59206.5 | 507399.71 | 8.57 | 59206.5 | 507399.71 | 1 | 59206.5 | 59206.5 | 8.236 | 58672.52 | 483226.885 | 7.683 | 57769.01 | 443839.28 | 7.57 | 0.887 | 448193.205 | 63560.425
78 | PILING : URVI - Pile Work | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 4.335 | 8200.01 | 35547.04 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 4.335 | 7604.12 | 32963.85 | 4.335 | 0 | 35547.043 | 2583.1934
79 | PILING : URVI - Pile Work | 10 | Started | Material | (M)Fine Sand | MT | 70 | 1312.5 | 91875 | 66.7 | 1312.5 | 87543.75 | 7 | 1312.5 | 9187.5 | 65.86 | 1312.5 | 86441.25 | 32.93 | 1312.5 | 43220.63 | 63 | 37.07 | 82687.5 | 48654.37
80 | PILING : URVI - Pile Work | 10 | Started | Material | (M)FLY ASH | MT | 1.195 | 1396.5 | 1668.82 | 0 | 0 | 0 | 0 | 1396.5 | 0 | 0 | 0 | 0 | 1.195 | 1396.5 | 1668.82 | 1.195 | 0 | 1668.818 | -0.0025
81 | PILING : URVI - Pile Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 1 | 36.58 | 36.58 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 22.05 | 55.46 | 1222.8 | 1 | -21.05 | 36.58 | -1186.22
82 | PILING : URVI - Pile Work | 10 | Started | Material | (M)M.C. SAND | MT | 828 | 1711.5 | 1417122 | 828 | 1711.5 | 1417122 | 83 | 1711.5 | 142054.5 | 824.89 | 1664.56 | 1373076.8625 | 18.358 | 1807.19 | 33176.32 | 745 | 809.642 | 1275067.5 | 1383945.68
83 | PILING : URVI - Pile Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 65 | 318.51 | 20703.47 | 1 | -64 | 283.59 | -20419.88
84 | PILING : URVI - Pile Work | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 1030 | 7257 | 7474710 | 955 | 7257 | 6930435 | 103 | 7257 | 747471 | 955 | 7350 | 7019249.951 | 962.7 | 7381.98 | 7106633.04 | 927 | 67.3 | 6727239 | 368076.96
85 | PILING : URVI - Pile Work | 10 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 20 | 120.36 | 2407.2 | 0 | 0 | 0 | 2 | 120.36 | 240.72 | 0 | 0 | 0 | 20 | 112.45 | 2248.9 | 18 | 0 | 2166.48 | 158.3
86 | PILING : URVI - Pile Work | 10 | Started | Material | (M)SIKAMENT 2003 NS | NOS | 1 | 49.56 | 49.56 | 0 | 0 | 0 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 49.56 | 49.56
87 | PILING : URVI - Pile Work | 10 | Started | Material | (M)SILVER SAND | CFT | 1385.2 | 25 | 34630 | 1385.2 | 25 | 34630 | 139 | 25 | 3475 | 1385.2 | 29 | 40170.8 | 456 | 33 | 15048 | 1246.2 | 929.2 | 31155 | 19582
88 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)CONCRETING M -25 (BATCHING PLANT ) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)CONCRETING M-25 (SITE MIX) | CUM | 983.675 | 572.3 | 562957.2 | 0 | 0 | 0 | 98 | 572.3 | 56085.4 | 954.3194 | 578.2 | 551787.486 | 954.3194 | 578.2 | 551787.45 | 885.675 | 29.3556 | 506871.803 | 11169.7525
90 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)CONCRETING M-25(RMC) | CUM | 1 | 122.59 | 122.59 | 0 | 0 | 0 | 0 | 122.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 122.59 | 122.59
91 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)EMPTY BORE FILLING BY SILVER SAND | RMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)EMPTY BORE FILLING BY SILVER SAND / EARTH | CUM | 217.5 | 153.4 | 33364.5 | 0 | 0 | 0 | 22 | 153.4 | 3374.8 | 0 | 0 | 0 | 0 | 0 | 0 | 195.5 | 217.5 | 29989.7 | 33364.5
93 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)MOBILIZATION CHARGES | RUPEES | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
94 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)PILE DRIVING | RMT | 5235.6 | 696.2 | 3645024.72 | 0 | 0 | 0 | 524 | 696.2 | 364808.8 | 5235.6 | 696.2 | 3645024.72 | 5235.6 | 696.2 | 3645024.72 | 4711.6 | 0 | 3280215.92 | 0
95 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK | MT | 47.02 | 4248 | 199740.96 | 0 | 0 | 0 | 5 | 4248 | 21240 | 44.966 | 4248 | 191015.56 | 44.966 | 4248 | 191015.56 | 42.02 | 2.054 | 178500.96 | 8725.4
96 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (12MM) | MT | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4130 | 4130
97 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (8MM) | MT | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4130 | 4130
98 | PILING : VENI - Pile Work | 10 | Started | Labour | (L)ROUTINE VERTICAL LOAD TEST OF WORKING PILE(235 MT X 4 NOS) | MT | 940 | 495.6 | 465864 | 0 | 0 | 0 | 94 | 495.6 | 46586.4 | 940 | 678.5 | 637790 | 940 | 678.5 | 637790 | 846 | 0 | 419277.6 | -171926
99 | PILING : VENI - Pile Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 560 | 1770 | 991200 | 387.43 | 1770 | 685751.1 | 56 | 1770 | 99120 | 387.43 | 1437.96 | 557108.5734 | 486.129 | 1461.33 | 710395.59 | 504 | 73.871 | 892080 | 280804.41
100 | PILING : VENI - Pile Work | 10 | Started | Material | (M)12 MM DIA TMT | MT | 38.7 | 54500 | 2109150 | 36.47 | 54500 | 1987615 | 4 | 54500 | 218000 | 36.47 | 57573.12 | 2099691.7589 | 38.527 | 57053.26 | 2198090.99 | 34.7 | 0.173 | 1891150 | -88940.99
101 | PILING : VENI - Pile Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 683 | 1750 | 1195250 | 561.305 | 1750 | 982283.75 | 68 | 1750 | 119000 | 561.305 | 2057.82 | 1155066.5438 | 620.984 | 2066.8 | 1283450.71 | 615 | 62.016 | 1076250 | -88200.71
102 | PILING : VENI - Pile Work | 10 | Started | Material | (M)6 MM MILD STEEL | MT | 9.15 | 59206.5 | 541739.48 | 8.82 | 59206.5 | 522201.33 | 1 | 59206.5 | 59206.5 | 8.82 | 56802.32 | 500996.42 | 7.521 | 57223.34 | 430376.77 | 8.15 | 1.629 | 482532.975 | 111362.705
103 | PILING : VENI - Pile Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 3173 | 36.58 | 116068.34 | 2993.73 | 36.58 | 109510.64 | 317 | 36.58 | 11595.86 | 2993.73 | 53.95 | 161500.563 | 2970.7 | 52.98 | 157401.61 | 2856 | 202.3 | 104472.48 | -41333.27
104 | PILING : VENI - Pile Work | 10 | Started | Material | (M)M.C. SAND | MT | 790.37 | 1711.5 | 1352718.26 | 768 | 1711.5 | 1314432 | 79 | 1711.5 | 135208.5 | 675.81 | 1715.29 | 1159213.335 | 706.934 | 1689.85 | 1194611.1 | 711.37 | 83.436 | 1217509.755 | 158107.155
105 | PILING : VENI - Pile Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 7932 | 283.59 | 2249435.88 | 7660 | 283.59 | 2172299.4 | 793 | 283.59 | 224886.87 | 7660 | 327.15 | 2505946.79 | 7773 | 321.8 | 2501326.04 | 7139 | 159 | 2024549.01 | -251890.16
106 | PILING : VENI - Pile Work | 10 | Started | Material | (M)SILVER SAND | CFT | 2611.8 | 25 | 65295 | 2611.8 | 25 | 65295 | 261 | 25 | 6525 | 2611.8 | 29.71 | 77606.2 | 3066 | 29.61 | 90777.99 | 2350.8 | -454.2 | 58770 | -25482.99
107 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)L/C for Mixing of Concrete incl. 10/7 Conc. Mixer with HSD | MTR | 441.1 | 118 | 52049.8 | 0 | 0 | 0 | 44 | 118 | 5192 | 441.1 | 118 | 52049.8 | 441.1 | 118 | 52049.8 | 397.1 | 0 | 46857.8 | 0
108 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)L/C for Pile Driving | MTR | 4959.15 | 920.4 | 4564401.66 | 0 | 0 | 0 | 496 | 920.4 | 456518.4 | 4959.15 | 920.4 | 4564401.66 | 4558.75 | 920.4 | 4195873.5 | 4463.15 | 400.4 | 4107883.26 | 368528.16
109 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)L/C for Pile Driving incl. RCC pouring & Reinf. lowering | MTR | 709.6 | 908.6 | 644742.56 | 0 | 0 | 0 | 71 | 908.6 | 64510.6 | 709.6 | 908.6 | 644742.56 | 709.6 | 908.6 | 644742.56 | 638.6 | 0 | 580231.96 | 0
110 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)L/C for Reinforcement Work -12mm Dia | MT | 36.815 | 4720 | 173766.8 | 0 | 0 | 0 | 4 | 4720 | 18880 | 36.815 | 4720 | 173766.8 | 32.541 | 4720 | 153593.52 | 32.815 | 4.274 | 154886.8 | 20173.28
111 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)L/C for Reinforcement Work -6mm Dia | MT | 7.47 | 4720 | 35258.4 | 0 | 0 | 0 | 1 | 4720 | 4720 | 7.47 | 4720 | 35258.4 | 6.488 | 4720 | 30623.36 | 6.47 | 0.982 | 30538.4 | 4635.04
112 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)PILE DRIVING | RMT | 1 | 696.2 | 696.2 | 0 | 0 | 0 | 0 | 696.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 696.2 | 696.2
113 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (12MM) | MT | 5.04 | 4130 | 20815.2 | 0 | 0 | 0 | 1 | 4130 | 4130 | 5.04 | 4484 | 22599.36 | 5.04 | 4484 | 22599.36 | 4.04 | 0 | 16685.2 | -1784.16
114 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (6MM DIA MILD STEEL) | MT | 1.019 | 5192 | 5290.65 | 0 | 0 | 0 | 0 | 5192 | 0 | 1.019 | 4484 | 4569.2 | 1.019 | 4484 | 4569.2 | 1.019 | 0 | 5290.648 | 721.448
115 | PILING : ANUPA - Pile Work | 10 | Started | Labour | (L)ROUTINE VERTICAL LOAD TEST (235 MT) | MT | 235 | 590 | 138650 | 0 | 0 | 0 | 24 | 590 | 14160 | 235 | 495.6 | 116466 | 235 | 495.6 | 116466 | 211 | 0 | 124490 | 22184
116 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 36 | 1770 | 63720 | 36 | 1770 | 63720 | 4 | 1770 | 7080 | 36 | 1554 | 55944 | 33.342 | 1522.4 | 50760 | 32 | 2.658 | 56640 | 12960
117 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)12 MM DIA TMT | MT | 42.52 | 54500 | 2317340 | 42.52 | 54500 | 2317340 | 4 | 54500 | 218000 | 42.52 | 53990.33 | 2295668.7583 | 39.427 | 54769.45 | 2159395.18 | 38.52 | 3.093 | 2099340 | 157944.82
118 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 108.31 | 1750 | 189542.5 | 108.31 | 1750 | 189542.5 | 11 | 1750 | 19250 | 108.31 | 2112.14 | 228765.87 | 69.966 | 2107.05 | 147421.72 | 97.31 | 38.344 | 170292.5 | 42120.78
119 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)3" DIA CANVAS PIPE | ROLL | 4 | 2301 | 9204 | 4 | 2301 | 9204 | 0 | 2301 | 0 | 4 | 2326.5 | 9306 | 4 | 2450.97 | 9803.87 | 4 | 0 | 9204 | -599.87
120 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)6 MM MILD STEEL | MT | 8.223 | 59206.5 | 486855.05 | 8.223 | 59206.5 | 486855.05 | 1 | 59206.5 | 59206.5 | 7.623 | 56439.39 | 430237.4385 | 7.784 | 58158.23 | 452703.64 | 7.223 | 0.439 | 427648.55 | 34151.4095
121 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)EMPTY CEMENT BAG. | NOS | 6500 | 3.25 | 21125 | 6500 | 3.25 | 21125 | 650 | 3.25 | 2112.5 | 6500 | 3.84 | 24927.5 | 5500 | 3.84 | 21092.5 | 5850 | 1000 | 19012.5 | 32.5
122 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)Fine Sand | MT | 74 | 1312.5 | 97125 | 40.23 | 1312.5 | 52801.88 | 7 | 1312.5 | 9187.5 | 40.23 | 1312.5 | 52801.88 | 73.16 | 1312.5 | 96022.51 | 67 | 0.84 | 87937.5 | 1102.49
123 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 900 | 36.58 | 32922 | 900 | 36.58 | 32922 | 90 | 36.58 | 3292.2 | 900 | 54.8 | 49320 | 340.05 | 54.48 | 18525.69 | 810 | 559.95 | 29629.8 | 14396.31
124 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)M.C. SAND | MT | 56 | 1711.5 | 95844 | 0 | 0 | 0 | 6 | 1711.5 | 10269 | 0 | 0 | 0 | 56.808 | 1691.02 | 96063.57 | 50 | -0.808 | 85575 | -219.57
125 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 1050 | 283.59 | 297769.5 | 1000 | 283.59 | 283590 | 105 | 283.59 | 29776.95 | 1000 | 298.5 | 298502.4 | 714 | 304.81 | 217636.31 | 945 | 336 | 267992.55 | 80133.19
126 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 949 | 7257 | 6886893 | 949 | 7257 | 6886893 | 95 | 7257 | 689415 | 949 | 7348.06 | 6973304.9282 | 938.6 | 7338.05 | 6887490.98 | 854 | 10.4 | 6197478 | -597.98
127 | PILING : ANUPA - Pile Work | 10 | Started | Material | (M)SILVER SAND | CFT | 912 | 25 | 22800 | 912 | 25 | 22800 | 91 | 25 | 2275 | 912 | 33 | 30096 | 456 | 33 | 15048 | 821 | 456 | 20525 | 7752
128 | PILING : PODIUM - Pile Work | 0 | Started | Labour | (L)L/C for M-25 Grade Concreting in Pile (M-25) | CUM | 280 | 578.2 | 161896 | 0 | 0 | 0 | 0 | 578.2 | 0 | 280 | 649 | 181720 | 0 | 0 | 0 | 280 | 280 | 161896 | 161896
129 | PILING : PODIUM - Pile Work | 0 | Started | Labour | (L)L/C for Pile Driving incl. RCC pouring & Reinf. lowering | MTR | 2050 | 908.6 | 1862630 | 0 | 0 | 0 | 0 | 908.6 | 0 | 2050 | 920.4 | 1886820 | 0 | 0 | 0 | 2050 | 2050 | 1862630 | 1862630
130 | PILING : PODIUM - Pile Work | 0 | Started | Labour | (L)REINFORCEMENT WORK (12MM) | MT | 14.25 | 4130 | 58852.5 | 0 | 0 | 0 | 0 | 4130 | 0 | 14.25 | 4720 | 67260 | 0 | 0 | 0 | 14.25 | 14.25 | 58852.5 | 58852.5
131 | PILING : PODIUM - Pile Work | 0 | Started | Labour | (L)REINFORCEMENT WORK (6MM DIA MILD STEEL) | MT | 2.705 | 5192 | 14044.36 | 0 | 0 | 0 | 0 | 5192 | 0 | 2.705 | 4720 | 12767.6 | 0 | 0 | 0 | 2.705 | 2.705 | 14044.36 | 14044.36
132 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 112.86 | 1770 | 199762.2 | 112.86 | 1770 | 199762.2 | 0 | 1770 | 0 | 112.86 | 1386 | 156423.96 | 0.053 | 1384.34 | 73.37 | 112.86 | 112.807 | 199762.2 | 199688.83
133 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)12 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 4.036 | 52441.46 | 211653.73 | 1 | -3.036 | 54500 | -157153.73
134 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)20 MM STONE CHIPS. | MT | 251.26 | 1750 | 439705 | 251.26 | 1750 | 439705 | 0 | 1750 | 0 | 251.26 | 1921.5 | 482796.1051 | 0 | 0 | 0 | 251.26 | 251.26 | 439705 | 439705
135 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)3" DIA CANVAS PIPE | ROLL | 4 | 2301 | 9204 | 0 | 0 | 0 | 0 | 2301 | 0 | 0 | 0 | 0 | 2 | 2352 | 4704 | 4 | 2 | 9204 | 4500
136 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)6 MM MILD STEEL | MT | 1 | 59206.5 | 59206.5 | 0 | 0 | 0 | 0 | 59206.5 | 0 | 0 | 0 | 0 | 0.824 | 54556.59 | 44954.63 | 1 | 0.176 | 59206.5 | 14251.87
137 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)8 MM DIA TMT | MT | 1 | 56000.01 | 56000.01 | 0 | 0 | 0 | 0 | 56000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 56000.01 | 56000.01
138 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 1151 | 36.58 | 42103.58 | 1151 | 36.58 | 42103.58 | 0 | 36.58 | 0 | 1151 | 54.33 | 62533.83 | 0 | 0 | 0 | 1151 | 1151 | 42103.58 | 42103.58
139 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)M.C. SAND | MT | 180.87 | 1711.5 | 309559.01 | 180.87 | 1711.5 | 309559.01 | 0 | 1711.5 | 0 | 180.87 | 1869 | 338046.0381 | 0.195 | 1860.21 | 362.74 | 180.87 | 180.675 | 309559.005 | 309196.265
140 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)PPC CEMENT | BAG | 2236 | 283.59 | 634107.24 | 2236 | 283.59 | 634107.24 | 0 | 283.59 | 0 | 0 | 0 | 0 | 3 | 285.58 | 856.74 | 2236 | 2233 | 634107.24 | 633250.5
141 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)RMC M-25 GRADE | CUM | 100 | 7257 | 725700 | 100 | 7257 | 725700 | 0 | 7257 | 0 | 100 | 7199.99 | 719999.444 | 100.6 | 7199.99 | 724319.21 | 100 | -0.6 | 725700 | 1380.79
142 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)SILVER SAND | CFT | 990 | 25 | 24750 | 990 | 25 | 24750 | 0 | 25 | 0 | 990 | 44 | 43560 | 990 | 44 | 43560 | 990 | 0 | 24750 | -18810
143 | PILING : PODIUM - Pile Work | 0 | Started | Material | (M)STEPLER PIN (BIG) | BOX | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
144 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)CONCRETING M -25 (BATCHING PLANT ) | CUM | 1 | 177 | 177 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 177 | 177
145 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)CONCRETING M-25 (SITE MIX) | CUM | 896.55 | 572.3 | 513095.57 | 0 | 0 | 0 | 90 | 572.3 | 51507 | 862.11 | 578.2 | 498472 | 862.11 | 578.2 | 498472 | 806.55 | 34.44 | 461588.565 | 14623.565
146 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)CONCRETING M-25(RMC) | CUM | 1 | 122.59 | 122.59 | 0 | 0 | 0 | 0 | 122.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 122.59 | 122.59
147 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)EMPTY BORE FILLING BY SILVER SAND | RMT | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
148 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)MOBILIZATION CHARGES | RUPEES | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
149 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)PILE DRIVING | RMT | 4768 | 696.2 | 3319481.6 | 0 | 0 | 0 | 477 | 696.2 | 332087.4 | 4714.91 | 696.2 | 3282520.34 | 4714.909 | 696.2 | 3282519.63 | 4291 | 53.091 | 2987394.2 | 36961.97
150 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK | MT | 42.72 | 4248 | 181474.56 | 0 | 0 | 0 | 4 | 4248 | 16992 | 41.603 | 4248 | 176729.54 | 41.603 | 4248 | 176729.54 | 38.72 | 1.117 | 164482.56 | 4745.02
151 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (12MM) | MT | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4130 | 4130
152 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)REINFORCEMENT WORK (8MM) | MT | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4130 | 4130
153 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)ROUTINE VERTICAL LOAD TEST OF WORKING PILE(235 MT X 4 NOS) | MT | 235 | 495.6 | 116466 | 0 | 0 | 0 | 24 | 495.6 | 11894.4 | 235 | 678.5 | 159447.5 | 235 | 678.5 | 159447.52 | 211 | 0 | 104571.6 | -42981.52
154 | PILING : PRAYAG - Pile Work | 10 | Started | Labour | (L)UNSKILLED LABOUR (12 HRS) | NOS | 250 | 525 | 131250 | 0 | 0 | 0 | 25 | 525 | 13125 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 250 | 118125 | 131250
155 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 510 | 1770 | 902700 | 505.45 | 1770 | 894646.5 | 51 | 1770 | 90270 | 505.45 | 1642.28 | 830090.5 | 451.523 | 1629.12 | 735583.65 | 459 | 58.477 | 812430 | 167116.35
156 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)12 MM DIA TMT | MT | 35.2 | 54500 | 1918400 | 35.2 | 54500 | 1918400 | 4 | 54500 | 218000 | 35.2 | 62257.03 | 2191447.625 | 35.166 | 60541.18 | 2128991.18 | 31.2 | 0.034 | 1700400 | -210591.18
157 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 622.925 | 1750 | 1090118.75 | 622.925 | 1750 | 1090118.75 | 62 | 1750 | 108500 | 615.31 | 2008.72 | 1235987.75 | 546.592 | 1998.1 | 1092145.7 | 560.925 | 76.333 | 981618.75 | -2026.95
158 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 430 | 55.6 | 23908 | 275 | 55.6 | 15290 | 43 | 55.6 | 2390.8 | 275 | 81.9 | 22522.5 | 0 | 0 | 0 | 387 | 430 | 21517.2 | 23908
159 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)6 MM MILD STEEL | MT | 8.1 | 59206.5 | 479572.65 | 8.1 | 59206.5 | 479572.65 | 1 | 59206.5 | 59206.5 | 8.1 | 63101.81 | 511124.67 | 6.842 | 62033.76 | 424435 | 7.1 | 1.258 | 420366.15 | 55137.65
160 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)8 MM DIA TMT | MT | 1 | 56000.01 | 56000.01 | 0 | 0 | 0 | 0 | 56000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 56000.01 | 56000.01
161 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)EMPTY CEMENT BAG. | NOS | 7500 | 3.25 | 24375 | 7500 | 3.25 | 24375 | 750 | 3.25 | 2437.5 | 7500 | 3.84 | 28762.5 | 750 | 3.84 | 2876.25 | 6750 | 6750 | 21937.5 | 21498.75
162 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 3415 | 36.58 | 124920.7 | 3375 | 36.58 | 123457.5 | 342 | 36.58 | 12510.36 | 3375 | 53.45 | 180400.5 | 2930.638 | 52.9 | 155019.29 | 3073 | 484.362 | 112410.34 | -30098.59
163 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)M.C. SAND | MT | 719.73 | 1711.5 | 1231817.9 | 701.035 | 1711.5 | 1199821.4 | 72 | 1711.5 | 123228 | 695.27 | 1686.34 | 1172461.71 | 649.8856 | 1673.55 | 1087614.74 | 647.73 | 69.8444 | 1108589.895 | 144203.155
164 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 7228 | 283.59 | 2049788.52 | 7099 | 283.59 | 2013205.41 | 723 | 283.59 | 205035.57 | 7099 | 310.62 | 2205064.7176 | 7036 | 308.88 | 2173274.2 | 6505 | 192 | 1844752.95 | -123485.68
165 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)SIKAMENT 2003 NS | NOS | 1 | 49.56 | 49.56 | 0 | 0 | 0 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 49.56 | 49.56
166 | PILING : PRAYAG - Pile Work | 10 | Started | Material | (M)SILVER SAND | CFT | 2600 | 25 | 65000 | 1839 | 25 | 45975 | 260 | 25 | 6500 | 1839 | 28.46 | 52333.5 | 2263.7 | 29 | 65647.3 | 2340 | 336.3 | 58500 | -647.3
167 | PILING : PRAYAG - MonoBlock Pump Rental | 10 | Started | Labour | (L)4" SUCKTION PIPE 60' 0" LONG | LS | 1 | 11800 | 11800 | 0 | 0 | 0 | 0 | 11800 | 0 | 1 | 11800 | 11800 | 1 | 11800 | 11800 | 1 | 0 | 11800 | 0
168 | PILING : PRAYAG - MonoBlock Pump Rental | 10 | Started | Labour | (L)5 HP HEAVY DUTY MONOBLOCK PUMP | Monthly | 5 | 8000 | 40000 | 0 | 0 | 0 | 1 | 8000 | 8000 | 2 | 9440 | 18880 | 2 | 9440 | 18880 | 4 | 3 | 32000 | 21120
169 | PILING : PRAYAG - Mixture Machine Transportation | 10 | Started | Labour | (L)HOOPER CONCRETE MIXTURE MACHINE HIRE CHARGE | Monthly | 4 | 7000 | 28000 | 0 | 0 | 0 | 0 | 7000 | 0 | 4 | 7000 | 28000 | 4 | 7000 | 28000 | 4 | 0 | 28000 | 0
170 | PILING : PRAYAG - Mixture Machine Transportation | 10 | Started | Labour | (L)TRANSPORTATION CHARGE | LS | 2 | 4720 | 9440 | 0 | 0 | 0 | 0 | 4720 | 0 | 2 | 3300 | 6600 | 2 | 3300 | 6600 | 2 | 0 | 9440 | 2840
171 | PILING : PRAYAG - Pile Integrity Test | 10 | Started | Labour | (L)Pile Integrity Test | NOS | 153 | 413 | 63189 | 0 | 0 | 0 | 15 | 413 | 6195 | 143 | 413 | 59059 | 143 | 413 | 59059 | 138 | 10 | 56994 | 4130
172 | PILING : PRAYAG - Rebound Hammer Test | 10 | Started | Labour | (L)Rebound Hammer Test | NOS | 153 | 472 | 72216 | 0 | 0 | 0 | 15 | 472 | 7080 | 104 | 472 | 49088 | 104 | 472 | 49088 | 138 | 49 | 65136 | 23128
173 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)10MM REBAR ANCHORING & CHEM. GROUTING | NOS | 100 | 94.4 | 9440 | 0 | 0 | 0 | 10 | 94.4 | 944 | 82 | 94.4 | 7740.8 | 82 | 94.4 | 7740.8 | 90 | 18 | 8496 | 1699.2
174 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)125 MM BRICK SHUTTERING | SQM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)12MM REBAR ANCHORING & CHEM. GROUTING | NOS | 50 | 129.8 | 6490 | 0 | 0 | 0 | 5 | 129.8 | 649 | 23 | 129.8 | 2985.4 | 23 | 129.8 | 2985.4 | 45 | 27 | 5841 | 3504.6
176 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)16MM REBAR ANCHORING & CHEM. GROUTING | NOS | 100 | 224.2 | 22420 | 0 | 0 | 0 | 10 | 224.2 | 2242 | 89 | 224.2 | 19953.8 | 89 | 224.2 | 19953.8 | 90 | 11 | 20178 | 2466.2
177 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)200 MM BRICK WORK SUB STRUCTURE | CUM | 1 | 650 | 650 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 650 | 650
178 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)20MM REBAR ANCHORING & CHEM. GROUTING | NOS | 15 | 377.6 | 5664 | 0 | 0 | 0 | 2 | 377.6 | 755.2 | 12 | 377.6 | 4531.2 | 12 | 377.6 | 4531.2 | 13 | 3 | 4908.8 | 1132.8
179 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)250/230/200 MM BRICK WORK | CUM | 14.322 | 700 | 10025.4 | 0 | 0 | 0 | 1 | 700 | 700 | 14.322 | 700 | 10025.4 | 14.322 | 700 | 10025.4 | 13.322 | 0 | 9325.4 | 0
180 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)8MM REBAR ANCHORING & CHEM. GROUTING | NOS | 40 | 64.9 | 2596 | 0 | 0 | 0 | 4 | 64.9 | 259.6 | 25 | 64.9 | 1622.5 | 25 | 64.9 | 1622.5 | 36 | 15 | 2336.4 | 973.5
181 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 3075 | 141.6 | 435420 | 0 | 0 | 0 | 308 | 141.6 | 43612.8 | 3028.75 | 125 | 378593.75 | 2309.127 | 125 | 288640.88 | 2767 | 765.873 | 391807.2 | 146779.12
182 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 449.586 | 82.6 | 37135.8 | 0 | 0 | 0 | 45 | 82.6 | 3717 | 449.586 | 75 | 33718.95 | 449.586 | 75 | 33718.95 | 404.586 | 0 | 33418.804 | 3416.8536
183 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 566.516 | 50 | 28325.8 | 0 | 0 | 0 | 57 | 50 | 2850 | 329.12 | 55 | 18101.6 | 329.12 | 55 | 18101.6 | 509.516 | 237.396 | 25475.8 | 10224.2
184 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)CARPENTER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Earthwork in Excavation from Grid W-E' | CUM | 1 | 153.4 | 153.4 | 0 | 0 | 0 | 0 | 153.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 153.4 | 153.4
186 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)EXTRA CHARGES OVER CONCRETING (OT) | CUM | 111.9 | 20 | 2238 | 0 | 0 | 0 | 11 | 20 | 220 | 33.9 | 20 | 678 | 33.9 | 20 | 678 | 100.9 | 78 | 2018 | 1560
187 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Hiring Charges for JCB on Daily Basis (8hrs Shift) | DAYS | 20 | 7552 | 151040 | 0 | 0 | 0 | 2 | 7552 | 15104 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 135936 | 151040
188 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)L/C for Mixing and Pouring M-25 Grade Concrete | CUM | 77.661 | 750 | 58245.75 | 0 | 0 | 0 | 8 | 750 | 6000 | 65.581 | 750 | 49185.75 | 65.581 | 750 | 49185.75 | 69.661 | 12.08 | 52245.75 | 9060
189 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 33.513 | 6490 | 217499.37 | 0 | 0 | 0 | 3 | 6490 | 19470 | 33.513 | 5500 | 184321.5 | 33.513 | 5500 | 184321.5 | 30.513 | 0 | 198029.37 | 33177.87
190 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)LABOUR CHARGES FOR RMC CONCRETING | CUM | 327 | 200.6 | 65596.2 | 0 | 0 | 0 | 33 | 200.6 | 6619.8 | 325.99 | 170 | 55418.3 | 325.99 | 170 | 55418.3 | 294 | 1.01 | 58976.4 | 10177.9
191 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)MANUAL EXCAVATION | CUM | 357.11 | 206.5 | 73743.22 | 0 | 0 | 0 | 36 | 206.5 | 7434 | 284.36 | 175 | 49763 | 284.36 | 175 | 49763 | 321.11 | 72.75 | 66309.215 | 23980.215
192 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)MECH. EXCAVATION (EGL-FDN. BOTT.)& STACKING IN SITE | CUM | 1100 | 188.8 | 207680 | 0 | 0 | 0 | 110 | 188.8 | 20768 | 950.627 | 188.8 | 179478.38 | 950.627 | 188.8 | 179478.38 | 990 | 149.373 | 186912 | 28201.62
193 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)MECH. EXCAVATION INCL. SOIL EXTRACTION(EGL-FDN. BOTTOM) | CUM | 1850 | 165.2 | 305620 | 0 | 0 | 0 | 185 | 165.2 | 30562 | 1808.7 | 165.2 | 298797.24 | 1808.7 | 165.2 | 298797.24 | 1665 | 41.3 | 275058 | 6822.76
194 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
195 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 42.489 | 700 | 29742.3 | 0 | 0 | 0 | 4 | 700 | 2800 | 42.36 | 750 | 31770 | 42.36 | 750 | 31770 | 38.489 | 0.129 | 26942.3 | -2027.7
196 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Operator Hiring Charges (8 hours shift) | MAN/DAY | 20 | 472 | 9440 | 0 | 0 | 0 | 2 | 472 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 8496 | 9440
197 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 153 | 118 | 18054 | 0 | 0 | 0 | 15 | 118 | 1770 | 153 | 100 | 15300 | 153 | 100 | 15300 | 138 | 0 | 16284 | 2754
198 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 153 | 40 | 6120 | 0 | 0 | 0 | 15 | 40 | 600 | 149 | 100 | 14900 | 149 | 100 | 14900 | 138 | 4 | 5520 | -8780
199 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)PILE HEAD DISMENTLING | RMT | 340 | 500 | 170000 | 0 | 0 | 0 | 34 | 500 | 17000 | 315.43 | 525 | 165600.75 | 315.43 | 525 | 165600.75 | 306 | 24.57 | 153000 | 4399.25
200 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Pile Head Grinding for NDT Tests | NOS | 100 | 59 | 5900 | 0 | 0 | 0 | 10 | 59 | 590 | 86 | 50 | 4300 | 86 | 50 | 4300 | 90 | 14 | 5310 | 1600
201 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)POCKLAIN TRANSPORTATION CHARGE ONE SIDE | LS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 1 | 17700 | 17700 | 1 | 17700 | 17700 | 1 | 0 | 17700 | 0
202 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 452 | 303.86 | 137344.72 | 0 | 0 | 0 | 45 | 303.86 | 13673.7 | 452 | 257.5 | 116390 | 452 | 257.5 | 116390 | 407 | 0 | 123671.02 | 20954.72
203 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 30 | 802.4 | 24072 | 0 | 0 | 0 | 3 | 802.4 | 2407.2 | 28.685 | 680 | 19505.8 | 28.685 | 680 | 19505.8 | 27 | 1.315 | 21664.8 | 4566.2
204 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 275 | 535 | 147125 | 0 | 0 | 0 | 28 | 535 | 14980 | 275 | 535 | 147125 | 275 | 535 | 147125 | 247 | 0 | 132145 | 0
205 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)Transportation charges for pocklain after initial deployment | LS | 4 | 8260 | 33040 | 0 | 0 | 0 | 0 | 8260 | 0 | 1 | 8260 | 8260 | 1 | 8260 | 8260 | 4 | 3 | 33040 | 24780
206 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 566.516 | 82.6 | 46794.22 | 0 | 0 | 0 | 57 | 82.6 | 4708.2 | 429.26 | 50 | 21463 | 429.26 | 50 | 21463 | 509.516 | 137.256 | 42086.022 | 25331.2216
207 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)1.5" NAIL | KG | 50 | 100 | 5000 | 50 | 100 | 5000 | 5 | 100 | 500 | 50 | 75.52 | 3776 | 63.2 | 76.83 | 4855.92 | 45 | -13.2 | 4500 | 144.08
208 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)10 MM DIA TMT | MT | 1 | 55000 | 55000 | 1 | 55000 | 55000 | 0 | 55000 | 0 | 1 | 55460 | 55460 | 1 | 55637.94 | 55637.94 | 1 | 0 | 55000 | -637.94
209 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 156 | 1770 | 276120 | 150 | 1770 | 265500 | 16 | 1770 | 28320 | 150 | 1522.5 | 228375 | 12.0965 | 1400.92 | 16946.22 | 140 | 143.9035 | 247800 | 259173.78
210 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)12 MM DIA TMT | MT | 9.42 | 54500 | 513390 | 9.42 | 54500 | 513390 | 1 | 54500 | 54500 | 9.42 | 55548.5 | 523266.88 | 9.42 | 57046.39 | 537377.01 | 8.42 | 0 | 458890 | -23987.01
211 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)12 MM PLY | NOS | 1 | 48 | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 48 | 48
212 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)16 MM DIA TMT | MT | 13 | 54500 | 708500 | 12.69 | 54500 | 691605 | 1 | 54500 | 54500 | 12.69 | 55179.53 | 700228.225 | 12.69 | 55237.57 | 700964.77 | 12 | 0.31 | 654000 | 7535.23
213 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)2" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
214 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)20 GAUGE BINDING WIRE | KG | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 150 | 79.18 | 11876.7 | 1 | -149 | 82.6 | -11794.1
215 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 8.39 | 50000 | 419500 | 8.39 | 50000 | 419500 | 1 | 50000 | 50000 | 8.39 | 55548.5 | 466051.91 | 8.39 | 55239.36 | 463458.26 | 7.39 | 0 | 369500 | -43958.26
216 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 284 | 1750 | 497000 | 143.73 | 1750 | 251527.5 | 28 | 1750 | 49000 | 143.73 | 2050 | 294646.5 | 86.412 | 2060.65 | 178064.51 | 256 | 197.588 | 448000 | 318935.49
217 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 360 | 55.6 | 20016 | 0 | 0 | 0 | 36 | 55.6 | 2001.6 | 0 | 0 | 0 | 231 | 81.37 | 18797.28 | 324 | 129 | 18014.4 | 1218.72
218 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 10000 | 10 | 100000 | 10000 | 10 | 100000 | 1000 | 10 | 10000 | 10000 | 10.2 | 102000 | 8826 | 9.97 | 88021.33 | 9000 | 1174 | 90000 | 11978.67
219 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)3" NAIL | KG | 130 | 51 | 6630 | 50 | 51 | 2550 | 13 | 51 | 663 | 50 | 70.8 | 3540 | 104.5 | 75.23 | 7861.73 | 117 | 25.5 | 5967 | -1231.73
220 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 430 | 430 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 430 | 430
221 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)3'' X 2'' X 4'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 330 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 330 | 330
222 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)4" NAIL | KG | 110 | 51 | 5610 | 50 | 51 | 2550 | 11 | 51 | 561 | 50 | 70.8 | 3540 | 75 | 74.98 | 5623.63 | 99 | 35 | 5049 | -13.63
223 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)8 MM DIA TMT | MT | 2.62 | 56000.01 | 146720.03 | 2.62 | 56000.01 | 146720.03 | 0 | 56000.01 | 0 | 2.62 | 57318.5 | 150174.48 | 2.62 | 57591.31 | 150889.24 | 2.62 | 0 | 146720.026 | -4169.2138
224 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)CONCRETE PUMP HIRE CHARGES | CUM | 65 | 236 | 15340 | 33 | 236 | 7788 | 7 | 236 | 1652 | 33 | 200 | 6599.9439 | 33 | 200 | 6599.95 | 58 | 32 | 13688 | 8740.05
225 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 2 | 424.8 | 849.6 | 2 | 424.8 | 849.6 | 0 | 424.8 | 0 | 2 | 442.5 | 885 | 2 | 442.5 | 885 | 2 | 0 | 849.6 | -35.4
226 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 724 | 36.58 | 26483.92 | 0 | 0 | 0 | 72 | 36.58 | 2633.76 | 0 | 0 | 0 | 60.5 | 53.12 | 3213.48 | 652 | 663.5 | 23850.16 | 23270.44
227 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)M.C. SAND | MT | 245 | 1711.5 | 419317.5 | 0 | 0 | 0 | 25 | 1711.5 | 42787.5 | 0 | 0 | 0 | 62.519 | 1689.65 | 105635 | 220 | 182.481 | 376530 | 313682.5
228 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 5343 | 11 | 58773 | 4350 | 11 | 47850 | 534 | 11 | 5874 | 4350 | 9 | 39150 | 5250 | 9 | 47250 | 4809 | 93 | 52899 | 11523
229 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 111 | 47.2 | 5239.2 | 100 | 47.2 | 4720 | 11 | 47.2 | 519.2 | 100 | 146.32 | 14632 | 59 | 143.22 | 8450.19 | 100 | 52 | 4720 | -3210.99
230 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 62 | 110 | 6820 | 45 | 110 | 4950 | 6 | 110 | 660 | 45 | 141.6 | 6372 | 56 | 141.6 | 7929.6 | 56 | 6 | 6160 | -1109.6
231 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)PPC CEMENT | BAG | 1700 | 283.59 | 482103 | 1200 | 283.59 | 340308 | 170 | 283.59 | 48210.3 | 1180 | 303.31 | 357900.032 | 424 | 331.39 | 140511.13 | 1530 | 1276 | 433892.7 | 341591.87
232 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 327.505 | 7257 | 2376703.79 | 327.505 | 7257 | 2376703.79 | 33 | 7257 | 239481 | 327.505 | 7256.18 | 2376435.0221 | 329.7 | 7255.65 | 2392189.31 | 294.505 | -2.195 | 2137222.785 | -15485.525
233 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 1 | 78 | 78 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 78 | 78
234 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)SIKA HIBOND | PKT | 10 | 507.4 | 5074 | 10 | 507.4 | 5074 | 1 | 507.4 | 507.4 | 10 | 507.4 | 5074 | 10 | 507.4 | 5074 | 9 | 0 | 4566.6 | 0
235 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)SIKAMENT 2003 NS | NOS | 1 | 49.56 | 49.56 | 0 | 0 | 0 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 49.56 | 49.56
236 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)SILVER SAND | CFT | 1500 | 25 | 37500 | 0 | 0 | 0 | 150 | 25 | 3750 | 0 | 0 | 0 | 521 | 29 | 15109 | 1350 | 979 | 33750 | 22391
237 | PILE CAP WITH TIE BEAM : PRAYAG - Embedded Column | 10 | Started | Material | (M)WIRE BRUSH | NOS | 3 | 59 | 177 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 5 | 59 | 295 | 3 | -2 | 177 | -118
238 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 200 | 82.6 | 16520 | 0 | 0 | 0 | 20 | 82.6 | 1652 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 200 | 14868 | 16520 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
239 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 172 | 50 | 8600 | 0 | 0 | 0 | 17 | 50 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 172 | 7750 | 8600 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
240 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)CONCRETING M-25 (SITE MIX) | CUM | 57.311 | 750 | 42983.25 | 0 | 0 | 0 | 6 | 750 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 51.311 | 57.311 | 38483.25 | 42983.25 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
241 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 7.8 | 6490 | 50622 | 0 | 0 | 0 | 1 | 6490 | 6490 | 7.8 | 5500 | 42900 | 7.8 | 5500 | 42900 | 6.8 | 0 | 44132 | 7722 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
242 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 12.9 | 700 | 9030 | 0 | 0 | 0 | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9 | 12.9 | 8330 | 9030 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
243 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)POLYTHENE SHEET LAYING | SQM | 175 | 50 | 8750 | 0 | 0 | 0 | 18 | 50 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 175 | 7850 | 8750 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
244 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 440 | 303.86 | 133698.4 | 0 | 0 | 0 | 44 | 303.86 | 13369.84 | 440 | 257.5 | 113300 | 440 | 257.5 | 113300 | 396 | 0 | 120328.56 | 20398.4 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
245 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)Supply of Carpenter (8 hours shift) | MAN/DAY | 5 | 708 | 3540 | 0 | 0 | 0 | 1 | 708 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 2832 | 3540 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
246 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)Supply of Fitter (8 Hrs) | MAN/DAY | 5 | 708 | 3540 | 0 | 0 | 0 | 1 | 708 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 2832 | 3540 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
247 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Labour | (L)Supply of Helper (8 hrs shift) | MAN/DAY | 10 | 590 | 5900 | 0 | 0 | 0 | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 5310 | 5900 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
248 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)10 MM DIA TMT | MT | 0.045 | 55000 | 2475 | 0.045 | 55000 | 2475 | 0 | 55000 | 0 | 0.045 | 54014.52 | 2430.6534 | 0.045 | 54519.11 | 2453.36 | 0.045 | 0 | 2475 | 21.64 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
249 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 30 | 1770 | 53100 | 0 | 0 | 0 | 3 | 1770 | 5310 | 0 | 0 | 0 | 21.776 | 1516.41 | 33021.36 | 27 | 8.224 | 47790 | 20078.64 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
250 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)12 MM DIA TMT | MT | 1 | 54500 | 54500 | 1 | 54500 | 54500 | 0 | 54500 | 0 | 1 | 55460 | 55460 | 1 | 54014.5 | 54014.5 | 1 | 0 | 54500 | 485.5 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
251 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)12 MM PLY | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
252 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)16 MM DIA TMT | MT | 4.908 | 54500 | 267486 | 4.908 | 54500 | 267486 | 0 | 54500 | 0 | 4.908 | 55460 | 272197.68 | 4.908 | 55237.57 | 271106 | 4.908 | 0 | 267486 | -3620 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
253 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 0.237 | 50000 | 11850 | 0.208 | 50000 | 10400 | 0 | 50000 | 0 | 0.208 | 54014.5 | 11235.0166 | 0.237 | 54018.02 | 12802.27 | 0.237 | 0 | 11850 | -952.27 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
254 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 67 | 1750 | 117250 | 0 | 0 | 0 | 7 | 1750 | 12250 | 0 | 0 | 0 | 53.51 | 2039.47 | 109131.97 | 60 | 13.49 | 105000 | 8118.03 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
255 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 85 | 55.6 | 4726 | 0 | 0 | 0 | 9 | 55.6 | 500.4 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 85 | 4225.6 | 4726 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
256 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)3" NAIL | KG | 80 | 51 | 4080 | 0 | 0 | 0 | 8 | 51 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 80 | 3672 | 4080 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
257 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)4" NAIL | KG | 80 | 51 | 4080 | 0 | 0 | 0 | 8 | 51 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 80 | 3672 | 4080 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
258 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)8 MM DIA TMT | MT | 1.605 | 56000.01 | 89880.02 | 1.605 | 56000.01 | 89880.02 | 0 | 56000.01 | 0 | 1.605 | 57230 | 91854.15 | 1.605 | 57591.31 | 92434.05 | 1.605 | 0 | 89880.016 | -2554.0339 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
259 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)HARDWOOD BATTENS | CFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
260 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 120 | 36.58 | 4389.6 | 0 | 0 | 0 | 12 | 36.58 | 438.96 | 0 | 0 | 0 | 117.6 | 55.46 | 6521.63 | 108 | 2.4 | 3950.64 | -2132.03 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
261 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)M.C. SAND | MT | 51 | 1711.5 | 87286.5 | 0 | 0 | 0 | 5 | 1711.5 | 8557.5 | 0 | 0 | 0 | 40.072 | 1690.01 | 67722.11 | 46 | 10.928 | 78729 | 19564.39 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
262 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 2290 | 11 | 25190 | 900 | 11 | 9900 | 229 | 11 | 2519 | 900 | 8.75 | 7875 | 0 | 0 | 0 | 2061 | 2290 | 22671 | 25190 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
263 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 48 | 47.2 | 2265.6 | 0 | 0 | 0 | 5 | 47.2 | 236 | 0 | 0 | 0 | 48 | 143.22 | 6874.72 | 43 | 0 | 2029.6 | -4609.12 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
264 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 27 | 110 | 2970 | 0 | 0 | 0 | 3 | 110 | 330 | 0 | 0 | 0 | 11 | 141.6 | 1557.6 | 24 | 16 | 2640 | 1412.4 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
265 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)PPC CEMENT | BAG | 511 | 283.59 | 144914.49 | 0 | 0 | 0 | 51 | 283.59 | 14463.09 | 0 | 0 | 0 | 392 | 322.18 | 126292.61 | 460 | 119 | 130451.4 | 18621.88 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
266 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 1 | 7257 | 7257 | 1 | 7257 | 7257 | 0 | 7257 | 0 | 1 | 7300 | 7299.9992 | 0 | 0 | 0 | 1 | 1 | 7257 | 7257 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
267 | PILE CAP WITH TIE BEAM : PRAYAG - Tie Beam | 10 | Started | Material | (M)SIKA HIBOND | PKT | 20 | 507.4 | 10148 | 20 | 507.4 | 10148 | 2 | 507.4 | 1014.8 | 20 | 507.4 | 10148 | 3 | 507.4 | 1522.2 | 18 | 17 | 9133.2 | 8625.8 | PILE CAP & FOUNDATION UPTO G.L | PILE CAP AND FOUNDATION
268 | PILE CAP WITH TIE BEAM : PRAYAG - Anti Termite | 0 | Tentative | Labour | (L)ANTI- TERMITE Imidacloprid 30.50 SC | SQM | 400 | 64.9 | 25960 | 0 | 0 | 0 | 0 | 64.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 25960 | 25960
269 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)10 MM DIA TMT STAIGHTENING, CUTTING, BENDING, BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
270 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)12 MM DIA TMT STAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 9735 | 9735 | 0 | 0 | 0 | 0 | 9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9735 | 9735
271 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)16 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
272 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)20 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
273 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)200 MM BRICK WORK SUB STRUCTURE | CUM | 1 | 650 | 650 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 650 | 650
274 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)25 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
275 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)8 MM DIA TMT CUTTING, BENDING, BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
276 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 141.6 | 141.6
277 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
278 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 1 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50 | 50
279 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)DISPOSAL OF EARTH WITHIN PROJECT SITE, MORE THAN 50'0" LEAD | CUM | 1 | 90 | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 90 | 90
280 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY AND ALLOWED TO TAKE OU | CUM | 1 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 65 | 65
281 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY AND RETAINED AT SITE | CUM | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
282 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)MANUAL EXCAVATION | CUM | 1 | 206.5 | 206.5 | 0 | 0 | 0 | 0 | 206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 206.5 | 206.5
283 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
284 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 700 | 700
285 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 118
286 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 40 | 40
287 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)PILE HEAD DISMENTLING | RMT | 1 | 500 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 500 | 500
288 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 1 | 295 | 295 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 295 | 295
289 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 20 | 885 | 17700 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 17700 | 17700
290 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 200 | 535 | 107000 | 0 | 0 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 107000 | 107000
291 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Labour | (L)VAPOUR BARRIER | SQM | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
292 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)1.5" NAIL | KG | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
293 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)10 MM DIA TMT | MT | 0.211 | 55000 | 11605 | 0.211 | 55000 | 11605 | 0 | 55000 | 0 | 0.211 | 51801.99 | 10930.22 | 0 | 0 | 0 | 0.211 | 0.211 | 11605 | 11605
294 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)10 MM STONE CHIPS. | MT | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1770 | 1770
295 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)12 MM DIA TMT | MT | 8.205 | 54500 | 447172.5 | 8.205 | 54500 | 447172.5 | 0 | 54500 | 0 | 8.205 | 51802 | 425035.4198 | 0 | 0 | 0 | 8.205 | 8.205 | 447172.5 | 447172.5
296 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)12 MM PLY | NOS | 1 | 48 | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 48 | 48
297 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)16 MM DIA TMT | MT | 14.296 | 54500 | 779132 | 14.296 | 54500 | 779132 | 0 | 54500 | 0 | 14.296 | 51802 | 740561.4006 | 0 | 0 | 0 | 14.296 | 14.296 | 779132 | 779132
298 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)2" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
299 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)20 GAUGE BINDING WIRE | KG | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
300 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)20 MM DIA TMT. | MT | 4.828 | 50000 | 241400 | 4.828 | 50000 | 241400 | 0 | 50000 | 0 | 4.828 | 51802 | 250100.0599 | 0 | 0 | 0 | 4.828 | 4.828 | 241400 | 241400
301 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)20 MM STONE CHIPS. | MT | 1 | 1750 | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1750 | 1750
302 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)22 GAUGE BINDING WIRE | KG | 1 | 55.6 | 55.6 | 0 | 0 | 0 | 0 | 55.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 55.6 | 55.6
303 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)25 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
304 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)2ND CLASS BRICKS | NOS | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 10 | 10
305 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)3" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
306 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 430 | 430 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 430 | 430
307 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)3'' X 2'' X 4'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 330 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 330 | 330
308 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)4" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
309 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)8 MM DIA TMT | MT | 0.121 | 55999.94 | 6775.99 | 0.121 | 55999.94 | 6775.99 | 0 | 55999.94 | 0 | 0.121 | 53985.04 | 6532.19 | 0 | 0 | 0 | 0.121 | 0.121 | 6775.993 | 6775.9927
310 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)HIND PLAST SUPER 160 | KG | 1 | 36.58 | 36.58 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 36.58 | 36.58
311 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1711.5 | 1711.5
312 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)PICKED JHAMA. | NOS | 1 | 11 | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11 | 11
313 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)PLY SHUTTERING OIL | LTR | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
314 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)POLYTHENE SHEET | KG | 1 | 110 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 110 | 110
315 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 283.59 | 283.59
316 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)SHUTTERING GREASE | KG | 1 | 78 | 78 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 78 | 78
317 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)SIKAMENT 2003 NS | NOS | 1 | 49.56 | 49.56 | 0 | 0 | 0 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 49.56 | 49.56
318 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)SIKAPLAST 2004 NS | KG | 1200 | 70.8 | 84960 | 1200 | 70.8 | 84960 | 0 | 70.8 | 0 | 1200 | 70.8 | 84960 | 0 | 0 | 0 | 1200 | 1200 | 84960 | 84960
319 | PILE CAP WITH TIE BEAM : URVI - Embedded Column | 0 | Tentative | Material | (M)SILVER SAND | CFT | 1 | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 25 | 25
320 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)10MM REBAR ANCHORING & CHEM. GROUTING | NOS | 100 | 94.4 | 9440 | 0 | 0 | 0 | 10 | 94.4 | 944 | 100 | 94.4 | 9440 | 0 | 0 | 0 | 90 | 100 | 8496 | 9440
321 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)12MM REBAR ANCHORING & CHEM. GROUTING | NOS | 50 | 129.8 | 6490 | 0 | 0 | 0 | 5 | 129.8 | 649 | 50 | 129.8 | 6490 | 0 | 0 | 0 | 45 | 50 | 5841 | 6490
322 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)16MM REBAR ANCHORING & CHEM. GROUTING | NOS | 100 | 224.2 | 22420 | 0 | 0 | 0 | 10 | 224.2 | 2242 | 100 | 224.2 | 22420 | 0 | 0 | 0 | 90 | 100 | 20178 | 22420
323 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)20MM REBAR ANCHORING & CHEM. GROUTING | NOS | 15 | 377.6 | 5664 | 0 | 0 | 0 | 2 | 377.6 | 755.2 | 15 | 377.6 | 5664 | 0 | 0 | 0 | 13 | 15 | 4908.8 | 5664
324 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)250/230/200 MM BRICK WORK | CUM | 15 | 700 | 10500 | 0 | 0 | 0 | 2 | 700 | 1400 | 14.221 | 700 | 9954.7 | 14.221 | 700 | 9954.7 | 13 | 0.779 | 9100 | 545.3
325 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)8MM REBAR ANCHORING & CHEM. GROUTING | NOS | 40 | 64.9 | 2596 | 0 | 0 | 0 | 4 | 64.9 | 259.6 | 40 | 64.9 | 2596 | 0 | 0 | 0 | 36 | 40 | 2336.4 | 2596
326 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 2600 | 141.6 | 368160 | 0 | 0 | 0 | 260 | 141.6 | 36816 | 1560.949 | 145.79 | 227572.35 | 903.949 | 150 | 135592.35 | 2340 | 1696.051 | 331344 | 232567.65
327 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 485 | 82.6 | 40061 | 0 | 0 | 0 | 49 | 82.6 | 4047.4 | 485 | 75 | 36375 | 485 | 75 | 36375 | 436 | 0 | 36013.6 | 3686
328 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 485 | 50 | 24250 | 0 | 0 | 0 | 49 | 50 | 2450 | 173.33 | 55 | 9533.15 | 23.33 | 55 | 1283.15 | 436 | 461.67 | 21800 | 22966.85
329 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)CHIPPER (12 HRS) | NOS | 30 | 700 | 21000 | 0 | 0 | 0 | 3 | 700 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 30 | 18900 | 21000
330 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)EXTRA CHARGES OVER CONCRETING (OT) | CUM | 70 | 20 | 1400 | 0 | 0 | 0 | 7 | 20 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 70 | 1260 | 1400
331 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)HIRE CH. FOR DUMPER | DAYS | 9 | 11210 | 100890 | 0 | 0 | 0 | 1 | 11210 | 11210 | 9 | 11210 | 100890 | 9 | 11210 | 100890 | 8 | 0 | 89680 | 0
332 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)HYDRA (FOR 4 HOURS) | DAYS | 10 | 3700 | 37000 | 0 | 0 | 0 | 1 | 3700 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 33300 | 37000
333 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)HYDRA (FOR 8 HOURS) | DAYS | 5 | 4500 | 22500 | 0 | 0 | 0 | 1 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 18000 | 22500
334 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)L/C for Board Making | SQM | 150 | 80 | 12000 | 0 | 0 | 0 | 15 | 80 | 1200 | 150 | 70 | 10500 | 150 | 70 | 10500 | 135 | 0 | 10800 | 1500
335 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 30.04 | 6490 | 194959.6 | 0 | 0 | 0 | 3 | 6490 | 19470 | 29.352 | 5800 | 170241.6 | 29.352 | 5800 | 170241.6 | 27.04 | 0.688 | 175489.6 | 24718
336 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)LABOUR CHARGES FOR RMC CONCRETING | CUM | 380.6 | 200.6 | 76348.36 | 0 | 0 | 0 | 38 | 200.6 | 7622.8 | 363.685 | 170 | 61826.45 | 363.685 | 170 | 61826.45 | 342.6 | 16.915 | 68725.56 | 14521.91
337 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)MANUAL EXCAVATION | CUM | 350 | 206.5 | 72275 | 0 | 0 | 0 | 35 | 206.5 | 7227.5 | 210 | 185.88 | 39034.5 | 118.62 | 175 | 20758.5 | 315 | 231.38 | 65047.5 | 51516.5
338 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)MECH. EXCAVATION (EGL-FDN. BOTT.)& STACKING IN SITE | CUM | 2241 | 188.8 | 423100.8 | 0 | 0 | 0 | 224 | 188.8 | 42291.2 | 2241 | 188.8 | 423100.8 | 2240.879 | 188.8 | 423077.96 | 2017 | 0.121 | 380809.6 | 22.84
339 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)MECH. EXCAVATION INCL. SOIL EXTRACTION(EGL-FDN. BOTTOM) | CUM | 1850 | 165.2 | 305620 | 0 | 0 | 0 | 185 | 165.2 | 30562 | 1850 | 165.2 | 305620 | 729.96 | 165.2 | 120589.4 | 1665 | 1120.04 | 275058 | 185030.6
340 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 36.4 | 700 | 25480 | 0 | 0 | 0 | 4 | 700 | 2800 | 36.4 | 750 | 27300 | 36.4 | 750 | 27300 | 32.4 | 0 | 22680 | -1820
341 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 169 | 118 | 19942 | 0 | 0 | 0 | 17 | 118 | 2006 | 169 | 110 | 18590 | 161 | 110 | 17710 | 152 | 8 | 17936 | 2232
342 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 169 | 40 | 6760 | 0 | 0 | 0 | 17 | 40 | 680 | 165 | 100 | 16500 | 165 | 100 | 16500 | 152 | 4 | 6080 | -9740
343 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)PILE HEAD DISMENTLING | RMT | 355 | 500 | 177500 | 0 | 0 | 0 | 36 | 500 | 18000 | 355 | 562.23 | 199593.15 | 315.49 | 555 | 175096.95 | 319 | 39.51 | 159500 | 2403.05
344 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)POCKLAIN TRANSPORTATION CHARGE ONE SIDE | LS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 17700 | 17700
345 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 556.02 | 303.86 | 168952.24 | 0 | 0 | 0 | 56 | 303.86 | 17016.16 | 556.02 | 200 | 111204 | 505.433 | 200 | 101086.6 | 500.02 | 50.587 | 151936.077 | 67865.6372
346 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 65 | 802.4 | 52156 | 0 | 0 | 0 | 7 | 802.4 | 5616.8 | 23.67 | 750 | 17752.5 | 8.67 | 750 | 6502.5 | 58 | 56.33 | 46539.2 | 45653.5
347 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 574 | 535 | 307090 | 0 | 0 | 0 | 57 | 535 | 30495 | 566.185 | 550.9 | 311908.975 | 366.185 | 535 | 195908.98 | 517 | 207.815 | 276595 | 111181.02
348 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)Transportation charges for pocklain after initial deployment | LS | 3 | 8260 | 24780 | 0 | 0 | 0 | 0 | 8260 | 0 | 3 | 8260 | 24780 | 3 | 8260 | 24780 | 3 | 0 | 24780 | 0
349 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 485 | 82.6 | 40061 | 0 | 0 | 0 | 49 | 82.6 | 4047.4 | 485 | 50 | 24250 | 464.126 | 50 | 23206.3 | 436 | 20.874 | 36013.6 | 16854.7
350 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)10 MM DIA TMT | MT | 1 | 55000 | 55000 | 0.51 | 55000 | 28050 | 0 | 55000 | 0 | 0.51 | 52864 | 26960.64 | 0.51 | 53801.2 | 27438.61 | 1 | 0.49 | 55000 | 27561.39
351 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 16.705 | 1540.19 | 25728.86 | 1 | -15.705 | 1770 | -23958.86
352 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)12 MM DIA TMT | MT | 10.964 | 54500 | 597538 | 9.334 | 54500 | 508703 | 1 | 54500 | 54500 | 9.334 | 54457.51 | 508306.4032 | 9.344 | 54464.41 | 508915.42 | 9.964 | 1.62 | 543038 | 88622.58
353 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 100 | 2194.8 | 219480 | 100 | 2194.8 | 219480 | 10 | 2194.8 | 21948 | 100 | 2190.08 | 219008 | 100 | 2190.08 | 219008 | 90 | 0 | 197532 | 472
354 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)16 MM DIA TMT | MT | 17.33 | 54500 | 944485 | 16.126 | 54500 | 878867 | 2 | 54500 | 109000 | 16.126 | 54343.49 | 876343.1235 | 16.126 | 54662.97 | 881495.07 | 15.33 | 1.204 | 835485 | 62989.93
355 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)20 GAUGE BINDING WIRE | KG | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
356 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)20 mm concrete cover block | NOS | 1000 | 1.78 | 1780 | 0 | 0 | 0 | 100 | 1.78 | 178 | 0 | 0 | 0 | 1000 | 1.18 | 1180 | 900 | 0 | 1602 | 600
357 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 6.05 | 50000 | 302500 | 5.96 | 50000 | 298000 | 1 | 50000 | 50000 | 5.96 | 53236.56 | 317289.905 | 5.96 | 53595.71 | 319430.46 | 5.05 | 0.09 | 252500 | -16930.46
358 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 54 | 1750 | 94500 | 34 | 1750 | 59500 | 5 | 1750 | 8750 | 33.27 | 2231.25 | 74233.6875 | 21.527 | 2154.11 | 46371.63 | 49 | 32.473 | 85750 | 48128.37
359 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 543.057 | 55.6 | 30193.97 | 168.057 | 55.6 | 9343.97 | 54 | 55.6 | 3002.4 | 168.057 | 77.94 | 13098.3626 | 500 | 75.66 | 37829.65 | 489.057 | 43.057 | 27191.569 | -7635.6808
360 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR) | NOS | 22 | 118 | 2596 | 0 | 0 | 0 | 2 | 118 | 236 | 0 | 0 | 0 | 22 | 83.98 | 1847.54 | 20 | 0 | 2360 | 748.46
361 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 5000 | 10 | 50000 | 5000 | 10 | 50000 | 500 | 10 | 5000 | 5000 | 9.5 | 47500 | 8294 | 9.71 | 80554.98 | 4500 | -3294 | 45000 | -30554.98
362 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 600 | 430 | 258000 | 116.21 | 430 | 49970.3 | 60 | 430 | 25800 | 116.21 | 519.2 | 60336.232 | 242.38 | 519.2 | 125843.7 | 540 | 357.62 | 232200 | 132156.3
363 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)3"X2" Pine Batten | CFT | 200 | 767 | 153400 | 0 | 0 | 0 | 20 | 767 | 15340 | 0 | 0 | 0 | 200 | 798.9 | 159780.26 | 180 | 0 | 138060 | -6380.26
364 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)4"X3"X 4 Ft Long Hardwood Batten (Special Quality) | CFT | 42.811 | 542.8 | 23237.81 | 0 | 0 | 0 | 4 | 542.8 | 2171.2 | 0 | 0 | 0 | 42.811 | 519.2 | 22227.46 | 38.811 | 0 | 21066.611 | 1010.3508
365 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)8 MM DIA TMT | MT | 0.11 | 56000.01 | 6160 | 0.107 | 56000.01 | 5992 | 0 | 56000.01 | 0 | 0.107 | 60151 | 6436.1565 | 0.107 | 59862.8 | 6405.32 | 0.11 | 0.003 | 6160.001 | -245.3189
366 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)ANTI TERMITE | LTR | 10 | 4720 | 47200 | 10 | 4720 | 47200 | 1 | 4720 | 4720 | 10 | 4720 | 47200 | 5 | 4720 | 23600 | 9 | 5 | 42480 | 23600
367 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)Concrete Pump Hire Charges on Per Day Basis | DAYS | 1 | 11800 | 11800 | 0 | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11800 | 11800
368 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 13 | 424.8 | 5522.4 | 12 | 424.8 | 5097.6 | 1 | 424.8 | 424.8 | 12 | 413 | 4956 | 4 | 496.3 | 1985.21 | 12 | 9 | 5097.6 | 3537.19
369 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 1 | 36.58 | 36.58 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 3.3 | 54.41 | 179.56 | 1 | -2.3 | 36.58 | -142.98
370 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)M.C. SAND | MT | 40 | 1711.5 | 68460 | 0 | 0 | 0 | 4 | 1711.5 | 6846 | 0 | 0 | 0 | 28.145 | 1193.25 | 33584.02 | 36 | 11.855 | 61614 | 34875.98
371 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 8040 | 11 | 88440 | 8040 | 11 | 88440 | 804 | 11 | 8844 | 8040 | 9.53 | 76600 | 3915 | 9.46 | 37038.8 | 7236 | 4125 | 79596 | 51401.2
372 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 150 | 120.74 | 18110.28 | 1 | -149 | 47.2 | -18063.08
373 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)Polythene Sheets | KG | 80 | 82.6 | 6608 | 80 | 82.6 | 6608 | 8 | 82.6 | 660.8 | 80 | 141.6 | 11328 | 30 | 141.6 | 4248 | 72 | 50 | 5947.2 | 2360
374 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)PPC CEMENT | BAG | 220 | 283.59 | 62389.8 | 220 | 283.59 | 62389.8 | 22 | 283.59 | 6238.98 | 220 | 285 | 62701.056 | 150 | 293.64 | 44045.7 | 198 | 70 | 56150.82 | 18344.1
375 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 388 | 7257 | 2815716 | 388 | 7257 | 2815716 | 39 | 7257 | 283023 | 388 | 7199.99 | 2793597.7281 | 389.68 | 7227.54 | 2816428.9 | 349 | -1.68 | 2532693 | -712.9
376 | PILE CAP WITH TIE BEAM : VENI - Embedded Column | 10 | Started | Material | (M)ROLLING BRUSH | NOS | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 1 | 141.6 | 141.6 | 1 | 0 | 141.6 | 0
377 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 148.48 | 82.6 | 12264.45 | 0 | 0 | 0 | 15 | 82.6 | 1239 | 148.48 | 75 | 11136 | 148.48 | 75 | 11136 | 133.48 | 0 | 11025.448 | 1128.448 | SUB -STRUCTURE
378 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 148.48 | 50 | 7424 | 0 | 0 | 0 | 15 | 50 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 133.48 | 148.48 | 6674 | 7424 | SUB -STRUCTURE
379 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)L/C for Board Making | SQM | 90 | 80 | 7200 | 0 | 0 | 0 | 9 | 80 | 720 | 89.619 | 70 | 6273.33 | 89.619 | 70 | 6273.33 | 81 | 0.381 | 6480 | 926.67 | SUB -STRUCTURE
380 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)L/C for Mixing and Pouring M-25 Grade Concrete | CUM | 49.48 | 750 | 37110 | 0 | 0 | 0 | 5 | 750 | 3750 | 49.48 | 1000 | 49480 | 34.048 | 1000 | 34048 | 44.48 | 15.432 | 33360 | 3062 | SUB -STRUCTURE
381 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 5.89 | 6490 | 38226.1 | 0 | 0 | 0 | 1 | 6490 | 6490 | 5.89 | 5800 | 34162 | 4.176 | 5800 | 24220.8 | 4.89 | 1.714 | 31736.1 | 14005.3 | SUB -STRUCTURE
382 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 11.14 | 700 | 7798 | 0 | 0 | 0 | 1 | 700 | 700 | 11.14 | 753.04 | 8388.825 | 10.9145 | 750 | 8185.88 | 10.14 | 0.2255 | 7098 | -387.88 | SUB -STRUCTURE
383 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 380 | 303.86 | 115466.8 | 0 | 0 | 0 | 38 | 303.86 | 11546.68 | 380 | 200 | 76000 | 275.89 | 200 | 55178 | 342 | 104.11 | 103920.12 | 60288.8 | SUB -STRUCTURE
384 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 148.48 | 82.6 | 12264.45 | 0 | 0 | 0 | 15 | 82.6 | 1239 | 148.48 | 50 | 7424 | 143.922 | 50 | 7196.1 | 133.48 | 4.558 | 11025.448 | 5068.348 | SUB -STRUCTURE
385 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)10 MM DIA TMT | MT | 0.046 | 55000 | 2530 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046 | 0.046 | 2530 | 2530 | SUB -STRUCTURE
386 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 37.83 | 1770 | 66959.1 | 37.83 | 1770 | 66959.1 | 4 | 1770 | 7080 | 37.83 | 1501.5 | 56801.745 | 31.287 | 1464.05 | 45805.65 | 33.83 | 6.543 | 59879.1 | 21153.45 | SUB -STRUCTURE
387 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)12 MM DIA TMT | MT | 0.971 | 54500 | 52919.5 | 0.821 | 54500 | 44744.5 | 0 | 54500 | 0 | 0.821 | 54013.09 | 44344.7502 | 0.811 | 54293.01 | 44031.63 | 0.971 | 0.16 | 52919.5 | 8887.87 | SUB -STRUCTURE
388 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)16 MM DIA TMT | MT | 4.009 | 54500 | 218490.5 | 4.009 | 54500 | 218490.5 | 0 | 54500 | 0 | 4.009 | 58381 | 234049.4102 | 4.009 | 58381 | 234049.42 | 4.009 | 0 | 218490.5 | -15558.92 | SUB -STRUCTURE
389 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 0.1 | 50000 | 5000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 5000 | 5000 | SUB -STRUCTURE
390 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 42.5 | 1750 | 74375 | 42.25 | 1750 | 73937.5 | 4 | 1750 | 7000 | 42.25 | 2068.5 | 87394.1208 | 35.283 | 2092.02 | 73812.69 | 38.5 | 7.217 | 67375 | 562.31 | SUB -STRUCTURE
391 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 70.74 | 55.6 | 3933.14 | 70.736 | 55.6 | 3932.92 | 7 | 55.6 | 389.2 | 70.736 | 77.94 | 5513.1638 | 50 | 76.08 | 3803.86 | 63.74 | 20.74 | 3543.944 | 129.284 | SUB -STRUCTURE
392 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)8 MM DIA TMT | MT | 1.55 | 56000.01 | 86800.02 | 1.52 | 56000.01 | 85120.02 | 0 | 56000.01 | 0 | 1.52 | 54634 | 83043.68 | 1.52 | 55271.08 | 84012.04 | 1.55 | 0.03 | 86800.016 | 2787.9755 | SUB -STRUCTURE
393 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 9 | 424.8 | 3823.2 | 9 | 424.8 | 3823.2 | 1 | 424.8 | 424.8 | 9 | 413 | 3717 | 0 | 0 | 0 | 8 | 9 | 3398.4 | 3823.2 | SUB -STRUCTURE
394 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 102 | 36.58 | 3731.16 | 0 | 0 | 0 | 10 | 36.58 | 365.8 | 0 | 0 | 0 | 17.01 | 54.41 | 925.54 | 92 | 84.99 | 3365.36 | 2805.62 | SUB -STRUCTURE
395 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)M.C. SAND | MT | 51.2 | 1711.5 | 87628.8 | 51.2 | 1711.5 | 87628.8 | 5 | 1711.5 | 8557.5 | 51.2 | 1890 | 96768 | 41.096 | 2133.03 | 87659.03 | 46.2 | 10.104 | 79071.3 | -30.23 | SUB -STRUCTURE
396 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 50 | 47.2 | 2360 | 0 | 0 | 0 | 5 | 47.2 | 236 | 0 | 0 | 0 | 50 | 120.74 | 6036.76 | 45 | 0 | 2124 | -3676.76 | SUB -STRUCTURE
397 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 20 | 110 | 2200 | 0 | 0 | 0 | 2 | 110 | 220 | 0 | 0 | 0 | 11 | 141.6 | 1557.6 | 18 | 9 | 1980 | 642.4 | SUB -STRUCTURE
398 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)Polythene Sheets | KG | 22 | 82.6 | 1817.2 | 0 | 0 | 0 | 2 | 82.6 | 165.2 | 0 | 0 | 0 | 10 | 141.6 | 1416 | 20 | 12 | 1652 | 401.2 | SUB -STRUCTURE
399 | PILE CAP WITH TIE BEAM : VENI - Tie Beam | 10 | Started | Material | (M)PPC CEMENT | BAG | 424 | 283.59 | 120242.16 | 424 | 283.59 | 120242.16 | 42 | 283.59 | 11910.78 | 424 | 276.28 | 117143.3472 | 280 | 278.35 | 77939.04 | 382 | 144 | 108331.38 | 42303.12 | SUB -STRUCTURE
400 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)10 MM DIA TMT STAIGHTENING, CUTTING, BENDING, BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
401 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)12 MM DIA TMT STAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 9735 | 9735 | 0 | 0 | 0 | 0 | 9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9735 | 9735
402 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)16 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
403 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)20 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
404 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)200 MM BRICK WORK SUB STRUCTURE | CUM | 1 | 650 | 650 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 650 | 650
405 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)25 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
406 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)8 MM DIA TMT CUTTING, BENDING, BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
407 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 141.6 | 141.6
408 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
409 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 1 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50 | 50
410 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)DISPOSAL OF EARTH WITHIN PROJECT SITE, MORE THAN 50'0" LEAD | CUM | 1 | 90 | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 90 | 90
411 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY AND ALLOWED TO TAKE OU | CUM | 1 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 65 | 65
412 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY AND RETAINED AT SITE | CUM | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
413 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)MANUAL EXCAVATION | CUM | 1 | 206.5 | 206.5 | 0 | 0 | 0 | 0 | 206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 206.5 | 206.5
414 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
415 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 700 | 700
416 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 118
417 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 40 | 40
418 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)PILE HEAD DISMENTLING | RMT | 1 | 500 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 500 | 500
419 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 1 | 295 | 295 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 295 | 295
420 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Labour | (L)VAPOUR BARRIER | SQM | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
421 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)1.5" NAIL | KG | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
422 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)10 MM DIA TMT | MT | 1 | 55000 | 55000 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 55000 | 55000
423 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)10 MM STONE CHIPS. | MT | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1770 | 1770
424 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)12 MM DIA TMT | MT | 1 | 54500 | 54500 | 0.08 | 54500 | 4360 | 0 | 54500 | 0 | 0.08 | 54014.5 | 4321.16 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
425 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)12 MM PLY | NOS | 1 | 48 | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 48 | 48
426 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)16 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
427 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)2" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
428 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)20 GAUGE BINDING WIRE | KG | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
429 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)20 MM DIA TMT. | MT | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50000 | 50000
430 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)20 MM STONE CHIPS. | MT | 1 | 1750 | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1750 | 1750
431 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)22 GAUGE BINDING WIRE | KG | 1 | 55.6 | 55.6 | 0 | 0 | 0 | 0 | 55.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 55.6 | 55.6
432 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)25 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
433 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)2ND CLASS BRICKS | NOS | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 10 | 10
434 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)3" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
435 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 430 | 430 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 430 | 430
436 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)3'' X 2'' X 4'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 330 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 330 | 330
437 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)4" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
438 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)8 MM DIA TMT | MT | 1 | 56000.01 | 56000.01 | 0 | 0 | 0 | 0 | 56000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 56000.01 | 56000.01
439 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)HIND PLAST SUPER 160 | KG | 1 | 36.58 | 36.58 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 36.58 | 36.58
440 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1711.5 | 1711.5
441 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)PICKED JHAMA. | NOS | 1 | 11 | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11 | 11
442 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)PLY SHUTTERING OIL | LTR | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
443 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)POLYTHENE SHEET | KG | 1 | 110 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 110 | 110
444 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 283.59 | 283.59
445 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)SHUTTERING GREASE | KG | 1 | 78 | 78 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 78 | 78
446 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)SIKAMENT 2003 NS | NOS | 1 | 49.56 | 49.56 | 0 | 0 | 0 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 49.56 | 49.56
447 | PILE CAP WITH TIE BEAM : ANUPA - Embedded Column | 0 | Tentative | Material | (M)SILVER SAND | CFT | 1 | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 25 | 25
448 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)10 MM DIA TMT STAIGHTENING, CUTTING, BENDING, BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
449 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)12 MM DIA TMT STAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 9735 | 9735 | 0 | 0 | 0 | 0 | 9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9735 | 9735
450 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)16 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
451 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)20 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
452 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)200 MM BRICK WORK SUB STRUCTURE | CUM | 1 | 650 | 650 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 650 | 650
453 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)25 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
454 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)8 MM DIA TMT CUTTING, BENDING, BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8250 | 8250
455 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 141.6 | 141.6
456 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
457 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 1 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50 | 50
458 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)DISPOSAL OF EARTH WITHIN PROJECT SITE, MORE THAN 50'0" LEAD | CUM | 1 | 90 | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 90 | 90
459 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY AND ALLOWED TO TAKE OU | CUM | 1 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 65 | 65
460 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY AND RETAINED AT SITE | CUM | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
461 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)MANUAL EXCAVATION | CUM | 1 | 206.5 | 206.5 | 0 | 0 | 0 | 0 | 206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 206.5 | 206.5
462 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
463 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 700 | 700
464 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 118
465 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 40 | 40
466 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)PILE HEAD DISMENTLING | RMT | 1 | 500 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 500 | 500
467 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 1 | 295 | 295 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 295 | 295
468 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Labour | (L)VAPOUR BARRIER | SQM | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
469 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)1.5" NAIL | KG | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
470 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)10 MM DIA TMT | MT | 1 | 55000 | 55000 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 55000 | 55000
471 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)10 MM STONE CHIPS. | MT | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1770 | 1770
472 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)12 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
473 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)12 MM PLY | NOS | 1 | 48 | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 48 | 48
474 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)16 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
475 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)2" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
476 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)20 GAUGE BINDING WIRE | KG | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
477 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)20 MM DIA TMT. | MT | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50000 | 50000
478 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)20 MM STONE CHIPS. | MT | 1 | 1750 | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1750 | 1750
479 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)22 GAUGE BINDING WIRE | KG | 1 | 55.6 | 55.6 | 0 | 0 | 0 | 0 | 55.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 55.6 | 55.6
480 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)25 MM DIA TMT | MT | 1 | 54500 | 54500 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 54500 | 54500
481 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)2ND CLASS BRICKS | NOS | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 10 | 10
482 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)3" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
483 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 430 | 430 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 430 | 430
484 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)3'' X 2'' X 4'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 1 | 330 | 330 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 330 | 330
485 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)4" NAIL | KG | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 51 | 51
486 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)8 MM DIA TMT | MT | 1 | 56000.01 | 56000.01 | 0 | 0 | 0 | 0 | 56000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 56000.01 | 56000.01
487 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)HIND PLAST SUPER 160 | KG | 1 | 36.58 | 36.58 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 36.58 | 36.58
488 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1711.5 | 1711.5
489 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)PICKED JHAMA. | NOS | 1 | 11 | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11 | 11
490 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)PLY SHUTTERING OIL | LTR | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
491 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)POLYTHENE SHEET | KG | 1 | 110 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 110 | 110
492 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 283.59 | 283.59
493 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)SHUTTERING GREASE | KG | 1 | 78 | 78 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 78 | 78
494 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)SIKAMENT 2003 NS | NOS | 1 | 49.56 | 49.56 | 0 | 0 | 0 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 49.56 | 49.56
495 | PILE CAP WITH TIE BEAM : PODIUM - Embedded Column | 0 | Tentative | Material | (M)SILVER SAND | CFT | 1 | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 25 | 25
496 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)L/C for M-25 Grade Concreting in RCC Walls & Col.(1L) | CUM | 72 | 300 | 21600 | 0 | 0 | 0 | 7 | 300 | 2100 | 70.26 | 300 | 21078 | 70.26 | 300 | 21078 | 65 | 1.74 | 19500 | 522
497 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)L/C for staging with Cup-Lock for Col. & Lift | CUM | 250 | 33.04 | 8260 | 0 | 0 | 0 | 25 | 33.04 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 250 | 7434 | 8260
498 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)L/C for staging with MS Pipe for Col & RCC Wall Support | CUM | 100 | 35.4 | 3540 | 0 | 0 | 0 | 10 | 35.4 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 100 | 3186 | 3540
499 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)L/C for Tie Rod Hole filling in Columns | NOS | 1600 | 6.5 | 10400 | 0 | 0 | 0 | 160 | 6.5 | 1040 | 1597 | 5.5 | 8783.5 | 1597 | 5.5 | 8783.5 | 1440 | 3 | 9360 | 1616.5
500 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)Labour Charges for Column/Wall Starter Making | RMT | 285 | 66.08 | 18832.8 | 0 | 0 | 0 | 29 | 66.08 | 1916.32 | 285 | 56 | 15960 | 285 | 56 | 15960 | 256 | 0 | 16916.48 | 2872.8
501 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 11.78 | 6490 | 76452.2 | 0 | 0 | 0 | 1 | 6490 | 6490 | 11.6381 | 5500 | 64009.55 | 11.6381 | 5500 | 64009.55 | 10.78 | 0.1419 | 69962.2 | 12442.65
502 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)REMOVAL & REBINDING OF REINFORCEMENT | MT | 1 | 4860 | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4860 | 4860
503 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 563 | 303.86 | 171073.18 | 0 | 0 | 0 | 56 | 303.86 | 17016.16 | 561.87 | 257.5 | 144681.525 | 561.87 | 257.5 | 144681.53 | 507 | 1.13 | 154057.02 | 26391.65
504 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 20 | 802.4 | 16048 | 0 | 0 | 0 | 2 | 802.4 | 1604.8 | 17.595 | 680 | 11964.6 | 17.595 | 680 | 11964.6 | 18 | 2.405 | 14443.2 | 4083.4
505 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 250 | 535 | 133750 | 0 | 0 | 0 | 25 | 535 | 13375 | 248.15 | 535 | 132760.25 | 248.15 | 535 | 132760.25 | 225 | 1.85 | 120375 | 989.75
506 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)10 MM DIA TMT | MT | 0.2 | 55000 | 11000 | 0.2 | 55000 | 11000 | 0 | 55000 | 0 | 0.2 | 54014.52 | 10802.904 | 0.2 | 54519.1 | 10903.82 | 0.2 | 0 | 11000 | 96.18
507 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 0.7 | 1770 | 1239 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 3.447 | 1516.28 | 5226.61 | 0.7 | -2.747 | 1239 | -3987.61
508 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)12 MM DIA TMT | MT | 0.325 | 54500 | 17712.5 | 0.245 | 54500 | 13352.5 | 0 | 54500 | 0 | 0.245 | 54604.5 | 13378.1036 | 0.245 | 54014.49 | 13233.55 | 0.325 | 0.08 | 17712.5 | 4478.95
509 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)16 MM DIA TMT | MT | 1.032 | 54500 | 56244 | 1.032 | 54500 | 56244 | 0 | 54500 | 0 | 1.032 | 55460 | 57234.72 | 1.032 | 55237.57 | 57005.17 | 1.032 | 0 | 56244 | -761.17
510 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 3.31 | 50000 | 165500 | 3.23 | 50000 | 161500 | 0 | 50000 | 0 | 3.23 | 54604.5 | 176372.535 | 3.23 | 55239.36 | 178423.12 | 3.31 | 0.08 | 165500 | -12923.12
511 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 1 | 1750 | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 8.399 | 2046.46 | 17188.25 | 1 | -7.399 | 1750 | -15438.25
512 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 83 | 55.6 | 4614.8 | 0 | 0 | 0 | 8 | 55.6 | 444.8 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 83 | 4170 | 4614.8
513 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 1378 | 10 | 13780 | 0 | 0 | 0 | 138 | 10 | 1380 | 0 | 0 | 0 | 867 | 9.82 | 8515.17 | 1240 | 511 | 12400 | 5264.83
514 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)8 MM DIA TMT | MT | 2.735 | 56000.01 | 153160.03 | 2.735 | 56000.01 | 153160.03 | 0 | 56000.01 | 0 | 2.735 | 56211.15 | 153737.485 | 2.735 | 56920.65 | 155677.98 | 2.735 | 0 | 153160.027 | -2517.9526
515 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)CEBEX - 100 | PKT | 10 | 59 | 590 | 10 | 59 | 590 | 1 | 59 | 59 | 10 | 76.11 | 761.1 | 10 | 76.11 | 761.1 | 9 | 0 | 531 | -171.1
516 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 14 | 424.8 | 5947.2 | 14 | 424.8 | 5947.2 | 1 | 424.8 | 424.8 | 14 | 501.5 | 7020.96 | 10 | 485.54 | 4855.42 | 13 | 4 | 5522.4 | 1091.78
517 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 87 | 36.58 | 3182.46 | 0 | 0 | 0 | 9 | 36.58 | 329.22 | 0 | 0 | 0 | 18.2 | 55.36 | 1007.47 | 78 | 68.8 | 2853.24 | 2174.99
518 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)M.C. SAND | MT | 2.1 | 1711.5 | 3594.15 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 7.569 | 1688.15 | 12777.64 | 2.1 | -5.469 | 3594.15 | -9183.49
519 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 100 | 283.59 | 28359 | 0 | 0 | 0 | 10 | 283.59 | 2835.9 | 0 | 0 | 0 | 73 | 319.89 | 23352.2 | 90 | 27 | 25523.1 | 5006.8
520 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 36.766 | 7257 | 266810.86 | 36.337 | 7257 | 263697.61 | 4 | 7257 | 29028 | 36.337 | 7239.65 | 263067.2618 | 35.142 | 7239.62 | 254414.57 | 32.766 | 1.624 | 237782.862 | 12396.292
521 | PILE CAP TO GR. FL. : PRAYAG - Grid Column Work | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 40 | 78 | 3120 | 0 | 0 | 0 | 4 | 78 | 312 | 0 | 0 | 0 | 30 | 155.76 | 4672.8 | 36 | 10 | 2808 | -1552.8
522 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)375 MM / 250 MM / 200 MM TH. BRICK WORK | CUM | 116.576 | 700 | 81603.2 | 0 | 0 | 0 | 12 | 700 | 8400 | 81.576 | 700 | 57103.2 | 37.562 | 700 | 26293.4 | 104.576 | 79.014 | 73203.2 | 55309.8
523 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 120 | 50 | 6000 | 0 | 0 | 0 | 12 | 50 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 120 | 5400 | 6000
524 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)CHIPPER (12 HRS) | NOS | 20 | 700 | 14000 | 0 | 0 | 0 | 2 | 700 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 12600 | 14000
525 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 14 | 700 | 9800 | 0 | 0 | 0 | 1 | 700 | 700 | 4.9 | 750 | 3675 | 4.9 | 750 | 3675 | 13 | 9.1 | 9100 | 6125
526 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
527 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
528 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 120 | 82.6 | 9912 | 0 | 0 | 0 | 12 | 82.6 | 991.2 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 120 | 8920.8 | 9912
529 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 1.059 | 1750 | 1853.25 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 1.059 | 2171.79 | 2299.93 | 1.059 | 0 | 1853.25 | -446.68
530 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 20000 | 10 | 200000 | 20000 | 10 | 200000 | 2000 | 10 | 20000 | 20000 | 9.63 | 192640 | 17308 | 9.53 | 165000.52 | 18000 | 2692 | 180000 | 34999.48
531 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Material | (M)ANTI TERMITE | LTR | 10 | 4720 | 47200 | 10 | 4720 | 47200 | 1 | 4720 | 4720 | 10 | 4720 | 47200 | 0 | 0 | 0 | 9 | 10 | 42480 | 47200
532 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 32.032 | 1700.39 | 54466.97 | 1 | -31.032 | 1711.5 | -52755.47
533 | PILE CAP TO GR. FL. : PRAYAG - Masonry up to Plinth | 10 | Started | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 97 | 294.42 | 28558.61 | 1 | -96 | 283.59 | -28275.02
534 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)L/C for Board Making | SQM | 120 | 80 | 9600 | 0 | 0 | 0 | 12 | 80 | 960 | 120 | 70 | 8400 | 120 | 70 | 8400 | 108 | 0 | 8640 | 1200
535 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)L/C for M-25 Grade Concreting in RCC Walls & Col.(1L) | CUM | 81.32 | 300 | 24396 | 0 | 0 | 0 | 8 | 300 | 2400 | 69.195 | 300 | 20758.5 | 69.195 | 300 | 20758.5 | 73.32 | 12.125 | 21996 | 3637.5
536 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)L/C for mixing & pouring M25 Gr. Conc. (RMC w/ head load) | CUM | 50 | 531 | 26550 | 0 | 0 | 0 | 5 | 531 | 2655 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 23895 | 26550
537 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)L/C for Mixing and Pouring M-25 Grade Concrete | CUM | 20 | 750 | 15000 | 0 | 0 | 0 | 2 | 750 | 1500 | 20 | 1000 | 20000 | 2.333 | 1000 | 2333 | 18 | 17.667 | 13500 | 12667
538 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)L/C for staging with Cup-Lock for Col. & Lift | CUM | 250 | 33.04 | 8260 | 0 | 0 | 0 | 25 | 33.04 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 250 | 7434 | 8260
539 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)L/C for staging with MS Pipe for Col & RCC Wall Support | CUM | 100 | 35.4 | 3540 | 0 | 0 | 0 | 10 | 35.4 | 354 | 99.999 | 30 | 2999.97 | 99.999 | 30 | 2999.97 | 90 | 0.001 | 3186 | 540.03
540 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)Labour Charges for Column/Wall Starter Making | RMT | 310 | 66.08 | 20484.8 | 0 | 0 | 0 | 31 | 66.08 | 2048.48 | 310 | 56 | 17360 | 244.398 | 56 | 13686.29 | 279 | 65.602 | 18436.32 | 6798.51
541 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 20.267 | 6490 | 131532.83 | 0 | 0 | 0 | 2 | 6490 | 12980 | 20.267 | 5800 | 117548.6 | 19.8845 | 5800 | 115330.1 | 18.267 | 0.3825 | 118552.83 | 16202.73
542 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)Making of Wailer (H-Sec.) by MS Hollow Sq. Bar (2"X2") | NOS | 80 | 94.4 | 7552 | 0 | 0 | 0 | 8 | 94.4 | 755.2 | 80 | 121.25 | 9699.6 | 80 | 121.25 | 9699.6 | 72 | 0 | 6796.8 | -2147.6
543 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 724 | 303.86 | 219994.64 | 0 | 0 | 0 | 72 | 303.86 | 21877.92 | 724 | 200 | 144800 | 574.32 | 200 | 114864 | 652 | 149.68 | 198116.72 | 105130.64
544 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 15 | 885 | 13275 | 0 | 0 | 0 | 2 | 885 | 1770 | 15 | 870 | 13050 | 0 | 0 | 0 | 13 | 15 | 11505 | 13275
545 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 60 | 535 | 32100 | 0 | 0 | 0 | 6 | 535 | 3210 | 60 | 580 | 34800 | 0 | 0 | 0 | 54 | 60 | 28890 | 32100
546 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)1.5" NAIL | KG | 250 | 100 | 25000 | 250 | 100 | 25000 | 25 | 100 | 2500 | 250 | 80.99 | 20246.5 | 40 | 79.37 | 3174.8 | 225 | 210 | 22500 | 21825.2
547 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)10 MM DIA TMT | MT | 0.381 | 55000 | 20955 | 0.081 | 55000 | 4455 | 0 | 55000 | 0 | 0.081 | 58380.94 | 4728.8563 | 0.081 | 58380.99 | 4728.86 | 0.381 | 0.3 | 20955 | 16226.14
548 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 2 | 1770 | 3540 | 2 | 1770 | 3540 | 0 | 1770 | 0 | 2 | 1501.5 | 3003 | 5.812 | 1458.47 | 8476.62 | 2 | -3.812 | 3540 | -4936.62
549 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)12 MM DIA TMT | MT | 2 | 54500 | 109000 | 2 | 54500 | 109000 | 0 | 54500 | 0 | 2 | 53395 | 106790 | 2 | 53683.53 | 107367.05 | 2 | 0 | 109000 | 1632.95
550 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)16 MM DIA TMT | MT | 3.267 | 54500 | 178051.5 | 3.267 | 54500 | 178051.5 | 0 | 54500 | 0 | 3.267 | 53802.49 | 175772.7339 | 3.267 | 53811.35 | 175801.68 | 3.267 | 0 | 178051.5 | 2249.82
551 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 10.2 | 50000 | 510000 | 10.2 | 50000 | 510000 | 1 | 50000 | 50000 | 10.2 | 53492.76 | 545626.1992 | 10.2 | 53468.23 | 545375.92 | 9.2 | 0 | 460000 | -35375.92
552 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 3 | 1750 | 5250 | 3 | 1750 | 5250 | 0 | 1750 | 0 | 3 | 2068.5 | 6205.5 | 6.402 | 2061.75 | 13199.34 | 3 | -3.402 | 5250 | -7949.34
553 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 253.528 | 55.6 | 14096.16 | 253.528 | 55.6 | 14096.16 | 25 | 55.6 | 1390 | 253.528 | 77.94 | 19759.9723 | 75 | 75.92 | 5693.81 | 228.528 | 178.528 | 12706.157 | 8402.3468
554 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR) | NOS | 14 | 118 | 1652 | 0 | 0 | 0 | 1 | 118 | 118 | 0 | 0 | 0 | 14 | 83.98 | 1175.7 | 13 | 0 | 1534 | 476.3
555 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)25 MM DIA TMT | MT | 1 | 54500 | 54500 | 0.5 | 54500 | 27250 | 0 | 54500 | 0 | 0.5 | 53395 | 26697.5 | 0.5 | 53395 | 26697.5 | 1 | 0.5 | 54500 | 27802.5
556 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 130 | 82.6 | 10738 | 130 | 82.6 | 10738 | 13 | 82.6 | 1073.8 | 130 | 69.62 | 9050.6 | 59 | 69.62 | 4107.58 | 117 | 71 | 9664.2 | 6630.42
557 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)3" NAIL | KG | 150 | 51 | 7650 | 150 | 51 | 7650 | 15 | 51 | 765 | 150 | 76.94 | 11541 | 175 | 81.63 | 14284.7 | 135 | -25 | 6885 | -6634.7
558 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 2050 | 3.06 | 6273 | 2050 | 3.06 | 6273 | 205 | 3.06 | 627.3 | 2050 | 3.56 | 7287.75 | 2050 | 3.48 | 7142.88 | 1845 | 0 | 5645.7 | -869.88
559 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)4" NAIL | KG | 100 | 51 | 5100 | 100 | 51 | 5100 | 10 | 51 | 510 | 100 | 76.24 | 7624 | 110 | 80.9 | 8898.55 | 90 | -10 | 4590 | -3798.55
560 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)50mm x 50mm x 3mm MS tube (each 6m long) | KG | 950 | 76.7 | 72865 | 920 | 76.7 | 70564 | 95 | 76.7 | 7286.5 | 920 | 81.73 | 75191.6 | 920 | 81.03 | 74551.37 | 855 | 30 | 65578.5 | -1686.37
561 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)8 MM DIA TMT | MT | 7 | 56000.01 | 392000.07 | 7 | 56000.01 | 392000.07 | 1 | 56000.01 | 56000.01 | 7 | 55165 | 386155 | 7 | 55271.08 | 386897.57 | 6 | 0 | 336000.06 | 5102.5
562 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 10 | 460.2 | 4602 | 10 | 460.2 | 4602 | 1 | 460.2 | 460.2 | 10 | 466.1 | 4661 | 0 | 0 | 0 | 9 | 10 | 4141.8 | 4602
563 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 9 | 424.8 | 3823.2 | 9 | 424.8 | 3823.2 | 1 | 424.8 | 424.8 | 9 | 413 | 3717 | 1 | 413 | 413 | 8 | 8 | 3398.4 | 3410.2
564 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 8.4 | 36.58 | 307.27 | 0 | 0 | 0 | 1 | 36.58 | 36.58 | 0 | 0 | 0 | 2.1 | 54.41 | 114.26 | 7.4 | 6.3 | 270.692 | 193.012
565 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)M.C. SAND | MT | 2.176 | 1711.5 | 3724.22 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 7.898 | 1807.21 | 14273.31 | 2.176 | -5.722 | 3724.224 | -10549.086
566 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)PIPE SLEEVE WRAPPING FOAM | MTR | 30 | 1 | 30 | 0 | 0 | 0 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 30 | 27 | 30
567 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 100 | 47.2 | 4720 | 100 | 47.2 | 4720 | 10 | 47.2 | 472 | 100 | 89.68 | 8968 | 150 | 120.74 | 18110.28 | 90 | -50 | 4248 | -13390.28
568 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 24 | 283.59 | 6806.16 | 24 | 283.59 | 6806.16 | 2 | 283.59 | 567.18 | 24 | 285 | 6840.1152 | 60 | 278.18 | 16690.6 | 22 | -36 | 6238.98 | -9884.44
569 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 82.5 | 7257 | 598702.5 | 82.5 | 7257 | 598702.5 | 8 | 7257 | 58056 | 82.5 | 7199.99 | 593999.5134 | 76.879 | 7270.16 | 558922.84 | 74.5 | 5.621 | 540646.5 | 39779.66
570 | PILE CAP TO GR. FL. : VENI - Grid Column Work | 10 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 18 | 82.6 | 1486.8 | 0 | 0 | 0 | 2 | 82.6 | 165.2 | 0 | 0 | 0 | 18 | 82.6 | 1486.8 | 16 | 0 | 1321.6 | 0
571 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)8MM REBAR ANCHORING & CHEM. GROUTING | NOS | 650 | 64.9 | 42185 | 0 | 0 | 0 | 65 | 64.9 | 4218.5 | 650 | 64.9 | 42185 | 600 | 64.9 | 38940 | 585 | 50 | 37966.5 | 3245 | SUPER STRUCTURE
572 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 9 | 90.1 | 810.9 | 90 | 90.1 | 8109 | 90 | 90.1 | 8109 | 81 | 0 | 7298.1 | 0 | SUPER STRUCTURE
573 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Joint Pin 0.280 Mtr | NOS | 3600 | 0.24 | 864 | 0 | 0 | 0 | 360 | 0.24 | 86.4 | 0 | 0 | 0 | 0 | 0 | 0 | 3240 | 3600 | 777.6 | 864 | SUPER STRUCTURE
574 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP-01 (PRAYAG) | SQM | 3910 | 227.9 | 891089 | 0 | 0 | 0 | 391 | 227.9 | 89108.9 | 3910 | 227.9 | 891089 | 3849.53 | 227.9 | 877307.89 | 3519 | 60.47 | 801980.1 | 13781.11 | SUPER STRUCTURE
575 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Alu. Panel Joint Pin hole Making (TYP-01 PRAYAG) | NOS | 4000 | 21.2 | 84800 | 0 | 0 | 0 | 400 | 21.2 | 8480 | 4000 | 21.2 | 84800 | 4000 | 21.2 | 84800 | 3600 | 0 | 76320 | 0 | SUPER STRUCTURE
576 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 1200 | 8 | 9600 | 0 | 0 | 0 | 120 | 8 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1200 | 8640 | 9600 | SUPER STRUCTURE
577 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
578 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 110 | 129.8 | 14278 | 0 | 0 | 0 | 11 | 129.8 | 1427.8 | 110 | 100.3 | 11033 | 58.5 | 100.3 | 5867.56 | 99 | 51.5 | 12850.2 | 8410.44 | SUPER STRUCTURE
579 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Fixing Grooves at Kitchen, Toilet, Balcony | LS | 1 | 38940 | 38940 | 0 | 0 | 0 | 0 | 38940 | 0 | 1 | 38940 | 38940 | 1 | 38940 | 38940 | 1 | 0 | 38940 | 0 | SUPER STRUCTURE
580 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 8000 | 5.5 | 44000 | 0 | 0 | 0 | 800 | 5.5 | 4400 | 6484 | 5.5 | 35662 | 6484 | 5.5 | 35662 | 7200 | 1516 | 39600 | 8338 | SUPER STRUCTURE
581 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Manual Lifting of Steel (TYP-01 PRAYAG) | MT | 40.82 | 212 | 8653.84 | 0 | 0 | 0 | 4 | 212 | 848 | 40.82 | 212 | 8653.84 | 40.507 | 212 | 8587.48 | 36.82 | 0.313 | 7805.84 | 66.36 | SUPER STRUCTURE
582 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Manual Lifting of Steel (TYP-02 PRAYAG) | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
583 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Manual Lifting of Steel (TYP-03 PRAYAG) | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
584 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-01 (PRAYAG) | FLOOR | 1 | 19500 | 19500 | 0 | 0 | 0 | 0 | 19500 | 0 | 1 | 19500 | 19500 | 1 | 19500 | 19500 | 1 | 0 | 19500 | 0 | SUPER STRUCTURE
585 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 40.82 | 11007.04 | 449307.37 | 0 | 0 | 0 | 4 | 11007.04 | 44028.16 | 40.82 | 9328 | 380768.96 | 40.507 | 9328 | 377849.3 | 36.82 | 0.313 | 405279.213 | 71458.0728 | SUPER STRUCTURE
586 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 348 | 177 | 61596 | 0 | 0 | 0 | 35 | 177 | 6195 | 338 | 150 | 50700 | 338 | 150 | 50700 | 313 | 10 | 55401 | 10896 | SUPER STRUCTURE
587 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 9 | 62.54 | 562.86 | 94 | 53 | 4982 | 83 | 53 | 4399 | 85 | 11 | 5315.9 | 1479.76 | SUPER STRUCTURE
588 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 7 | 22.52 | 157.64 | 65 | 19.08 | 1240.2 | 64 | 19.08 | 1221.12 | 58 | 1 | 1306.16 | 242.68 | SUPER STRUCTURE
589 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 120 | 18.76 | 2251.2 | 1200 | 15.9 | 19080 | 0 | 0 | 0 | 1080 | 1200 | 20260.8 | 22512 | SUPER STRUCTURE
590 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Shifting Charges for MIVAN from Yard to T-1 (Prayag) | LS | 1 | 236000 | 236000 | 0 | 0 | 0 | 0 | 236000 | 0 | 1 | 200000 | 200000 | 1 | 200000 | 200000 | 1 | 0 | 236000 | 36000 | SUPER STRUCTURE
591 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Supply of Plumber on Daily Basis | NOS | 60 | 826 | 49560 | 0 | 0 | 0 | 6 | 826 | 4956 | 60 | 826 | 49560 | 15 | 826 | 12390 | 54 | 45 | 44604 | 37170 | SUPER STRUCTURE
592 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 60 | 590 | 35400 | 0 | 0 | 0 | 6 | 590 | 3540 | 60 | 590 | 35400 | 0 | 0 | 0 | 54 | 60 | 31860 | 35400 | SUPER STRUCTURE
593 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 28 | 802.4 | 22467.2 | 0 | 0 | 0 | 3 | 802.4 | 2407.2 | 28 | 750 | 21000 | 28 | 750 | 21000 | 25 | 0 | 20060 | 1467.2 | SUPER STRUCTURE
594 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 326.58 | 535 | 174720.3 | 0 | 0 | 0 | 33 | 535 | 17655 | 326.58 | 535 | 174720.3 | 326.58 | 535 | 174720.3 | 293.58 | 0 | 157065.3 | 0 | SUPER STRUCTURE
595 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 6 | 53.78 | 322.68 | 60 | 45.58 | 2734.8 | 60 | 45.58 | 2734.8 | 54 | 0 | 2904.12 | 492 | SUPER STRUCTURE
596 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)Tie Rod Hole making in Alu. Plate for TYP-01 (PRAYAG) | NOS | 300 | 50.04 | 15012 | 0 | 0 | 0 | 30 | 50.04 | 1501.2 | 300 | 42.4 | 12720 | 263 | 42.4 | 11151.2 | 270 | 37 | 13510.8 | 3860.8 | SUPER STRUCTURE
597 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)TRANSPORTATION CHARGES | NOS | 1020 | 25.96 | 26479.2 | 0 | 0 | 0 | 102 | 25.96 | 2647.92 | 1000 | 35 | 35000 | 1000 | 35 | 35000 | 918 | 20 | 23831.28 | -8520.8 | SUPER STRUCTURE
598 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 4 | 100.06 | 400.24 | 44 | 84.8 | 3731.2 | 44 | 84.8 | 3731.2 | 40 | 0 | 4002.4 | 671.44 | SUPER STRUCTURE
599 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Labour | (L)WOODEN KICKER FIXING | SQM | 19.2 | 87.56 | 1681.15 | 0 | 0 | 0 | 2 | 87.56 | 175.12 | 19.2 | 74.2 | 1424.64 | 19.09 | 74.2 | 1416.48 | 17.2 | 0.11 | 1506.032 | 264.672 | SUPER STRUCTURE
600 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)10 MM DIA TMT | MT | 4.155 | 55000 | 228525 | 4.15 | 55000 | 228250 | 0 | 55000 | 0 | 4.15 | 54329.39 | 225466.9841 | 3.872 | 54540.58 | 211181.14 | 4.155 | 0.283 | 228525 | 17343.86 | SUPER STRUCTURE
601 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 286 | 1770 | 506220 | 29 | 1770 | 51330 | 286 | 1543.5 | 441441 | 0.772 | 1384.16 | 1068.57 | 257 | 285.228 | 454890 | 505151.43 | SUPER STRUCTURE
602 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)12 MM DIA TMT | MT | 2.97 | 54500 | 161865 | 2.97 | 54500 | 161865 | 0 | 54500 | 0 | 2.97 | 53954.91 | 160246.07 | 2.97 | 53812.43 | 159822.93 | 2.97 | 0 | 161865 | 2042.07 | SUPER STRUCTURE
603 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.55 | 82.6 | 7314.23 | 88.55 | 82.6 | 7314.23 | 9 | 82.6 | 743.4 | 88.55 | 78.94 | 6990.137 | 70 | 78.38 | 5486.91 | 79.55 | 18.55 | 6570.83 | 1827.32 | SUPER STRUCTURE
604 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)16 MM DIA TMT | MT | 8.684 | 54500 | 473278 | 8.664 | 54500 | 472188 | 1 | 54500 | 54500 | 8.664 | 53930.64 | 467255.0409 | 8.664 | 53658.03 | 464893.17 | 7.684 | 0.02 | 418778 | 8384.83 | SUPER STRUCTURE
605 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)20 mm concrete cover block | NOS | 20000 | 1.78 | 35600 | 20000 | 1.78 | 35600 | 2000 | 1.78 | 3560 | 20000 | 1.18 | 23600 | 4500 | 1.18 | 5310 | 18000 | 15500 | 32040 | 30290 | SUPER STRUCTURE
606 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 7.888 | 50000 | 394400 | 7.888 | 50000 | 394400 | 1 | 50000 | 50000 | 7.888 | 53270.45 | 420197.3195 | 6.711 | 53459.55 | 358767.04 | 6.888 | 1.177 | 344400 | 35632.96 | SUPER STRUCTURE
607 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 10000 | 2.24 | 22400 | 9500 | 2.24 | 21280 | 1000 | 2.24 | 2240 | 9500 | 2.12 | 20178 | 0 | 0 | 0 | 9000 | 10000 | 20160 | 22400 | SUPER STRUCTURE
608 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 1000 | 55.6 | 55600 | 1000 | 55.6 | 55600 | 100 | 55.6 | 5560 | 1000 | 75.52 | 75520 | 0 | 0 | 0 | 900 | 1000 | 50040 | 55600 | SUPER STRUCTURE
609 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR LONG) | MTR | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 2 | 23.6 | 47.2 | 18 | 27 | 486 | 40 | 26.48 | 1059.08 | 16 | -22 | 377.6 | -634.28 | SUPER STRUCTURE
610 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)25 MM DIA TMT | MT | 0.266 | 54500 | 14497 | 0.121 | 54500 | 6594.5 | 0 | 54500 | 0 | 0.121 | 50503.99 | 6110.9829 | 0 | 0 | 0 | 0.266 | 0.266 | 14497 | 14497 | SUPER STRUCTURE
611 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 3 | 82.6 | 247.8 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 22 | 25 | 1817.2 | 2065 | SUPER STRUCTURE
612 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 144 | 10 | 1440 | 0 | 0 | 0 | 14 | 10 | 140 | 0 | 0 | 0 | 144 | 9 | 1296 | 130 | 0 | 1300 | 144 | SUPER STRUCTURE
613 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 4000 | 3.06 | 12240 | 4000 | 3.06 | 12240 | 400 | 3.06 | 1224 | 4000 | 3.01 | 12036 | 1000 | 3.01 | 3009 | 3600 | 3000 | 11016 | 9231 | SUPER STRUCTURE
614 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)32 MM ID PPR PIPE 3 MTR LENGHT | NOS | 18 | 365.8 | 6584.4 | 0 | 0 | 0 | 2 | 365.8 | 731.6 | 0 | 0 | 0 | 20 | 369.89 | 7397.84 | 16 | -2 | 5852.8 | -813.44 | SUPER STRUCTURE
615 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 2 | 23.6 | 47.2 | 0 | 0 | 0 | 18 | 22.38 | 402.83 | 16 | 0 | 377.6 | 21.97 | SUPER STRUCTURE
616 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 2 | 47.2 | 94.4 | 0 | 0 | 0 | 18 | 45.6 | 820.86 | 16 | 0 | 755.2 | 28.74 | SUPER STRUCTURE
617 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 7500 | 5.32 | 39900 | 7500 | 5.32 | 39900 | 750 | 5.32 | 3990 | 7500 | 3.89 | 29205 | 0 | 0 | 0 | 6750 | 7500 | 35910 | 39900 | SUPER STRUCTURE
618 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)6 MM DRILL BIT | NOS | 100 | 82.6 | 8260 | 100 | 82.6 | 8260 | 10 | 82.6 | 826 | 100 | 70.21 | 7021 | 45 | 70.21 | 3159.45 | 90 | 55 | 7434 | 5100.55 | SUPER STRUCTURE
619 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)6 X 75MM BOLT, NUT & WASHER . | NOS | 3000 | 11.8 | 35400 | 3000 | 11.8 | 35400 | 300 | 11.8 | 3540 | 3000 | 6.25 | 18762 | 550 | 6.16 | 3389.98 | 2700 | 2450 | 31860 | 32010.02 | SUPER STRUCTURE
620 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)8 MM DIA TMT | MT | 20.689 | 56000.01 | 1158584.21 | 20.616 | 56000.01 | 1154496.21 | 2 | 56000.01 | 112000.02 | 20.616 | 56024.8 | 1155007.3575 | 19.82 | 56075.76 | 1111421.49 | 18.689 | 0.869 | 1046584.187 | 47162.7169 | SUPER STRUCTURE
621 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)ALMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN) | NOS | 200 | 115 | 23000 | 200 | 115 | 23000 | 20 | 115 | 2300 | 200 | 174.64 | 34928 | 200 | 174.09 | 34818.86 | 180 | 0 | 20700 | -11818.86 | SUPER STRUCTURE
622 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)AT-NANO PUMP (200 GMS) | PKT | 200 | 129.8 | 25960 | 200 | 129.8 | 25960 | 20 | 129.8 | 2596 | 200 | 180.54 | 36108 | 200 | 179.99 | 35998.26 | 180 | 0 | 23364 | -10038.26 | SUPER STRUCTURE
623 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)BROWN TAPE | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 1 | 36.41 | 36.41 | 1 | 0 | 47.2 | 10.79 | SUPER STRUCTURE
624 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 0 | 0 | 0 | 2 | 59 | 118 | 0 | 0 | 0 | 23 | 60.12 | 1382.86 | 13 | -8 | 767 | -497.86 | SUPER STRUCTURE
625 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 136 | 8200.01 | 1115201.36 | 14 | 8200.01 | 114800.14 | 136 | 7694.94 | 1046512 | 0 | 0 | 0 | 122 | 136 | 1000401.22 | 1115201.36 | SUPER STRUCTURE
626 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)CONCRETE PUMP HIRE CHARGES | CUM | 78 | 236 | 18408 | 78 | 236 | 18408 | 8 | 236 | 1888 | 78 | 175.01 | 13650.4602 | 78 | 175.01 | 13650.46 | 70 | 0 | 16520 | 4757.54 | SUPER STRUCTURE
627 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)FLY ASH | MT | 80.42 | 1396.5 | 112306.53 | 80.42 | 1396.5 | 112306.53 | 8 | 1396.5 | 11172 | 80.42 | 1396.5 | 112306.54 | 0 | 0 | 0 | 72.42 | 80.42 | 101134.53 | 112306.53 | SUPER STRUCTURE
628 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 2 | 424.8 | 849.6 | 0 | 0 | 0 | 0 | 424.8 | 0 | 0 | 0 | 0 | 6 | 413 | 2478 | 2 | -4 | 849.6 | -1628.4 | SUPER STRUCTURE
629 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)HOLE SAW CUTTER AND SET (50 MM) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
630 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)HSS Hole Saw 51mm | NOS | 3 | 594.72 | 1784.16 | 3 | 594.72 | 1784.16 | 0 | 594.72 | 0 | 3 | 621.71 | 1865.13 | 0 | 0 | 0 | 3 | 3 | 1784.16 | 1784.16 | SUPER STRUCTURE
631 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)HSS Hole Saw Kit | SET | 1 | 3416.1 | 3416.1 | 1 | 3416.1 | 3416.1 | 0 | 3416.1 | 0 | 1 | 3571.13 | 3571.13 | 0 | 0 | 0 | 1 | 1 | 3416.1 | 3416.1 | SUPER STRUCTURE
632 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)M.C. SAND | MT | 255 | 1711.5 | 436432.5 | 250 | 1711.5 | 427875 | 26 | 1711.5 | 44499 | 250 | 1627.5 | 406875 | 5.754 | 1690.31 | 9726.05 | 229 | 249.246 | 391933.5 | 426706.45 | SUPER STRUCTURE
633 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)MS NUT 16 MM (ROCKER) | NOS | 500 | 0 | 0 | 500 | 0 | 0 | 50 | 0 | 0 | 500 | 4.63 | 2315 | 0 | 0 | 0 | 450 | 500 | 0 | 0 | SUPER STRUCTURE
634 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)PPC CEMENT | BAG | 40 | 283.59 | 11343.6 | 40 | 283.59 | 11343.6 | 4 | 283.59 | 1134.36 | 40 | 262.99 | 10519.552 | 45 | 286.83 | 12907.48 | 36 | -5 | 10209.24 | -1563.88 | SUPER STRUCTURE
635 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)RMC M-25 FREE FLOW | CUM | 1 | 7599.2 | 7599.2 | 0 | 0 | 0 | 0 | 7599.2 | 0 | 0 | 0 | 0 | 342 | 7600 | 2599201.03 | 1 | -341 | 7599.2 | -2591601.83 | SUPER STRUCTURE
636 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)ROLLING BRUSH | NOS | 20 | 141.6 | 2832 | 20 | 141.6 | 2832 | 2 | 141.6 | 283.2 | 20 | 141.6 | 2832 | 4 | 141.6 | 566.4 | 18 | 16 | 2548.8 | 2265.6 | SUPER STRUCTURE
637 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 336 | 78 | 26208 | 306 | 78 | 23868 | 34 | 78 | 2652 | 306 | 156.94 | 48023.64 | 336 | 156.86 | 52705.43 | 302 | 0 | 23556 | -26497.43 | SUPER STRUCTURE
638 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)SIKA HIBOND | PKT | 2 | 507.4 | 1014.8 | 0 | 0 | 0 | 0 | 507.4 | 0 | 0 | 0 | 0 | 2 | 443.87 | 887.74 | 2 | 0 | 1014.8 | 127.06 | SUPER STRUCTURE
639 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1435 | 120.36 | 172716.6 | 1435 | 120.36 | 172716.6 | 144 | 120.36 | 17331.84 | 1435 | 113.84 | 163360.4 | 0 | 0 | 0 | 1291 | 1435 | 155384.76 | 172716.6 | SUPER STRUCTURE
640 | MIVAN : PRAYAG TYP 01 - T1 (+3.40M . +6.45M) | 10 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 15 | 82.6 | 1239 | 0 | 0 | 0 | 2 | 82.6 | 165.2 | 0 | 0 | 0 | 15 | 82.6 | 1239 | 13 | 0 | 1073.8 | 0 | SUPER STRUCTURE
641 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)8MM REBAR ANCHORING & CHEM. GROUTING | NOS | 150 | 64.9 | 9735 | 0 | 0 | 0 | 15 | 64.9 | 973.5 | 150 | 64.9 | 9735 | 0 | 0 | 0 | 135 | 150 | 8761.5 | 9735 | SUPER STRUCTURE
642 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 239 | 90.1 | 21533.9 | 0 | 0 | 0 | 24 | 90.1 | 2162.4 | 239 | 90.1 | 21533.9 | 239 | 90.1 | 21533.9 | 215 | 0 | 19371.5 | 0 | SUPER STRUCTURE
643 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 391 | 169.6 | 66313.6 | 3910 | 169.6 | 663136 | 3879.43 | 169.6 | 657951.33 | 3519 | 30.57 | 596822.4 | 5184.67 | SUPER STRUCTURE
644 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 1200 | 8 | 9600 | 0 | 0 | 0 | 120 | 8 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1200 | 8640 | 9600 | SUPER STRUCTURE
645 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
646 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 8000 | 5.5 | 44000 | 0 | 0 | 0 | 800 | 5.5 | 4400 | 6484 | 5.5 | 35662 | 6484 | 5.5 | 35662 | 7200 | 1516 | 39600 | 8338 | SUPER STRUCTURE
647 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Manual Lifting of Steel (TYP-02 PRAYAG) | MT | 41.3 | 318 | 13133.4 | 0 | 0 | 0 | 4 | 318 | 1272 | 41.3 | 318 | 13133.4 | 40.596 | 318 | 12909.53 | 37.3 | 0.704 | 11861.4 | 223.87 | SUPER STRUCTURE
648 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-02 (PRAYAG) | FLOOR | 1 | 20500 | 20500 | 0 | 0 | 0 | 0 | 20500 | 0 | 1 | 20500 | 20500 | 1 | 20500 | 20500 | 1 | 0 | 20500 | 0 | SUPER STRUCTURE
649 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 41.3 | 11007.04 | 454590.75 | 0 | 0 | 0 | 4 | 11007.04 | 44028.16 | 41.3 | 9328 | 385246.4 | 40.596 | 9328 | 378679.49 | 37.3 | 0.704 | 410562.592 | 75911.262 | SUPER STRUCTURE
650 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 348 | 177 | 61596 | 0 | 0 | 0 | 35 | 177 | 6195 | 344 | 150 | 51600 | 344 | 150 | 51600 | 313 | 4 | 55401 | 9996 | SUPER STRUCTURE
651 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 9 | 62.54 | 562.86 | 94 | 53 | 4982 | 77 | 53 | 4081 | 85 | 17 | 5315.9 | 1797.76 | SUPER STRUCTURE
652 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 7 | 22.52 | 157.64 | 65 | 19.08 | 1240.2 | 64 | 19.08 | 1221.12 | 58 | 1 | 1306.16 | 242.68 | SUPER STRUCTURE
653 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 120 | 18.76 | 2251.2 | 1200 | 15.9 | 19080 | 1012 | 15.9 | 16090.8 | 1080 | 188 | 20260.8 | 6421.2 | SUPER STRUCTURE
654 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 59 | 802.4 | 47341.6 | 0 | 0 | 0 | 6 | 802.4 | 4814.4 | 59 | 750 | 44250 | 59 | 750 | 44250 | 53 | 0 | 42527.2 | 3091.6 | SUPER STRUCTURE
655 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 181 | 535 | 96835 | 0 | 0 | 0 | 18 | 535 | 9630 | 181 | 553.65 | 100210 | 181 | 553.65 | 100210 | 163 | 0 | 87205 | -3375 | SUPER STRUCTURE
656 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 6 | 53.78 | 322.68 | 60 | 45.58 | 2734.8 | 60 | 45.58 | 2734.8 | 54 | 0 | 2904.12 | 492 | SUPER STRUCTURE
657 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 4 | 100.06 | 400.24 | 44 | 84.8 | 3731.2 | 44 | 84.8 | 3731.2 | 40 | 0 | 4002.4 | 671.44 | SUPER STRUCTURE
658 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)10 MM DIA TMT | MT | 4.809 | 55000 | 264495 | 4.399 | 55000 | 241945 | 0 | 55000 | 0 | 4.399 | 54093.84 | 237958.7837 | 3.629 | 54855.52 | 199070.69 | 4.809 | 1.18 | 264495 | 65424.31 | SUPER STRUCTURE
659 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 7.89 | 1770 | 13965.3 | 7.89 | 1770 | 13965.3 | 1 | 1770 | 1770 | 7.89 | 1543.5 | 12178.2197 | 231.625 | 1534.5 | 355429.27 | 6.89 | -223.735 | 12195.3 | -341463.97 | SUPER STRUCTURE
660 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)12 MM DIA TMT | MT | 3.17 | 54500 | 172765 | 3 | 54500 | 163500 | 0 | 54500 | 0 | 3 | 54014.5 | 162043.5 | 3 | 55603.15 | 166809.44 | 3.17 | 0.17 | 172765 | 5955.56 | SUPER STRUCTURE
661 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.55 | 82.6 | 7314.23 | 88.55 | 82.6 | 7314.23 | 9 | 82.6 | 743.4 | 88.55 | 78.94 | 6990.137 | 70.5 | 78.37 | 5525.18 | 79.55 | 18.05 | 6570.83 | 1789.05 | SUPER STRUCTURE
662 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)16 MM DIA TMT | MT | 9.45 | 54500 | 515025 | 9.45 | 54500 | 515025 | 1 | 54500 | 54500 | 9.45 | 53951.9 | 509845.4549 | 8.793 | 53911.81 | 474046.55 | 8.45 | 0.657 | 460525 | 40978.45 | SUPER STRUCTURE
663 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)20 mm concrete cover block | NOS | 4500 | 1.78 | 8010 | 0 | 0 | 0 | 450 | 1.78 | 801 | 0 | 0 | 0 | 4500 | 1.18 | 5310 | 4050 | 0 | 7209 | 2700 | SUPER STRUCTURE
664 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 4.928 | 50000 | 246400 | 4.838 | 50000 | 241900 | 0 | 50000 | 0 | 4.838 | 53486.26 | 258766.5097 | 4.11 | 54012.93 | 221993.16 | 4.928 | 0.818 | 246400 | 24406.84 | SUPER STRUCTURE
665 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 0 | 0 | 0 | 44 | 55.6 | 2446.4 | 0 | 0 | 0 | 0 | 0 | -139.3 | 396 | 440 | 22017.6 | 24603.3 | SUPER STRUCTURE
666 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR LONG) | MTR | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 2 | 23.6 | 47.2 | 18 | 27 | 486 | 50 | 26.48 | 1323.85 | 16 | -32 | 377.6 | -899.05 | SUPER STRUCTURE
667 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 3 | 82.6 | 247.8 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 22 | 25 | 1817.2 | 2065 | SUPER STRUCTURE
668 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 2300 | 3.06 | 7038 | 0 | 0 | 0 | 230 | 3.06 | 703.8 | 0 | 0 | 0 | 900 | 2.27 | 2042.68 | 2070 | 1400 | 6334.2 | 4995.32 | SUPER STRUCTURE
669 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)32 MM ID PPR PIPE 3 MTR LENGHT | NOS | 18 | 365.8 | 6584.4 | 0 | 0 | 0 | 2 | 365.8 | 731.6 | 0 | 0 | 0 | 20 | 369.89 | 7397.84 | 16 | -2 | 5852.8 | -813.44 | SUPER STRUCTURE
670 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)32 MM PPR PLAIN ELBOW | NOS | 25 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25 | 0 | 0 | SUPER STRUCTURE
671 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 2 | 23.6 | 47.2 | 0 | 0 | 0 | 18 | 22.38 | 402.83 | 16 | 0 | 377.6 | 21.97 | SUPER STRUCTURE
672 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)32 MM PPR TEE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 45.6 | 912.06 | 0 | -20 | 0 | -912.06 | SUPER STRUCTURE
673 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 2200 | 5.32 | 11704 | 0 | 0 | 0 | 220 | 5.32 | 1170.4 | 0 | 0 | 0 | 0 | 0 | -341.8 | 1980 | 2200 | 10533.6 | 12045.8 | SUPER STRUCTURE
674 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)6 X 75MM BOLT, NUT & WASHER . | NOS | 50 | 11.8 | 590 | 0 | 0 | 0 | 5 | 11.8 | 59 | 0 | 0 | 0 | 600 | 6.16 | 3698.16 | 45 | -550 | 531 | -3108.16 | SUPER STRUCTURE
675 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)8 MM DIA TMT | MT | 20.778 | 56000.01 | 1163568.21 | 20.778 | 56000.01 | 1163568.21 | 2 | 56000.01 | 112000.02 | 20.778 | 56236.31 | 1168478.051 | 19.851 | 56305.23 | 1117715.05 | 18.778 | 0.927 | 1051568.188 | 45853.1578 | SUPER STRUCTURE
676 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)ALMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN) | NOS | 200 | 115 | 23000 | 200 | 115 | 23000 | 20 | 115 | 2300 | 200 | 174.64 | 34928 | 200 | 174.09 | 34818.84 | 180 | 0 | 20700 | -11818.84 | SUPER STRUCTURE
677 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)BROWN TAPE | NOS | 8 | 47.2 | 377.6 | 0 | 0 | 0 | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 6 | 41.3 | 247.8 | 7 | 2 | 330.4 | 129.8 | SUPER STRUCTURE
678 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)CEBEX - 100 | PKT | 10 | 59 | 590 | 10 | 59 | 590 | 1 | 59 | 59 | 10 | 69.62 | 696.2 | 15 | 67.82 | 1017.26 | 9 | -5 | 531 | -427.26 | SUPER STRUCTURE
679 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 15 | 8200.01 | 123000.15 | 15 | 8200.01 | 123000.15 | 2 | 8200.01 | 16400.02 | 15 | 8000 | 120000 | 92.163 | 7729.99 | 712419.13 | 13 | -77.163 | 106600.13 | -589418.98 | SUPER STRUCTURE
680 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)FLY ASH | MT | 42 | 1396.5 | 58653 | 0 | 0 | 0 | 4 | 1396.5 | 5586 | 0 | 0 | 0 | 41.782 | 1396.5 | 58348.57 | 38 | 0.218 | 53067 | 304.43 | SUPER STRUCTURE
681 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 1 | 424.8 | 424.8 | 0 | 0 | 0 | 0 | 424.8 | 0 | 0 | 0 | 0 | 2 | 413 | 826 | 1 | -1 | 424.8 | -401.2 | SUPER STRUCTURE
682 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)M.C. SAND | MT | 7.9 | 1711.5 | 13520.85 | 7.9 | 1711.5 | 13520.85 | 1 | 1711.5 | 1711.5 | 7.9 | 1627.5 | 12857.2603 | 222.66 | 1682.8 | 374693 | 6.9 | -214.76 | 11809.35 | -361172.15 | SUPER STRUCTURE
683 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)PPC CEMENT | BAG | 40 | 283.59 | 11343.6 | 40 | 283.59 | 11343.6 | 4 | 283.59 | 1134.36 | 40 | 262.99 | 10519.552 | 46 | 280.34 | 12895.48 | 36 | -6 | 10209.24 | -1551.88 | SUPER STRUCTURE
684 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)PPR 32 MM 90° ELBOW | NOS | 25 | 35.4 | 885 | 0 | 0 | 0 | 3 | 35.4 | 106.2 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25 | 778.8 | 885 | SUPER STRUCTURE
685 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)RMC M-25 FREE FLOW | CUM | 348 | 7599.2 | 2644521.6 | 348 | 7599.2 | 2644521.6 | 35 | 7599.2 | 265972 | 348 | 7600 | 2644800.8352 | 84 | 7600 | 638400.27 | 313 | 264 | 2378549.6 | 2006121.33 | SUPER STRUCTURE
686 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)ROLLING BRUSH | NOS | 10 | 141.6 | 1416 | 0 | 0 | 0 | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 10 | 141.6 | 1416 | 9 | 0 | 1274.4 | 0 | SUPER STRUCTURE
687 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 30 | 78 | 2340 | 300 | 156.94 | 47082 | 300 | 156.9 | 47071.11 | 270 | 0 | 21060 | -23671.11 | SUPER STRUCTURE
688 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)SIKA HIBOND | PKT | 15 | 507.4 | 7611 | 0 | 0 | 0 | 2 | 507.4 | 1014.8 | 0 | 0 | 0 | 11 | 443.72 | 4880.9 | 13 | 4 | 6596.2 | 2730.1 | SUPER STRUCTURE
689 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1435 | 120.36 | 172716.6 | 1210 | 120.36 | 145635.6 | 144 | 120.36 | 17331.84 | 1210 | 113.84 | 137746.4 | 619 | 113.57 | 70298.9 | 1291 | 816 | 155384.76 | 102417.7 | SUPER STRUCTURE
690 | MIVAN : PRAYAG TYP 02 - T2 (+6.45M . +9.50M) | 10 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 14 | 82.6 | 1156.4 | 0 | 0 | 0 | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 14 | 82.6 | 1156.4 | 13 | 0 | 1073.8 | 0 | SUPER STRUCTURE
691 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 260 | 90.1 | 23426 | 0 | 0 | 0 | 26 | 90.1 | 2342.6 | 250 | 90.1 | 22525 | 202 | 90.1 | 18200.2 | 234 | 58 | 21083.4 | 5225.8 | SUPER STRUCTURE
692 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 391 | 169.6 | 66313.6 | 3910 | 169.6 | 663136 | 3824.78 | 169.6 | 648682.69 | 3519 | 85.22 | 596822.4 | 14453.31 | SUPER STRUCTURE
693 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
694 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
695 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 8000 | 5.5 | 44000 | 0 | 0 | 0 | 800 | 5.5 | 4400 | 8000 | 5.5 | 44000 | 4484 | 5.5 | 24662 | 7200 | 3516 | 39600 | 19338 | SUPER STRUCTURE
696 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Manual Lifting of Steel (TYP-03 PRAYAG) | MT | 39.52 | 360.4 | 14243.01 | 0 | 0 | 0 | 4 | 360.4 | 1441.6 | 39.52 | 360.4 | 14243.008 | 38.34 | 360.4 | 13817.74 | 35.52 | 1.18 | 12801.408 | 425.268 | SUPER STRUCTURE
697 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-03 (PRAYAG) | FLOOR | 1 | 21500 | 21500 | 0 | 0 | 0 | 0 | 21500 | 0 | 1 | 21500 | 21500 | 1 | 21500 | 21500 | 1 | 0 | 21500 | 0 | SUPER STRUCTURE
698 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 39.52 | 11007.04 | 434998.22 | 0 | 0 | 0 | 4 | 11007.04 | 44028.16 | 39.52 | 9328 | 368642.56 | 38.34 | 9328 | 357635.52 | 35.52 | 1.18 | 390970.061 | 77362.7008 | SUPER STRUCTURE
699 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 348 | 177 | 61596 | 0 | 0 | 0 | 35 | 177 | 6195 | 320.93 | 150 | 48139.5 | 320.93 | 150 | 48139.5 | 313 | 27.07 | 55401 | 13456.5 | SUPER STRUCTURE
700 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 9 | 62.54 | 562.86 | 94 | 53 | 4982 | 89 | 53 | 4717 | 85 | 5 | 5315.9 | 1161.76 | SUPER STRUCTURE
701 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 7 | 22.52 | 157.64 | 65 | 19.08 | 1240.2 | 64 | 19.08 | 1221.12 | 58 | 1 | 1306.16 | 242.68 | SUPER STRUCTURE
702 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 120 | 18.76 | 2251.2 | 1200 | 15.9 | 19080 | 1012 | 15.9 | 16090.8 | 1080 | 188 | 20260.8 | 6421.2 | SUPER STRUCTURE
703 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 22 | 802.4 | 17652.8 | 0 | 0 | 0 | 2 | 802.4 | 1604.8 | 22 | 750 | 16500 | 0 | 0 | 0 | 20 | 22 | 16048 | 17652.8 | SUPER STRUCTURE
704 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 75 | 535 | 40125 | 0 | 0 | 0 | 8 | 535 | 4280 | 75 | 580 | 43500 | 29 | 580 | 16820 | 67 | 46 | 35845 | 23305 | SUPER STRUCTURE
705 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 6 | 53.78 | 322.68 | 60 | 45.58 | 2734.8 | 60 | 45.58 | 2734.8 | 54 | 0 | 2904.12 | 492 | SUPER STRUCTURE
706 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 4 | 100.06 | 400.24 | 44 | 84.8 | 3731.2 | 44 | 84.8 | 3731.2 | 40 | 0 | 4002.4 | 671.44 | SUPER STRUCTURE
707 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)10 MM DIA TMT | MT | 5.016 | 55000 | 275880 | 5.016 | 55000 | 275880 | 1 | 55000 | 55000 | 5.016 | 57234.58 | 287088.637 | 4.561 | 57825.6 | 263742.58 | 4.016 | 0.455 | 220880 | 12137.42 | SUPER STRUCTURE
708 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 210.63 | 1770 | 372815.1 | 210.63 | 1770 | 372815.1 | 21 | 1770 | 37170 | 210.63 | 1501.5 | 316260.945 | 278.054 | 1513.27 | 420771.95 | 189.63 | -67.424 | 335645.1 | -47956.85 | SUPER STRUCTURE
709 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)12 MM DIA TMT | MT | 3.121 | 54500 | 170094.5 | 2.18 | 54500 | 118810 | 0 | 54500 | 0 | 2.18 | 53724.64 | 117119.7193 | 2 | 55603.15 | 111206.29 | 3.121 | 1.121 | 170094.5 | 58888.21 | SUPER STRUCTURE
710 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.55 | 82.6 | 7314.23 | 88.55 | 82.6 | 7314.23 | 9 | 82.6 | 743.4 | 88.55 | 78.94 | 6990.137 | 70 | 78.26 | 5478.32 | 79.55 | 18.55 | 6570.83 | 1835.91 | SUPER STRUCTURE
711 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)16 MM DIA TMT | MT | 9.301 | 54500 | 506904.5 | 8.664 | 54500 | 472188 | 1 | 54500 | 54500 | 8.664 | 56429.85 | 488908.2501 | 7.917 | 56988.98 | 451181.77 | 8.301 | 1.384 | 452404.5 | 55722.73 | SUPER STRUCTURE
712 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)20 mm concrete cover block | NOS | 4500 | 1.78 | 8010 | 0 | 0 | 0 | 450 | 1.78 | 801 | 0 | 0 | 0 | 4500 | 1.23 | 5515.2 | 4050 | 0 | 7209 | 2494.8 | SUPER STRUCTURE
713 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 2.022 | 50000 | 101100 | 2.022 | 50000 | 101100 | 0 | 50000 | 0 | 2.022 | 57332.08 | 115925.4658 | 1.807 | 58122.75 | 105027.81 | 2.022 | 0.215 | 101100 | -3927.81 | SUPER STRUCTURE
714 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1500 | 2.24 | 3360 | 0 | 0 | 0 | 150 | 2.24 | 336 | 0 | 0 | 0 | 900 | 2.12 | 1911.6 | 1350 | 600 | 3024 | 1448.4 | SUPER STRUCTURE
715 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 375 | 55.6 | 20850 | 0 | 0 | 0 | 38 | 55.6 | 2112.8 | 0 | 0 | 0 | 200 | 76.08 | 15215.44 | 337 | 175 | 18737.2 | 5634.56 | SUPER STRUCTURE
716 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR LONG) | MTR | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 2 | 23.6 | 47.2 | 18 | 27 | 486 | 0 | 0 | 0 | 16 | 18 | 377.6 | 424.8 | SUPER STRUCTURE
717 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 3 | 82.6 | 247.8 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 22 | 25 | 1817.2 | 2065 | SUPER STRUCTURE
718 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 1600 | 3.06 | 4896 | 1600 | 3.06 | 4896 | 160 | 3.06 | 489.6 | 1600 | 3.56 | 5688 | 1700 | 3.48 | 5923.48 | 1440 | -100 | 4406.4 | -1027.48 | SUPER STRUCTURE
719 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)32 MM ID PPR PIPE 3 MTR LENGHT | NOS | 18 | 365.8 | 6584.4 | 0 | 0 | 0 | 2 | 365.8 | 731.6 | 0 | 0 | 0 | 20 | 369.89 | 7397.84 | 16 | -2 | 5852.8 | -813.44 | SUPER STRUCTURE
720 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 2 | 23.6 | 47.2 | 0 | 0 | 0 | 19 | 22.62 | 429.81 | 16 | -1 | 377.6 | -5.01 | SUPER STRUCTURE
721 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 2 | 47.2 | 94.4 | 0 | 0 | 0 | 20 | 45.77 | 915.42 | 16 | -2 | 755.2 | -65.82 | SUPER STRUCTURE
722 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1000 | 5.32 | 5320 | 0 | 0 | 0 | 100 | 5.32 | 532 | 0 | 0 | 0 | 1000 | 4.06 | 4064.9 | 900 | 0 | 4788 | 1255.1 | SUPER STRUCTURE
723 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)6 X 75MM BOLT, NUT & WASHER . | NOS | 100 | 11.8 | 1180 | 0 | 0 | 0 | 10 | 11.8 | 118 | 0 | 0 | 0 | 150 | 6.16 | 924.54 | 90 | -50 | 1062 | 255.46 | SUPER STRUCTURE
724 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)8 MM DIA TMT | MT | 20.41 | 56000.01 | 1142960.2 | 20.146 | 56000.01 | 1128176.2 | 2 | 56000.01 | 112000.02 | 20.146 | 59533.8 | 1199368.0205 | 19.851 | 59456.92 | 1180279.37 | 18.41 | 0.559 | 1030960.184 | -37319.1659 | SUPER STRUCTURE
725 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)ALMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN) | NOS | 200 | 115 | 23000 | 200 | 115 | 23000 | 20 | 115 | 2300 | 200 | 174.64 | 34928 | 200 | 174.09 | 34818.86 | 180 | 0 | 20700 | -11818.86 | SUPER STRUCTURE
726 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)BROWN TAPE | NOS | 5 | 47.2 | 236 | 3 | 47.2 | 141.6 | 1 | 47.2 | 47.2 | 3 | 42.48 | 127.44 | 0 | 0 | 0 | 4 | 5 | 188.8 | 236 | SUPER STRUCTURE
727 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 2 | 59 | 118 | 15 | 69.62 | 1044.3 | 8 | 63.23 | 505.81 | 13 | 7 | 767 | 379.19 | SUPER STRUCTURE
728 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 102.925 | 8200.01 | 843986.03 | 102.925 | 8200.01 | 843986.03 | 10 | 8200.01 | 82000.1 | 102.925 | 7800 | 802815 | 108.219 | 7777.95 | 841721.79 | 92.925 | -5.294 | 761985.929 | 2264.2393 | SUPER STRUCTURE
729 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)FLY ASH | MT | 35 | 1396.5 | 48877.5 | 35 | 1396.5 | 48877.5 | 4 | 1396.5 | 5586 | 35 | 1396.5 | 48877.5 | 50.756 | 1396.5 | 70880.76 | 31 | -15.756 | 43291.5 | -22003.26 | SUPER STRUCTURE
730 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 2 | 424.8 | 849.6 | 0 | 0 | 0 | 0 | 424.8 | 0 | 0 | 0 | 0 | 2 | 413 | 826 | 2 | 0 | 849.6 | 23.6 | SUPER STRUCTURE
731 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)M.C. SAND | MT | 183 | 1711.5 | 313204.5 | 183 | 1711.5 | 313204.5 | 18 | 1711.5 | 30807 | 183 | 1890 | 345870 | 279.891 | 1748.42 | 489365.8 | 165 | -96.891 | 282397.5 | -176161.3 | SUPER STRUCTURE
732 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)PPC CEMENT | BAG | 40 | 283.59 | 11343.6 | 40 | 283.59 | 11343.6 | 4 | 283.59 | 1134.36 | 40 | 262.99 | 10519.552 | 42 | 276.53 | 11614.16 | 36 | -2 | 10209.24 | -270.56 | SUPER STRUCTURE
733 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)RMC M-25 FREE FLOW | CUM | 104 | 7599.2 | 790316.8 | 104 | 7599.2 | 790316.8 | 10 | 7599.2 | 75992 | 104 | 7600 | 790400.2566 | 12 | 7600 | 91200.04 | 94 | 92 | 714324.8 | 699116.76 | SUPER STRUCTURE
734 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 30 | 78 | 2340 | 300 | 156.94 | 47082 | 300 | 156.93 | 47079.21 | 270 | 0 | 21060 | -23679.21 | SUPER STRUCTURE
735 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)SIKA HIBOND | PKT | 19 | 507.4 | 9640.6 | 15 | 507.4 | 7611 | 2 | 507.4 | 1014.8 | 15 | 442.5 | 6637.5 | 4 | 507.4 | 2029.6 | 17 | 15 | 8625.8 | 7611 | SUPER STRUCTURE
736 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1435 | 120.36 | 172716.6 | 1435 | 120.36 | 172716.6 | 144 | 120.36 | 17331.84 | 1435 | 113.84 | 163360.4 | 983 | 112.45 | 110533.44 | 1291 | 452 | 155384.76 | 62183.16 | SUPER STRUCTURE
737 | MIVAN : PRAYAG TYP 03 - T3 (+9.50M . +12.55M) | 10 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 14 | 82.6 | 1156.4 | 0 | 0 | 0 | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 9 | 94.17 | 847.52 | 13 | 5 | 1073.8 | 308.88 | SUPER STRUCTURE
738 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 260 | 90.1 | 23426 | 0 | 0 | 0 | 26 | 90.1 | 2342.6 | 250 | 90.1 | 22525 | 210 | 90.1 | 18921 | 234 | 50 | 21083.4 | 4505 | SUPER STRUCTURE
739 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 391 | 169.6 | 66313.6 | 3910 | 169.6 | 663136 | 3880.52 | 169.6 | 658136.19 | 3519 | 29.48 | 596822.4 | 4999.81 | SUPER STRUCTURE
740 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
741 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
742 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
743 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 35 | 315 | 11025 | 348 | 315 | 109620 | 291.083 | 315 | 91691.15 | 313 | 56.917 | 98595 | 17928.85 | SUPER STRUCTURE
744 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 4 | 53 | 212 | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 31.04 | 35.04 | 1645.12 | 1857.12 | SUPER STRUCTURE
745 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
746 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 37.04 | 11007.04 | 407700.76 | 0 | 0 | 0 | 4 | 11007.04 | 44028.16 | 37.04 | 9328 | 345509.12 | 36.92 | 9328 | 344389.76 | 33.04 | 0.12 | 363672.602 | 63311.0016 | SUPER STRUCTURE
747 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
748 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 9 | 62.54 | 562.86 | 94 | 53 | 4982 | 75 | 53 | 3975 | 85 | 19 | 5315.9 | 1903.76 | SUPER STRUCTURE
749 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 7 | 22.52 | 157.64 | 65 | 19.08 | 1240.2 | 64 | 19.08 | 1221.12 | 58 | 1 | 1306.16 | 242.68 | SUPER STRUCTURE
750 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 120 | 18.76 | 2251.2 | 1200 | 15.9 | 19080 | 945 | 15.9 | 15025.5 | 1080 | 255 | 20260.8 | 7486.5 | SUPER STRUCTURE
751 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 10 | 885 | 8850 | 0 | 0 | 0 | 1 | 885 | 885 | 10 | 750 | 7500 | 0 | 0 | 0 | 9 | 10 | 7965 | 8850 | SUPER STRUCTURE
752 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 100 | 535 | 53500 | 0 | 0 | 0 | 10 | 535 | 5350 | 100 | 580 | 58000 | 0 | 0 | 0 | 90 | 100 | 48150 | 53500 | SUPER STRUCTURE
753 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 6 | 53.78 | 322.68 | 60 | 45.58 | 2734.8 | 60 | 45.58 | 2734.8 | 54 | 0 | 2904.12 | 492 | SUPER STRUCTURE
754 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 4 | 100.06 | 400.24 | 44 | 84.8 | 3731.2 | 44 | 84.8 | 3731.2 | 40 | 0 | 4002.4 | 671.44 | SUPER STRUCTURE
755 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)1.5" NAIL | KG | 10 | 100 | 1000 | 0 | 0 | 0 | 1 | 100 | 100 | 0 | 0 | 0 | 10 | 79.37 | 793.7 | 9 | 0 | 900 | 206.3 | SUPER STRUCTURE
756 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)10 MM DIA TMT | MT | 5.614 | 55000 | 308770 | 5.529 | 55000 | 304095 | 1 | 55000 | 55000 | 5.529 | 54512.48 | 301399.494 | 4.581 | 55429.93 | 253924.5 | 4.614 | 1.033 | 253770 | 54845.5 | SUPER STRUCTURE
757 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 316.52 | 1770 | 560240.4 | 316.52 | 1770 | 560240.4 | 32 | 1770 | 56640 | 316.52 | 1501.5 | 475254.78 | 319.068 | 1504.62 | 480074.52 | 284.52 | -2.548 | 503600.4 | 80165.88 | SUPER STRUCTURE
758 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)12 MM DIA TMT | MT | 3.683 | 54500 | 200723.5 | 3.617 | 54500 | 197126.5 | 0 | 54500 | 0 | 3.617 | 54784.23 | 198154.5764 | 3.2 | 57450.77 | 183842.47 | 3.683 | 0.483 | 200723.5 | 16881.03 | SUPER STRUCTURE
759 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.55 | 82.6 | 7314.23 | 88.55 | 82.6 | 7314.23 | 9 | 82.6 | 743.4 | 88.55 | 78.94 | 6990.137 | 68.55 | 78.24 | 5363.31 | 79.55 | 20 | 6570.83 | 1950.92 | SUPER STRUCTURE
760 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)16 MM DIA TMT | MT | 7.859 | 54500 | 428315.5 | 7.81 | 54500 | 425645 | 1 | 54500 | 54500 | 7.81 | 55058.9 | 430010.0472 | 7.353 | 55366.13 | 407107.15 | 6.859 | 0.506 | 373815.5 | 21208.35 | SUPER STRUCTURE
761 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)20 mm concrete cover block | NOS | 4500 | 1.78 | 8010 | 0 | 0 | 0 | 450 | 1.78 | 801 | 0 | 0 | 0 | 4500 | 1.23 | 5515.2 | 4050 | 0 | 7209 | 2494.8 | SUPER STRUCTURE
762 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 0.747 | 50000 | 37350 | 0.513 | 50000 | 25650 | 0 | 50000 | 0 | 0.513 | 55022.09 | 28226.3333 | 0.441 | 56506.76 | 24919.48 | 0.747 | 0.306 | 37350 | 12430.52 | SUPER STRUCTURE
763 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1000 | 2.24 | 2240 | 0 | 0 | 0 | 100 | 2.24 | 224 | 0 | 0 | 0 | 900 | 2.12 | 1911.6 | 900 | 100 | 2016 | 328.4 | SUPER STRUCTURE
764 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 320 | 55.6 | 17792 | 44 | 55.6 | 2446.4 | 320 | 75.52 | 24166.4 | 350 | 76.08 | 26627.02 | 396 | 90 | 22017.6 | -2163.02 | SUPER STRUCTURE
765 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR LONG) | MTR | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 2 | 23.6 | 47.2 | 18 | 27 | 486 | 0 | 0 | 0 | 16 | 18 | 377.6 | 424.8 | SUPER STRUCTURE
766 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 3 | 82.6 | 247.8 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 22 | 25 | 1817.2 | 2065 | SUPER STRUCTURE
767 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)3" NAIL | KG | 10 | 51 | 510 | 0 | 0 | 0 | 1 | 51 | 51 | 0 | 0 | 0 | 10 | 80.83 | 808.34 | 9 | 0 | 459 | -298.34 | SUPER STRUCTURE
768 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 2300 | 3.06 | 7038 | 2300 | 3.06 | 7038 | 230 | 3.06 | 703.8 | 2300 | 3.56 | 8176.5 | 1700 | 3.48 | 5923.48 | 2070 | 600 | 6334.2 | 1114.52 | SUPER STRUCTURE
769 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)32 MM ID PPR PIPE 3 MTR LENGHT | NOS | 18 | 365.8 | 6584.4 | 0 | 0 | 0 | 2 | 365.8 | 731.6 | 0 | 0 | 0 | 18 | 369.89 | 6658.06 | 16 | 0 | 5852.8 | -73.66 | SUPER STRUCTURE
770 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 2 | 23.6 | 47.2 | 0 | 0 | 0 | 18 | 26.99 | 485.81 | 16 | 0 | 377.6 | -61.01 | SUPER STRUCTURE
771 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 2 | 47.2 | 94.4 | 0 | 0 | 0 | 18 | 47.28 | 851.05 | 16 | 0 | 755.2 | -1.45 | SUPER STRUCTURE
772 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1000 | 5.32 | 5320 | 0 | 0 | 0 | 100 | 5.32 | 532 | 0 | 0 | 0 | 1000 | 4.06 | 4064.9 | 900 | 0 | 4788 | 1255.1 | SUPER STRUCTURE
773 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)6 X 75 MM BOLT, NUT& WASHER | SET | 50 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 0 | 0 | SUPER STRUCTURE
774 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)6 X 75MM BOLT, NUT & WASHER . | NOS | 50 | 11.8 | 590 | 0 | 0 | 0 | 5 | 11.8 | 59 | 0 | 0 | 0 | 50 | 6.16 | 308.18 | 45 | 0 | 531 | 281.82 | SUPER STRUCTURE
775 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)8 MM DIA TMT | MT | 20.763 | 56000.01 | 1162728.21 | 20.763 | 56000.01 | 1162728.21 | 2 | 56000.01 | 112000.02 | 20.763 | 56902.29 | 1181462.2608 | 19.863 | 57295.61 | 1138062.76 | 18.763 | 0.9 | 1050728.188 | 24665.4476 | SUPER STRUCTURE
776 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 20 | 177 | 3540 | 200 | 173.46 | 34692 | 200 | 172.91 | 34582.12 | 180 | 0 | 31860 | 817.88 | SUPER STRUCTURE
777 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)BROWN TAPE | NOS | 5 | 47.2 | 236 | 5 | 47.2 | 236 | 1 | 47.2 | 47.2 | 5 | 42.48 | 212.4 | 1 | 42.28 | 42.28 | 4 | 4 | 188.8 | 193.72 | SUPER STRUCTURE
778 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 2 | 59 | 118 | 15 | 69.62 | 1044.3 | 8 | 63.23 | 505.81 | 13 | 7 | 767 | 379.19 | SUPER STRUCTURE
779 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 136 | 8200.01 | 1115201.36 | 14 | 8200.01 | 114800.14 | 136 | 7697.14 | 1046811 | 119.06 | 7705.03 | 917360.81 | 122 | 16.94 | 1000401.22 | 197840.55 | SUPER STRUCTURE
780 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 43.53 | 1396.5 | 60789.65 | 9 | 1396.5 | 12568.5 | 43.53 | 1396.5 | 60789.6406 | 51.664 | 1396.5 | 72148.78 | 78.05 | 35.386 | 108996.825 | 49416.545 | SUPER STRUCTURE
781 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)M.C. SAND | MT | 307 | 1711.5 | 525430.5 | 297.51 | 1711.5 | 509188.37 | 31 | 1711.5 | 53056.5 | 297.51 | 1890 | 562293.9 | 306.931 | 1796.6 | 551433.11 | 276 | 0.069 | 472374 | -26002.61 | SUPER STRUCTURE
782 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)PPC CEMENT | BAG | 40 | 283.59 | 11343.6 | 40 | 283.59 | 11343.6 | 4 | 283.59 | 1134.36 | 40 | 262.99 | 10519.552 | 13 | 267.84 | 3481.86 | 36 | 27 | 10209.24 | 7861.74 | SUPER STRUCTURE
783 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 30 | 78 | 2340 | 300 | 156.94 | 47082 | 300 | 156.93 | 47079.18 | 270 | 0 | 21060 | -23679.18 | SUPER STRUCTURE
784 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)SIKA HIBOND | PKT | 15 | 507.4 | 7611 | 15 | 507.4 | 7611 | 2 | 507.4 | 1014.8 | 15 | 442.5 | 6637.5 | 0 | 0 | 0 | 13 | 15 | 6596.2 | 7611 | SUPER STRUCTURE
785 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1067.17 | 120.36 | 128444.58 | 1067 | 120.36 | 128424.12 | 107 | 120.36 | 12878.52 | 1067 | 110.92 | 118351.64 | 837 | 112.44 | 94116.38 | 960.17 | 230.17 | 115566.061 | 34328.2012 | SUPER STRUCTURE
786 | MIVAN : PRAYAG TYP 04 - T4 (+12.55M . +15.60M) | 10 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 16 | 82.6 | 1321.6 | 0 | 0 | 0 | 2 | 82.6 | 165.2 | 0 | 0 | 0 | 16 | 82.6 | 1321.6 | 14 | 0 | 1156.4 | 0 | SUPER STRUCTURE
787 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 0 | 90.1 | 0 | 90 | 85 | 7650 | 90 | 85 | 7650 | 90 | 0 | 8109 | 459 | SUPER STRUCTURE
788 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 3849.534 | 160 | 615925.44 | 3849.534 | 160 | 615925.44 | 3910 | 60.466 | 663136 | 47210.56 | SUPER STRUCTURE
789 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 1000 | 8 | 8000 | 0 | 0 | 0 | 0 | 8 | 0 | 1000 | 8 | 8000 | 1000 | 8 | 8000 | 1000 | 0 | 8000 | 0 | SUPER STRUCTURE
790 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
791 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
792 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 293.038 | 315 | 92306.97 | 348 | 54.962 | 109620 | 17313.03 | SUPER STRUCTURE
793 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 0 | 53 | 0 | 35.034 | 50 | 1751.7 | 35.034 | 50 | 1751.7 | 35.04 | 0.006 | 1857.12 | 105.42 | SUPER STRUCTURE
794 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
795 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 35.04 | 11007.04 | 385686.68 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 35.034 | 8800 | 308299.2 | 35.034 | 8800 | 308299.2 | 35.04 | 0.006 | 385686.682 | 77387.4816 | SUPER STRUCTURE
796 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE
797 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 5878.76 | 5878.76 | SUPER STRUCTURE
798 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 64 | 18 | 1152 | 64 | 18 | 1152 | 65 | 1 | 1463.8 | 311.8 | SUPER STRUCTURE
799 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 1012 | 15 | 15180 | 1012 | 15 | 15180 | 1200 | 188 | 22512 | 7332 | SUPER STRUCTURE
800 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 10 | 885 | 8850 | 0 | 0 | 0 | 0 | 885 | 0 | 10 | 750 | 7500 | 0 | 0 | 0 | 10 | 10 | 8850 | 8850 | SUPER STRUCTURE
801 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 100 | 535 | 53500 | 0 | 0 | 0 | 0 | 535 | 0 | 100 | 580 | 58000 | 0 | 0 | 0 | 100 | 100 | 53500 | 53500 | SUPER STRUCTURE
802 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 60 | 43 | 2580 | 60 | 43 | 2580 | 60 | 0 | 3226.8 | 646.8 | SUPER STRUCTURE
803 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 44 | 80 | 3520 | 44 | 80 | 3520 | 44 | 0 | 4402.64 | 882.64 | SUPER STRUCTURE
804 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 6.447 | 55000 | 354585 | 6.054 | 55000 | 332970 | 0 | 55000 | 0 | 6.054 | 53587.25 | 324417.2013 | 5.067 | 54124.95 | 274251.13 | 6.447 | 1.38 | 354585 | 80333.87 | SUPER STRUCTURE
805 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 286 | 1770 | 506220 | 0 | 1770 | 0 | 286 | 1556.55 | 445172 | 297.816 | 1524.52 | 454025.67 | 286 | -11.816 | 506220 | 52194.33 | SUPER STRUCTURE
806 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 4.127 | 54500 | 224921.5 | 4.086 | 54500 | 222687 | 0 | 54500 | 0 | 4.086 | 53779.73 | 219743.9663 | 3.659 | 57046.4 | 208732.79 | 4.127 | 0.468 | 224921.5 | 16188.71 | SUPER STRUCTURE
807 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.55 | 82.6 | 7314.23 | 88.55 | 82.6 | 7314.23 | 0 | 82.6 | 0 | 88.55 | 78.94 | 6990.137 | 80 | 78.24 | 6259.15 | 88.55 | 8.55 | 7314.23 | 1055.08 | SUPER STRUCTURE
808 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 6.562 | 54500 | 357629 | 6.562 | 54500 | 357629 | 0 | 54500 | 0 | 6.562 | 53971.33 | 354159.8577 | 5.981 | 53952.81 | 322691.74 | 6.562 | 0.581 | 357629 | 34937.26 | SUPER STRUCTURE
809 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 5 | 188.8 | 944 | 9 | 4 | 9 | -935 | SUPER STRUCTURE
810 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 3500 | 1.78 | 6230 | 3500 | 1.78 | 6230 | 0 | 1.78 | 0 | 3500 | 1.29 | 4515 | 4000 | 1.23 | 4902.4 | 3500 | -500 | 6230 | 1327.6 | SUPER STRUCTURE
811 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.468 | 50000 | 23400 | 0.468 | 50000 | 23400 | 0 | 50000 | 0 | 0.468 | 54162.01 | 25347.82 | 0.468 | 54162.01 | 25347.82 | 0.468 | 0 | 23400 | -1947.82 | SUPER STRUCTURE
812 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1000 | 2.24 | 2240 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 | 0 | 0 | 900 | 2.12 | 1911.6 | 1000 | 100 | 2240 | 328.4 | SUPER STRUCTURE
813 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 440 | 55.6 | 24464 | 0 | 55.6 | 0 | 440 | 75.52 | 33228.8 | 300 | 76.08 | 22823.16 | 440 | 140 | 24464 | 1640.84 | SUPER STRUCTURE
814 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR LONG) | MTR | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 27 | 486 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8 | SUPER STRUCTURE
815 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 0 | 0 | 0 | 7 | 69.62 | 487.34 | 25 | 18 | 2065 | 1577.66 | SUPER STRUCTURE
816 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 2300 | 3.06 | 7038 | 2300 | 3.06 | 7038 | 0 | 3.06 | 0 | 2300 | 3.56 | 8176.5 | 1700 | 3.48 | 5923.31 | 2300 | 600 | 7038 | 1114.69 | SUPER STRUCTURE
817 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)32 MM ID PPR PIPE 3 MTR LENGHT | NOS | 20 | 365.8 | 7316 | 0 | 0 | 0 | 0 | 365.8 | 0 | 0 | 0 | 0 | 7 | 369.89 | 2589.25 | 20 | 13 | 7316 | 4726.75 | SUPER STRUCTURE
818 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 18 | 26.99 | 485.8 | 18 | 0 | 424.8 | -61 | SUPER STRUCTURE
819 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 18 | 47.28 | 851.05 | 18 | 0 | 849.6 | -1.45 | SUPER STRUCTURE
820 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 130 | 5.32 | 691.6 | 130 | 5.32 | 691.6 | 0 | 5.32 | 0 | 130 | 4.53 | 588.9 | 830 | 4.06 | 3373.87 | 130 | -700 | 691.6 | -2682.27 | SUPER STRUCTURE
821 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 20.644 | 56000.01 | 1156064.21 | 20.644 | 56000.01 | 1156064.21 | 0 | 56000.01 | 0 | 20.644 | 55793.26 | 1151796.0026 | 19.861 | 56036.72 | 1112945.23 | 20.644 | 0.783 | 1156064.206 | 43118.9764 | SUPER STRUCTURE
822 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.46 | 34692 | 200 | 172.91 | 34582.12 | 200 | 0 | 35400 | 817.88 | SUPER STRUCTURE
823 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)BROWN TAPE | NOS | 6 | 47.2 | 283.2 | 6 | 47.2 | 283.2 | 0 | 47.2 | 0 | 6 | 42.48 | 254.88 | 4 | 42.48 | 169.92 | 6 | 2 | 283.2 | 113.28 | SUPER STRUCTURE
824 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 69.62 | 1044.3 | 8 | 63.23 | 505.81 | 15 | 7 | 885 | 379.19 | SUPER STRUCTURE
825 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 115 | 8200.01 | 943001.15 | 0 | 8200.01 | 0 | 115 | 7600 | 874000 | 120.199 | 7652.46 | 919817.59 | 136 | 15.801 | 1115201.36 | 195383.77 | SUPER STRUCTURE
826 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 0 | 0 | 0 | 1 | 1 | 460.2 | 460.2 | SUPER STRUCTURE
827 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 52.9 | 1396.5 | 73874.85 | 0 | 1396.5 | 0 | 52.9 | 1396.5 | 73874.8606 | 47.507 | 1396.5 | 66343.54 | 87.05 | 39.543 | 121565.325 | 55221.785 | SUPER STRUCTURE
828 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)M.C. SAND | MT | 333.166 | 1711.5 | 570213.61 | 290 | 1711.5 | 496335 | 0 | 1711.5 | 0 | 290 | 1871.9 | 542850 | 333.166 | 1828.48 | 609186.29 | 333.166 | 0 | 570213.609 | -38972.681 | SUPER STRUCTURE
829 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)PPC CEMENT | BAG | 40 | 283.59 | 11343.6 | 40 | 283.59 | 11343.6 | 0 | 283.59 | 0 | 40 | 262.99 | 10519.552 | 22 | 267.84 | 5892.38 | 40 | 18 | 11343.6 | 5451.22 | SUPER STRUCTURE
830 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 300 | 156.93 | 47079.21 | 300 | 0 | 23400 | -23679.21 | SUPER STRUCTURE
831 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)SIKA HIBOND | PKT | 15 | 507.4 | 7611 | 15 | 507.4 | 7611 | 0 | 507.4 | 0 | 15 | 442.5 | 6637.5 | 0 | 0 | 0 | 15 | 15 | 7611 | 7611 | SUPER STRUCTURE
832 | MIVAN : PRAYAG TYP 05 - T5 (+15.60M . +18.65M) | 0 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1407 | 120.36 | 169346.52 | 1407 | 120.36 | 169346.52 | 0 | 120.36 | 0 | 1407 | 110.92 | 156064.44 | 768 | 112.45 | 86357.76 | 1407 | 639 | 169346.52 | 82988.76 | SUPER STRUCTURE
833 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 0 | 90.1 | 0 | 90 | 85 | 7650 | 90 | 85 | 7650 | 90 | 0 | 8109 | 459
834 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 3879.43 | 160 | 620708.8 | 3879.43 | 160 | 620708.8 | 3910 | 30.57 | 663136 | 42427.2
835 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
836 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
837 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
838 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 290.955 | 315 | 91650.83 | 348 | 57.045 | 109620 | 17969.17
839 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.16 | 53 | 1863.48 | 0 | 0 | 0 | 0 | 53 | 0 | 35.04 | 50 | 1752 | 35.04 | 50 | 1752 | 35.16 | 0.12 | 1863.48 | 111.48
840 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
841 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 35.16 | 11007.04 | 387007.53 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 35.04 | 8800 | 308352 | 35.04 | 8800 | 308352 | 35.16 | 0.12 | 387007.526 | 78655.5264
842 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
843 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 94 | 45 | 4230 | 78 | 45 | 3510 | 94 | 16 | 5878.76 | 2368.76
844 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 64 | 18 | 1152 | 64 | 18 | 1152 | 65 | 1 | 1463.8 | 311.8
845 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 1104 | 15 | 16560 | 1104 | 15 | 16560 | 1200 | 96 | 22512 | 5952
846 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 10 | 885 | 8850 | 0 | 0 | 0 | 0 | 885 | 0 | 10 | 750 | 7500 | 0 | 0 | 0 | 10 | 10 | 8850 | 8850
847 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 100 | 535 | 53500 | 0 | 0 | 0 | 0 | 535 | 0 | 100 | 580 | 58000 | 0 | 0 | 0 | 100 | 100 | 53500 | 53500
848 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 60 | 43 | 2580 | 60 | 43 | 2580 | 60 | 0 | 3226.8 | 646.8
849 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 44 | 80 | 3520 | 44 | 80 | 3520 | 44 | 0 | 4402.64 | 882.64
850 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 6.366 | 55000 | 350130 | 6.263 | 55000 | 344465 | 0 | 55000 | 0 | 6.263 | 52996.45 | 331916.7741 | 6.223 | 53002.12 | 329832.18 | 6.366 | 0.143 | 350130 | 20297.82
851 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 286 | 1770 | 506220 | 0 | 1770 | 0 | 285.17 | 1441.34 | 411026.2847 | 306.561 | 1440.14 | 441489.84 | 286 | -20.561 | 506220 | 64730.16
852 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 3.998 | 54500 | 217891 | 3.998 | 54500 | 217891 | 0 | 54500 | 0 | 3.998 | 52955.27 | 211715.1838 | 3.647 | 55063.74 | 200817.46 | 3.998 | 0.351 | 217891 | 17073.54
853 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 80.07 | 82.6 | 6613.78 | 0 | 82.6 | 0 | 80.07 | 78.68 | 6299.9076 | 80 | 78.24 | 6259.15 | 88.5 | 8.5 | 7310.1 | 1050.95
854 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 5.324 | 54500 | 290158 | 5.324 | 54500 | 290158 | 0 | 54500 | 0 | 5.324 | 53158.42 | 283015.4245 | 5.324 | 53158.42 | 283015.42 | 5.324 | 0 | 290158 | 7142.58
855 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 9 | 188.8 | 1699.2 | 9 | 0 | 9 | -1690.2
856 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 4500 | 1.78 | 8010 | 4500 | 1.78 | 8010 | 0 | 1.78 | 0 | 4500 | 1.29 | 5805 | 4500 | 1.23 | 5515.2 | 4500 | 0 | 8010 | 2494.8
857 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.397 | 50000 | 19850 | 0.396 | 50000 | 19800 | 0 | 50000 | 0 | 0.396 | 54046.36 | 21402.36 | 0.396 | 54046.36 | 21402.36 | 0.397 | 0.001 | 19850 | -1552.36
858 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1000 | 2.24 | 2240 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 | 0 | 0 | 1000 | 2.12 | 2124 | 1000 | 0 | 2240 | 116
859 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 440 | 55.6 | 24464 | 0 | 55.6 | 0 | 440 | 75.52 | 33228.8 | 300 | 76.08 | 22823.16 | 440 | 140 | 24464 | 1640.84
860 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 6 | 69.62 | 417.72 | 25 | 19 | 2065 | 1647.28
861 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 2300 | 3.06 | 7038 | 2300 | 3.06 | 7038 | 0 | 3.06 | 0 | 2300 | 3.56 | 8176.5 | 1600 | 3.48 | 5574.91 | 2300 | 700 | 7038 | 1463.09
862 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 18 | 30.25 | 544.41 | 18 | 0 | 424.8 | -119.61
863 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 18 | 59.96 | 1079.32 | 18 | 0 | 849.6 | -229.72
864 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 2200 | 5.32 | 11704 | 2200 | 5.32 | 11704 | 0 | 5.32 | 0 | 2200 | 4.53 | 9966 | 1100 | 4.06 | 4471.39 | 2200 | 1100 | 11704 | 7232.61
865 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 20.774 | 56000.01 | 1163344.21 | 20.766 | 56000.01 | 1162896.21 | 0 | 56000.01 | 0 | 20.766 | 54803.59 | 1138051.2837 | 19.96 | 54999.02 | 1097780.49 | 20.774 | 0.814 | 1163344.208 | 65563.7177
866 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.46 | 34692 | 200 | 172.86 | 34571.92 | 200 | 0 | 35400 | 828.08
867 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)BROWN TAPE | NOS | 6 | 47.2 | 283.2 | 6 | 47.2 | 283.2 | 0 | 47.2 | 0 | 6 | 42.48 | 254.88 | 0 | 0 | 0 | 6 | 6 | 283.2 | 283.2
868 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 69.62 | 1044.3 | 11 | 62.61 | 688.66 | 15 | 4 | 885 | 196.34
869 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 120 | 8200.01 | 984001.2 | 0 | 8200.01 | 0 | 120 | 7600 | 912000 | 117.986 | 7616.57 | 898648.17 | 136 | 18.014 | 1115201.36 | 216553.19
870 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 55200 | 55200
871 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 1 | 468.42 | 468.42 | 1 | 0 | 460.2 | -8.22
872 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 75.58 | 1396.5 | 105547.47 | 0 | 1396.5 | 0 | 75.58 | 1396.5 | 105547.4807 | 45.418 | 1396.5 | 63426.25 | 87.05 | 41.632 | 121565.325 | 58139.075
873 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)M.C. SAND | MT | 317.173 | 1711.5 | 542841.59 | 293 | 1711.5 | 501469.5 | 0 | 1711.5 | 0 | 293 | 1853.87 | 543184.5467 | 317.173 | 1833.8 | 581631.99 | 317.173 | 0 | 542841.59 | -38790.4005
874 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)PPC CEMENT | BAG | 40 | 283.59 | 11343.6 | 40 | 283.59 | 11343.6 | 0 | 283.59 | 0 | 40 | 262.99 | 10519.552 | 23 | 277.81 | 6389.64 | 40 | 17 | 11343.6 | 4953.96
875 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)PPR 32 MM 90° ELBOW | NOS | 2 | 35.4 | 70.8 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 2 | 33.36 | 66.72 | 2 | 0 | 70.8 | 4.08
876 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 300 | 156.94 | 47081.28 | 300 | 0 | 23400 | -23681.28
877 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)SIKA HIBOND | PKT | 15 | 507.4 | 7611 | 15 | 507.4 | 7611 | 0 | 507.4 | 0 | 15 | 442.5 | 6637.5 | 0 | 0 | 0 | 15 | 15 | 7611 | 7611
878 | MIVAN : PRAYAG TYP 06 - T6 (+18.65M . +21.70M) | 0 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1407 | 120.36 | 169346.52 | 76.3 | 120.36 | 9183.47 | 0 | 120.36 | 0 | 76 | 110.92 | 8429.92 | 763 | 112.44 | 85795.46 | 1407 | 644 | 169346.52 | 83551.06
879 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 250 | 90.1 | 22525 | 0 | 0 | 0 | 0 | 90.1 | 0 | 250 | 85 | 21250 | 100 | 85 | 8500 | 250 | 150 | 22525 | 14025
880 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 3910 | 160 | 625600 | 3870.58 | 160 | 619292.8 | 3910 | 39.42 | 663136 | 43843.2
881 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
882 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
883 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
884 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 213.24 | 315 | 67170.6 | 348 | 134.76 | 109620 | 42449.4
885 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 37.822 | 53 | 2004.57 | 0 | 0 | 0 | 0 | 53 | 0 | 37.822 | 50 | 1891.1 | 36.023 | 50 | 1801.15 | 37.822 | 1.799 | 2004.566 | 203.416
886 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
887 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 37.822 | 11007.04 | 416308.27 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 37.822 | 8800 | 332833.6 | 36.023 | 8800 | 317002.4 | 37.822 | 1.799 | 416308.267 | 99305.8669
888 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
889 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 94 | 45 | 4230 | 89 | 45 | 4005 | 94 | 5 | 5878.76 | 1873.76
890 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 65 | 18 | 1170 | 64 | 18 | 1152 | 65 | 1 | 1463.8 | 311.8
891 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 1200 | 15 | 18000 | 0 | 0 | 0 | 1200 | 1200 | 22512 | 22512
892 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)Scaffolding Charges for FRP | LS | 1 | 318600 | 318600 | 0 | 0 | 0 | 0 | 318600 | 0 | 1 | 270000 | 270000 | 0.75 | 270000 | 202500 | 1 | 0.25 | 318600 | 116100
893 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 10 | 885 | 8850 | 0 | 0 | 0 | 0 | 885 | 0 | 10 | 750 | 7500 | 0 | 0 | 0 | 10 | 10 | 8850 | 8850
894 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 100 | 535 | 53500 | 0 | 0 | 0 | 0 | 535 | 0 | 100 | 580 | 58000 | 0 | 0 | 0 | 100 | 100 | 53500 | 53500
895 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 60 | 43 | 2580 | 60 | 43 | 2580 | 60 | 0 | 3226.8 | 646.8
896 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 44 | 80 | 3520 | 44 | 80 | 3520 | 44 | 0 | 4402.64 | 882.64
897 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 5.566 | 55000 | 306130 | 5.566 | 55000 | 306130 | 0 | 55000 | 0 | 5.566 | 51765.23 | 288125.2632 | 4.726 | 51980.73 | 245660.91 | 5.566 | 0.84 | 306130 | 60469.09
898 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 286 | 1770 | 506220 | 0 | 1770 | 0 | 258.001 | 1414.1 | 364838.2448 | 309.87 | 1368.94 | 424192.97 | 286 | -23.87 | 506220 | 82027.03
899 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 4.048 | 54500 | 220616 | 4.048 | 54500 | 220616 | 0 | 54500 | 0 | 4.048 | 51734.04 | 209419.3809 | 3.034 | 53148.67 | 161253.07 | 4.048 | 1.014 | 220616 | 59362.93
900 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 80.07 | 82.6 | 6613.78 | 0 | 82.6 | 0 | 80.07 | 78.68 | 6299.9076 | 80 | 78.24 | 6259.2 | 88.5 | 8.5 | 7310.1 | 1050.9
901 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 7.402 | 54500 | 403409 | 5.201 | 54500 | 283454.5 | 0 | 54500 | 0 | 5.201 | 52060.26 | 270765.3877 | 4.732 | 52089.23 | 246486.24 | 7.402 | 2.67 | 403409 | 156922.76
902 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 6 | 188.8 | 1132.8 | 9 | 3 | 9 | -1123.8
903 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 1500 | 1.78 | 2670 | 1500 | 1.78 | 2670 | 0 | 1.78 | 0 | 1500 | 1.34 | 2010 | 5430 | 1.31 | 7088.96 | 1500 | -3930 | 2670 | -4418.96
904 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.7 | 50000 | 35000 | 0.583 | 50000 | 29150 | 0 | 50000 | 0 | 0.583 | 52585.15 | 30657.145 | 0.593 | 52544.1 | 31158.65 | 0.7 | 0.107 | 35000 | 3841.35
905 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 900 | 2.24 | 2016 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 | 0 | 0 | 900 | 2.12 | 1911.6 | 900 | 0 | 2016 | 104.4
906 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 300 | 55.6 | 16680 | 0 | 0 | 0 | 0 | 55.6 | 0 | 0 | 0 | 0 | 350 | 76.32 | 26710.92 | 300 | -50 | 16680 | -10030.92
907 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)25 MM DIA TMT | MT | 0.761 | 50000 | 38050 | 0.761 | 50000 | 38050 | 0 | 50000 | 0 | 0.761 | 50503.99 | 38433.5371 | 0 | 0 | 0 | 0.761 | 0.761 | 38050 | 38050
908 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 25 | 25 | 2065 | 2065
909 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 1700 | 3.06 | 5202 | 0 | 0 | 0 | 0 | 3.06 | 0 | 0 | 0 | 0 | 1700 | 3.48 | 5923.48 | 1700 | 0 | 5202 | -721.48
910 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)32 MM PPR SOCKET | NOS | 15 | 23.6 | 354 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 15 | 30.25 | 453.75 | 15 | 0 | 354 | -99.75
911 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)32 MM PPR TEE | NOS | 15 | 47.2 | 708 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 15 | 59.96 | 899.4 | 15 | 0 | 708 | -191.4
912 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1100 | 5.32 | 5852 | 0 | 0 | 0 | 0 | 5.32 | 0 | 0 | 0 | 0 | 1100 | 4.06 | 4471.39 | 1100 | 0 | 5852 | 1380.61
913 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 21.4 | 56000 | 1198400 | 21.375 | 56000 | 1197000 | 0 | 56000 | 0 | 21.375 | 53676.85 | 1147342.6439 | 19.006 | 53742.1 | 1021422.41 | 21.4 | 2.394 | 1198400 | 176977.59
914 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.37 | 34674 | 200 | 172.86 | 34571.92 | 200 | 0 | 35400 | 828.08
915 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)BROWN TAPE | NOS | 4 | 47.2 | 188.8 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 4 | 36.41 | 145.64 | 4 | 0 | 188.8 | 43.16
916 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 57.79 | 866.85 | 6 | 56.64 | 339.84 | 15 | 9 | 885 | 545.16
917 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 136 | 8200.01 | 1115201.36 | 0 | 8200.01 | 0 | 136 | 7600 | 1033600 | 119.08 | 7604.12 | 905498.43 | 136 | 16.92 | 1115201.36 | 209702.93
918 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 600 | 92 | 55200 | 0 | 92 | 0 | 600 | 91.76 | 55056 | 600 | 91.76 | 55056 | 600 | 0 | 55200 | 144
919 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 2 | 468.42 | 936.84 | 1 | -1 | 460.2 | -476.64
920 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 87 | 1396.5 | 121495.5 | 0 | 1396.5 | 0 | 87 | 1396.5 | 121495.5 | 44.22 | 1396.5 | 61753.24 | 87.05 | 42.83 | 121565.325 | 59812.085
921 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)M.C. SAND | MT | 341.072 | 1711.5 | 583744.73 | 303 | 1711.5 | 518584.5 | 0 | 1711.5 | 0 | 303 | 1846.68 | 559545 | 341.072 | 1841.03 | 627924.5 | 341.072 | 0 | 583744.728 | -44179.772
922 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)PPC CEMENT | BAG | 20 | 283.59 | 5671.8 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 16 | 285.58 | 4569.28 | 20 | 4 | 5671.8 | 1102.52
923 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 300 | 156.94 | 47082 | 300 | 0 | 23400 | -23682
924 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1450 | 120.36 | 174522 | 1450 | 120.36 | 174522 | 0 | 120.36 | 0 | 1450 | 110.92 | 160834 | 619 | 112.45 | 69603.46 | 1450 | 831 | 174522 | 104918.54
925 | MIVAN : PRAYAG TYP 07 - T7 (+21.70M . +24.75M) | 0 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 5 | 82.6 | 413 | 5 | 82.6 | 413 | 0 | 82.6 | 0 | 5 | 106.2 | 531 | 18 | 98.8 | 1778.33 | 5 | -13 | 413 | -1365.33
926 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 250 | 90.1 | 22525 | 0 | 0 | 0 | 0 | 90.1 | 0 | 250 | 85 | 21250 | 0 | 0 | 0 | 250 | 250 | 22525 | 22525
927 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 3910 | 160 | 625600 | 0 | 0 | 0 | 3910 | 3910 | 663136 | 663136
928 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
929 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
930 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
931 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 0 | 0 | 0 | 348 | 348 | 109620 | 109620
932 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 36.24 | 53 | 1920.72 | 0 | 0 | 0 | 0 | 53 | 0 | 35.36 | 50 | 1768 | 0 | 0 | 0 | 36.24 | 36.24 | 1920.72 | 1920.72
933 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
934 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 36.24 | 11007.04 | 398895.13 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 35.36 | 8800 | 311168 | 0 | 0 | 0 | 36.24 | 36.24 | 398895.13 | 398895.1296
935 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
936 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 94 | 45 | 4230 | 0 | 0 | 0 | 94 | 94 | 5878.76 | 5878.76
937 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 65 | 18 | 1170 | 0 | 0 | 0 | 65 | 65 | 1463.8 | 1463.8
938 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 1200 | 15 | 18000 | 0 | 0 | 0 | 1200 | 1200 | 22512 | 22512
939 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 10 | 885 | 8850 | 0 | 0 | 0 | 0 | 885 | 0 | 10 | 750 | 7500 | 0 | 0 | 0 | 10 | 10 | 8850 | 8850
940 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 100 | 535 | 53500 | 0 | 0 | 0 | 0 | 535 | 0 | 100 | 580 | 58000 | 0 | 0 | 0 | 100 | 100 | 53500 | 53500
941 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 60 | 43 | 2580 | 0 | 0 | 0 | 60 | 60 | 3226.8 | 3226.8
942 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 44 | 80 | 3520 | 0 | 0 | 0 | 44 | 44 | 4402.64 | 4402.64
943 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 4.666 | 55000 | 256630 | 4.666 | 55000 | 256630 | 0 | 55000 | 0 | 4.666 | 50613.5 | 236162.5749 | 4.666 | 50613.39 | 236162.09 | 4.666 | 0 | 256630 | 20467.91
944 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 285 | 1770 | 504450 | 0 | 1770 | 0 | 285 | 1376.7 | 392358.12 | 283.452 | 1386 | 392864.47 | 286 | 2.548 | 506220 | 113355.53
945 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 3.266 | 54500 | 177997 | 3.266 | 54500 | 177997 | 0 | 54500 | 0 | 3.266 | 50563 | 165138.7573 | 3.266 | 51396.19 | 167859.96 | 3.266 | 0 | 177997 | 10137.04
946 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 80.07 | 82.6 | 6613.78 | 0 | 82.6 | 0 | 80.07 | 78.68 | 6299.9076 | 76 | 78.24 | 5946.24 | 88.5 | 12.5 | 7310.1 | 1363.86
947 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 7.402 | 54500 | 403409 | 4.971 | 54500 | 270919.5 | 0 | 54500 | 0 | 4.971 | 50563 | 251348.67 | 4.971 | 50563 | 251348.67 | 7.402 | 2.431 | 403409 | 152060.33
948 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 9 | 188.8 | 1699.2 | 9 | 0 | 9 | -1690.2
949 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 4000 | 1.78 | 7120 | 4000 | 1.78 | 7120 | 0 | 1.78 | 0 | 4000 | 1.34 | 5360 | 5000 | 1.26 | 6300 | 4000 | -1000 | 7120 | 820
950 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.665 | 50000 | 33250 | 0.365 | 50000 | 18250 | 0 | 50000 | 0 | 0.365 | 50582.78 | 18462.715 | 0.365 | 50582.79 | 18462.72 | 0.665 | 0.3 | 33250 | 14787.28
951 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1 | 2.24 | 2.24 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 | 0 | 0 | 1800 | 2.17 | 3906 | 1 | -1799 | 2.24 | -3903.76
952 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 300 | 55.6 | 16680 | 0 | 0 | 0 | 0 | 55.6 | 0 | 0 | 0 | 0 | 350 | 76.47 | 26763.99 | 300 | -50 | 16680 | -10083.99
953 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 15 | 69.62 | 1044.3 | 25 | 10 | 2065 | 1020.7
954 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 1 | 3.06 | 3.06 | 0 | 0 | 0 | 0 | 3.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3.06 | 3.06
955 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)32 MM PPR PIPE | MTR | 54 | 1 | 54 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 54 | 155.05 | 8372.7 | 54 | 0 | 54 | -8318.7
956 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 18 | 30.74 | 553.32 | 18 | 0 | 424.8 | -128.52
957 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 18 | 61.88 | 1113.84 | 18 | 0 | 849.6 | -264.24
958 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1000 | 5.32 | 5320 | 0 | 0 | 0 | 0 | 5.32 | 0 | 0 | 0 | 0 | 1000 | 4.19 | 4190 | 1000 | 0 | 5320 | 1130
959 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 19.851 | 56000.01 | 1111656.2 | 19.851 | 56000.01 | 1111656.2 | 0 | 56000.01 | 0 | 19.851 | 52333 | 1038862.3909 | 19.851 | 52539.24 | 1042956.38 | 19.851 | 0 | 1111656.199 | 68699.8185
960 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.37 | 34674 | 200 | 172.85 | 34570 | 200 | 0 | 35400 | 830
961 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)BROWN TAPE | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 11 | 36.41 | 400.51 | 1 | -10 | 47.2 | -353.31
962 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 57.79 | 866.85 | 0 | 0 | 0 | 15 | 15 | 885 | 885
963 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 136 | 8200.01 | 1115201.36 | 0 | 8200.01 | 0 | 136 | 7600 | 1033600 | 121.941 | 7600 | 926751.6 | 136 | 14.059 | 1115201.36 | 188449.76
964 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 600 | 92 | 55200 | 0 | 92 | 0 | 600 | 91.76 | 55056 | 600 | 91.76 | 55056 | 600 | 0 | 55200 | 144
965 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 1 | 467.57 | 467.57 | 1 | 0 | 460.2 | -7.37
966 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 87 | 1396.5 | 121495.5 | 0 | 1396.5 | 0 | 87 | 1396.5 | 121495.5 | 43.769 | 1396.5 | 61123.41 | 87.05 | 43.281 | 121565.325 | 60441.915
967 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)M.C. SAND | MT | 310.21 | 1711.5 | 530924.42 | 310.21 | 1711.5 | 530924.42 | 0 | 1711.5 | 0 | 310.21 | 1890 | 586296.9 | 321.301 | 1889.79 | 607192.81 | 310.21 | -11.091 | 530924.415 | -76268.395
968 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)PPC CEMENT | BAG | 10 | 283.59 | 2835.9 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 24 | 288.16 | 6915.94 | 10 | -14 | 2835.9 | -4080.04
969 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 300 | 156.94 | 47082 | 300 | 0 | 23400 | -23682
970 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1100 | 120.36 | 132396 | 1100 | 120.36 | 132396 | 0 | 120.36 | 0 | 1100 | 110.92 | 122012 | 868 | 110.92 | 96278.56 | 1100 | 232 | 132396 | 36117.44
971 | MIVAN : PRAYAG TYP 08 - T8 (+24.75M . +27.80M) | 0 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 5 | 82.6 | 413 | 5 | 82.6 | 413 | 0 | 82.6 | 0 | 5 | 106.2 | 531 | 10 | 105.09 | 1050.89 | 5 | -5 | 413 | -637.89
972 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 0 | 90.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 8109 | 8109
973 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3910 | 3910 | 663136 | 663136
974 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
975 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
976 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
977 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 0 | 0 | 0 | 348 | 348 | 109620 | 109620
978 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 1857.12 | 1857.12
979 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
980 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 35.04 | 11007.04 | 385686.68 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 385686.682 | 385686.6816
981 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
982 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 5878.76 | 5878.76
983 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 1463.8 | 1463.8
984 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 22512 | 22512
985 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 3226.8 | 3226.8
986 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 4402.64 | 4402.64
987 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 4.666 | 55000 | 256630 | 3.63 | 55000 | 199650 | 0 | 55000 | 0 | 3.63 | 50150 | 182044.5 | 3.63 | 50150 | 182044.5 | 4.666 | 1.036 | 256630 | 74585.5
988 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 50.12 | 1770 | 88712.4 | 0 | 1770 | 0 | 50.12 | 1386 | 69466.32 | 0 | 0 | 0 | 286 | 286 | 506220 | 506220
989 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 3.266 | 54500 | 177997 | 3.26 | 54500 | 177670 | 0 | 54500 | 0 | 3.26 | 50150 | 163489 | 3.26 | 51217.18 | 166968.01 | 3.266 | 0.006 | 177997 | 11028.99
990 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 80.07 | 82.6 | 6613.78 | 0 | 82.6 | 0 | 80.07 | 78.68 | 6299.9076 | 0 | 0 | 0 | 88.5 | 88.5 | 7310.1 | 7310.1
991 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 8.554 | 54500 | 466193 | 8.554 | 54500 | 466193 | 0 | 54500 | 0 | 8.41 | 50150 | 421761.5 | 8.41 | 50150 | 421761.5 | 8.554 | 0.144 | 466193 | 44431.5
992 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 0 | 0 | 0 | 9 | 9 | 9 | 9
993 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 4000 | 1.78 | 7120 | 4000 | 1.78 | 7120 | 0 | 1.78 | 0 | 4000 | 1.34 | 5360 | 0 | 0 | 0 | 4000 | 4000 | 7120 | 7120
994 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.73 | 50000 | 36500 | 0.73 | 50000 | 36500 | 0 | 50000 | 0 | 0.73 | 50150 | 36609.5 | 0.73 | 50150 | 36609.5 | 0.73 | 0 | 36500 | -109.5
995 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 25 | 25 | 2065 | 2065
996 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)30 mm clear PVC round cover block | NOS | 1300 | 100 | 130000 | 1300 | 100 | 130000 | 0 | 100 | 0 | 1300 | 3.7 | 4803.5 | 0 | 0 | 0 | 1300 | 1300 | 130000 | 130000
997 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
998 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 19.851 | 56000.01 | 1111656.2 | 19.85 | 56000.01 | 1111600.2 | 0 | 56000.01 | 0 | 19.85 | 51920 | 1030612 | 19.85 | 52004.35 | 1032286.3 | 19.851 | 0.001 | 1111656.199 | 79369.8985
999 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.37 | 34674 | 0 | 0 | 0 | 200 | 200 | 35400 | 35400
1000 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 57.79 | 866.85 | 0 | 0 | 0 | 15 | 15 | 885 | 885
1001 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 136 | 1115201.36 | 1115201.36
1002 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 55200 | 55200
1003 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 0 | 0 | 0 | 1 | 1 | 460.2 | 460.2
1004 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 0 | 0 | 0 | 0 | 1396.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.05 | 87.05 | 121565.325 | 121565.325
1005 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)M.C. SAND | MT | 250 | 1711.5 | 427875 | 28.76 | 1711.5 | 49222.74 | 0 | 1711.5 | 0 | 28.76 | 1890 | 54356.4 | 0 | 0 | 0 | 250 | 250 | 427875 | 427875
1006 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 0 | 0 | 0 | 300 | 300 | 23400 | 23400
1007 | MIVAN : PRAYAG TYP 09 - T9 (+27.80M . +30.85M) | 0 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 5 | 82.6 | 413 | 5 | 82.6 | 413 | 0 | 82.6 | 0 | 5 | 106.2 | 531 | 0 | 0 | 0 | 5 | 5 | 413 | 413
1008 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 0 | 90.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 8109 | 8109
1009 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3910 | 3910 | 663136 | 663136
1010 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1011 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1012 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1013 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 0 | 0 | 0 | 348 | 348 | 109620 | 109620
1014 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 1857.12 | 1857.12
1015 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1016 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 35.04 | 11007.04 | 385686.68 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 385686.682 | 385686.6816
1017 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1018 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 5878.76 | 5878.76
1019 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 1463.8 | 1463.8
1020 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 22512 | 22512
1021 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 3226.8 | 3226.8
1022 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 4402.64 | 4402.64
1023 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 5.35 | 55000 | 294250 | 5.35 | 55000 | 294250 | 0 | 55000 | 0 | 5.35 | 54298.49 | 290496.939 | 5.29 | 51568.48 | 272797.25 | 5.35 | 0.06 | 294250 | 21452.75
1024 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 286 | 1770 | 506220 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 286 | 506220 | 506220
1025 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 3.6 | 54500 | 196200 | 3.536 | 54500 | 192712 | 0 | 54500 | 0 | 3.536 | 54189.7 | 191614.7776 | 3.506 | 52081.21 | 182596.73 | 3.6 | 0.094 | 196200 | 13603.27
1026 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 80.07 | 82.6 | 6613.78 | 0 | 82.6 | 0 | 80.07 | 78.68 | 6299.9076 | 0 | 0 | 0 | 88.5 | 88.5 | 7310.1 | 7310.1
1027 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 7.402 | 54500 | 403409 | 5.012 | 54500 | 273154 | 0 | 54500 | 0 | 5.012 | 55197.03 | 276647.52 | 5.012 | 55197.03 | 276647.52 | 7.402 | 2.39 | 403409 | 126761.48
1028 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 0 | 0 | 0 | 9 | 9 | 9 | 9
1029 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 5000 | 1.78 | 8900 | 5000 | 1.78 | 8900 | 0 | 1.78 | 0 | 5000 | 1.25 | 6250 | 0 | 0 | 0 | 5000 | 5000 | 8900 | 8900
1030 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.665 | 50000 | 33250 | 0.365 | 50000 | 18250 | 0 | 50000 | 0 | 0.365 | 53297.21 | 19453.48 | 0.355 | 53385.86 | 18951.98 | 0.665 | 0.31 | 33250 | 14298.02
1031 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1000 | 2.24 | 2240 | 1000 | 2.24 | 2240 | 0 | 2.24 | 0 | 1000 | 2.25 | 2254 | 0 | 0 | 0 | 1000 | 1000 | 2240 | 2240
1032 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 350 | 55.6 | 19460 | 0 | 55.6 | 0 | 350 | 76.87 | 26904.5 | 0 | 0 | 0 | 440 | 440 | 24464 | 24464
1033 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 25 | 25 | 2065 | 2065
1034 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 1800 | 3.06 | 5508 | 1800 | 3.06 | 5508 | 0 | 3.06 | 0 | 1800 | 3.45 | 6201 | 0 | 0 | 0 | 1800 | 1800 | 5508 | 5508
1035 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1200 | 5.32 | 6384 | 1200 | 5.32 | 6384 | 0 | 5.32 | 0 | 1200 | 4.39 | 5268 | 0 | 0 | 0 | 1200 | 1200 | 6384 | 6384
1036 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 19.851 | 56000.01 | 1111656.2 | 14.709 | 56000.01 | 823704.15 | 0 | 56000.01 | 0 | 14.709 | 56683.01 | 833750.4087 | 14.569 | 55820.39 | 813247.21 | 19.851 | 5.282 | 1111656.199 | 298408.9885
1037 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.37 | 34674 | 0 | 0 | 0 | 200 | 200 | 35400 | 35400
1038 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 57.79 | 866.85 | 0 | 0 | 0 | 15 | 15 | 885 | 885
1039 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 136 | 8200.01 | 1115201.36 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 136 | 1115201.36 | 1115201.36
1040 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 55200 | 55200
1041 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 0 | 0 | 0 | 1 | 1 | 460.2 | 460.2
1042 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)FLY ASH | MT | 87.05 | 1396.5 | 121565.33 | 0 | 0 | 0 | 0 | 1396.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.05 | 87.05 | 121565.325 | 121565.325
1043 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)M.C. SAND | MT | 250 | 1711.5 | 427875 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 427875 | 427875
1044 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 0 | 0 | 0 | 300 | 300 | 23400 | 23400
1045 | MIVAN : PRAYAG TYP 10 - T10 (+30.85M . +33.90M) | 0 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 4 | 82.6 | 330.4 | 4 | 82.6 | 330.4 | 0 | 82.6 | 0 | 4 | 106.2 | 424.8 | 0 | 0 | 0 | 4 | 4 | 330.4 | 330.4
1046 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 0 | 90.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 8109 | 8109
1047 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3910 | 3910 | 663136 | 663136
1048 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 0 | 0 | 0 | 348 | 348 | 109620 | 109620
1052 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 1857.12 | 1857.12
1053 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1054 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 35.04 | 11007.04 | 385686.68 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 385686.682 | 385686.6816
1055 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 5878.76 | 5878.76
1057 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 1463.8 | 1463.8
1058 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 22512 | 22512
1059 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 3226.8 | 3226.8
1060 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 4402.64 | 4402.64
1061 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)10 MM DIA TMT | MT | 6.709 | 55000 | 368995 | 6.709 | 55000 | 368995 | 0 | 55000 | 0 | 6.709 | 55224 | 370497.8113 | 6.697 | 51801.99 | 346917.93 | 6.709 | 0.012 | 368995 | 22077.07
1062 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 3.655 | 54500 | 199197.5 | 3.655 | 54500 | 199197.5 | 0 | 54500 | 0 | 3.655 | 55224 | 201843.7222 | 3.536 | 52275.35 | 184845.64 | 3.655 | 0.119 | 199197.5 | 14351.86
1063 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 80.07 | 82.6 | 6613.78 | 0 | 82.6 | 0 | 80.07 | 78.68 | 6299.9076 | 0 | 0 | 0 | 88.5 | 88.5 | 7310.1 | 7310.1
1064 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)16 MM DIA TMT | MT | 5.403 | 54500 | 294463.5 | 5.403 | 54500 | 294463.5 | 0 | 54500 | 0 | 5.403 | 55224 | 298375.2698 | 5.397 | 55224 | 298043.93 | 5.403 | 0.006 | 294463.5 | -3580.43
1065 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 0 | 0 | 0 | 9 | 9 | 9 | 9
1066 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 5000 | 1.78 | 8900 | 5000 | 1.78 | 8900 | 0 | 1.78 | 0 | 5000 | 1.25 | 6250 | 0 | 0 | 0 | 5000 | 5000 | 8900 | 8900
1067 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 0.685 | 50000 | 34250 | 0.685 | 50000 | 34250 | 0 | 50000 | 0 | 0.685 | 55224 | 37828.44 | 0.675 | 55224 | 37276.2 | 0.685 | 0.01 | 34250 | -3026.2
1068 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1000 | 2.24 | 2240 | 1000 | 2.24 | 2240 | 0 | 2.24 | 0 | 1000 | 2.25 | 2254 | 0 | 0 | 0 | 1000 | 1000 | 2240 | 2240
1069 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 350 | 55.6 | 19460 | 0 | 55.6 | 0 | 350 | 76.87 | 26904.5 | 0 | 0 | 0 | 440 | 440 | 24464 | 24464
1070 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)25 MM DIA TMT | MT | 0.785 | 50000 | 39250 | 0.785 | 50000 | 39250 | 0 | 50000 | 0 | 0.785 | 55224 | 43350.84 | 0.784 | 55224.01 | 43295.62 | 0.785 | 0.001 | 39250 | -4045.62
1071 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 25 | 25 | 2065 | 2065
1072 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 1800 | 3.06 | 5508 | 1800 | 3.06 | 5508 | 0 | 3.06 | 0 | 1800 | 3.45 | 6201 | 0 | 0 | 0 | 1800 | 1800 | 5508 | 5508
1073 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1200 | 5.32 | 6384 | 1200 | 5.32 | 6384 | 0 | 5.32 | 0 | 1200 | 4.39 | 5268 | 0 | 0 | 0 | 1200 | 1200 | 6384 | 6384
1074 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 20.763 | 56000.01 | 1162728.21 | 20.763 | 56000.01 | 1162728.21 | 0 | 56000.01 | 0 | 20.763 | 56994 | 1183366.4199 | 20.763 | 54009.55 | 1121400.33 | 20.763 | 0 | 1162728.208 | 41327.8776
1075 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.37 | 34674 | 0 | 0 | 0 | 200 | 200 | 35400 | 35400
1076 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 57.79 | 866.85 | 0 | 0 | 0 | 15 | 15 | 885 | 885
1077 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 55200 | 55200
1078 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 0 | 0 | 0 | 1 | 1 | 460.2 | 460.2
1079 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)M.C. SAND | MT | 250 | 1711.5 | 427875 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 427875 | 427875
1080 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 0 | 0 | 0 | 300 | 300 | 23400 | 23400
1081 | MIVAN : PRAYAG TYP 11 - T11 (+33.90M : +36.95M) | 0 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 4 | 82.6 | 330.4 | 4 | 82.6 | 330.4 | 0 | 82.6 | 0 | 4 | 106.2 | 424.8 | 0 | 0 | 0 | 4 | 4 | 330.4 | 330.4
1082 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)Bracket Fixing & Removing TYP 01-12 (PRAYAG) | NOS | 90 | 90.1 | 8109 | 0 | 0 | 0 | 0 | 90.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 8109 | 8109
1083 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for Alu-Form Shutt. TYP 02-12 (PRAYAG) | SQM | 3910 | 169.6 | 663136 | 0 | 0 | 0 | 0 | 169.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3910 | 3910 | 663136 | 663136
1084 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for Cement Cutting & Silo Feeding TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1085 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1086 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for Hole Filling Work TYP 01-12 (PRAYAG) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1087 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for M25 SCC pouring incl. complete civil works | CUM | 348 | 315 | 109620 | 0 | 0 | 0 | 0 | 315 | 0 | 348 | 315 | 109620 | 0 | 0 | 0 | 348 | 348 | 109620 | 109620
1088 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for MECH. Lifting of Steel for TYP. Floors (PRAYAG) | MT | 35.04 | 53 | 1857.12 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 1857.12 | 1857.12
1089 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for Mortar Packing incl. lifting TYP-04-12 (PRAYAG) | FLOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1090 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for Reinforcement Work TYP 01-12(PRAYAG) | MT | 35.04 | 11007.04 | 385686.68 | 0 | 0 | 0 | 0 | 11007.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.04 | 35.04 | 385686.682 | 385686.6816
1091 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)L/C for RMC M-25 Gr. SCC Pouring in TYP 01-12 (PRAYAG) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1092 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)MS Insert Plate Fixing for TYP 01-12 (PRAYAG) | NOS | 94 | 62.54 | 5878.76 | 0 | 0 | 0 | 0 | 62.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 5878.76 | 5878.76
1093 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)PVC Pipe Sleeve Fixing for TYP 01-12 (PRAYAG) | NOS | 65 | 22.52 | 1463.8 | 0 | 0 | 0 | 0 | 22.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 1463.8 | 1463.8
1094 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)Safety Net Fixing & Removing for TYP 01-12 (PRAYAG) | SQM | 1200 | 18.76 | 22512 | 0 | 0 | 0 | 0 | 18.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 22512 | 22512
1095 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)Thermocol fixing in Cut-Outs for TYP 01-12 (PRAYAG) | NOS | 60 | 53.78 | 3226.8 | 0 | 0 | 0 | 0 | 53.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 3226.8 | 3226.8
1096 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Labour | (L)WOODEN BATTEN FIXING IN SLAB | NOS | 44 | 100.06 | 4402.64 | 0 | 0 | 0 | 0 | 100.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 4402.64 | 4402.64
1097 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)12 MM DIA TMT | MT | 0.737 | 54500 | 40166.5 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.737 | 0.737 | 40166.5 | 40166.5
1098 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 88.5 | 82.6 | 7310.1 | 85.58 | 82.6 | 7068.91 | 0 | 82.6 | 0 | 85.58 | 78.48 | 6716.0278 | 0 | 0 | 0 | 88.5 | 88.5 | 7310.1 | 7310.1
1099 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 0 | 0 | 0 | 9 | 9 | 9 | 9
1100 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 5000 | 1.78 | 8900 | 5000 | 1.78 | 8900 | 0 | 1.78 | 0 | 5000 | 1.25 | 6250 | 0 | 0 | 0 | 5000 | 5000 | 8900 | 8900
1101 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)20mm Circular PVC Cover Block | NOS | 1000 | 2.24 | 2240 | 1000 | 2.24 | 2240 | 0 | 2.24 | 0 | 1000 | 2.25 | 2254 | 0 | 0 | 0 | 1000 | 1000 | 2240 | 2240
1102 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 440 | 55.6 | 24464 | 350 | 55.6 | 19460 | 0 | 55.6 | 0 | 350 | 76.87 | 26904.5 | 75 | 76.47 | 5735.25 | 440 | 365 | 24464 | 18728.75
1103 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 0 | 82.6 | 0 | 25 | 69.62 | 1740.5 | 0 | 0 | 0 | 25 | 25 | 2065 | 2065
1104 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 1800 | 3.06 | 5508 | 1800 | 3.06 | 5508 | 0 | 3.06 | 0 | 1800 | 3.45 | 6201 | 0 | 0 | 0 | 1800 | 1800 | 5508 | 5508
1105 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 1200 | 5.32 | 6384 | 1200 | 5.32 | 6384 | 0 | 5.32 | 0 | 1200 | 4.39 | 5268 | 0 | 0 | 0 | 1200 | 1200 | 6384 | 6384
1106 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)8 MM DIA TMT | MT | 0.737 | 56000.01 | 41272.01 | 0 | 0 | 0 | 0 | 56000.01 | 0 | 0 | 0 | 0 | 0.737 | 73545.45 | 54203 | 0.737 | 0 | 41272.007 | -12930.9926
1107 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 200 | 177 | 35400 | 200 | 177 | 35400 | 0 | 177 | 0 | 200 | 173.37 | 34674 | 0 | 0 | 0 | 200 | 200 | 35400 | 35400
1108 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)CEBEX - 100 | PKT | 15 | 59 | 885 | 15 | 59 | 885 | 0 | 59 | 0 | 15 | 57.79 | 866.85 | 0 | 0 | 0 | 15 | 15 | 885 | 885
1109 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)Diesel | LTR | 600 | 92 | 55200 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 55200 | 55200
1110 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 1 | 460.2 | 460.2 | 1 | 460.2 | 460.2 | 0 | 460.2 | 0 | 1 | 466.1 | 466.1 | 0 | 0 | 0 | 1 | 1 | 460.2 | 460.2
1111 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)M.C. SAND | MT | 250 | 1711.5 | 427875 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 427875 | 427875
1112 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 300 | 78 | 23400 | 300 | 78 | 23400 | 0 | 78 | 0 | 300 | 156.94 | 47082 | 0 | 0 | 0 | 300 | 300 | 23400 | 23400
1113 | MIVAN : PRAYAG TYP 12 - T12 (+36.95M . +40.0M) | 0 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 4 | 82.6 | 330.4 | 4 | 82.6 | 330.4 | 0 | 82.6 | 0 | 4 | 106.2 | 424.8 | 0 | 0 | 0 | 4 | 4 | 330.4 | 330.4
1114 | MIVAN : VENI TYP 02 - T2 (+6.45 M TO +9.50 M) | 0 | Tentative | Material | (M)2"CONCRETE NAIL | KG | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 188.8 | 1888 | 0 | 0 | 0 | 10 | 10 | 10 | 10
1115 | MIVAN : VENI TYP 03 - T3 (+9.50 M TO +12.55M) | 0 | Tentative | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 0 | 0 | 0 | 9 | 9 | 9 | 9
1116 | MIVAN : VENI TYP 04 : T4 (+12.55M TO +15.60M) | 0 | Tentative | Material | (M)2"CONCRETE NAIL | KG | 9 | 1 | 9 | 9 | 1 | 9 | 0 | 1 | 0 | 9 | 188.8 | 1699.2 | 0 | 0 | 0 | 9 | 9 | 9 | 9
1117 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Acro-Span 2.5m X 2.5m | NOS | 5100 | 5.9 | 30090 | 0 | 0 | 0 | 510 | 5.9 | 3009 | 4600 | 5.9 | 27140 | 4600 | 5.9 | 27140 | 4590 | 500 | 27081 | 2950 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1118 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Adj. Tel. CT Prop Jack 2 Mtr X 2.5Mtr | NOS | 28589 | 2.6 | 74331.4 | 0 | 0 | 0 | 2859 | 2.6 | 7433.4 | 20999 | 2.6 | 54513.4 | 20999 | 2.6 | 54513.4 | 25730 | 7590 | 66898 | 19818 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1119 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Adj. Tel. CT Prop Jack 2 Mtr X 3Mtr | NOS | 27000 | 2.96 | 79920 | 0 | 0 | 0 | 2700 | 2.96 | 7992 | 12453 | 2.95 | 36736.36 | 12453 | 2.95 | 36736.36 | 24300 | 14547 | 71928 | 43183.64 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1120 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Adj. Tel. CT Prop Jack 2.5 Mtr X 2.5Mtr | NOS | 27000 | 2.96 | 79920 | 0 | 0 | 0 | 2700 | 2.96 | 7992 | 12788 | 2.95 | 37724.6 | 12788 | 2.95 | 37724.62 | 24300 | 14212 | 71928 | 42195.38 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1121 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Base Jack 0.375 Mtr. | NOS | 36000 | 0.53 | 19080 | 0 | 0 | 0 | 3600 | 0.53 | 1908 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 36000 | 17172 | 19080 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1122 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)CT Tel. Adjustable Prop Jack(2mX3m)-Base Type | NOS | 144000 | 1.78 | 256320 | 0 | 0 | 0 | 14400 | 1.78 | 25632 | 0 | 0 | 0 | 0 | 0 | 0 | 129600 | 144000 | 230688 | 256320 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1123 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)CT Tel. Adjustable Prop Jack(2mX3m)-U Head type | NOS | 90000 | 1.78 | 160200 | 0 | 0 | 0 | 9000 | 1.78 | 16020 | 79000 | 1.77 | 139830 | 79000 | 1.77 | 139830 | 81000 | 11000 | 144180 | 20370 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1124 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Ledger Horizontal 0.950 Mtr. | NOS | 108000 | 0.53 | 57240 | 0 | 0 | 0 | 10800 | 0.53 | 5724 | 26208 | 0.53 | 13916.44 | 26208 | 0.53 | 13916.44 | 97200 | 81792 | 51516 | 43323.56 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1125 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Ledger Horizontal 1.450 Mtr. | NOS | 108000 | 0.8 | 86400 | 0 | 0 | 0 | 10800 | 0.8 | 8640 | 11232 | 0.8 | 9012.56 | 11232 | 0.8 | 9012.56 | 97200 | 96768 | 77760 | 77387.44 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1126 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Ledger Horizontal 1.950 Mtr. | NOS | 45000 | 1.06 | 47700 | 0 | 0 | 0 | 4500 | 1.06 | 4770 | 20592 | 1.06 | 21868.7 | 20592 | 1.06 | 21868.7 | 40500 | 24408 | 42930 | 25831.3 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1127 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Std. Vertical 2.0 Mtr | NOS | 90000 | 1.06 | 95400 | 0 | 0 | 0 | 9000 | 1.06 | 9540 | 11648 | 1.06 | 12370.18 | 11648 | 1.06 | 12370.18 | 81000 | 78352 | 85860 | 83029.82 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1128 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)EXTRA CHARGES OVER CONCRETING (OT) | CUM | 78 | 20 | 1560 | 0 | 0 | 0 | 8 | 20 | 160 | 78 | 20 | 1560 | 78 | 20 | 1560 | 70 | 0 | 1400 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1129 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Joint Pin 0.280 Mtr | NOS | 45000 | 0.24 | 10800 | 0 | 0 | 0 | 4500 | 0.24 | 1080 | 5824 | 0.24 | 1374.46 | 5824 | 0.24 | 1374.46 | 40500 | 39176 | 9720 | 9425.54 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1130 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Board Making | SQM | 500 | 80 | 40000 | 0 | 0 | 0 | 50 | 80 | 4000 | 500 | 80 | 40000 | 500 | 80 | 40000 | 450 | 0 | 36000 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1131 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Conduit/DB/JB fixing in Slab/Wall before casting | PER/SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1132 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Conventional Shuttering (+1.50m - +3.4m) | SQM | 2300 | 255 | 586500 | 0 | 0 | 0 | 230 | 255 | 58650 | 1569.916 | 255 | 400328.58 | 1569.916 | 255 | 400328.58 | 2070 | 730.084 | 527850 | 186171.42 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1133 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Cut Out Making & Fixing (Thermocol) | NOS | 70 | 50 | 3500 | 0 | 0 | 0 | 7 | 50 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 70 | 3150 | 3500 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1134 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Cut-Out Making & Fixing (Ply) | NOS | 15 | 100 | 1500 | 0 | 0 | 0 | 2 | 100 | 200 | 15 | 100 | 1500 | 15 | 100 | 1500 | 13 | 0 | 1300 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1135 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for fixing 20mm/25mm PVC pipe excluding bracket fixing | NOS | 2000 | 40 | 80000 | 0 | 0 | 0 | 200 | 40 | 8000 | 88 | 40 | 3520 | 88 | 40 | 3520 | 1800 | 1912 | 72000 | 76480 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1136 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for fixing of MS Insert Plate | NOS | 80 | 50 | 4000 | 0 | 0 | 0 | 8 | 50 | 400 | 63 | 50 | 3150 | 63 | 50 | 3150 | 72 | 17 | 3600 | 850 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1137 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for M-25 Gr. Concrete Pouring in Column & Wall (2L) | CUM | 60 | 325 | 19500 | 0 | 0 | 0 | 6 | 325 | 1950 | 49.08 | 325 | 15951 | 49.08 | 325 | 15951 | 54 | 10.92 | 17550 | 3549 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1138 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Reinforcement Work (+1.50m - +3.40m) | MT | 40 | 6000 | 240000 | 0 | 0 | 0 | 4 | 6000 | 24000 | 25.464 | 6000 | 152784 | 25.464 | 6000 | 152784 | 36 | 14.536 | 216000 | 87216 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1139 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Staging Work (Above 3.0Mtr from Base) | CUM | 1000 | 29.5 | 29500 | 0 | 0 | 0 | 100 | 29.5 | 2950 | 871.162 | 25 | 21779.05 | 871.162 | 25 | 21779.05 | 900 | 128.838 | 26550 | 7720.95 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1140 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)LABOUR CHARGES FOR RMC CONCRETING | CUM | 170 | 200.6 | 34102 | 0 | 0 | 0 | 17 | 200.6 | 3410.2 | 167.1 | 170 | 28407 | 167.1 | 170 | 28407 | 153 | 2.9 | 30691.8 | 5695 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1141 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Lifting Charges of Rebar (1st Floor) | MT | 20 | 236 | 4720 | 0 | 0 | 0 | 2 | 236 | 472 | 14.782 | 200 | 2956.4 | 14.782 | 200 | 2956.4 | 18 | 5.218 | 4248 | 1763.6 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1142 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 10 | 802.4 | 8024 | 0 | 0 | 0 | 1 | 802.4 | 802.4 | 3 | 750 | 2250 | 3 | 750 | 2250 | 9 | 7 | 7221.6 | 5774 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1143 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 100 | 535 | 53500 | 0 | 0 | 0 | 10 | 535 | 5350 | 3 | 535 | 1605 | 3 | 535 | 1605 | 90 | 97 | 48150 | 51895 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1144 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)TRIP CHARGES( VSPL GODOWN TO AMRITAYA) | TRIP | 4 | 11800 | 47200 | 0 | 0 | 0 | 0 | 11800 | 0 | 2 | 10000 | 20000 | 2 | 10000 | 20000 | 4 | 2 | 47200 | 27200 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1145 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)1.5" NAIL | KG | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 22 | 76.83 | 1690.35 | 1 | -21 | 100 | -1590.35 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1146 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)10 MM DIA TMT | MT | 4.223 | 55000 | 232265 | 3.94 | 55000 | 216700 | 0 | 55000 | 0 | 3.94 | 53729.98 | 211696.135 | 3.94 | 53789.74 | 211931.59 | 4.223 | 0.283 | 232265 | 20333.41 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1147 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)12 MM DIA TMT | MT | 6.805 | 54500 | 370872.5 | 6.805 | 54500 | 370872.5 | 1 | 54500 | 54500 | 6.805 | 54080.83 | 368020.026 | 6.805 | 54014.5 | 367568.68 | 5.805 | 0 | 316372.5 | 3303.82 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1148 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 550 | 2194.8 | 1207140 | 550 | 2194.8 | 1207140 | 55 | 2194.8 | 120714 | 550 | 2190.08 | 1204544 | 580 | 2190.08 | 1270246.4 | 495 | -30 | 1086426 | -63106.4 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1149 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 85 | 82.6 | 7021 | 83.25 | 82.6 | 6876.45 | 9 | 82.6 | 743.4 | 83.25 | 78.58 | 6541.5546 | 57.708 | 78.37 | 4522.65 | 76 | 27.292 | 6277.6 | 2498.35 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1150 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)16 MM DIA TMT | MT | 12.226 | 54500 | 666317 | 12.226 | 54500 | 666317 | 1 | 54500 | 54500 | 12.226 | 54087.9 | 661278.667 | 12.226 | 54190.64 | 662534.76 | 11.226 | 0 | 611817 | 3782.24 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1151 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)2.5" NAIL | KG | 50 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1152 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 17.272 | 50000 | 863600 | 17.272 | 50000 | 863600 | 2 | 50000 | 100000 | 17.272 | 54621.31 | 943419.2096 | 17.262 | 54674.07 | 943783.72 | 15.272 | 0.01 | 763600 | -80183.72 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1153 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)25 MM CONDUIT PIPE MEDIUM DUTY (3 MTR) | NOS | 50 | 118 | 5900 | 50 | 118 | 5900 | 5 | 118 | 590 | 50 | 86.14 | 4307 | 14 | 83.98 | 1175.71 | 45 | 36 | 5310 | 4724.29 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1154 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)25 MM DIA TMT | MT | 2 | 54500 | 109000 | 2 | 54500 | 109000 | 0 | 54500 | 0 | 2 | 53454 | 106908 | 2 | 53454 | 106908 | 2 | 0 | 109000 | 2092 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1155 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)3" NAIL | KG | 300 | 51 | 15300 | 300 | 51 | 15300 | 30 | 51 | 1530 | 250 | 84.96 | 21240 | 138.7 | 77.88 | 10802.03 | 270 | 161.3 | 13770 | 4497.97 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1156 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 731 | 430 | 314330 | 730.06 | 430 | 313925.8 | 73 | 430 | 31390 | 730.06 | 519.2 | 379047.152 | 603.89 | 519.2 | 313539.68 | 658 | 127.11 | 282940 | 790.32 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1157 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)3"X2" Pine Batten | CFT | 1200 | 767 | 920400 | 1200 | 767 | 920400 | 120 | 767 | 92040 | 1200 | 800.43 | 960516 | 1000 | 798.9 | 798901.3 | 1080 | 200 | 828360 | 121498.7 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1158 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)32 MM ID PPR PIPE 3 MTR LENGHT | NOS | 100 | 365.8 | 36580 | 100 | 365.8 | 36580 | 10 | 365.8 | 3658 | 100 | 371.35 | 37134.8 | 15 | 369.89 | 5548.38 | 90 | 85 | 32922 | 31031.62 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1159 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)32 MM PPR END CAP | NOS | 100 | 23.6 | 2360 | 100 | 23.6 | 2360 | 10 | 23.6 | 236 | 100 | 20.34 | 2034.4 | 0 | 0 | 0 | 90 | 100 | 2124 | 2360 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1160 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)32 MM PPR SOCKET | NOS | 100 | 23.6 | 2360 | 100 | 23.6 | 2360 | 10 | 23.6 | 236 | 100 | 22.47 | 2246.9 | 0 | 0 | -157.21 | 90 | 100 | 2124 | 2517.21 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1161 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)32 MM PPR TEE | NOS | 120 | 47.2 | 5664 | 120 | 47.2 | 5664 | 12 | 47.2 | 566.4 | 120 | 45.78 | 5494.08 | 0 | 0 | -215.35 | 108 | 120 | 5097.6 | 5879.35 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1162 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)4" NAIL | KG | 250 | 51 | 12750 | 250 | 51 | 12750 | 25 | 51 | 1275 | 250 | 84.96 | 21240 | 160 | 78.87 | 12619.63 | 225 | 90 | 11475 | 130.37 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1163 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)4"X3"X 4 Ft Long Hardwood Batten (Special Quality) | CFT | 650 | 542.8 | 352820 | 417.621 | 542.8 | 226684.68 | 65 | 542.8 | 35282 | 417.621 | 519.2 | 216828.8205 | 374.81 | 519.2 | 194601.37 | 585 | 275.19 | 317538 | 158218.63 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1164 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)8 MM DIA TMT | MT | 15.55 | 56000.01 | 870800.16 | 15.5 | 56000.01 | 868000.16 | 2 | 56000.01 | 112000.02 | 15.5 | 55712.18 | 863538.75 | 15.5 | 55927.59 | 866877.58 | 13.55 | 0.05 | 758800.136 | 3922.5755 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1165 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)BASE JACK 0.375 MTR. | PIECE/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1166 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)BROWN TAPE | NOS | 50 | 47.2 | 2360 | 50 | 47.2 | 2360 | 5 | 47.2 | 236 | 50 | 41.3 | 2065 | 59 | 39.31 | 2319.34 | 45 | -9 | 2124 | 40.66 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1167 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CEBEX - 100 | PKT | 30 | 59 | 1770 | 30 | 59 | 1770 | 3 | 59 | 177 | 30 | 65.37 | 1961.108 | 10 | 76.11 | 761.1 | 27 | 20 | 1593 | 1008.9 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1168 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CONCRETE PUMP HIRE CHARGES | CUM | 78 | 236 | 18408 | 78 | 236 | 18408 | 8 | 236 | 1888 | 78 | 200 | 15599.8612 | 78 | 200 | 15599.86 | 70 | 0 | 16520 | 2808.14 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1169 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)Concrete Pump Hire Charges on Per Day Basis | DAYS | 1 | 11800 | 11800 | 1 | 11800 | 11800 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11800 | 11800 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1170 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CUP-LOCK LEDGER HORIZONTAL 0.950 MTR. | PIECE/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1171 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CUP-LOCK LEDGER HORIZONTAL 1.450 MTR. | PIECE/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1172 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CUP-LOCK LEDGER HORIZONTAL 1.950 MTR. | PIECE/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1173 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CUP-LOCK VERTICAL STD. 2.0 MTR | PIECE/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1174 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)FUSION MACHINE 20MM TO 50 MM | NOS | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 0 | 5900 | 0 | 1 | 6055.98 | 6055.98 | 0 | 0 | 0 | 1 | 1 | 5900 | 5900 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1175 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)JOINT PIN 0.280 MTR. | PIECE/DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1176 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 200 | 47.2 | 9440 | 200 | 47.2 | 9440 | 20 | 47.2 | 944 | 200 | 177 | 35400 | 154 | 143.22 | 22056.4 | 180 | 46 | 8496 | -12616.4 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1177 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 1 | 297.04 | 297.04 | 1 | 0 | 283.59 | -13.45 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1178 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)PPR 32 MM 90° ELBOW | NOS | 60 | 35.4 | 2124 | 60 | 35.4 | 2124 | 6 | 35.4 | 212.4 | 60 | 33.49 | 2009.22 | 20 | 33.36 | 667.11 | 54 | 40 | 1911.6 | 1456.89 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1179 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 262.77 | 7257 | 1906921.89 | 249.058 | 7257 | 1807413.91 | 26 | 7257 | 188682 | 249.058 | 7205.93 | 1794695.2207 | 242.058 | 7206.31 | 1744344.22 | 236.77 | 20.712 | 1718239.89 | 162577.67 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1180 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 20 | 78 | 1560 | 0 | 0 | 0 | 2 | 78 | 156 | 0 | 0 | 0 | 6 | 155.76 | 934.56 | 18 | 14 | 1404 | 625.44 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1181 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)SIKA LATEX POWER | KG | 60 | 212.4 | 12744 | 60 | 212.4 | 12744 | 6 | 212.4 | 1274.4 | 60 | 226.17 | 13570.2 | 21 | 225.42 | 4733.79 | 54 | 39 | 11469.6 | 8010.21 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1182 | CONVEN. PLY SHUTTERING : PRAYAG G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)THERMOCOL ( 50 MM ) | NOS | 200 | 82.6 | 16520 | 100 | 82.6 | 8260 | 20 | 82.6 | 1652 | 100 | 82.6 | 8260 | 27 | 83.22 | 2246.86 | 180 | 173 | 14868 | 14273.14 | SUPER STRUCTURE | GROUND FLOOR TO 1ST FLOOR
1183 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Acro-Span 2.5m X 2.5m | NOS | 10700 | 5.9 | 63130 | 0 | 0 | 0 | 1070 | 5.9 | 6313 | 10700 | 5.9 | 63130 | 9200 | 5.9 | 54280 | 9630 | 1500 | 56817 | 8850
1184 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Adj. Tel. CT Prop Jack 2 Mtr X 2.5Mtr | NOS | 62142 | 2.6 | 161569.2 | 0 | 0 | 0 | 6214 | 2.6 | 16156.4 | 61742 | 2.6 | 160282.24 | 46552 | 2.6 | 120848.96 | 55928 | 15590 | 145412.8 | 40720.24
1185 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Adj. Tel. CT Prop Jack 2 Mtr X 3Mtr | NOS | 27000 | 2.96 | 79920 | 0 | 0 | 0 | 2700 | 2.96 | 7992 | 27000 | 2.95 | 79650 | 25392 | 2.95 | 74906.4 | 24300 | 1608 | 71928 | 5013.6
1186 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Adj. Tel. CT Prop Jack 2.5 Mtr X 2.5Mtr | NOS | 28650 | 2.96 | 84804 | 0 | 0 | 0 | 2865 | 2.96 | 8480.4 | 27000 | 2.95 | 79650 | 25576 | 2.95 | 75449.24 | 25785 | 3074 | 76323.6 | 9354.76
1187 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Base Jack 0.375 Mtr. | NOS | 36000 | 0.53 | 19080 | 0 | 0 | 0 | 3600 | 0.53 | 1908 | 36000 | 0.53 | 19116 | 0 | 0 | 0 | 32400 | 36000 | 17172 | 19080
1188 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)CT Tel. Adjustable Prop Jack(2mX3m)-Base Type | NOS | 144000 | 1.78 | 256320 | 0 | 0 | 0 | 14400 | 1.78 | 25632 | 144000 | 1.77 | 254880 | 0 | 0 | 0 | 129600 | 144000 | 230688 | 256320
1189 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)CT Tel. Adjustable Prop Jack(2mX3m)-U Head type | NOS | 183000 | 1.78 | 325740 | 0 | 0 | 0 | 18300 | 1.78 | 32574 | 183000 | 1.77 | 323910 | 183000 | 1.77 | 323910 | 164700 | 0 | 293166 | 1830
1190 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Ledger Horizontal 0.950 Mtr. | NOS | 108000 | 0.53 | 57240 | 0 | 0 | 0 | 10800 | 0.53 | 5724 | 108000 | 0.53 | 57348 | 46368 | 0.53 | 24621.44 | 97200 | 61632 | 51516 | 32618.56
1191 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Ledger Horizontal 1.450 Mtr. | NOS | 108000 | 0.8 | 86400 | 0 | 0 | 0 | 10800 | 0.8 | 8640 | 108000 | 0.8 | 86659.2 | 19872 | 0.8 | 15945.32 | 97200 | 88128 | 77760 | 70454.68
1192 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Ledger Horizontal 1.950 Mtr. | NOS | 45000 | 1.06 | 47700 | 0 | 0 | 0 | 4500 | 1.06 | 4770 | 45000 | 1.06 | 47790 | 36432 | 1.06 | 38690.8 | 40500 | 8568 | 42930 | 9009.2
1193 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Cup-Lock Std. Vertical 2.0 Mtr | NOS | 90000 | 1.06 | 95400 | 0 | 0 | 0 | 9000 | 1.06 | 9540 | 90000 | 1.06 | 95580 | 20608 | 1.06 | 21885.68 | 81000 | 69392 | 85860 | 73514.32
1194 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Joint Pin 0.280 Mtr | NOS | 49000 | 0.24 | 11760 | 0 | 0 | 0 | 4900 | 0.24 | 1176 | 48600 | 0.24 | 11469.6 | 15284 | 0.24 | 3607.04 | 44100 | 33716 | 10584 | 8152.96
1195 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Board Making | SQM | 700 | 80 | 56000 | 0 | 0 | 0 | 70 | 80 | 5600 | 700 | 80 | 56000 | 0 | 0 | 0 | 630 | 700 | 50400 | 56000
1196 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Concreting in Conventional Slab | CUM | 175 | 236 | 41300 | 0 | 0 | 0 | 18 | 236 | 4248 | 175 | 200 | 35000 | 0 | 0 | 0 | 157 | 175 | 37052 | 41300
1197 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Conventional Shuttering (+1.50m - +3.4m) | SQM | 2150 | 255 | 548250 | 0 | 0 | 0 | 215 | 255 | 54825 | 2150 | 255 | 548250 | 0 | 0 | 0 | 1935 | 2150 | 493425 | 548250
1198 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Cut Out Making & Fixing (Thermocol) | NOS | 70 | 50 | 3500 | 0 | 0 | 0 | 7 | 50 | 350 | 70 | 50 | 3500 | 0 | 0 | 0 | 63 | 70 | 3150 | 3500
1199 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Cut-Out Making & Fixing (Ply) | NOS | 20 | 100 | 2000 | 0 | 0 | 0 | 2 | 100 | 200 | 20 | 100 | 2000 | 0 | 0 | 0 | 18 | 20 | 1800 | 2000
1200 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for fixing 20mm/25mm PVC pipe excluding bracket fixing | NOS | 500 | 40 | 20000 | 0 | 0 | 0 | 50 | 40 | 2000 | 500 | 40 | 20000 | 0 | 0 | 0 | 450 | 500 | 18000 | 20000
1201 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Reinforcement Work (+1.50m - +3.40m) | MT | 31.75 | 6000 | 190500 | 0 | 0 | 0 | 3 | 6000 | 18000 | 31.75 | 6000 | 190500 | 0 | 0 | 0 | 28.75 | 31.75 | 172500 | 190500
1202 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)L/C for Staging Work (Above 3.0Mtr from Base) | CUM | 1000 | 29.5 | 29500 | 0 | 0 | 0 | 100 | 29.5 | 2950 | 1000 | 25 | 25000 | 0 | 0 | 0 | 900 | 1000 | 26550 | 29500
1203 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 15 | 885 | 13275 | 0 | 0 | 0 | 2 | 885 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 15 | 11505 | 13275
1204 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 50 | 535 | 26750 | 0 | 0 | 0 | 5 | 535 | 2675 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 24075 | 26750
1205 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)1.5" NAIL | KG | 250 | 100 | 25000 | 250 | 100 | 25000 | 25 | 100 | 2500 | 250 | 77.14 | 19285 | 55 | 79.03 | 4346.45 | 225 | 195 | 22500 | 20653.55
1206 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)10 MM DIA TMT | MT | 4.134 | 55000 | 227370 | 2.427 | 55000 | 133485 | 0 | 55000 | 0 | 2.427 | 52995.39 | 128619.8103 | 2.427 | 52829.42 | 128217 | 4.134 | 1.707 | 227370 | 99153
1207 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 113.219 | 1770 | 200397.63 | 113.219 | 1770 | 200397.63 | 11 | 1770 | 19470 | 113.219 | 1307.25 | 148005.5378 | 39.452 | 1384.09 | 54605.3 | 102.219 | 73.767 | 180927.63 | 145792.33
1208 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)12 MM DIA TMT | MT | 2.162 | 54500 | 117829 | 0.149 | 54500 | 8120.5 | 0 | 54500 | 0 | 0.149 | 56343.81 | 8395.2278 | 0.149 | 57060.54 | 8502.02 | 2.162 | 2.013 | 117829 | 109326.98
1209 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 302 | 2194.8 | 662829.6 | 302 | 2194.8 | 662829.6 | 30 | 2194.8 | 65844 | 302 | 2201.42 | 664828.84 | 202 | 2199.5 | 444298.45 | 272 | 100 | 596985.6 | 218531.15
1210 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)12mm Th. MS Insert Plate (100mm X 100mm) | KG | 80 | 82.6 | 6608 | 0 | 0 | 0 | 8 | 82.6 | 660.8 | 0 | 0 | 0 | 25 | 78.24 | 1956 | 72 | 55 | 5947.2 | 4652
1211 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)16 MM DIA TMT | MT | 8.31 | 54500 | 452895 | 8.31 | 54500 | 452895 | 1 | 54500 | 54500 | 8.31 | 54559.45 | 453389.04 | 8.31 | 54545.07 | 453269.52 | 7.31 | 0 | 398395 | -374.52
1212 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)2"CONCRETE NAIL | KG | 18 | 1 | 18 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 9 | 188.8 | 1699.2 | 16 | 9 | 16 | -1681.2
1213 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)20 mm concrete cover block | NOS | 40930 | 1.78 | 72855.4 | 40930 | 1.78 | 72855.4 | 4093 | 1.78 | 7285.54 | 40930 | 1.22 | 49999.7 | 2500 | 1.26 | 3150 | 36837 | 38430 | 65569.86 | 69705.4
1214 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 11.416 | 50000 | 570800 | 11.416 | 50000 | 570800 | 1 | 50000 | 50000 | 11.416 | 57234.43 | 653388.1961 | 11.416 | 57268 | 653771.47 | 10.416 | 0 | 520800 | -82971.47
1215 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 87.842 | 1750 | 153723.5 | 87.842 | 1750 | 153723.5 | 9 | 1750 | 15750 | 72.2 | 1937.25 | 139869.4428 | 41.926 | 1988.87 | 83385.51 | 78.842 | 45.916 | 137973.5 | 70337.99
1216 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 400 | 55.6 | 22240 | 383.359 | 55.6 | 21314.76 | 40 | 55.6 | 2224 | 383.359 | 77.82 | 29833.0005 | 125 | 76.47 | 9558.54 | 360 | 275 | 20016 | 12681.46
1217 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 200 | 82.6 | 16520 | 200 | 82.6 | 16520 | 20 | 82.6 | 1652 | 200 | 69.62 | 13924 | 6 | 69.62 | 417.72 | 180 | 194 | 14868 | 16102.28
1218 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)3" NAIL | KG | 235 | 51 | 11985 | 200 | 51 | 10200 | 24 | 51 | 1224 | 200 | 74.72 | 14944 | 183 | 79.1 | 14475.18 | 211 | 52 | 10761 | -2490.18
1219 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)3"X2" Pine Batten | CFT | 750 | 796.5 | 597375 | 750 | 796.5 | 597375 | 75 | 796.5 | 59737.5 | 750 | 806.09 | 604567.5 | 600 | 812.88 | 487730.41 | 675 | 150 | 537637.5 | 109644.59
1220 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)3'' X 2'' X 7'0"-8' 0"HARDWOOD | CFT | 350 | 430 | 150500 | 350 | 430 | 150500 | 35 | 430 | 15050 | 350 | 519.2 | 181720 | 93.09 | 519.2 | 48332.33 | 315 | 256.91 | 135450 | 102167.67
1221 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 4050 | 3.06 | 12393 | 4050 | 3.06 | 12393 | 405 | 3.06 | 1239.3 | 4050 | 3.46 | 14017.75 | 1550 | 3.48 | 5400.77 | 3645 | 2500 | 11153.7 | 6992.23
1222 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)4" NAIL | KG | 150 | 51 | 7650 | 150 | 51 | 7650 | 15 | 51 | 765 | 150 | 72.31 | 10846.5 | 42 | 80.9 | 3397.63 | 135 | 108 | 6885 | 4252.37
1223 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)8 MM DIA TMT | MT | 14.226 | 56000.01 | 796656.14 | 12.204 | 56000.01 | 683424.12 | 1 | 56000.01 | 56000.01 | 12.204 | 54930.89 | 670376.6309 | 12.21 | 55030.42 | 671921.48 | 13.226 | 2.016 | 740656.132 | 124734.6623
1224 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 1 | 8200.01 | 8200.01 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 21.267 | 7600 | 161629.2 | 1 | -20.267 | 8200.01 | -153429.19
1225 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)Diesel | LTR | 200 | 92 | 18400 | 200 | 92 | 18400 | 20 | 92 | 1840 | 200 | 91.76 | 18352 | 200 | 91.76 | 18352 | 180 | 0 | 16560 | 48
1226 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)FLY ASH | MT | 1 | 1396.5 | 1396.5 | 0 | 0 | 0 | 0 | 1396.5 | 0 | 0 | 0 | 0 | 7.959 | 1396.5 | 11114.74 | 1 | -6.959 | 1396.5 | -9718.24
1227 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 1 | 424.8 | 424.8 | 0 | 0 | 0 | 0 | 424.8 | 0 | 0 | 0 | 0 | 4 | 413 | 1652 | 1 | -3 | 424.8 | -1227.2
1228 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)M.C. SAND | MT | 151.458 | 1711.5 | 259220.37 | 151.458 | 1711.5 | 259220.37 | 15 | 1711.5 | 25672.5 | 142.79 | 1837.5 | 262376.6388 | 62.131 | 1859.78 | 115549.69 | 136.458 | 89.327 | 233547.867 | 143670.677
1229 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 110 | 47.2 | 5192 | 110 | 47.2 | 5192 | 11 | 47.2 | 519.2 | 110 | 89.68 | 9864.8 | 0 | 0 | 0 | 99 | 110 | 4672.8 | 5192
1230 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)PPC CEMENT | BAG | 1405 | 283.59 | 398443.95 | 1400 | 283.59 | 397026 | 141 | 283.59 | 39986.19 | 1400 | 290.01 | 406013.44 | 39 | 285.58 | 11137.63 | 1264 | 1366 | 358457.76 | 387306.32
1231 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 73 | 7257 | 529761 | 73 | 7257 | 529761 | 7 | 7257 | 50799 | 73 | 7199.99 | 525599.5716 | 46.761 | 7269.45 | 339926.79 | 66 | 26.239 | 478962 | 189834.21
1232 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)Sika Rustoff 100 | KG | 5 | 247.8 | 1239 | 5 | 247.8 | 1239 | 1 | 247.8 | 247.8 | 5 | 225 | 1125.005 | 0 | 0 | 0 | 4 | 5 | 991.2 | 1239
1233 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)Sika Rustop | PKT | 4 | 295 | 1180 | 4 | 295 | 1180 | 0 | 295 | 0 | 4 | 200 | 800 | 0 | 0 | 0 | 4 | 4 | 1180 | 1180
1234 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 1 | 120.36 | 120.36 | 0 | 0 | 0 | 0 | 120.36 | 0 | 0 | 0 | 0 | 131 | 111.59 | 14618.5 | 1 | -130 | 120.36 | -14498.14
1235 | CONVEN. PLY SHUTTERING : VENI G+1 - +1.50 M TO +3.40M | 10 | Started | Material | (M)SIKAPLAST 2004 NS | KG | 610.01 | 70.8 | 43188.71 | 610.01 | 70.8 | 43188.71 | 61 | 70.8 | 4318.8 | 610.01 | 70.8 | 43188.708 | 0 | 0 | 0 | 549.01 | 610.01 | 38869.908 | 43188.708
1236 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Board Making | SQM | 500 | 80 | 40000 | 0 | 0 | 0 | 50 | 80 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 500 | 36000 | 40000
1237 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Concreting in Conventional Slab | CUM | 190 | 236 | 44840 | 0 | 0 | 0 | 19 | 236 | 4484 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 190 | 40356 | 44840
1238 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Conventional Shuttering (+3.40m - +6.45m) | SQM | 2165 | 275 | 595375 | 0 | 0 | 0 | 217 | 275 | 59675 | 0 | 0 | 0 | 0 | 0 | 0 | 1948 | 2165 | 535700 | 595375
1239 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Cut Out Making & Fixing (Thermocol) | NOS | 70 | 50 | 3500 | 0 | 0 | 0 | 7 | 50 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 70 | 3150 | 3500
1240 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Cut-Out Making & Fixing (Ply) | NOS | 20 | 100 | 2000 | 0 | 0 | 0 | 2 | 100 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 1800 | 2000
1241 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for fixing 20mm/25mm PVC pipe excluding bracket fixing | NOS | 500 | 40 | 20000 | 0 | 0 | 0 | 50 | 40 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 500 | 18000 | 20000
1242 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for fixing of MS Insert Plate | NOS | 80 | 50 | 4000 | 0 | 0 | 0 | 8 | 50 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 80 | 3600 | 4000
1243 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Lifting of Reinforcement Steel | MT | 33.692 | 200 | 6738.4 | 0 | 0 | 0 | 3 | 200 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 30.692 | 33.692 | 6138.4 | 6738.4
1244 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Lifting of Shuttering Material | PER/SQFT | 23305 | 5 | 116525 | 0 | 0 | 0 | 2331 | 5 | 11655 | 0 | 0 | 0 | 0 | 0 | 0 | 20974 | 23305 | 104870 | 116525
1245 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for RCC Pouring in Wall/Col. incl. pipeline making | CUM | 91 | 300 | 27300 | 0 | 0 | 0 | 9 | 300 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 91 | 24600 | 27300
1246 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Reinforcement Work (+3.40m - +6.45m) | MT | 33.692 | 6100 | 205521.2 | 0 | 0 | 0 | 3 | 6100 | 18300 | 0 | 0 | 0 | 0 | 0 | 0 | 30.692 | 33.692 | 187221.2 | 205521.2
1247 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)L/C for Staging/Gangway for Col. & RCC Wall | CUM | 450 | 33.04 | 14868 | 0 | 0 | 0 | 45 | 33.04 | 1486.8 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 450 | 13381.2 | 14868
1248 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Labour | (L)Labour Charges for Column/Wall Starter Making | RMT | 306 | 66.08 | 20220.48 | 0 | 0 | 0 | 31 | 66.08 | 2048.48 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 306 | 18172 | 20220.48
1249 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)10 MM DIA TMT | MT | 3.021 | 55000 | 166155 | 0.725 | 55000 | 39875 | 0 | 55000 | 0 | 0.725 | 52220.61 | 37859.9455 | 0.426 | 52928.52 | 22547.55 | 3.021 | 2.595 | 166155 | 143607.45
1250 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 180 | 1770 | 318600 | 0 | 0 | 0 | 18 | 1770 | 31860 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 180 | 286740 | 318600
1251 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)12 MM DIA TMT | MT | 2.189 | 54500 | 119300.5 | 1.495 | 54500 | 81477.5 | 0 | 54500 | 0 | 1.495 | 51523.69 | 77027.9168 | 1.526 | 54676.14 | 83435.79 | 2.189 | 0.663 | 119300.5 | 35864.71
1252 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)16 MM DIA TMT | MT | 8.5 | 54500 | 463250 | 8.061 | 54500 | 439324.5 | 1 | 54500 | 54500 | 8.061 | 51421 | 414504.6537 | 8.025 | 51421.93 | 412661.01 | 7.5 | 0.475 | 408750 | 50588.99
1253 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 8.872 | 50000 | 443600 | 8.872 | 50000 | 443600 | 1 | 50000 | 50000 | 8.872 | 54386.01 | 482512.6833 | 8.859 | 54318.61 | 481208.6 | 7.872 | 0.013 | 393600 | -37608.6
1254 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 140 | 1750 | 245000 | 0 | 0 | 0 | 14 | 1750 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 140 | 220500 | 245000
1255 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 400 | 55.6 | 22240 | 150 | 55.6 | 8340 | 40 | 55.6 | 2224 | 150 | 77.71 | 11656.5 | 0 | 0 | 0 | 360 | 400 | 20016 | 22240
1256 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 200 | 82.6 | 16520 | 200 | 82.6 | 16520 | 20 | 82.6 | 1652 | 200 | 69.62 | 13924 | 0 | 0 | 0 | 180 | 200 | 14868 | 16520
1257 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)30mm Circular PVC Cover Block | NOS | 13000 | 3.06 | 39780 | 13000 | 3.06 | 39780 | 1300 | 3.06 | 3978 | 13000 | 3.37 | 43745 | 0 | 0 | 0 | 11700 | 13000 | 35802 | 39780
1258 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)8 MM DIA TMT | MT | 13.66 | 56000.01 | 764960.14 | 7.228 | 56000.01 | 404768.07 | 1 | 56000.01 | 56000.01 | 7.228 | 55634.19 | 402123.9223 | 7.301 | 55769.04 | 407169.73 | 12.66 | 6.359 | 708960.127 | 357790.4066
1259 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)M.C. SAND | MT | 243.32 | 1711.5 | 416442.18 | 0 | 0 | 0 | 24 | 1711.5 | 41076 | 0 | 0 | 0 | 0 | 0 | 0 | 219.32 | 243.32 | 375366.18 | 416442.18
1260 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)PPC CEMENT | BAG | 2252 | 283.59 | 638644.68 | 100 | 283.59 | 28359 | 225 | 283.59 | 63807.75 | 100 | 290.01 | 29000.96 | 0 | 0 | 0 | 2027 | 2252 | 574836.93 | 638644.68
1261 | CONVEN. PLY SHUTTERING : VENI G+2 - +3.40M TO +6.45M | 10 | Started | Material | (M)SIKAPLAST 2004 NS | KG | 965 | 70.8 | 68322 | 740 | 70.8 | 52392 | 97 | 70.8 | 6867.6 | 740 | 70.8 | 52392 | 0 | 0 | 0 | 868 | 965 | 61454.4 | 68322
1262 | MASONRY : PRAYAG T-1 | 0 | Started | Material | (M)FLY ASH BRICKS | NOS | 7000 | 1 | 7000 | 7000 | 1 | 7000 | 0 | 1 | 0 | 7000 | 8.96 | 62720 | 600 | 8.96 | 5376 | 7000 | 6400 | 7000 | 1624 | SUPER STRUCTURE
1263 | MASONRY : PRAYAG T-1 | 0 | Started | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0.584 | 1860.22 | 1086.37 | 1 | 0.416 | 1711.5 | 625.13 | SUPER STRUCTURE
1264 | MASONRY : PRAYAG T-1 | 0 | Started | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 4 | 285.58 | 1142.32 | 1 | -3 | 283.59 | -858.73 | SUPER STRUCTURE
1265 | LOCAL VENDER MATERIALS - Sup. Material from Local | 10 | Started | Material | (M)10 MM (1/2")STONE CHIPS | CFT | 9000 | 78.76 | 708840 | 8810 | 78.76 | 693875.6 | 900 | 78.76 | 70884 | 8810 | 78.75 | 693787.5 | 8810 | 78.75 | 693787.5 | 8100 | 190 | 637956 | 15052.5 | SUPER STRUCTURE
1266 | LOCAL VENDER MATERIALS - Sup. Material from Local | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 75000 | 10 | 750000 | 65000 | 10 | 650000 | 7500 | 10 | 75000 | 65000 | 12.6 | 819000 | 65000 | 12.35 | 802652.5 | 67500 | 10000 | 675000 | -52652.5 | SUPER STRUCTURE
1267 | LOCAL VENDER MATERIALS - Sup. Material from Local | 10 | Started | Material | (M)5/8 Stone Chips-20MM | CFT | 31800 | 80 | 2544000 | 31365 | 80 | 2509200 | 3180 | 80 | 254400 | 31365 | 82.52 | 2588260 | 27865 | 82.84 | 2308259.99 | 28620 | 3935 | 2289600 | 235740.01 | SUPER STRUCTURE
1268 | LOCAL VENDER MATERIALS - Sup. Material from Local | 10 | Started | Material | (M)M/c Sand | CFT | 32300 | 73.33 | 2368559 | 32285 | 73.33 | 2367459.05 | 3230 | 73.33 | 236855.9 | 32285 | 72.41 | 2337897.4 | 28785 | 72.71 | 2092897.42 | 29070 | 3515 | 2131703.1 | 275661.58 | SUPER STRUCTURE
1269 | UGR : CIVIL WORK | 0 | Started | Labour | (L)250/230/200 MM BRICK WORK | CUM | 26 | 700 | 18200 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 18200 | 18200
1270 | UGR : CIVIL WORK | 0 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 1200 | 141.6 | 169920 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 169920 | 169920
1271 | UGR : CIVIL WORK | 0 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 510 | 82.6 | 42126 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 510 | 42126 | 42126
1272 | UGR : CIVIL WORK | 0 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 376 | 50 | 18800 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 376 | 18800 | 18800
1273 | UGR : CIVIL WORK | 0 | Started | Labour | (L)EARTH WORK IN ALL EXCAVATION MECHANICALLY | CUM | 2630 | 305 | 802150 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | 2630 | 802150 | 802150
1274 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Board Making | SQM | 595.8 | 80 | 47664 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.8 | 595.8 | 47664 | 47664
1275 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Conventional Shuttering Works | SQM | 1500 | 257 | 385500 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 385500 | 385500
1276 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Cut-Out Making & Fixing (Ply) | NOS | 20 | 100 | 2000 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 2000 | 2000
1277 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for driving Z Section Sheet Piles by Power Winch | MT | 53.295 | 5500 | 293122.5 | 0 | 0 | 0 | 0 | 5500 | 0 | 53.295 | 5500 | 293122.5 | 41.76 | 5500 | 229680 | 53.295 | 11.535 | 293122.5 | 63442.5
1278 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for extracting Z section Sheet Piles by Power Winch | MT | 53.295 | 5700 | 303781.5 | 0 | 0 | 0 | 0 | 5700 | 0 | 53.295 | 5700 | 303781.5 | 0 | 0 | 0 | 53.295 | 53.295 | 303781.5 | 303781.5
1279 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Fabrication & Erection of supporting Str. Members | MT | 7 | 7000 | 49000 | 0 | 0 | 0 | 0 | 7000 | 0 | 7 | 7000 | 49000 | 0 | 0 | 0 | 7 | 7 | 49000 | 49000
1280 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for M-25 Grade Pouring in Col. (Head Load) | CUM | 30 | 450 | 13500 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 13500 | 13500
1281 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Manhole Cover Fixing | NOS | 13 | 425 | 5525 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 5525 | 5525
1282 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for RCC M-25 Pouring in Fdn. (w/concrete pump pipeline ) | CUM | 275 | 236 | 64900 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 275 | 64900 | 64900
1283 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for RCC Pouring in Wall/Col. incl. pipeline making | CUM | 120 | 300 | 36000 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 36000 | 36000
1284 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Rung Ladder Fixing | NOS | 141 | 177 | 24957 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 141 | 24957 | 24957
1285 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Staging Work (Above 3.0Mtr from Base) | CUM | 400 | 29.5 | 11800 | 0 | 0 | 0 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 11800 | 11800
1286 | UGR : CIVIL WORK | 0 | Started | Labour | (L)L/C for Staging/Gangway for Col. & RCC Wall | CUM | 934 | 33.04 | 30859.36 | 0 | 0 | 0 | 0 | 33.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 934 | 30859.36 | 30859.36
1287 | UGR : CIVIL WORK | 0 | Started | Labour | (L)Labour Charges for Column/Wall Starter Making | RMT | 297 | 66.08 | 19625.76 | 0 | 0 | 0 | 0 | 66.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 297 | 19625.76 | 19625.76
1288 | UGR : CIVIL WORK | 0 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 40 | 6490 | 259600 | 0 | 0 | 0 | 0 | 6490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 259600 | 259600
1289 | UGR : CIVIL WORK | 0 | Started | Labour | (L)MANUAL EXCAVATION | CUM | 152 | 206.5 | 31388 | 0 | 0 | 0 | 0 | 206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 152 | 31388 | 31388
1290 | UGR : CIVIL WORK | 0 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 30 | 700 | 21000 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 21000 | 21000
1291 | UGR : CIVIL WORK | 0 | Started | Labour | (L)MS SLEEVE FIXING | NOS | 30 | 320 | 9600 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 9600 | 9600
1292 | UGR : CIVIL WORK | 0 | Started | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 46 | 118 | 5428 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 5428 | 5428
1293 | UGR : CIVIL WORK | 0 | Started | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 46 | 40 | 1840 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 1840 | 1840
1294 | UGR : CIVIL WORK | 0 | Started | Labour | (L)PILE HEAD DISMENTLING | RMT | 231 | 500 | 115500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 231 | 115500 | 115500
1295 | UGR : CIVIL WORK | 0 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 50 | 885 | 44250 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 44250 | 44250
1296 | UGR : CIVIL WORK | 0 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 500 | 535 | 267500 | 0 | 0 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 267500 | 267500
1297 | UGR : CIVIL WORK | 0 | Started | Labour | (L)VAPOUR BARRIER | SQM | 376 | 82.6 | 31057.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 376 | 31057.6 | 31057.6
1298 | UGR : CIVIL WORK | 0 | Started | Material | (M)1.5" NAIL | KG | 150 | 100 | 15000 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 15000 | 15000
1299 | UGR : CIVIL WORK | 0 | Started | Material | (M)10 MM DIA TMT | MT | 6.516 | 55000 | 358380 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.516 | 6.516 | 358380 | 358380
1300 | UGR : CIVIL WORK | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 275 | 1770 | 486750 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 275 | 486750 | 486750
1301 | UGR : CIVIL WORK | 0 | Started | Material | (M)12 MM DIA TMT | MT | 2.401 | 54500 | 130854.5 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.401 | 2.401 | 130854.5 | 130854.5
1302 | UGR : CIVIL WORK | 0 | Started | Material | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 115 | 2194.8 | 252402 | 0 | 0 | 0 | 0 | 2194.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 115 | 252402 | 252402
1303 | UGR : CIVIL WORK | 0 | Started | Material | (M)2" NAIL | KG | 200 | 51 | 10200 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 10200 | 10200
1304 | UGR : CIVIL WORK | 0 | Started | Material | (M)20 mm concrete cover block | NOS | 300 | 1.78 | 534 | 0 | 0 | 0 | 0 | 1.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 534 | 534
1305 | UGR : CIVIL WORK | 0 | Started | Material | (M)20 MM DIA TMT. | MT | 2.212 | 50000 | 110600 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.212 | 2.212 | 110600 | 110600
1306 | UGR : CIVIL WORK | 0 | Started | Material | (M)20 MM STONE CHIPS. | MT | 280 | 1750 | 490000 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 490000 | 490000
1307 | UGR : CIVIL WORK | 0 | Started | Material | (M)2ND CLASS BRICKS | NOS | 11130 | 10 | 111300 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11130 | 11130 | 111300 | 111300
1308 | UGR : CIVIL WORK | 0 | Started | Material | (M)3" NAIL | KG | 200 | 51 | 10200 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 10200 | 10200
1309 | UGR : CIVIL WORK | 0 | Started | Material | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 400 | 430 | 172000 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 172000 | 172000
1310 | UGR : CIVIL WORK | 0 | Started | Material | (M)3"X2" Pine Batten | CFT | 100 | 767 | 76700 | 0 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 76700 | 76700
1311 | UGR : CIVIL WORK | 0 | Started | Material | (M)4" NAIL | KG | 100 | 51 | 5100 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 5100 | 5100
1312 | UGR : CIVIL WORK | 0 | Started | Material | (M)40mm Circular PVC Cover Block | NOS | 200 | 5.32 | 1064 | 0 | 0 | 0 | 0 | 5.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 1064 | 1064
1313 | UGR : CIVIL WORK | 0 | Started | Material | (M)50mm Concrete Cover Block | NOS | 400 | 3.54 | 1416 | 0 | 0 | 0 | 0 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 1416 | 1416
1314 | UGR : CIVIL WORK | 0 | Started | Material | (M)50mm PVC round Cover Block | NOS | 950 | 4.14 | 3933 | 0 | 0 | 0 | 0 | 4.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 950 | 3933 | 3933
1315 | UGR : CIVIL WORK | 0 | Started | Material | (M)75 mm Concrete Cover Block | NOS | 350 | 4.72 | 1652 | 0 | 0 | 0 | 0 | 4.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 1652 | 1652
1316 | UGR : CIVIL WORK | 0 | Started | Material | (M)8 MM DIA TMT | MT | 3.7 | 56000.01 | 207200.04 | 2.957 | 56000.01 | 165592.03 | 0 | 56000.01 | 0 | 2.957 | 52274 | 154574.2207 | 0 | 0 | 0 | 3.7 | 3.7 | 207200.037 | 207200.037
1317 | UGR : CIVIL WORK | 0 | Started | Material | (M)M.C. SAND | MT | 435 | 1711.5 | 744502.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435 | 435 | 744502.5 | 744502.5
1318 | UGR : CIVIL WORK | 0 | Started | Material | (M)PICKED JHAMA. | NOS | 13400 | 11 | 147400 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13400 | 13400 | 147400 | 147400
1319 | UGR : CIVIL WORK | 0 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 350 | 47.2 | 16520 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 16520 | 16520
1320 | UGR : CIVIL WORK | 0 | Started | Material | (M)POLYTHENE SHEET | KG | 180 | 110 | 19800 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 19800 | 19800
1321 | UGR : CIVIL WORK | 0 | Started | Material | (M)PPC CEMENT | BAG | 3700 | 283.59 | 1049283 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 3700 | 1049283 | 1049283
1322 | UGR : CIVIL WORK | 0 | Started | Material | (M)SIKAPLAST 2004 NS | KG | 1490 | 70.8 | 105492 | 0 | 0 | 0 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1490 | 1490 | 105492 | 105492
1323 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 645 | 141.6 | 91332 | 0 | 0 | 0 | 65 | 141.6 | 9204 | 645 | 150 | 96750 | 0 | 0 | 0 | 580 | 645 | 82128 | 91332
1324 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 225.21 | 50 | 11260.5 | 0 | 0 | 0 | 23 | 50 | 1150 | 225.21 | 55 | 12386.55 | 0 | 0 | 0 | 202.21 | 225.21 | 10110.5 | 11260.5
1325 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY BEYOND 3M BUT UPTO 5 M | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1326 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY UPTO 3M FROM EGL | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1327 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)HIRE CH. FOR DUMPER | DAYS | 8 | 11210 | 89680 | 0 | 0 | 0 | 1 | 11210 | 11210 | 8 | 11210 | 89680 | 0 | 0 | 0 | 7 | 8 | 78470 | 89680
1328 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for 450mm Dia Auger Pile in RWHT | LS | 1 | 206500 | 206500 | 0 | 0 | 0 | 0 | 206500 | 0 | 1 | 206500 | 206500 | 1 | 206500 | 206500 | 1 | 0 | 206500 | 0
1329 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for Board Making | SQM | 500 | 80 | 40000 | 0 | 0 | 0 | 50 | 80 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 500 | 36000 | 40000
1330 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for M-25 Grade Pouring in Col. (Head Load) | CUM | 2.46 | 450 | 1107 | 0 | 0 | 0 | 0 | 450 | 0 | 2.46 | 450 | 1107 | 0 | 0 | 0 | 2.46 | 2.46 | 1107 | 1107
1331 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for Manhole Cover Fixing | NOS | 6 | 425 | 2550 | 0 | 0 | 0 | 1 | 425 | 425 | 6 | 425 | 2550 | 0 | 0 | 0 | 5 | 6 | 2125 | 2550
1332 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for RMC Concreting in RCC Walls | CUM | 100.08 | 354 | 35428.32 | 0 | 0 | 0 | 10 | 354 | 3540 | 100.08 | 300 | 30024 | 0 | 0 | 0 | 90.08 | 100.08 | 31888.32 | 35428.32
1333 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for Rung Ladder Fixing | NOS | 48 | 177 | 8496 | 0 | 0 | 0 | 5 | 177 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 48 | 7611 | 8496
1334 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for Staging Work (Above 3.0Mtr from Base) | CUM | 86 | 29.5 | 2537 | 0 | 0 | 0 | 9 | 29.5 | 265.5 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 86 | 2271.5 | 2537
1335 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for Staging/Gangway for Col. & RCC Wall | CUM | 472 | 33.04 | 15594.88 | 0 | 0 | 0 | 47 | 33.04 | 1552.88 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 472 | 14042 | 15594.88
1336 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)L/C for Tie Rod Hole filling in Columns | NOS | 950 | 6.5 | 6175 | 0 | 0 | 0 | 95 | 6.5 | 617.5 | 950 | 5.5 | 5225 | 0 | 0 | 0 | 855 | 950 | 5557.5 | 6175
1337 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)Labour Charges for Column/Wall Starter Making | RMT | 96.1 | 66.08 | 6350.29 | 0 | 0 | 0 | 10 | 66.08 | 660.8 | 0 | 0 | 0 | 0 | 0 | 0 | 86.1 | 96.1 | 5689.488 | 6350.288
1338 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)Labour Charges for Reinforcement Steel Work | MT | 21.019 | 6490 | 136413.31 | 0 | 0 | 0 | 2 | 6490 | 12980 | 0 | 0 | 0 | 0 | 0 | 0 | 19.019 | 21.019 | 123433.31 | 136413.31
1339 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)LABOUR CHARGES FOR RMC CONCRETING | CUM | 112.92 | 200.6 | 22651.75 | 0 | 0 | 0 | 11 | 200.6 | 2206.6 | 112.92 | 170 | 19196.4 | 0 | 0 | 0 | 101.92 | 112.92 | 20445.152 | 22651.752
1340 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)MECH. EXCAVATION (EGL-FDN. BOTT.)& STACKING IN SITE | CUM | 3157 | 188.8 | 596041.6 | 0 | 0 | 0 | 316 | 188.8 | 59660.8 | 3157 | 188.8 | 596041.6 | 0 | 0 | 0 | 2841 | 3157 | 536380.8 | 596041.6
1341 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 17.4 | 700 | 12180 | 0 | 0 | 0 | 2 | 700 | 1400 | 17.4 | 750 | 13050 | 0 | 0 | 0 | 15.4 | 17.4 | 10780 | 12180
1342 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 7 | 118 | 826 | 0 | 0 | 0 | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 708 | 826
1343 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 7 | 40 | 280 | 0 | 0 | 0 | 1 | 40 | 40 | 7 | 100 | 700 | 0 | 0 | 0 | 6 | 7 | 240 | 280
1344 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)PILE HEAD DISMENTLING | RMT | 30.45 | 500 | 15225 | 0 | 0 | 0 | 3 | 500 | 1500 | 30.45 | 565 | 17204.25 | 0 | 0 | 0 | 27.45 | 30.45 | 13725 | 15225
1345 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)POCKLAIN TRANSPORTATION CHARGE ONE SIDE | LS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1346 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)Shutterring with Centering using Ply/Mivan Panels | SQM | 850 | 303.86 | 258281 | 0 | 0 | 0 | 85 | 303.86 | 25828.1 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 850 | 232452.9 | 258281
1347 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)Transportation charges for pocklain after initial deployment | LS | 3 | 8260 | 24780 | 0 | 0 | 0 | 0 | 8260 | 0 | 3 | 8260 | 24780 | 0 | 0 | 0 | 3 | 3 | 24780 | 24780
1348 | RWHT - Civil Work and Recharge PIT | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 225.21 | 82.6 | 18602.35 | 0 | 0 | 0 | 23 | 82.6 | 1899.8 | 225.21 | 50 | 11260.5 | 0 | 0 | 0 | 202.21 | 225.21 | 16702.546 | 18602.346
1349 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)1.5" NAIL | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1350 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)10 MM DIA TMT | MT | 0.415 | 55000 | 22825 | 0.411 | 55000 | 22605 | 0 | 55000 | 0 | 0.411 | 58380.99 | 23994.5849 | 0 | 0 | 1906.66 | 0.415 | 0.415 | 22825 | 20918.34
1351 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 9 | 1770 | 15930 | 9 | 1770 | 15930 | 1 | 1770 | 1770 | 9 | 1501.5 | 13513.5 | 0 | 0 | 0 | 8 | 9 | 14160 | 15930
1352 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)12 MM DIA TMT | MT | 16.598 | 54500 | 904591 | 16.598 | 54500 | 904591 | 2 | 54500 | 109000 | 16.598 | 58381 | 969007.7616 | 0.736 | 147192.08 | 108333.37 | 14.598 | 15.862 | 795591 | 796257.63
1353 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 30 | 2194.8 | 65844 | 30 | 2194.8 | 65844 | 3 | 2194.8 | 6584.4 | 30 | 2190.08 | 65702.4 | 0 | 0 | 0 | 27 | 30 | 59259.6 | 65844
1354 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)16 MM DIA TMT | MT | 2.803 | 54500 | 152763.5 | 2.803 | 54500 | 152763.5 | 0 | 54500 | 0 | 2.803 | 58381 | 163641.9298 | 0 | 0 | 17862.13 | 2.803 | 2.803 | 152763.5 | 134901.37
1355 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 0.18 | 50000 | 9000 | 0.175 | 50000 | 8750 | 0 | 50000 | 0 | 0.175 | 58381 | 10216.6743 | 0 | 0 | 1115.17 | 0.18 | 0.18 | 9000 | 7884.83
1356 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 18 | 1750 | 31500 | 18 | 1750 | 31500 | 2 | 1750 | 3500 | 18 | 2068.5 | 37233 | 0 | 0 | 0 | 16 | 18 | 28000 | 31500
1357 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 250 | 55.6 | 13900 | 241.08 | 55.6 | 13404.05 | 25 | 55.6 | 1390 | 241.08 | 75.52 | 18206.3616 | 10 | 75.52 | 755.2 | 225 | 240 | 12510 | 13144.8
1358 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1359 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)3" NAIL | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1360 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)3"X2" Pine Batten | CFT | 150 | 767 | 115050 | 150 | 767 | 115050 | 15 | 767 | 11505 | 150 | 827.97 | 124195.5 | 0 | 0 | 0 | 135 | 150 | 103545 | 115050
1361 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)4" NAIL | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1362 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)6 MM MILD STEEL | MT | 0.165 | 59206.5 | 9769.07 | 0.161 | 59206.5 | 9532.25 | 0 | 59206.5 | 0 | 0.161 | 59206.55 | 9532.255 | 0.161 | 58392.86 | 9401.25 | 0.165 | 0.004 | 9769.073 | 367.8225
1363 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)600 MM DIA (DOUBLE SEAL) (H.D 45MT CAP.) DI CASTING MANHOLE | NOS | 5 | 18290 | 91450 | 5 | 18290 | 91450 | 1 | 18290 | 18290 | 5 | 10006.4 | 50032 | 0 | 0 | 0 | 4 | 5 | 73160 | 91450
1364 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)600 MM DIA RCPC (15 MT) MANHOLE COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1365 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)8 MM DIA TMT | MT | 1.77 | 56000.01 | 99120.02 | 1.769 | 56000.01 | 99064.02 | 0 | 56000.01 | 0 | 1.769 | 60150.99 | 106407.11 | 0 | 0 | 10716.94 | 1.77 | 1.77 | 99120.018 | 88403.0777
1366 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 1.965 | 8200.01 | 16113.02 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.965 | 1.965 | 16113.02 | 16113.0197
1367 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)FRP COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1368 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)GRIT 2 MM SIZE | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1369 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1370 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)M.C. SAND | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1371 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)PEBBLES 20 MM SIZE | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1372 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)PEBBLES 6 MM SIZE | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1373 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 8000 | 11 | 88000 | 8000 | 11 | 88000 | 800 | 11 | 8800 | 8000 | 8.75 | 70000 | 0 | 0 | 0 | 7200 | 8000 | 79200 | 88000
1374 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1375 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 110 | 110 | 12100 | 105.85 | 110 | 11643.5 | 11 | 110 | 1210 | 105.85 | 141.6 | 14988.36 | 0 | 0 | 0 | 99 | 110 | 10890 | 12100
1376 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)PPC CEMENT | BAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1377 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 17.5 | 7257 | 126997.5 | 17.5 | 7257 | 126997.5 | 2 | 7257 | 14514 | 17.5 | 7350 | 128624.9965 | 16.2 | 7350 | 119069.98 | 15.5 | 1.3 | 112483.5 | 7927.52
1378 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)RUNG LADDER. | NOS | 46 | 1 | 46 | 46 | 1 | 46 | 5 | 1 | 5 | 46 | 135.7 | 6242.2 | 0 | 0 | 0 | 41 | 46 | 41 | 46
1379 | RWHT - Civil Work and Recharge PIT | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1380 | RWHT - Anti Termite and Recharge PIT | 0 | Tentative | Labour | (L)ANTI- TERMITE Imidacloprid 30.50 SC | SQM | 323.97 | 64.9 | 21025.65 | 0 | 0 | 0 | 0 | 64.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323.97 | 323.97 | 21025.653 | 21025.653
1381 | EMBANKMENT PROTECTION - Soil Testing & Survey | 10 | Started | Labour | (L)BATHYMETRY SURVEY | LS | 1 | 59000 | 59000 | 0 | 0 | 0 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 59000 | 0
1382 | EMBANKMENT PROTECTION - Soil Testing & Survey | 10 | Started | Labour | (L)SOIL TESTING | LS | 1 | 88500 | 88500 | 0 | 0 | 0 | 0 | 88500 | 0 | 1 | 88500 | 88500 | 1 | 88500 | 88500 | 1 | 0 | 88500 | 0
1383 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Erection of Tie Rod with Turn Buckle | SET | 150 | 12015.94 | 1802391 | 0 | 0 | 0 | 0 | 12015.94 | 0 | 150 | 12015.94 | 1802391 | 0 | 0 | 0 | 150 | 150 | 1802391 | 1802391 | INFRA
1384 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Fabrication & Erection of Waller | MT | 65.63 | 42775 | 2807323.25 | 0 | 0 | 0 | 0 | 42775 | 0 | 65.63 | 42775 | 2807323.26 | 13.91 | 42775 | 595000.26 | 65.63 | 51.72 | 2807323.25 | 2212322.99 | INFRA
1385 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Fabrication and Painting of Turn Buckle | PCS | 150 | 12154 | 1823100 | 0 | 0 | 0 | 0 | 12154 | 0 | 150 | 12154 | 1823100 | 0 | 0 | 0 | 150 | 150 | 1823100 | 1823100 | INFRA
1386 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Hiring Charges for JCB on Daily Basis (8hrs Shift) | DAYS | 10 | 7552 | 75520 | 0 | 0 | 0 | 0 | 7552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 75520 | 75520 | INFRA
1387 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)HYDRA (FOR 4 HOURS) | DAYS | 40 | 3700 | 148000 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 148000 | 148000 | INFRA
1388 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)HYDRA (FOR 8 HOURS) | DAYS | 15 | 4500 | 67500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 67500 | 67500 | INFRA
1389 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Installation of Sheet Pile by Vibratory Hammer & Crane | MT | 656.1 | 10620 | 6967782 | 0 | 0 | 0 | 0 | 10620 | 0 | 656.097 | 10620 | 6967750.14 | 656.097 | 10620 | 6967750.14 | 656.1 | 0.003 | 6967782 | 31.86 | INFRA
1390 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Mobilisation of Machinery & Manpower (Sheet Pile) | LS | 1 | 708000 | 708000 | 0 | 0 | 0 | 0 | 708000 | 0 | 1 | 708000 | 708000 | 1 | 708000 | 708000 | 1 | 0 | 708000 | 0 | INFRA
1391 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Operator Hiring Charges (8 hours shift) | MAN/DAY | 10 | 472 | 4720 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 4720 | 4720 | INFRA
1392 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Supply, Fab. & Threading of M24 Bolts/Hex Nut of Turn Buckle | NOS | 600 | 348.1 | 208860 | 0 | 0 | 0 | 0 | 348.1 | 0 | 600 | 348.1 | 208860 | 0 | 0 | 0 | 600 | 600 | 208860 | 208860 | INFRA
1393 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Supply, Fabrication & Threading of M64 Hex Nut | PCS | 600 | 634.84 | 380904 | 0 | 0 | 0 | 0 | 634.84 | 0 | 600 | 634.84 | 380904 | 0 | 0 | 0 | 600 | 600 | 380904 | 380904 | INFRA
1394 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)Threading of MS Round bar 63mm OD | SET | 150 | 4720 | 708000 | 0 | 0 | 0 | 0 | 4720 | 0 | 150 | 4720 | 708000 | 0 | 0 | 0 | 150 | 150 | 708000 | 708000 | INFRA
1395 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)TRANSPORT CHARGES FOR 14.50 MTR SHEET PILE | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFRA
1396 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)TRANSPORT CHARGES FOR 4.0 MTR SHEET PILE | MT | 102.4512 | 630 | 64544.26 | 0 | 0 | 0 | 0 | 630 | 0 | 102.4512 | 708 | 72535.44 | 102.45 | 708 | 72534.6 | 102.4512 | 0.0012 | 64544.256 | -7990.344 | INFRA
1397 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Labour | (L)TRANSPORTATION CHARGES FOR 14.5 MTR SHEET PILE | MT | 371.3856 | 1357 | 503970.26 | 0 | 0 | 0 | 0 | 1357 | 0 | 371.3856 | 1357 | 503970.26 | 371.3856 | 1357 | 503970.26 | 371.3856 | 0 | 503970.259 | -0.0008 | INFRA
1398 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)12 MM TH. M.S. PLATE | MT | 10.6 | 70800 | 750480 | 10.5 | 70800 | 743400 | 0 | 70800 | 0 | 10.5 | 65557.43 | 688353 | 10.5 | 65557.43 | 688353 | 10.6 | 0.1 | 750480 | 62127 | INFRA
1399 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)16 MM TH. M.S. PLATE | MT | 17.99 | 70800 | 1273692 | 17.99 | 70800 | 1273692 | 0 | 70800 | 0 | 17.99 | 66318.75 | 1193074.4 | 17.99 | 66318.75 | 1193074.4 | 17.99 | 0 | 1273692 | 80617.6 | INFRA
1400 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)16mm Th. MS Plate (300X300MM) | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFRA
1401 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)25 MM TH. MS PLATE | MT | 4.26 | 81420 | 346849.2 | 4.26 | 81420 | 346849.2 | 0 | 81420 | 0 | 4.26 | 69620 | 296581.2 | 4.26 | 69620 | 296581.2 | 4.26 | 0 | 346849.2 | 50268 | INFRA
1402 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)63 MM DIA MS ROD (E - 350 GRADE) | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFRA
1403 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)63 MM DIA MS ROD (SAE -1018 GRADE) | MT | 66.08 | 64900 | 4288592 | 66.08 | 64900 | 4288592 | 0 | 64900 | 0 | 66.08 | 75283.04 | 4974703 | 66.08 | 75039.81 | 4958630.81 | 66.08 | 0 | 4288592 | -670038.81 | INFRA
1404 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)75 MM TH MS PLATE | MT | 6.582 | 86140 | 566973.48 | 6.58 | 86140 | 566801.2 | 0 | 86140 | 0 | 6.58 | 77290 | 508568.2 | 6.58 | 77290 | 508568.2 | 6.582 | 0.002 | 566973.48 | 58405.28 | INFRA
1405 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)Cutting of PU-32 Sheet Pile | NOS | 580 | 590 | 342200 | 580 | 590 | 342200 | 0 | 590 | 0 | 580 | 590 | 342200 | 580 | 590 | 342200 | 580 | 0 | 342200 | 0 | INFRA
1406 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)I.S.M.C. 100 | MT | 1.545 | 64900 | 100270.5 | 1.54 | 64900 | 99946 | 0 | 64900 | 0 | 1.54 | 63720 | 98128.8 | 1.54 | 63720 | 98128.8 | 1.545 | 0.005 | 100270.5 | 2141.7 | INFRA
1407 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)I.S.M.C. 400 | MT | 37.7 | 68440 | 2580188 | 36.68 | 68440 | 2510379.2 | 0 | 68440 | 0 | 36.68 | 65703.93 | 2410020.2 | 36.68 | 65703.93 | 2410020.2 | 37.7 | 1.02 | 2580188 | 170167.8 | INFRA
1408 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)ISMB 250 | MT | 3.7 | 65490 | 242313 | 3.68 | 65490 | 241003.2 | 0 | 65490 | 0 | 3.68 | 63720 | 234489.6 | 3.68 | 63720 | 234489.6 | 3.7 | 0.02 | 242313 | 7823.4 | INFRA
1409 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)POLYTHENE SHEET | KG | 70 | 110 | 7700 | 70 | 110 | 7700 | 0 | 110 | 0 | 70 | 141.6 | 9912 | 0 | 0 | 0 | 70 | 70 | 7700 | 7700 | INFRA
1410 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)U-Type Hot Rolled Sheet Pile (PU-32) -EN10248(14.5 Mtr.) | NOS | 290 | 150360.36 | 43604504.4 | 290 | 150360.36 | 43604504.4 | 0 | 150360.36 | 0 | 290 | 150360.37 | 43604506.488 | 290 | 150360.37 | 43604506.44 | 290 | 0 | 43604504.4 | -2.04 | INFRA
1411 | EMBANKMENT PROTECTION - Sheet Piling Work | 0 | Started | Material | (M)U-Type Hot Rolled Sheet Pile (PU-32) -EN10248(4.0 Mtr.) | NOS | 290 | 41478.18 | 12028672.2 | 290 | 41478.18 | 12028672.2 | 0 | 41478.18 | 0 | 290 | 41478.18 | 12028672.2 | 290 | 41478.18 | 12028672.2 | 290 | 0 | 12028672.2 | 0 | INFRA
1412 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for 3" Granite Strip Fixing in Kitchen-SIA | RFT | 99.814 | 30 | 2994.42 | 0 | 0 | 0 | 0 | 30 | 0 | 99.814 | 30 | 2994.42 | 0 | 0 | 0 | 99.814 | 99.814 | 2994.42 | 2994.42
1413 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Acid Wash-SIA | SQFT | 10730.69 | 1.5 | 16096.04 | 0 | 0 | 0 | 0 | 1.5 | 0 | 10730.69 | 1.5 | 16096.035 | 0 | 0 | 0 | 10730.69 | 10730.69 | 16096.035 | 16096.035
1414 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Ceramic Tile Dado - SIA | SQFT | 2985.86 | 27 | 80618.22 | 0 | 0 | 0 | 0 | 27 | 0 | 2985.86 | 27 | 80618.22 | 0 | 0 | 0 | 2985.86 | 2985.86 | 80618.22 | 80618.22
1415 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Gas Hole cutting in Kit. Slab-SIA | NOS | 8 | 75 | 600 | 0 | 0 | 0 | 0 | 75 | 0 | 8 | 75 | 600 | 0 | 0 | 0 | 8 | 8 | 600 | 600
1416 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Granite Slab fixing in Kitchen-SIA | SQFT | 168 | 35 | 5880 | 0 | 0 | 0 | 0 | 35 | 0 | 168 | 35 | 5880 | 0 | 0 | 0 | 168 | 168 | 5880 | 5880
1417 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Pigmentation-SIA | SQFT | 10730.69 | 1.5 | 16096.04 | 0 | 0 | 0 | 0 | 1.5 | 0 | 10730.69 | 1.5 | 16096.035 | 0 | 0 | 0 | 10730.69 | 10730.69 | 16096.035 | 16096.035
1418 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Sink Hole Cutting-SIA | NOS | 8 | 300 | 2400 | 0 | 0 | 0 | 0 | 300 | 0 | 8 | 300 | 2400 | 0 | 0 | 0 | 8 | 8 | 2400 | 2400
1419 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Surface Chipping-SIA | SQFT | 10922.88 | 2.5 | 27307.2 | 0 | 0 | 0 | 0 | 2.5 | 0 | 10922.88 | 2.5 | 27307.2 | 0 | 0 | 0 | 10922.88 | 10922.88 | 27307.2 | 27307.2
1420 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for V-Groove in Tile Corner Joints-SIA | RFT | 250 | 20 | 5000 | 0 | 0 | 0 | 0 | 20 | 0 | 250 | 20 | 5000 | 0 | 0 | 0 | 250 | 250 | 5000 | 5000
1421 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Vit. Flooring (600 X 600 )-SIA | SQFT | 5311.34 | 24 | 127472.16 | 0 | 0 | 0 | 0 | 24 | 0 | 5311.34 | 21 | 111538.14 | 0 | 0 | 0 | 5311.34 | 5311.34 | 127472.16 | 127472.16
1422 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Vit. Flooring with Spacer (600X1200)-SIA | SQFT | 1761.75 | 24 | 42282 | 0 | 0 | 0 | 0 | 24 | 0 | 1761.75 | 24 | 42282 | 0 | 0 | 0 | 1761.75 | 1761.75 | 42282 | 42282
1423 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C for Vit. Tile Skirting-SIA | RFT | 2046 | 13 | 26598 | 0 | 0 | 0 | 0 | 13 | 0 | 2046 | 13 | 26598 | 0 | 0 | 0 | 2046 | 2046 | 26598 | 26598
1424 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)L/C Granite Edge/Nose moulding in Kitchen-SIA | RFT | 99.81 | 25 | 2495.25 | 0 | 0 | 0 | 0 | 25 | 0 | 99.81 | 25 | 2495.25 | 0 | 0 | 0 | 99.81 | 99.81 | 2495.25 | 2495.25
1425 | TILES WORK : PRAYAG T-1 |  | Tentative | Labour | (L)Lifting Charges-SIA | SQFT | 10922.88 | 1.5 | 16384.32 | 0 | 0 | 0 | 0 | 1.5 | 0 | 10922.88 | 1.5 | 16384.32 | 0 | 0 | 0 | 10922.88 | 10922.88 | 16384.32 | 16384.32
1426 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)4 MM TILE SPACER(PVC) | PKT | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 0 | 1.18 | 0 | 6 | 141.6 | 849.6 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
1427 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)IGLOO H/L 300X600 | BOX | 41 | 360.17 | 14766.97 | 41 | 360.17 | 14766.97 | 0 | 360.17 | 0 | 41 | 360.17 | 14767.03 | 0 | 0 | 0 | 41 | 41 | 14766.97 | 14766.97
1428 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)ISHAN DK 300X600 | BOX | 301 | 360.17 | 108411.17 | 301 | 360.17 | 108411.17 | 0 | 360.17 | 0 | 301 | 360.17 | 108411.5914 | 0 | 0 | 0 | 301 | 301 | 108411.17 | 108411.17
1429 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)MEGNA DOVE 600X600 | BOX | 50 | 668.31 | 33415.5 | 50 | 668.31 | 33415.5 | 0 | 668.31 | 0 | 50 | 668.32 | 33415.84 | 0 | 0 | 0 | 50 | 50 | 33415.5 | 33415.5
1430 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)META BIANCO 600 X 1200 | BOX | 152 | 708.74 | 107728.48 | 152 | 708.74 | 107728.48 | 0 | 708.74 | 0 | 152 | 708.73 | 107727.2032 | 0 | 0 | 0 | 152 | 152 | 107728.48 | 107728.48
1431 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)META BIANCO 600 X 600 | BOX | 268 | 649.29 | 174009.72 | 268 | 649.29 | 174009.72 | 0 | 649.29 | 0 | 268 | 649.3 | 174011.06 | 0 | 0 | 0 | 268 | 268 | 174009.72 | 174009.72
1432 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)NOVEN NATURAL 600X600 | BOX | 77 | 530.42 | 40842.34 | 77 | 530.42 | 40842.34 | 0 | 530.42 | 0 | 77 | 530.41 | 40841.5777 | 0 | 0 | 0 | 77 | 77 | 40842.34 | 40842.34
1433 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)SIFON GRISS 600X600 | BOX | 70 | 668.31 | 46781.7 | 70 | 668.31 | 46781.7 | 0 | 668.31 | 0 | 70 | 668.32 | 46782.162 | 0 | 0 | 0 | 70 | 70 | 46781.7 | 46781.7
1434 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)STEEL GREY GRANITE (30" WIDE) | SQFT | 264.09 | 110.26 | 29118.56 | 264.09 | 110.26 | 29118.56 | 0 | 110.26 | 0 | 264.09 | 123.9 | 32720.751 | 0 | 0 | 0 | 264.09 | 264.09 | 29118.563 | 29118.5634
1435 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)TILOFIX | PKT | 285 | 1 | 285 | 285 | 1 | 285 | 0 | 1 | 0 | 285 | 228.98 | 65258.787 | 0 | 0 | 0 | 285 | 285 | 285 | 285
1436 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)TORO DK 300X600 | BOX | 28 | 360.17 | 10084.76 | 28 | 360.17 | 10084.76 | 0 | 360.17 | 0 | 28 | 360.17 | 10084.7992 | 0 | 0 | 0 | 28 | 28 | 10084.76 | 10084.76
1437 | TILES WORK : PRAYAG T-1 |  | Tentative | Material | (M)TRACHIRO GREY H/L 300X600 | BOX | 40 | 360.17 | 14406.8 | 40 | 360.17 | 14406.8 | 0 | 360.17 | 0 | 40 | 360.17 | 14406.86 | 0 | 0 | 0 | 40 | 40 | 14406.8 | 14406.8
1438 | PUTTY : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for rendering Putty in Int. Walls & Ceiling | PER/SQFT | 25521 | 8.86 | 226116.06 | 0 | 0 | 0 | 0 | 8.86 | 0 | 25521 | 8.85 | 225860.86 | 0 | 0 | 0 | 25521 | 25521 | 226116.06 | 226116.06
1439 | PUTTY : PRAYAG T.2 | 0 | Started | Labour | (L)L/C for rendering Putty in Int. Walls & Ceiling | PER/SQFT | 25521 | 8.86 | 226116.06 | 0 | 0 | 0 | 0 | 8.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25521 | 25521 | 226116.06 | 226116.06
1440 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)SD1 (2400mm X 2150mm) | SQFT | 166.627 | 427.16 | 71176.39 | 0 | 0 | 0 | 0 | 427.16 | 0 | 166.627 | 542.8 | 90445.14 | 0 | 0 | 0 | 166.627 | 166.627 | 71176.389 | 71176.3893
1441 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)SD2 (2250mm X 2150mm) | SQFT | 156.213 | 558.14 | 87188.72 | 0 | 0 | 0 | 0 | 558.14 | 0 | 156.213 | 558.14 | 87188.729 | 0 | 0 | 0 | 156.213 | 156.213 | 87188.724 | 87188.7238
1442 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)SD3 (1800mm X 2150mm) | SQFT | 41.657 | 601.8 | 25069.18 | 0 | 0 | 0 | 0 | 601.8 | 0 | 41.657 | 601.8 | 25069.19 | 0 | 0 | 0 | 41.657 | 41.657 | 25069.183 | 25069.1826
1443 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)SD4 (1550mm X 2150mm) | SQFT | 35.871 | 536.9 | 19259.14 | 0 | 0 | 0 | 0 | 536.9 | 0 | 35.871 | 536.9 | 19259.145 | 0 | 0 | 0 | 35.871 | 35.871 | 19259.14 | 19259.1399
1444 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)SW (1200mm X 1800mm) | SQFT | 46.5 | 427.16 | 19862.94 | 0 | 0 | 0 | 0 | 427.16 | 0 | 46.5 | 427.16 | 19862.94 | 0 | 0 | 0 | 46.5 | 46.5 | 19862.94 | 19862.94
1445 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)V1 (900mm X 400mm) | SQFT | 3.875 | 431.88 | 1673.54 | 0 | 0 | 0 | 0 | 431.88 | 0 | 3.875 | 431.88 | 1673.53 | 0 | 0 | 0 | 3.875 | 3.875 | 1673.535 | 1673.535
1446 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W1 (1500 mm X 1800 mm) | SQFT | 203.44 | 581.74 | 118349.19 | 0 | 0 | 0 | 0 | 581.74 | 0 | 203.44 | 581.74 | 118349.18 | 0 | 0 | 0 | 203.44 | 203.44 | 118349.186 | 118349.1856
1447 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W1' (1500 mm X 1800 mm) | SQFT | 58.126 | 436.6 | 25377.81 | 0 | 0 | 0 | 0 | 436.6 | 0 | 58.126 | 436.6 | 25377.82 | 0 | 0 | 0 | 58.126 | 58.126 | 25377.812 | 25377.8116
1448 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W2 (1200 mm X 1800 mm) | SQFT | 139.501 | 594.72 | 82964.03 | 0 | 0 | 0 | 0 | 594.72 | 0 | 139.501 | 594.72 | 82964.044 | 0 | 0 | 0 | 139.501 | 139.501 | 82964.035 | 82964.0347
1449 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W2' (1200 mm X 1800 mm) | SQFT | 93.001 | 520.38 | 48395.86 | 0 | 0 | 0 | 0 | 520.38 | 0 | 93.001 | 520.38 | 48395.861 | 0 | 0 | 0 | 93.001 | 93.001 | 48395.86 | 48395.8604
1450 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W3 (1050 mm X 1050 mm) | SQFT | 47.469 | 719.8 | 34168.19 | 0 | 0 | 0 | 0 | 719.8 | 0 | 47.469 | 719.8 | 34168.19 | 0 | 0 | 0 | 47.469 | 47.469 | 34168.186 | 34168.1862
1451 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W3' (500 mm X 1050 mm) | SQFT | 22.604 | 756.38 | 17097.21 | 0 | 0 | 0 | 0 | 756.38 | 0 | 22.604 | 756.38 | 17097.204 | 0 | 0 | 0 | 22.604 | 22.604 | 17097.214 | 17097.2135
1452 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W4 (850mm X 1800mm) | SQFT | 32.938 | 697.38 | 22970.3 | 0 | 0 | 0 | 0 | 697.38 | 0 | 32.938 | 697.38 | 22970.298 | 0 | 0 | 0 | 32.938 | 32.938 | 22970.302 | 22970.3024
1453 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W5 (600mm X 900mm) | SQFT | 93.001 | 421.26 | 39177.6 | 0 | 0 | 0 | 0 | 421.26 | 0 | 93.001 | 421.26 | 39177.597 | 0 | 0 | 0 | 93.001 | 93.001 | 39177.601 | 39177.6013
1454 | ALUMINIUM WORKS : PRAYAG T-1 | 0 | Tentative | Labour | (L)W7 (700mm X 1800mm) | SQFT | 27.125 | 604.16 | 16387.84 | 0 | 0 | 0 | 0 | 604.16 | 0 | 27.125 | 604.16 | 16387.84 | 0 | 0 | 0 | 27.125 | 27.125 | 16387.84 | 16387.84
1455 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1456 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1457 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)1-1/2''Door Frame Moulding Bit | NOS | 108 | 1.18 | 127.44 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 108 | 127.44 | 127.44
1458 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)3" DOOR BUFFER | NOS | 40 | 23.6 | 944 | 40 | 23.6 | 944 | 0 | 23.6 | 0 | 40 | 21.45 | 858 | 0 | 0 | 0 | 40 | 40 | 944 | 944
1459 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)30 MM Door Shutter D3 (810X2075) | NOS | 26 | 3071.54 | 79860.04 | 26 | 3071.54 | 79860.04 | 0 | 3071.54 | 0 | 26 | 2455.03 | 63830.6604 | 0 | 0 | 0 | 26 | 26 | 79860.04 | 79860.04
1460 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)30 MM door Shutter D4 (660X2075) | NOS | 22 | 2559.42 | 56307.24 | 22 | 2559.42 | 56307.24 | 0 | 2559.42 | 0 | 22 | 2000.4 | 44008.701 | 0 | 0 | 0 | 22 | 22 | 56307.24 | 56307.24
1461 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)32 MM Door Shutter D1 (1010X2075) | NOS | 8 | 3164.76 | 25318.08 | 8 | 3164.76 | 25318.08 | 0 | 3164.76 | 0 | 8 | 4897.93 | 39183.46 | 0 | 0 | 0 | 8 | 8 | 25318.08 | 25318.08
1462 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)4" Hinges | NOS | 144 | 63.72 | 9175.68 | 144 | 63.72 | 9175.68 | 0 | 63.72 | 0 | 144 | 59.59 | 8580.96 | 0 | 0 | 0 | 144 | 144 | 9175.68 | 9175.68
1463 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)5" Hinges | NOS | 32 | 86.14 | 2756.48 | 32 | 86.14 | 2756.48 | 0 | 86.14 | 0 | 32 | 83.43 | 2669.76 | 0 | 0 | 0 | 32 | 32 | 2756.48 | 2756.48
1464 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)8" Main Door Handle (BTT) | NOS | 8 | 720 | 5760 | 8 | 720 | 5760 | 0 | 720 | 0 | 8 | 798.5 | 6388 | 0 | 0 | 0 | 8 | 8 | 5760 | 5760
1465 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)BABY LATCH SMALL | NOS | 22 | 165.2 | 3634.4 | 22 | 165.2 | 3634.4 | 0 | 165.2 | 0 | 22 | 95.34 | 2097.48 | 0 | 0 | 0 | 22 | 22 | 3634.4 | 3634.4
1466 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)DOOR EYE (ZINK) | NOS | 8 | 153.4 | 1227.2 | 8 | 153.4 | 1227.2 | 0 | 153.4 | 0 | 8 | 73.89 | 591.12 | 0 | 0 | 0 | 8 | 8 | 1227.2 | 1227.2
1467 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)Fischer SXR 10X120 WZ Fasteners | NOS | 430 | 1 | 430 | 430 | 1 | 430 | 0 | 1 | 0 | 430 | 42.24 | 18164.67 | 379 | 42.17 | 15982.98 | 430 | 51 | 430 | -15552.98
1468 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)MORTISE HANDLE LOCK WITH ROSE | NOS | 26 | 1557.6 | 40497.6 | 26 | 1557.6 | 40497.6 | 0 | 1557.6 | 0 | 26 | 1376.53 | 35789.78 | 0 | 0 | 0 | 26 | 26 | 40497.6 | 40497.6
1469 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)MORTISE HANDLE LOCK WITHOUT ROSE | NOS | 22 | 879.1 | 19340.2 | 22 | 879.1 | 19340.2 | 0 | 879.1 | 0 | 22 | 780.63 | 17173.86 | 0 | 0 | 0 | 22 | 22 | 19340.2 | 19340.2
1470 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)NIGHT LATCH WITH KEY & KNOB | NOS | 8 | 837.8 | 6702.4 | 8 | 837.8 | 6702.4 | 0 | 837.8 | 0 | 8 | 804.46 | 6435.68 | 0 | 0 | 0 | 8 | 8 | 6702.4 | 6702.4
1471 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)WPC DOOR FRAME D1 (1090 x 2140) MM | SET | 8 | 4126.46 | 33011.68 | 8 | 4126.46 | 33011.68 | 0 | 4126.46 | 0 | 8 | 4126.46 | 33011.68 | 9 | 4126.46 | 37138.14 | 8 | -1 | 33011.68 | -4126.46
1472 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)WPC DOOR FRAME D3 (890 x 2140) MM | SET | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 0 | 2751.76 | 0 | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 26 | 0 | 71545.76 | 0
1473 | CARPENTARY WORKS : PRAYAG T-1 | 0 | Started | Material | (M)WPC DOOR FRAME D4 (740 x 2140) MM | SET | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 0 | 2672.7 | 0 | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 22 | 0 | 58799.4 | 0
1474 | CARPENTARY WORKS : PRAYAG T-2 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1475 | CARPENTARY WORKS : PRAYAG T-2 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1476 | CARPENTARY WORKS : PRAYAG T-2 | 0 | Tentative | Material | (M)Fischer SXR 10X120 WZ Fasteners | NOS | 379 | 1 | 379 | 378 | 1 | 378 | 0 | 1 | 0 | 378 | 41.6 | 15724.8 | 0 | 0 | 0 | 379 | 379 | 379 | 379
1477 | CARPENTARY WORKS : PRAYAG T-2 | 0 | Tentative | Material | (M)WPC DOOR FRAME D1 (1090 x 2140) MM | SET | 9 | 4126.46 | 37138.14 | 9 | 4126.46 | 37138.14 | 0 | 4126.46 | 0 | 1 | 4126.46 | 4126.46 | 0 | 0 | 0 | 9 | 9 | 37138.14 | 37138.14
1478 | CARPENTARY WORKS : PRAYAG T-2 | 0 | Tentative | Material | (M)WPC DOOR FRAME D3 (890 x 2140) MM | SET | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 0 | 2751.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 71545.76 | 71545.76
1479 | CARPENTARY WORKS : PRAYAG T-2 | 0 | Tentative | Material | (M)WPC DOOR FRAME D4 (740 x 2140) MM | SET | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 0 | 2672.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 58799.4 | 58799.4
1480 | CARPENTARY WORKS : PRAYAG T-3 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1481 | CARPENTARY WORKS : PRAYAG T-3 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1482 | CARPENTARY WORKS : PRAYAG T-3 | 0 | Tentative | Material | (M)Fischer SXR 10X120 WZ Fasteners | NOS | 379 | 1 | 379 | 378 | 1 | 378 | 0 | 1 | 0 | 378 | 41.6 | 15724.8 | 0 | 0 | 0 | 379 | 379 | 379 | 379
1483 | CARPENTARY WORKS : PRAYAG T-3 | 0 | Tentative | Material | (M)WPC DOOR FRAME D1 (1090 x 2140) MM | SET | 8 | 4126.46 | 33011.68 | 8 | 4126.46 | 33011.68 | 0 | 4126.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 33011.68 | 33011.68
1484 | CARPENTARY WORKS : PRAYAG T-3 | 0 | Tentative | Material | (M)WPC DOOR FRAME D3 (890 x 2140) MM | SET | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 0 | 2751.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 71545.76 | 71545.76
1485 | CARPENTARY WORKS : PRAYAG T-3 | 0 | Tentative | Material | (M)WPC DOOR FRAME D4 (740 x 2140) MM | SET | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 0 | 2672.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 58799.4 | 58799.4
1486 | CARPENTARY WORKS : PRAYAG T-4 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1487 | CARPENTARY WORKS : PRAYAG T-4 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1488 | CARPENTARY WORKS : PRAYAG T-4 | 0 | Tentative | Material | (M)Fischer SXR 10X120 WZ Fasteners | NOS | 379 | 1 | 379 | 378 | 1 | 378 | 0 | 1 | 0 | 378 | 41.6 | 15724.8 | 0 | 0 | 0 | 379 | 379 | 379 | 379
1489 | CARPENTARY WORKS : PRAYAG T-4 | 0 | Tentative | Material | (M)WPC DOOR FRAME D1 (1090 x 2140) MM | SET | 8 | 4126.46 | 33011.68 | 8 | 4126.46 | 33011.68 | 0 | 4126.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 33011.68 | 33011.68
1490 | CARPENTARY WORKS : PRAYAG T-4 | 0 | Tentative | Material | (M)WPC DOOR FRAME D3 (890 x 2140) MM | SET | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 0 | 2751.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 71545.76 | 71545.76
1491 | CARPENTARY WORKS : PRAYAG T-4 | 0 | Tentative | Material | (M)WPC DOOR FRAME D4 (740 x 2140) MM | SET | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 0 | 2672.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 58799.4 | 58799.4
1492 | CARPENTARY WORKS : PRAYAG T-5 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1493 | CARPENTARY WORKS : PRAYAG T-5 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1494 | CARPENTARY WORKS : PRAYAG T-5 | 0 | Tentative | Material | (M)Fischer SXR 10X120 WZ Fasteners | NOS | 379 | 1 | 379 | 378 | 1 | 378 | 0 | 1 | 0 | 378 | 41.6 | 15724.8 | 0 | 0 | 0 | 379 | 379 | 379 | 379
1495 | CARPENTARY WORKS : PRAYAG T-5 | 0 | Tentative | Material | (M)WPC DOOR FRAME D1 (1090 x 2140) MM | SET | 8 | 4126.46 | 33011.68 | 8 | 4126.46 | 33011.68 | 0 | 4126.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 33011.68 | 33011.68
1496 | CARPENTARY WORKS : PRAYAG T-5 | 0 | Tentative | Material | (M)WPC DOOR FRAME D3 (890 x 2140) MM | SET | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 0 | 2751.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 71545.76 | 71545.76
1497 | CARPENTARY WORKS : PRAYAG T-5 | 0 | Tentative | Material | (M)WPC DOOR FRAME D4 (740 x 2140) MM | SET | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 0 | 2672.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 58799.4 | 58799.4
1498 | CARPENTARY WORKS : PRAYAG T-6 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1499 | CARPENTARY WORKS : PRAYAG T-6 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1500 | CARPENTARY WORKS : PRAYAG T-6 | 0 | Tentative | Material | (M)Fischer SXR 10X120 WZ Fasteners | NOS | 379 | 1 | 379 | 378 | 1 | 378 | 0 | 1 | 0 | 378 | 41.6 | 15724.8 | 0 | 0 | 0 | 379 | 379 | 379 | 379
1501 | CARPENTARY WORKS : PRAYAG T-6 | 0 | Tentative | Material | (M)WPC DOOR FRAME D1 (1090 x 2140) MM | SET | 8 | 4126.46 | 33011.68 | 8 | 4126.46 | 33011.68 | 0 | 4126.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 33011.68 | 33011.68
1502 | CARPENTARY WORKS : PRAYAG T-6 | 0 | Tentative | Material | (M)WPC DOOR FRAME D3 (890 x 2140) MM | SET | 26 | 2751.76 | 71545.76 | 26 | 2751.76 | 71545.76 | 0 | 2751.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 71545.76 | 71545.76
1503 | CARPENTARY WORKS : PRAYAG T-6 | 0 | Tentative | Material | (M)WPC DOOR FRAME D4 (740 x 2140) MM | SET | 22 | 2672.7 | 58799.4 | 22 | 2672.7 | 58799.4 | 0 | 2672.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 58799.4 | 58799.4
1504 | CARPENTARY WORKS : PRAYAG T-7 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1505 | CARPENTARY WORKS : PRAYAG T-7 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1506 | CARPENTARY WORKS : PRAYAG T-8 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1507 | CARPENTARY WORKS : PRAYAG T-8 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1508 | CARPENTARY WORKS : PRAYAG T-9 | 0 | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1509 | CARPENTARY WORKS : PRAYAG T-9 | 0 | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1510 | CARPENTARY WORKS : PRAYAG T-10 |  | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1511 | CARPENTARY WORKS : PRAYAG T-10 |  | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1512 | CARPENTARY WORKS : PRAYAG T-11 |  | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1513 | CARPENTARY WORKS : PRAYAG T-11 |  | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1514 | CARPENTARY WORKS : PRAYAG T-12 |  | Tentative | Labour | (L)L/C for Door Frame Fixing (with 6/7 Fasteners) | NOS | 56 | 275 | 15400 | 0 | 0 | 0 | 0 | 275 | 0 | 56 | 324.5 | 18172 | 0 | 0 | 0 | 56 | 56 | 15400 | 15400
1515 | CARPENTARY WORKS : PRAYAG T-12 |  | Tentative | Labour | (L)L/C for Foam Filling b/w Door Frame & Wall | FLOOR | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
1516 | LIFT : PRAYAG - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)10 Pax /13S / SS Finish / MRL | NOS | 2 | 1938696.34 | 3877392.68 | 0 | 0 | 0 | 0 | 1938696.34 | 0 | 2 | 1938696.34 | 3877392.68 | 0.1 | 1938696.2 | 193869.62 | 2 | 1.9 | 3877392.68 | 3683523.06
1517 | LIFT : PRAYAG - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)15 Pax /13S / MS Finish / MRL | NOS | 1 | 1947182.9 | 1947182.9 | 0 | 0 | 0 | 0 | 1947182.9 | 0 | 1 | 1947182.9 | 1947182.9 | 0.05 | 1947183 | 97359.15 | 1 | 0.95 | 1947182.9 | 1849823.75
1518 | LIFT : VENI - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)10 Pax /13S / SS Finish / MRL | NOS | 2 | 1938696.34 | 3877392.68 | 0 | 0 | 0 | 0 | 1938696.34 | 0 | 2 | 1938696.34 | 3877392.68 | 0.1 | 1938696.2 | 193869.62 | 2 | 1.9 | 3877392.68 | 3683523.06
1519 | LIFT : VENI - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)15 Pax /13S / MS Finish / MRL | NOS | 1 | 1947182.9 | 1947182.9 | 0 | 0 | 0 | 0 | 1947182.9 | 0 | 1 | 1947182.9 | 1947182.9 | 0.05 | 1947183 | 97359.15 | 1 | 0.95 | 1947182.9 | 1849823.75
1520 | LIFT : URVI - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)10 Pax /12S / SS Finish / MRL | NOS | 2 | 1880688.72 | 3761377.44 | 0 | 0 | 0 | 0 | 1880688.72 | 0 | 2 | 1880688.72 | 3761377.44 | 0.1 | 1880688.6 | 188068.86 | 2 | 1.9 | 3761377.44 | 3573308.58
1521 | LIFT : URVI - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)15 Pax /12S / MS Finish / MRL | NOS | 1 | 1892892.28 | 1892892.28 | 0 | 0 | 0 | 0 | 1892892.28 | 0 | 1 | 1892892.28 | 1892892.28 | 0.05 | 1892892 | 94644.6 | 1 | 0.95 | 1892892.28 | 1798247.68
1522 | LIFT : ANUPA - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)10 Pax /13S / SS Finish / MRL | NOS | 2 | 1938696.34 | 3877392.68 | 0 | 0 | 0 | 0 | 1938696.34 | 0 | 2 | 1938696.34 | 3877392.68 | 0.1 | 1938696.2 | 193869.62 | 2 | 1.9 | 3877392.68 | 3683523.06
1523 | LIFT : ANUPA - PASSENGER & SERVICE LIFTS | 0 | Started | Labour | (L)15 Pax /13S / MS Finish / MRL | NOS | 1 | 1947182.9 | 1947182.9 | 0 | 0 | 0 | 0 | 1947182.9 | 0 | 1 | 1947182.9 | 1947182.9 | 0.05 | 1947183 | 97359.15 | 1 | 0.95 | 1947182.9 | 1849823.75
1524 | M.S WORK : PRAYAG T-1 | 0 | Started | Labour | (L)M.S. Work in A.C. Ledge | KG | 772.5 | 119.18 | 92066.55 | 0 | 0 | 0 | 0 | 119.18 | 0 | 772.5 | 119.18 | 92066.56 | 0 | 0 | 0 | 772.5 | 772.5 | 92066.55 | 92066.55
1525 | M.S WORK : PRAYAG T-1 | 0 | Started | Labour | (L)M.S. Work in Balconies & Wash Zone | KG | 1387 | 112.1 | 155482.7 | 0 | 0 | 0 | 0 | 112.1 | 0 | 1387 | 112.1 | 155482.7 | 0 | 0 | 0 | 1387 | 1387 | 155482.7 | 155482.7
1526 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 9370.24 | 8 | 74961.92 | 0 | 0 | 0 | 0 | 8 | 0 | 9370.24 | 8 | 74961.92 | 8542.1 | 8 | 68336.8 | 9370.24 | 828.14 | 74961.92 | 6625.12
1527 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 9370.24 | 4 | 37480.96 | 0 | 0 | 0 | 0 | 4 | 0 | 9370.24 | 4 | 37480.96 | 0 | 0 | 0 | 9370.24 | 9370.24 | 37480.96 | 37480.96
1528 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 9370.24 | 1.18 | 11056.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 9370.24 | 1 | 9370.24 | 0 | 0 | 0 | 9370.24 | 9370.24 | 11056.883 | 11056.8832
1529 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 9370.24 | 4.72 | 44227.53 | 0 | 0 | 0 | 0 | 4.72 | 0 | 9370.24 | 4 | 37480.96 | 0 | 0 | 0 | 9370.24 | 9370.24 | 44227.533 | 44227.5328
1530 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 9370.24 | 4.72 | 44227.53 | 0 | 0 | 0 | 0 | 4.72 | 0 | 9370.24 | 4 | 37480.96 | 0 | 0 | 0 | 9370.24 | 9370.24 | 44227.533 | 44227.5328
1531 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 9370.24 | 17.7 | 165853.25 | 9370.24 | 17.7 | 165853.25 | 0 | 17.7 | 0 | 9370.24 | 17.7 | 165853.248 | 8542.1 | 17.7 | 151195.17 | 9370.24 | 828.14 | 165853.248 | 14658.078
1532 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 9370.24 | 17.7 | 165853.25 | 9370.24 | 17.7 | 165853.25 | 0 | 17.7 | 0 | 9370.24 | 17.7 | 165853.248 | 0 | 0 | 0 | 9370.24 | 9370.24 | 165853.248 | 165853.248
1533 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 9370.24 | 14.16 | 132682.6 | 9370.24 | 14.16 | 132682.6 | 0 | 14.16 | 0 | 9370.24 | 14.16 | 132682.5984 | 0 | 0 | 0 | 9370.24 | 9370.24 | 132682.598 | 132682.5984
1534 | ELECTRICAL : PRAYAG GROUND FLOOR | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 9370.24 | 20.06 | 187967.01 | 9370.24 | 20.06 | 187967.01 | 0 | 20.06 | 0 | 9370.24 | 20.06 | 187967.0144 | 0 | 0 | 0 | 9370.24 | 9370.24 | 187967.014 | 187967.0144
1535 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1536 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1537 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1538 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1539 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1540 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.66 | 17.7 | 147965.98 | 8359.66 | 0 | 147965.982 | 0.002
1541 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1542 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1543 | ELECTRICAL : PRAYAG T-1 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1544 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1545 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1546 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1547 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1548 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1549 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.66 | 17.7 | 147965.98 | 8359.66 | 0 | 147965.982 | 0.002
1550 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1551 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1552 | ELECTRICAL : PRAYAG T-2 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1553 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1554 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1555 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1556 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1557 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1558 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.66 | 17.7 | 147965.98 | 8359.66 | 0 | 147965.982 | 0.002
1559 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1560 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1561 | ELECTRICAL : PRAYAG T-3 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1562 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1563 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1564 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1565 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1566 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1567 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.66 | 17.7 | 147965.98 | 8359.66 | 0 | 147965.982 | 0.002
1568 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1569 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1570 | ELECTRICAL : PRAYAG T-4 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1571 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1572 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1573 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1574 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1575 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1576 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.65 | 17.7 | 147965.81 | 8359.66 | 0.01 | 147965.982 | 0.172
1577 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1578 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1579 | ELECTRICAL : PRAYAG T-5 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1580 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1581 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1582 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1583 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1584 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1585 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.66 | 17.7 | 147965.98 | 8359.66 | 0 | 147965.982 | 0.002
1586 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1587 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1588 | ELECTRICAL : PRAYAG T-6 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1589 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 8359.66 | 8 | 66877.28 | 8359.66 | 0 | 66877.28 | 0
1590 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1591 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1592 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1593 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1594 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 8359.66 | 17.7 | 147965.98 | 8359.66 | 0 | 147965.982 | 0.002
1595 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1596 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1597 | ELECTRICAL : PRAYAG T-7 | 0 | Started | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1598 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 8359.66 | 8359.66 | 66877.28 | 66877.28
1599 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1600 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1601 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1602 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1603 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1604 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1605 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1606 | ELECTRICAL : PRAYAG T-8 | 0 | Confirm | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1607 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 8359.66 | 8359.66 | 66877.28 | 66877.28
1608 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1609 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1610 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1611 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1612 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1613 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1614 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1615 | ELECTRICAL : PRAYAG T-9 | 0 | Confirm | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1616 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 8359.66 | 8359.66 | 66877.28 | 66877.28
1617 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1618 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1619 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1620 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1621 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1622 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1623 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1624 | ELECTRICAL : PRAYAG T-10 | 0 | Confirm | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1625 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 8359.66 | 8359.66 | 66877.28 | 66877.28
1626 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1627 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1628 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1629 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1630 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1631 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1632 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1633 | ELECTRICAL : PRAYAG T-11 | 0 | Confirm | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1634 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Labour | (L)L/C for Concealed Electrical Works | SQFT | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 0 | 8 | 0 | 8359.66 | 8 | 66877.28 | 0 | 0 | 0 | 8359.66 | 8359.66 | 66877.28 | 66877.28
1635 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Labour | (L)L/C for Main Line Wiring | SQFT | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 0 | 4 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 33438.64 | 33438.64
1636 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Labour | (L)L/C for Testing Commissioning & Handover | SQFT | 8359.66 | 1.18 | 9864.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 8359.66 | 1 | 8359.66 | 0 | 0 | 0 | 8359.66 | 8359.66 | 9864.399 | 9864.3988
1637 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Labour | (L)L/C for Wire Pulling from Flat DB to individual points | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1638 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Labour | (L)L/C of fixing elec. fittings incl. connection & DB dressing | SQFT | 8359.66 | 4.72 | 39457.6 | 0 | 0 | 0 | 0 | 4.72 | 0 | 8359.66 | 4 | 33438.64 | 0 | 0 | 0 | 8359.66 | 8359.66 | 39457.595 | 39457.5952
1639 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Material | (M)SUPPLY OF CONCEALED ELEC. ITEMS | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1640 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Material | (M)SUPPLY OF ELECTRICAL FITTINGS & FIXTURES | SQFT | 8359.66 | 17.7 | 147965.98 | 8359.66 | 17.7 | 147965.98 | 0 | 17.7 | 0 | 8359.66 | 17.7 | 147965.982 | 0 | 0 | 0 | 8359.66 | 8359.66 | 147965.982 | 147965.982
1641 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Material | (M)SUPPLY OF MAIN LINE WIRING | SQFT | 8359.66 | 14.16 | 118372.79 | 8359.66 | 14.16 | 118372.79 | 0 | 14.16 | 0 | 8359.66 | 14.16 | 118372.7856 | 0 | 0 | 0 | 8359.66 | 8359.66 | 118372.786 | 118372.7856
1642 | ELECTRICAL : PRAYAG T-12 | 0 | Confirm | Material | (M)SUPPLY OF WIRE & CABLES FOR INTERNAL ELEC. WORKS | SQFT | 8359.66 | 20.06 | 167694.78 | 8359.66 | 20.06 | 167694.78 | 0 | 20.06 | 0 | 8359.66 | 20.06 | 167694.7796 | 0 | 0 | 0 | 8359.66 | 8359.66 | 167694.78 | 167694.7796
1643 | PHE : PRAYAG T-1 | 0 | Started | Labour | (L)L/C for Internal Plumbing Works | PER/SQFT | 8232 | 19.48 | 160359.36 | 0 | 0 | 0 | 0 | 19.48 | 0 | 8232 | 19.47 | 160277.04 | 0 | 0 | 0 | 8232 | 8232 | 160359.36 | 160359.36
1644 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)'U' BOLT 110 mm | NOS | 88 | 64.9 | 5711.2 | 88 | 64.9 | 5711.2 | 0 | 64.9 | 0 | 88 | 64.9 | 5711.2 | 60 | 64.9 | 3894 | 88 | 28 | 5711.2 | 1817.2
1645 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)1" UPVC PIPE (10' LENGTH) | NOS | 75 | 1 | 75 | 25 | 1 | 25 | 0 | 1 | 0 | 25 | 213.36 | 5333.89 | 13 | 213.36 | 2773.68 | 75 | 62 | 75 | -2698.68
1646 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)1/2" test plug | NOS | 152 | 11.8 | 1793.6 | 152 | 11.8 | 1793.6 | 0 | 11.8 | 0 | 152 | 4.81 | 731.7736 | 145 | 4.81 | 697.45 | 152 | 7 | 1793.6 | 1096.15
1647 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)1/2" X 3/4" UPVC R TEE | NOS | 15 | 1 | 15 | 15 | 1 | 15 | 0 | 1 | 0 | 15 | 10.9 | 163.5405 | 0 | 0 | 0 | 15 | 15 | 15 | 15
1648 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 1.93 | 1770 | 3416.1 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0.579 | 1378.77 | 798.31 | 1.93 | 1.351 | 3416.1 | 2617.79
1649 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm SWR 'P' Trap | NOS | 24 | 250.16 | 6003.84 | 24 | 250.16 | 6003.84 | 0 | 250.16 | 0 | 24 | 166.43 | 3994.26 | 24 | 166.43 | 3994.27 | 24 | 0 | 6003.84 | 2009.57
1650 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm SWR 'Y' Tee | NOS | 16 | 227.74 | 3643.84 | 16 | 227.74 | 3643.84 | 0 | 227.74 | 0 | 16 | 126.76 | 2028.08 | 16 | 126.76 | 2028.08 | 16 | 0 | 3643.84 | 1615.76
1651 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm SWR Plain Bend | NOS | 63 | 167.56 | 10556.28 | 63 | 167.56 | 10556.28 | 0 | 167.56 | 0 | 63 | 69.18 | 4358.5479 | 38 | 69.18 | 2628.84 | 63 | 25 | 10556.28 | 7927.44
1652 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm universal clamp | NOS | 58 | 53.1 | 3079.8 | 58 | 53.1 | 3079.8 | 0 | 53.1 | 0 | 58 | 53.1 | 3079.8 | 20 | 53.1 | 1062 | 58 | 38 | 3079.8 | 2017.8
1653 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x 2'0" D/S Pipe | NOS | 32 | 259.6 | 8307.2 | 32 | 259.6 | 8307.2 | 0 | 259.6 | 0 | 32 | 161.9 | 5180.6816 | 10 | 161.91 | 1619.06 | 32 | 22 | 8307.2 | 6688.14
1654 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x 4'0" D/S Pipe | NOS | 23 | 440.14 | 10123.22 | 23 | 440.14 | 10123.22 | 0 | 440.14 | 0 | 23 | 303.73 | 6985.8406 | 10 | 303.73 | 3037.3 | 23 | 13 | 10123.22 | 7085.92
1655 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x 45° Swr half Bend | NOS | 39 | 133.34 | 5200.26 | 39 | 133.34 | 5200.26 | 0 | 133.34 | 0 | 39 | 61.68 | 2405.7033 | 30 | 61.69 | 1850.6 | 39 | 9 | 5200.26 | 3349.66
1656 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x 6'0" D/S Pipe | NOS | 18 | 690.3 | 12425.4 | 18 | 690.3 | 12425.4 | 0 | 690.3 | 0 | 18 | 451.47 | 8126.4204 | 14 | 451.47 | 6320.58 | 18 | 4 | 12425.4 | 6104.82
1657 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x 75 mm 'Y' Tee | NOS | 14 | 227.74 | 3188.36 | 14 | 227.74 | 3188.36 | 0 | 227.74 | 0 | 14 | 105.71 | 1479.9498 | 0 | 0 | 0 | 14 | 14 | 3188.36 | 3188.36
1658 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x 75 mm R/ Tee | NOS | 16 | 186.44 | 2983.04 | 16 | 186.44 | 2983.04 | 0 | 186.44 | 0 | 16 | 100.63 | 1610.08 | 16 | 100.63 | 1610.08 | 16 | 0 | 2983.04 | 1372.96
1659 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mm x10'0" SWR S/S Pipe | NOS | 44 | 906.24 | 39874.56 | 44 | 906.24 | 39874.56 | 0 | 906.24 | 0 | 44 | 571.12 | 25129.28 | 38 | 571.12 | 21702.56 | 44 | 6 | 39874.56 | 18172
1660 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)110 mmX 110 mm swept tee | NOS | 33 | 182.9 | 6035.7 | 33 | 182.9 | 6035.7 | 0 | 182.9 | 0 | 33 | 125.55 | 4143.0147 | 28 | 125.55 | 3515.4 | 33 | 5 | 6035.7 | 2520.3
1661 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 MM 'U' BOLT | NOS | 50 | 21.24 | 1062 | 50 | 21.24 | 1062 | 0 | 21.24 | 0 | 50 | 14.16 | 708 | 50 | 14.16 | 708 | 50 | 0 | 1062 | 354
1662 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 MM CHINA CLIP | PKT | 300 | 118 | 35400 | 300 | 118 | 35400 | 0 | 118 | 0 | 300 | 19.35 | 5805 | 300 | 19.1 | 5729.49 | 300 | 0 | 35400 | 29670.51
1663 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm cpvc elbow | NOS | 304 | 23.6 | 7174.4 | 304 | 23.6 | 7174.4 | 0 | 23.6 | 0 | 304 | 11.23 | 3415.0144 | 140 | 11.23 | 1572.2 | 304 | 164 | 7174.4 | 5602.2
1664 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm CPVC pipe | MTR | 300 | 70.8 | 21240 | 300 | 70.8 | 21240 | 0 | 70.8 | 0 | 300 | 59.25 | 17773.56 | 300 | 59.25 | 17773.56 | 300 | 0 | 21240 | 3466.44
1665 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm CPVC socket | NOS | 40 | 11.8 | 472 | 40 | 11.8 | 472 | 0 | 11.8 | 0 | 40 | 8.43 | 337 | 40 | 8.43 | 337 | 40 | 0 | 472 | 135
1666 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm cpvc tee | NOS | 112 | 21.24 | 2378.88 | 112 | 21.24 | 2378.88 | 0 | 21.24 | 0 | 112 | 16.05 | 1797.376 | 80 | 16.05 | 1284 | 112 | 32 | 2378.88 | 1094.88
1667 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 MM UPVC END CAP SCH-80 | NOS | 50 | 1.18 | 59 | 50 | 1.18 | 59 | 0 | 1.18 | 0 | 50 | 4.21 | 210.64 | 7 | 4.21 | 29.47 | 50 | 43 | 59 | 29.53
1668 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 MM UPVC TEE | NOS | 50 | 1 | 50 | 50 | 1 | 50 | 0 | 1 | 0 | 50 | 12.89 | 644.28 | 37 | 12.88 | 476.63 | 50 | 13 | 50 | -426.63
1669 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm x 1/2" CPVC Metal MTA | NOS | 64 | 76.7 | 4908.8 | 64 | 76.7 | 4908.8 | 0 | 76.7 | 0 | 64 | 74.22 | 4750.2016 | 40 | 74.22 | 2968.8 | 64 | 24 | 4908.8 | 1940
1670 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm x 15 mm Brass FT Elbow | NOS | 156 | 47.2 | 7363.2 | 156 | 47.2 | 7363.2 | 0 | 47.2 | 0 | 156 | 40.12 | 6258.72 | 144 | 40.12 | 5777.28 | 156 | 12 | 7363.2 | 1585.92
1671 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm x 20 mm Tranjction bush | NOS | 40 | 11.8 | 472 | 40 | 11.8 | 472 | 0 | 11.8 | 0 | 40 | 8.43 | 337 | 40 | 8.43 | 337 | 40 | 0 | 472 | 135
1672 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)20 mm x 45° CPVC half elbow | NOS | 240 | 18.88 | 4531.2 | 240 | 18.88 | 4531.2 | 0 | 18.88 | 0 | 240 | 16.05 | 3851.52 | 149 | 16.05 | 2391.45 | 240 | 91 | 4531.2 | 2139.75
1673 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)200 MM SIZE WALL BRACKET | NOS | 16 | 47.8 | 764.8 | 16 | 47.8 | 764.8 | 0 | 47.8 | 0 | 16 | 193.5 | 3096 | 16 | 190.98 | 3055.73 | 16 | 0 | 764.8 | -2290.93
1674 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)25 MM 'U' BOLT | NOS | 20 | 29.5 | 590 | 20 | 29.5 | 590 | 0 | 29.5 | 0 | 20 | 17.7 | 354 | 20 | 17.7 | 354 | 20 | 0 | 590 | 236
1675 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)25 MM END CAP UPVC | NOS | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 6.69 | 66.9 | 3 | 6.69 | 20.07 | 10 | 7 | 10 | -10.07
1676 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)25 MM UPVC SOCKET | NOS | 10 | 23.6 | 236 | 10 | 23.6 | 236 | 0 | 23.6 | 0 | 10 | 9.66 | 96.64 | 2 | 9.66 | 19.32 | 10 | 8 | 236 | 216.68
1677 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)25 MM X 20 MM TEE UPVC | NOS | 20 | 1 | 20 | 20 | 1 | 20 | 0 | 1 | 0 | 20 | 18.34 | 366.74 | 13 | 18.34 | 238.39 | 20 | 7 | 20 | -218.39
1678 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)25 MM X 20 MM UPVC REDUCER | NOS | 10 | 1 | 10 | 10 | 1 | 10 | 0 | 1 | 0 | 10 | 12.89 | 128.86 | 5 | 12.89 | 64.45 | 10 | 5 | 10 | -54.45
1679 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)3/4" UPVC BALL VALVE | NOS | 34 | 212.4 | 7221.6 | 34 | 212.4 | 7221.6 | 0 | 212.4 | 0 | 34 | 80.29 | 2729.7614 | 40 | 88.2 | 3528 | 34 | -6 | 7221.6 | 3693.6
1680 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)3/4" UPVC PIPE (10'0" ) LONG | MTR | 120 | 256.06 | 30727.2 | 120 | 256.06 | 30727.2 | 0 | 256.06 | 0 | 120 | 47.73 | 5728.152 | 84 | 47.74 | 4009.92 | 120 | 36 | 30727.2 | 26717.28
1681 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)3/4" UPVC SOCKET | NOS | 50 | 12.98 | 649 | 50 | 12.98 | 649 | 0 | 12.98 | 0 | 50 | 6.94 | 346.92 | 6 | 7.26 | 43.57 | 50 | 44 | 649 | 605.43
1682 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)32 MM AGRICULTURE ELBOW | NOS | 34 | 18.88 | 641.92 | 34 | 18.88 | 641.92 | 0 | 18.88 | 0 | 34 | 7.67 | 260.78 | 34 | 7.67 | 260.78 | 34 | 0 | 641.92 | 381.14
1683 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)32 MM AGRICULTURE HALF BEND | NOS | 15 | 61.36 | 920.4 | 15 | 61.36 | 920.4 | 0 | 61.36 | 0 | 15 | 8.26 | 123.9 | 15 | 8.26 | 123.9 | 15 | 0 | 920.4 | 796.5
1684 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)32 MM AGRICULTURE PIPE | MTR | 36 | 56.64 | 2039.04 | 36 | 56.64 | 2039.04 | 0 | 56.64 | 0 | 36 | 34.13 | 1228.5216 | 36 | 34.13 | 1228.52 | 36 | 0 | 2039.04 | 810.52
1685 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)35 x 7 ms screw | NOS | 600 | 3.54 | 2124 | 600 | 3.54 | 2124 | 0 | 3.54 | 0 | 600 | 0.64 | 384 | 0 | 0 | 0 | 600 | 600 | 2124 | 2124
1686 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)40 MM AGRICULTURE ELBOW | NOS | 17 | 20.06 | 341.02 | 17 | 20.06 | 341.02 | 0 | 20.06 | 0 | 17 | 12.39 | 210.6402 | 17 | 12.39 | 210.64 | 17 | 0 | 341.02 | 130.38
1687 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)40 MM AGRICULTURE HALF BEND | NOS | 13 | 112.1 | 1457.3 | 13 | 112.1 | 1457.3 | 0 | 112.1 | 0 | 13 | 11.21 | 145.7404 | 13 | 11.21 | 145.74 | 13 | 0 | 1457.3 | 1311.56
1688 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)40 MM AGRICULTURE PIPE | MTR | 24 | 22.42 | 538.08 | 24 | 22.42 | 538.08 | 0 | 22.42 | 0 | 24 | 35.01 | 840.2592 | 24 | 35.01 | 840.26 | 24 | 0 | 538.08 | -302.18
1689 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)40 X 32 MM AGRICULTURE REDUCING BUSH | NOS | 13 | 20.06 | 260.78 | 13 | 20.06 | 260.78 | 0 | 20.06 | 0 | 13 | 5.01 | 65.1898 | 13 | 5.01 | 65.19 | 13 | 0 | 260.78 | 195.59
1690 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)40 X 40 MM AGRICULTURE TEE | NOS | 13 | 24.78 | 322.14 | 13 | 24.78 | 322.14 | 0 | 24.78 | 0 | 13 | 15.93 | 207.1004 | 13 | 15.93 | 207.1 | 13 | 0 | 322.14 | 115.04
1691 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 MM 'U' BOLT | NOS | 32 | 41.3 | 1321.6 | 32 | 41.3 | 1321.6 | 0 | 41.3 | 0 | 32 | 35.4 | 1132.8 | 32 | 35.4 | 1132.8 | 32 | 0 | 1321.6 | 188.8
1692 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 mm agriculture elbow | NOS | 44 | 59 | 2596 | 44 | 59 | 2596 | 0 | 59 | 0 | 44 | 18.69 | 822.4216 | 40 | 18.69 | 747.6 | 44 | 4 | 2596 | 1848.4
1693 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 mm Agriculture Half Elbow | NOS | 24 | 18.88 | 453.12 | 24 | 18.88 | 453.12 | 0 | 18.88 | 0 | 24 | 15.29 | 367.02 | 10 | 15.29 | 152.9 | 24 | 14 | 453.12 | 300.22
1694 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 mm agriculture pipe | MTR | 48 | 186.44 | 8949.12 | 16 | 186.44 | 2983.04 | 0 | 186.44 | 0 | 16 | 56.64 | 906.24 | 15 | 56.64 | 849.6 | 48 | 33 | 8949.12 | 8099.52
1695 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 mm agriculture socket | NOS | 16 | 14.16 | 226.56 | 16 | 14.16 | 226.56 | 0 | 14.16 | 0 | 16 | 10.48 | 167.6608 | 6 | 10.48 | 62.88 | 16 | 10 | 226.56 | 163.68
1696 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 mm agriculture Tee | NOS | 19 | 28.32 | 538.08 | 19 | 28.32 | 538.08 | 0 | 28.32 | 0 | 19 | 24.92 | 473.5199 | 16 | 24.92 | 398.72 | 19 | 3 | 538.08 | 139.36
1697 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)50 mm universal clamp | NOS | 20 | 35.4 | 708 | 20 | 35.4 | 708 | 0 | 35.4 | 0 | 20 | 35.4 | 708 | 1 | 35.4 | 35.4 | 20 | 19 | 708 | 672.6
1698 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)500 MM SIZE WALL BRACKET | NOS | 16 | 1 | 16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 16
1699 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)600 MM SIZE WALL BRACKET | NOS | 16 | 90.28 | 1444.48 | 16 | 90.28 | 1444.48 | 0 | 90.28 | 0 | 16 | 335.4 | 5366.4 | 16 | 331.04 | 5296.6 | 16 | 0 | 1444.48 | -3852.12
1700 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)700 MM SIZE WALL BRACKET | NOS | 28 | 191.16 | 5352.48 | 28 | 191.16 | 5352.48 | 0 | 191.16 | 0 | 28 | 425.7 | 11919.6 | 10 | 420.16 | 4201.6 | 28 | 18 | 5352.48 | 1150.88
1701 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)75 MM X 10 MM FASTNER | NOS | 100 | 1.18 | 118 | 100 | 1.18 | 118 | 0 | 1.18 | 0 | 100 | 23.6 | 2360 | 97 | 23.6 | 2289.2 | 100 | 3 | 118 | -2171.2
1702 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)75MM X 50MM AGRICULTURE R BUSH | NOS | 40 | 25.96 | 1038.4 | 40 | 25.96 | 1038.4 | 0 | 25.96 | 0 | 40 | 17.28 | 691 | 16 | 17.27 | 276.36 | 40 | 24 | 1038.4 | 762.04
1703 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)8 mm drofing fastener | NOS | 100 | 177 | 17700 | 100 | 177 | 17700 | 0 | 177 | 0 | 100 | 5.16 | 516 | 57 | 5.09 | 290.14 | 100 | 43 | 17700 | 17409.86
1704 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)8 mm nut with washer | NOS | 200 | 1 | 200 | 200 | 1 | 200 | 0 | 1 | 0 | 200 | 3.87 | 774 | 132 | 3.82 | 504.24 | 200 | 68 | 200 | -304.24
1705 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)8 mm tie rod | MTR | 20 | 29.5 | 590 | 20 | 29.5 | 590 | 0 | 29.5 | 0 | 20 | 64.5 | 1290 | 16 | 63.66 | 1018.56 | 20 | 4 | 590 | -428.56
1706 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)CEBEX - 100 | PKT | 20 | 59 | 1180 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 2 | 63.23 | 126.45 | 20 | 18 | 1180 | 1053.55
1707 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)CONCEALED BODY FOR SINGLE LEVER DIVERTER 40MM CARTRIDGE | NOS | 16 | 1 | 16 | 16 | 1 | 16 | 0 | 1 | 0 | 16 | 1632.29 | 26116.7008 | 10 | 1632.29 | 16322.9 | 16 | 6 | 16 | -16306.9
1708 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)CPVC SOLVENT CEMENT. | NOS | 8 | 481.44 | 3851.52 | 8 | 481.44 | 3851.52 | 0 | 481.44 | 0 | 8 | 481.44 | 3851.52 | 5 | 481.44 | 2407.2 | 8 | 3 | 3851.52 | 1444.32
1709 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)LUBRICANT | NOS | 6 | 141.6 | 849.6 | 6 | 141.6 | 849.6 | 0 | 141.6 | 0 | 6 | 65.7 | 394.2198 | 2 | 65.7 | 131.4 | 6 | 4 | 849.6 | 718.2
1710 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)M.C. SAND | MT | 1.35 | 1711.5 | 2310.53 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0.405 | 1856.96 | 752.07 | 1.35 | 0.945 | 2310.525 | 1558.455
1711 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)PPC CEMENT | BAG | 10 | 283.59 | 2835.9 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 3 | 285.58 | 856.74 | 10 | 7 | 2835.9 | 1979.16
1712 | PHE : PRAYAG T-1 | 0 | Started | Material | (M)TEFLON TAPE | NOS | 40 | 23.6 | 944 | 40 | 23.6 | 944 | 0 | 23.6 | 0 | 40 | 32.25 | 1290 | 24 | 31.83 | 763.92 | 40 | 16 | 944 | 180.08
1713 | PHE : PRAYAG T-2 | 0 | Started | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1714 | PHE : PRAYAG T-2 | 0 | Started | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1715 | PHE : PRAYAG T-2 | 0 | Started | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1716 | PHE : PRAYAG T-2 | 0 | Started | Material | (M)110 mm x10'0" SWR S/S Pipe | NOS | 12 | 906.24 | 10874.88 | 12 | 906.24 | 10874.88 | 0 | 906.24 | 0 | 12 | 592.54 | 7110.4464 | 12 | 589.48 | 7073.76 | 12 | 0 | 10874.88 | 3801.12
1717 | PHE : PRAYAG T-3 | 0 | Started | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1718 | PHE : PRAYAG T-3 | 0 | Started | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1719 | PHE : PRAYAG T-3 | 0 | Started | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1720 | PHE : PRAYAG T-3 | 0 | Started | Material | (M)110 mm x10'0" SWR S/S Pipe | NOS | 12 | 906.24 | 10874.88 | 12 | 906.24 | 10874.88 | 0 | 906.24 | 0 | 12 | 592.54 | 7110.4464 | 12 | 589.48 | 7073.76 | 12 | 0 | 10874.88 | 3801.12
1721 | PHE : PRAYAG T-4 | 0 | Started | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1722 | PHE : PRAYAG T-4 | 0 | Started | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1723 | PHE : PRAYAG T-4 | 0 | Started | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1724 | PHE : PRAYAG T-4 | 0 | Started | Material | (M)110 mm x10'0" SWR S/S Pipe | NOS | 12 | 906.24 | 10874.88 | 12 | 906.24 | 10874.88 | 0 | 906.24 | 0 | 12 | 592.54 | 7110.4464 | 12 | 589.48 | 7073.76 | 12 | 0 | 10874.88 | 3801.12
1725 | PHE : PRAYAG T-4 | 0 | Started | Material | (M)BROWN TAPE | NOS | 36 | 47.2 | 1699.2 | 36 | 47.2 | 1699.2 | 0 | 47.2 | 0 | 36 | 33.04 | 1189.44 | 0 | 0 | 0 | 36 | 36 | 1699.2 | 1699.2
1726 | PHE : PRAYAG T-5 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1727 | PHE : PRAYAG T-5 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1728 | PHE : PRAYAG T-5 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1729 | PHE : PRAYAG T-5 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 10 | 23.6 | 236 | 10 | 23.6 | 236 | 0 | 23.6 | 0 | 10 | 31.27 | 312.7 | 0 | 0 | 0 | 10 | 10 | 236 | 236
1730 | PHE : PRAYAG T-6 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1731 | PHE : PRAYAG T-6 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1732 | PHE : PRAYAG T-6 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1733 | PHE : PRAYAG T-6 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1734 | PHE : PRAYAG T-6 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 5 | 47.2 | 236 | 5 | 47.2 | 236 | 0 | 47.2 | 0 | 5 | 63.72 | 318.6 | 0 | 0 | 0 | 5 | 5 | 236 | 236
1735 | PHE : PRAYAG T-7 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1736 | PHE : PRAYAG T-7 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1737 | PHE : PRAYAG T-7 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1738 | PHE : PRAYAG T-7 | 0 | Tentative | Material | (M)32 MM PPR PIPE | MTR | 60 | 1 | 60 | 5 | 1 | 5 | 0 | 1 | 0 | 5 | 155.05 | 775.26 | 0 | 0 | 0 | 60 | 60 | 60 | 60
1739 | PHE : PRAYAG T-7 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1740 | PHE : PRAYAG T-7 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 18 | 47.2 | 849.6 | 0 | 47.2 | 0 | 18 | 63.72 | 1146.96 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
1741 | PHE : PRAYAG T-8 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1742 | PHE : PRAYAG T-8 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1743 | PHE : PRAYAG T-8 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1744 | PHE : PRAYAG T-8 | 0 | Tentative | Material | (M)32 MM PPR PIPE | MTR | 60 | 1 | 60 | 50 | 1 | 50 | 0 | 1 | 0 | 50 | 155.05 | 7752.6 | 0 | 0 | 0 | 60 | 60 | 60 | 60
1745 | PHE : PRAYAG T-8 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1746 | PHE : PRAYAG T-8 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 18 | 47.2 | 849.6 | 0 | 47.2 | 0 | 18 | 63.72 | 1146.96 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
1747 | PHE : PRAYAG T-9 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1748 | PHE : PRAYAG T-9 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1749 | PHE : PRAYAG T-9 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1750 | PHE : PRAYAG T-9 | 0 | Tentative | Material | (M)32 MM PPR PIPE | MTR | 80 | 1 | 80 | 80 | 1 | 80 | 0 | 1 | 0 | 80 | 155.05 | 12404.16 | 0 | 0 | 0 | 80 | 80 | 80 | 80
1751 | PHE : PRAYAG T-9 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1752 | PHE : PRAYAG T-9 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 18 | 47.2 | 849.6 | 0 | 47.2 | 0 | 18 | 63.72 | 1146.96 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
1753 | PHE : PRAYAG T-10 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1754 | PHE : PRAYAG T-10 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1755 | PHE : PRAYAG T-10 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1756 | PHE : PRAYAG T-10 | 0 | Tentative | Material | (M)32 MM PPR PIPE | MTR | 60 | 1 | 60 | 60 | 1 | 60 | 0 | 1 | 0 | 60 | 155.05 | 9303.12 | 0 | 0 | 0 | 60 | 60 | 60 | 60
1757 | PHE : PRAYAG T-10 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1758 | PHE : PRAYAG T-10 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 18 | 47.2 | 849.6 | 0 | 47.2 | 0 | 18 | 63.72 | 1146.96 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
1759 | PHE : PRAYAG T-11 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1760 | PHE : PRAYAG T-11 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1761 | PHE : PRAYAG T-11 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1762 | PHE : PRAYAG T-11 | 0 | Tentative | Material | (M)32 MM PPR PIPE | MTR | 60 | 1 | 60 | 60 | 1 | 60 | 0 | 1 | 0 | 60 | 155.05 | 9303.12 | 0 | 0 | 0 | 60 | 60 | 60 | 60
1763 | PHE : PRAYAG T-11 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1764 | PHE : PRAYAG T-11 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 18 | 47.2 | 849.6 | 0 | 47.2 | 0 | 18 | 63.72 | 1146.96 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
1765 | PHE : PRAYAG T-12 | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 98 | 129.8 | 12720.4 | 0 | 0 | 0 | 0 | 129.8 | 0 | 98 | 100.3 | 9829.4 | 0 | 0 | 0 | 98 | 98 | 12720.4 | 12720.4
1766 | PHE : PRAYAG T-12 | 0 | Tentative | Labour | (L)Supply of Plumber on Daily Basis | NOS | 2 | 826 | 1652 | 0 | 0 | 0 | 0 | 826 | 0 | 2 | 826 | 1652 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
1767 | PHE : PRAYAG T-12 | 0 | Tentative | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 0 | 0 | 0 | 4 | 4 | 2360 | 2360
1768 | PHE : PRAYAG T-12 | 0 | Tentative | Material | (M)32 MM PPR PIPE | MTR | 60 | 1 | 60 | 60 | 1 | 60 | 0 | 1 | 0 | 60 | 155.05 | 9303.12 | 0 | 0 | 0 | 60 | 60 | 60 | 60
1769 | PHE : PRAYAG T-12 | 0 | Tentative | Material | (M)32 MM PPR SOCKET | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 31.27 | 562.86 | 0 | 0 | 0 | 18 | 18 | 424.8 | 424.8
1770 | PHE : PRAYAG T-12 | 0 | Tentative | Material | (M)32 MM PPR TEE | NOS | 18 | 47.2 | 849.6 | 18 | 47.2 | 849.6 | 0 | 47.2 | 0 | 18 | 63.72 | 1146.96 | 0 | 0 | 0 | 18 | 18 | 849.6 | 849.6
1771 | PHE : PRAYAG PHE : PRAYAG GROUND FLOOR | 0 | Tentative | Labour | (L)L/C for Fixing 32 mm Dia PPR AC Drain Out Pipe | MTR | 280 | 129.8 | 36344 | 0 | 0 | 0 | 0 | 129.8 | 0 | 280 | 100.3 | 28084 | 0 | 0 | 0 | 280 | 280 | 36344 | 36344
1772 | WATER PROOFING : PRAYAG T.1 | 0 | Started | Labour | (L)L/C for executing Screed Concrete (In Flats) | SQFT | 651.026 | 21.24 | 13827.79 | 0 | 0 | 0 | 0 | 21.24 | 0 | 651.026 | 21.24 | 13827.788 | 0 | 0 | 0 | 651.026 | 651.026 | 13827.792 | 13827.7922 | FINISHING
1773 | WATER PROOFING : PRAYAG T.1 | 0 | Started | Labour | (L)Waterproofing Chem. protective layer (In Flats) | SQFT | 3692.37 | 29.5 | 108924.92 | 0 | 0 | 0 | 0 | 29.5 | 0 | 3692.37 | 29.5 | 108924.91 | 0 | 0 | 0 | 3692.37 | 3692.37 | 108924.915 | 108924.915 | FINISHING
1774 | WATER PROOFING : PRAYAG T.1 | 0 | Started | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0.2 | 1860.25 | 372.05 | 1 | 0.8 | 1711.5 | 1339.45 | FINISHING
1775 | WATER PROOFING : PRAYAG T.1 | 0 | Started | Material | (M)PPC CEMENT | BAG | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 2 | 285.58 | 571.16 | 1 | -1 | 283.59 | -287.57 | FINISHING
1776 | WATER PROOFING : PRAYAG T.2 | 0 | Started | Labour | (L)L/C for executing Screed Concrete (In Flats) | SQFT | 651.026 | 21.24 | 13827.79 | 0 | 0 | 0 | 0 | 21.24 | 0 | 651.026 | 21.24 | 13827.788 | 0 | 0 | 0 | 651.026 | 651.026 | 13827.792 | 13827.7922 | FINISHING
1777 | WATER PROOFING : PRAYAG T.2 | 0 | Started | Labour | (L)Waterproofing Chem. protective layer (In Flats) | SQFT | 3692.37 | 29.5 | 108924.92 | 0 | 0 | 0 | 0 | 29.5 | 0 | 3692.37 | 33.04 | 121995.9 | 0 | 0 | 0 | 3692.37 | 3692.37 | 108924.915 | 108924.915 | FINISHING
1778 | WATER PROOFING : PRAYAG T.2 | 0 | Started | Material | (M)M.C. SAND | MT | 0.2 | 1711.5 | 342.3 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0.1 | 1890 | 189 | 0.2 | 0.1 | 342.3 | 153.3 | FINISHING
1779 | WATER PROOFING : PRAYAG T.2 | 0 | Started | Material | (M)PPC CEMENT | BAG | 2 | 283.59 | 567.18 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 1 | 290.01 | 290.01 | 2 | 1 | 567.18 | 277.17 | FINISHING
1780 | CAR PARKING - Rotary Parking | 0 | Tentative | Labour | (L)Rotary Parking - SM125SU | NOS | 48 | 483800 | 23222400 | 0 | 0 | 0 | 0 | 483800 | 0 | 48 | 483800 | 23222400 | 0 | 0 | 0 | 48 | 48 | 23222400 | 23222400
1781 | CAR PARKING - MLCP | 0 | Tentative | Labour | (L)Wohr Combilift 543(2.0.T) | NOS | 90 | 1.18 | 106.2 | 0 | 0 | 0 | 0 | 1.18 | 0 | 90 | 11800 | 1062000 | 0 | 0 | 0 | 90 | 90 | 106.2 | 106.2
1782 | CAR PARKING - MLCP | 0 | Tentative | Labour | (L)Wohr Combilift 551(2.0.T) | NOS | 30 | 11800 | 354000 | 0 | 0 | 0 | 0 | 11800 | 0 | 30 | 11800 | 354000 | 0 | 0 | 0 | 30 | 30 | 354000 | 354000
1783 | CAR PARKING - MLCP | 0 | Tentative | Labour | (L)Wohr Combilift 552(2.0.T) | NOS | 19 | 11800 | 224200 | 0 | 0 | 0 | 0 | 11800 | 0 | 19 | 11800 | 224200 | 0 | 0 | 0 | 19 | 19 | 224200 | 224200
1784 | CAR PARKING - MLCP | 0 | Tentative | Material | (M)WOHR CL – 543 2.0 TONS | NOS | 90 | 212400 | 19116000 | 90 | 212400 | 19116000 | 0 | 212400 | 0 | 90 | 212400 | 19116000 | 0 | 0 | 0 | 90 | 90 | 19116000 | 19116000
1785 | CAR PARKING - MLCP | 0 | Tentative | Material | (M)WOHR CL – 551 2.0 TONS | NOS | 30 | 212400 | 6372000 | 30 | 212400 | 6372000 | 0 | 212400 | 0 | 30 | 212400 | 6372000 | 0 | 0 | 0 | 30 | 30 | 6372000 | 6372000
1786 | CAR PARKING - MLCP | 0 | Tentative | Material | (M)WOHR CL – 552 2.0 TONS | NOS | 19 | 1.18 | 22.42 | 19 | 1.18 | 22.42 | 0 | 1.18 | 0 | 19 | 236000 | 4484000 | 0 | 0 | 0 | 19 | 19 | 22.42 | 22.42
1787 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)16 PORT SWITCH | NOS | 1 | 9086 | 9086 | 0 | 0 | 0 | 0 | 9086 | 0 | 0 | 0 | 0 | 1 | 9086 | 9086 | 1 | 0 | 9086 | 0
1788 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)6TB HARDDISK | NOS | 1 | 14396 | 14396 | 0 | 0 | 0 | 0 | 14396 | 0 | 0 | 0 | 0 | 1 | 14396 | 14396 | 1 | 0 | 14396 | 0
1789 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)ASSEMBLED DESKTOP | NOS | 1 | 83933.4 | 83933.4 | 0 | 0 | 0 | 0 | 83933.4 | 0 | 0 | 0 | 0 | 2 | 83927.5 | 167855 | 1 | -1 | 83933.4 | -83921.6
1790 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)Asus External USB DVD-RW Drive | NOS | 2 | 2041.4 | 4082.8 | 0 | 0 | 0 | 0 | 2041.4 | 0 | 0 | 0 | 0 | 1 | 2035.5 | 2035.5 | 2 | 1 | 4082.8 | 2047.3
1791 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)Asus Vivobook Laptop | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 39412 | 118236 | 3 | 0 | 0 | -118236
1792 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)AUDIO CABLE | COIL | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4589.65 | 9179.29 | 2 | 0 | 0 | -9179.29
1793 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)AutoCAD including Specialized Toolset AD Commercial | NOS | 2 | 101480 | 202960 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 0 | 0 | 2 | 101480 | 202960 | 2 | 0 | 202960 | 0
1794 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)CABINET | NOS | 1 | 890.9 | 890.9 | 0 | 0 | 0 | 0 | 890.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 890.9 | 890.9
1795 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)CADMATE Professional standalone 2024 | NOS | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 59000 | 0
1796 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)COMPUTER SMPS | NOS | 1 | 1593 | 1593 | 0 | 0 | 0 | 0 | 1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1593 | 1593
1797 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)Power Cable Imported | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1798 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)SERVICE CHARGES | NOS | 1 | 1817.2 | 1817.2 | 0 | 0 | 0 | 0 | 1817.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1817.2 | 1817.2
1799 | INFRA. SITE EXP. - Computer Expenses | 0 | Started | Material | (M)Windows-11 Home. | NOS | 2 | 9322 | 18644 | 1 | 9322 | 9322 | 0 | 9322 | 0 | 1 | 11682 | 11682 | 1 | 9322 | 9322 | 2 | 1 | 18644 | 9322
1800 | INFRA. SITE EXP. - Security and Housekeeping | 10 | Started | Labour | (L)Gun Man | NOS | 24 | 20000 | 480000 | 0 | 0 | 0 | 2 | 20000 | 40000 | 23.9643 | 23600 | 565557.48 | 23.9643 | 23600 | 565557.48 | 22 | 0.0357 | 440000 | -85557.48
1801 | INFRA. SITE EXP. - Security and Housekeeping | 10 | Started | Labour | (L)Housekeeping Boys | NOS | 180 | 11500 | 2070000 | 0 | 0 | 0 | 18 | 11500 | 207000 | 177.5908 | 13217.09 | 2347233.16 | 141.078 | 13172.55 | 1858357.41 | 162 | 38.922 | 1863000 | 211642.59
1802 | INFRA. SITE EXP. - Security and Housekeeping | 10 | Started | Labour | (L)Security Guard | NOS | 282 | 15104 | 4259328 | 0 | 0 | 0 | 28 | 15104 | 422912 | 282 | 15540.84 | 4382517.46 | 195.0196 | 15278.59 | 2979623.9 | 254 | 86.9804 | 3836416 | 1279704.1
1803 | INFRA. SITE EXP. - Cash Expenses | 10 | Started | Labour | (L)CASH EXPENCESS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1804 | INFRA. SITE EXP. - Cash Expenses | 10 | Started | Labour | (L)Fees for Structural Review | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1805 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)10" TUB | NOS | 10 | 31.61 | 316.1 | 0 | 0 | 0 | 1 | 31.61 | 31.61 | 10 | 61.31 | 613.1 | 10 | 61.31 | 613.1 | 9 | 0 | 284.49 | -297
1806 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)16" GAMLA | NOS | 5 | 31.61 | 158.05 | 0 | 0 | 0 | 1 | 31.61 | 31.61 | 5 | 61.31 | 306.55 | 5 | 61.31 | 306.55 | 4 | 0 | 126.44 | -148.5
1807 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)8" TUBE | NOS | 12 | 31.61 | 379.32 | 0 | 0 | 0 | 1 | 31.61 | 31.61 | 12 | 61.31 | 735.72 | 12 | 61.31 | 735.72 | 11 | 0 | 347.71 | -356.4
1808 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)ARICA PLUM - BIG | NOS | 5 | 61.31 | 306.55 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 5 | 61.31 | 306.55 | 5 | 61.31 | 306.55 | 4 | 0 | 245.24 | 0
1809 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)ARICA PLUM - MEDIUM | NOS | 10 | 61.31 | 613.1 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 10 | 61.31 | 613.1 | 10 | 61.31 | 613.1 | 9 | 0 | 551.79 | 0
1810 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)BOUGANVALIA - BIG | NOS | 4 | 61.31 | 245.24 | 0 | 0 | 0 | 0 | 61.31 | 0 | 4 | 61.31 | 245.24 | 4 | 61.31 | 245.24 | 4 | 0 | 245.24 | 0
1811 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)BOUGANVALIA - SMALL | NOS | 10 | 61.31 | 613.1 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 10 | 61.31 | 613.1 | 10 | 61.31 | 613.1 | 9 | 0 | 551.79 | 0
1812 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)CLOROMA DRECEANA | NOS | 10 | 31.61 | 316.1 | 0 | 0 | 0 | 1 | 31.61 | 31.61 | 10 | 61.31 | 613.1 | 10 | 61.31 | 613.1 | 9 | 0 | 284.49 | -297
1813 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)CROTON PLANTS | NOS | 10 | 61.31 | 613.1 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 10 | 61.31 | 613.1 | 10 | 61.31 | 613.1 | 9 | 0 | 551.79 | 0
1814 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)DIFENBICHA | NOS | 10 | 61.31 | 613.1 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 10 | 61.31 | 613.1 | 10 | 61.31 | 613.1 | 9 | 0 | 551.79 | 0
1815 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)HANGING PLANTS | NOS | 25 | 61.31 | 1532.75 | 0 | 0 | 0 | 3 | 61.31 | 183.93 | 25 | 61.31 | 1532.75 | 25 | 61.31 | 1532.75 | 22 | 0 | 1348.82 | 0
1816 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)INSIDE LABOUR CHARGE FOR PLANTATION | LS | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 1 | 7000 | 7000 | 1 | 7000 | 7000 | 1 | 0 | 7000 | 0
1817 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)LIPSTIC PLANTS | NOS | 5 | 61.31 | 306.55 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 5 | 61.31 | 306.55 | 5 | 61.31 | 306.55 | 4 | 0 | 245.24 | 0
1818 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)MANDAVILLA | NOS | 5 | 31.61 | 158.05 | 0 | 0 | 0 | 1 | 31.61 | 31.61 | 5 | 61.31 | 306.55 | 5 | 61.31 | 306.55 | 4 | 0 | 126.44 | -148.5
1819 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)OUTSIDE LABOUR CHARGE FOR PLANTATION | LS | 1 | 13000 | 13000 | 0 | 0 | 0 | 0 | 13000 | 0 | 1 | 13000 | 13000 | 1 | 13000 | 13000 | 1 | 0 | 13000 | 0
1820 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)SILVER YEOKKA PLANTS | NOS | 5 | 31.61 | 158.05 | 0 | 0 | 0 | 1 | 31.61 | 31.61 | 5 | 61.31 | 306.55 | 5 | 61.31 | 306.55 | 4 | 0 | 126.44 | -148.5
1821 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)TRANSPORTATION CHARGE | LS | 1 | 4720 | 4720 | 0 | 0 | 0 | 0 | 4720 | 0 | 1 | 4000 | 4000 | 1 | 4000 | 4000 | 1 | 0 | 4720 | 720
1822 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Labour | (L)VICTORIA PLANT | NOS | 11 | 61.31 | 674.41 | 0 | 0 | 0 | 1 | 61.31 | 61.31 | 11 | 61.31 | 674.41 | 11 | 61.31 | 674.41 | 10 | 0 | 613.1 | 0
1823 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)1" GARDEN PIPE | MTR | 200 | 70.8 | 14160 | 200 | 70.8 | 14160 | 20 | 70.8 | 1416 | 200 | 56.64 | 11328 | 200 | 56.64 | 11328 | 180 | 0 | 12744 | 2832
1824 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)ACLAONIMA SNOW WHITE | NOS | 699 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 699 | 81.7 | 57111.1 | 629 | 0 | 0 | -57111.1
1825 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)BEGUM BAHAR | NOS | 50 | 40 | 2000 | 0 | 0 | 0 | 5 | 40 | 200 | 0 | 0 | 0 | 50 | 41.19 | 2059.4 | 45 | 0 | 1800 | -59.4
1826 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)BELIS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 40.95 | 2866.68 | 1 | -69 | 0 | -2866.68
1827 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)BREEDING HEART-PLANT | NOS | 90 | 40 | 3600 | 90 | 40 | 3600 | 9 | 40 | 360 | 90 | 41.9 | 3771 | 90 | 41.9 | 3770.75 | 81 | 0 | 3240 | -170.75
1828 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)BUXES PLANTS | NOS | 50 | 40 | 2000 | 0 | 0 | 0 | 5 | 40 | 200 | 0 | 0 | 0 | 50 | 41.2 | 2060.2 | 45 | 0 | 1800 | -60.2
1829 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)CHINESE TOGOR | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403 | 40.85 | 16463.36 | 3 | -400 | 0 | -16463.36
1830 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)DHAINTHUS PLANT | NOS | 30 | 30 | 900 | 30 | 30 | 900 | 3 | 30 | 90 | 30 | 31.42 | 942.6 | 30 | 31.42 | 942.69 | 27 | 0 | 810 | -42.69
1831 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)DURANTA | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 50 | 41.2 | 2060.2 | 1 | -49 | 40 | -2020.2
1832 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)ERANTHEMUM | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 60 | 41.19 | 2471.28 | 1 | -59 | 40 | -2431.28
1833 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)FERNS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 102.13 | 3574.55 | 1 | -34 | 0 | -3574.55
1834 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)FICUS PANDA | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 20 | 41.2 | 824.08 | 1 | -19 | 40 | -784.08
1835 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)FOXTAIL | NOS | 3 | 1000 | 3000 | 3 | 1000 | 3000 | 0 | 1000 | 0 | 3 | 1047.43 | 3142.29 | 3 | 1047.43 | 3142.29 | 3 | 0 | 3000 | -142.29
1836 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)GARDENIA(GANDHORAJ) | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 20 | 41.2 | 824.08 | 1 | -19 | 40 | -784.08
1837 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)GARDENOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 40.85 | 16340.8 | 1 | -399 | 0 | -16340.8
1838 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)GREEN DREACEANA-PLANT | NOS | 55 | 40 | 2200 | 55 | 40 | 2200 | 6 | 40 | 240 | 55 | 41.9 | 2304.5 | 55 | 41.9 | 2304.35 | 49 | 0 | 1960 | -104.35
1839 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)HELICONIA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 81.7 | 1225.56 | 1 | -14 | 0 | -1225.56
1840 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)IMPRETION | NOS | 10 | 30 | 300 | 10 | 30 | 300 | 1 | 30 | 30 | 10 | 31.42 | 314.2 | 10 | 31.42 | 314.23 | 9 | 0 | 270 | -14.23
1841 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)INCA MARI GOLD | NOS | 30 | 20 | 600 | 30 | 20 | 600 | 3 | 20 | 60 | 30 | 26.19 | 785.7 | 40 | 24.75 | 989.83 | 27 | -10 | 540 | -389.83
1842 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)IRAMTHAMUM | NOS | 90 | 40 | 3600 | 90 | 40 | 3600 | 9 | 40 | 360 | 90 | 41.9 | 3771 | 140 | 41.65 | 5830.95 | 81 | -50 | 3240 | -2230.95
1843 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)KAMINI | NOS | 2000 | 50 | 100000 | 2000 | 50 | 100000 | 200 | 50 | 10000 | 2000 | 20.95 | 41900 | 2040 | 22.51 | 45926.38 | 1800 | -40 | 90000 | 54073.62
1844 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)MANURE | LS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1840.98 | 1840.98 | 1 | 0 | 0 | -1840.98
1845 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)PANDANAS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 81.01 | 810.07 | 1 | -9 | 0 | -810.07
1846 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)PITUNIA-PLANT | NOS | 30 | 30 | 900 | 30 | 30 | 900 | 3 | 30 | 90 | 30 | 31.42 | 942.6 | 30 | 31.42 | 942.69 | 27 | 0 | 810 | -42.69
1847 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)RODHO CACTUS | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 130 | 41.19 | 5354.44 | 1 | -129 | 40 | -5314.44
1848 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)ROSE | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 60 | 41.19 | 2471.28 | 1 | -59 | 40 | -2431.28
1849 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)RUELIA | NOS | 100 | 40 | 4000 | 100 | 40 | 4000 | 10 | 40 | 400 | 100 | 31.42 | 3142 | 100 | 31.42 | 3142.29 | 90 | 0 | 3600 | 857.71
1850 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)STUBISCUS-PLANT | NOS | 80 | 40 | 3200 | 80 | 40 | 3200 | 8 | 40 | 320 | 80 | 41.9 | 3352 | 80 | 41.9 | 3351.78 | 72 | 0 | 2880 | -151.78
1851 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)VARIEGATED TAGOR | NOS | 60 | 40 | 2400 | 60 | 40 | 2400 | 6 | 40 | 240 | 60 | 31.42 | 1885.2 | 110 | 35.87 | 3945.57 | 54 | -50 | 2160 | -1545.57
1852 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)VERIEGATED TAGOR & KAMINI | NOS | 1 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 120 | 41.19 | 4942.56 | 1 | -119 | 40 | -4902.56
1853 | INFRA. SITE EXP. - Plantation Work | 10 | Started | Material | (M)XORA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 79.43 | 3971.71 | 1 | -49 | 0 | -3971.71
1854 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)2KG ABC Type Fire Extinguisher (Refill) | SET | 1 | 472 | 472 | 0 | 0 | 0 | 0 | 472 | 0 | 1 | 472 | 472 | 1 | 472 | 472 | 1 | 0 | 472 | 0
1855 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)4.5KG CO2 Type Fire Extinguisher (Refill) | SET | 2 | 1003 | 2006 | 0 | 0 | 0 | 0 | 1003 | 0 | 2 | 1003 | 2006 | 2 | 1003 | 2006 | 2 | 0 | 2006 | 0
1856 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)6KG ABC Type Fire Extinguisher(Refill) | SET | 5 | 826 | 4130 | 0 | 0 | 0 | 1 | 826 | 826 | 5 | 826 | 4130 | 5 | 826 | 4130 | 4 | 0 | 3304 | 0
1857 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Iron Halo-Pipe Frame with Flex Making & Mounting | NOS | 9 | 849.6 | 7646.4 | 0 | 0 | 0 | 1 | 849.6 | 849.6 | 9 | 1062 | 9558 | 9 | 1062 | 9558 | 8 | 0 | 6796.8 | -1911.6
1858 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Making & Supplying H.S.E Banners w/M.S. Frame | PER/SQFT | 168 | 47.2 | 7929.6 | 0 | 0 | 0 | 17 | 47.2 | 802.4 | 168 | 47.2 | 7929.6 | 168 | 47.2 | 7929.6 | 151 | 0 | 7127.2 | 0
1859 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Making Ch. for HSE banners w/MS Frame (2'2"X1'2") | PCS | 7 | 708 | 4956 | 0 | 0 | 0 | 1 | 708 | 708 | 7 | 708 | 4956 | 7 | 708 | 4956 | 6 | 0 | 4248 | 0
1860 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Making Ch. for HSE banners w/MS Frame (4'X3') | PCS | 6 | 1770 | 10620 | 0 | 0 | 0 | 1 | 1770 | 1770 | 6 | 1770 | 10620 | 6 | 1770 | 10620 | 5 | 0 | 8850 | 0
1861 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Making Ch. for HSE banners w/MS Frame (4'X3'X15nos) | SQFT | 180 | 59 | 10620 | 0 | 0 | 0 | 18 | 59 | 1062 | 180 | 59 | 10620 | 180 | 59 | 10620 | 162 | 0 | 9558 | 0
1862 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)QS Hire (Prayag 1st Fl. Conv./Veni Sub Str/Urvi Piling) | LS | 1 | 29500 | 29500 | 0 | 0 | 0 | 0 | 29500 | 0 | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 1 | 0 | 29500 | 4500
1863 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)QS Hire( Prayag TYP-01) | LS | 1 | 11800 | 11800 | 0 | 0 | 0 | 0 | 11800 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 0 | 11800 | 1800
1864 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Site Expenses | NOS | 275000 | 1.18 | 324500 | 0 | 0 | 0 | 27500 | 1.18 | 32450 | 275000 | 1.18 | 324500 | 21408.68 | 1.18 | 25262.24 | 247500 | 253591.32 | 292050 | 299237.76
1865 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Supply & Fitting of CO2 Fire Ext. Horn | SET | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 1 | 236 | 236 | 1 | 236 | 236 | 1 | 0 | 236 | 0
1866 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Labour | (L)Supply & Fitting of Pressure Gauze | SET | 2 | 159.3 | 318.6 | 0 | 0 | 0 | 0 | 159.3 | 0 | 2 | 159.3 | 318.6 | 2 | 159.3 | 318.6 | 2 | 0 | 318.6 | 0
1867 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)12MM ROPE | MTR | 220 | 33.28 | 7321.6 | 220 | 33.28 | 7321.6 | 22 | 33.28 | 732.16 | 220 | 33.26 | 7318.124 | 220 | 33.26 | 7318.12 | 198 | 0 | 6589.44 | 3.48
1868 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)26 MM LIFELINE ROPE | ROLL | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 1 | 19516 | 19516 | 0 | 0 | 0 | 1 | 1 | 118 | 118
1869 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)5 MTR MEASUREMENT TAPE | NOS | 10 | 141.6 | 1416 | 10 | 141.6 | 1416 | 1 | 141.6 | 141.6 | 10 | 182.9 | 1829 | 10 | 182.9 | 1829 | 9 | 0 | 1274.4 | -413
1870 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)6 KG ABC Type Fire Extinguisher (refill) | SET | 3 | 826 | 2478 | 3 | 826 | 2478 | 0 | 826 | 0 | 3 | 826 | 2478 | 3 | 826 | 2478 | 3 | 0 | 2478 | 0
1871 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)6TB HARDDISK | NOS | 1 | 14396 | 14396 | 1 | 14396 | 14396 | 0 | 14396 | 0 | 1 | 14396 | 14396 | 1 | 14396 | 14396 | 1 | 0 | 14396 | 0
1872 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)A4 size Paper | PKT | 12 | 291.2 | 3494.4 | 12 | 291.2 | 3494.4 | 1 | 291.2 | 291.2 | 12 | 244.16 | 2929.92 | 6 | 244.16 | 1464.96 | 11 | 6 | 3203.2 | 2029.44
1873 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Alpin (T Pin) | BOX | 6 | 47.2 | 283.2 | 0 | 0 | 0 | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 6 | 41.3 | 247.8 | 5 | 0 | 236 | 35.4
1874 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)APRON | NOS | 2 | 531 | 1062 | 2 | 531 | 1062 | 0 | 531 | 0 | 2 | 177.71 | 355.42 | 0 | 0 | 0 | 2 | 2 | 1062 | 1062
1875 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)AQUATEX’ MAKE DOMESTIC PRESSURE BOOSTER SYSTEM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 31049.87 | 31049.87 | 1 | 0 | 0 | -31049.87
1876 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Arch file (Big) | PCS | 6 | 106.2 | 637.2 | 6 | 106.2 | 637.2 | 1 | 106.2 | 106.2 | 6 | 96.76 | 580.56 | 6 | 96.76 | 580.56 | 5 | 0 | 531 | 56.64
1877 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)AUTOMATIC SHOE COVER DISPENSER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 47505.06 | 47505.06 | 1 | 0 | 0 | -47505.06
1878 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)BIG UMBRELLA | NOS | 10 | 708 | 7080 | 10 | 708 | 7080 | 1 | 708 | 708 | 10 | 495.6 | 4956 | 10 | 495.6 | 4956 | 9 | 0 | 6372 | 2124
1879 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)BLACK MARKER PEN | NOS | 10 | 23.6 | 236 | 10 | 23.6 | 236 | 1 | 23.6 | 23.6 | 10 | 15.58 | 155.76 | 10 | 15.58 | 155.76 | 9 | 0 | 212.4 | 80.24
1880 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)BLACK PEN | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 1 | 1.18 | 1.18 | 10 | 3.54 | 35.4 | 10 | 3.54 | 35.4 | 9 | 0 | 10.62 | -23.6
1881 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)BLUE PEN | NOS | 30 | 1.18 | 35.4 | 30 | 1.18 | 35.4 | 3 | 1.18 | 3.54 | 30 | 3.38 | 101.48 | 10 | 3.54 | 35.4 | 27 | 20 | 31.86 | 0
1882 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)BROWN TAPE | NOS | 3 | 47.2 | 141.6 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 39 | 41.74 | 1627.92 | 3 | -36 | 141.6 | -1486.32
1883 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)CARBON PAPER (BLUE) | PKT | 1 | 106.2 | 106.2 | 1 | 106.2 | 106.2 | 0 | 106.2 | 0 | 1 | 149.28 | 149.28 | 1 | 149.28 | 149.28 | 1 | 0 | 106.2 | -43.08
1884 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)CAT 6 CABLE | MTR | 5 | 35.4 | 177 | 5 | 35.4 | 177 | 1 | 35.4 | 35.4 | 5 | 29.5 | 147.5 | 5 | 29.5 | 147.5 | 4 | 0 | 141.6 | 29.5
1885 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)COMPUTER PAPER | PKT | 2 | 1770 | 3540 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 2 | 1770 | 3540 | 2 | 0 | 3540 | 0
1886 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)COVER FILE | PICS | 30 | 47.2 | 1416 | 30 | 47.2 | 1416 | 3 | 47.2 | 141.6 | 30 | 29.5 | 885 | 30 | 29.5 | 885 | 27 | 0 | 1274.4 | 531
1887 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)DIAMOND CUP WHEEL (X TRA - POWER) | NOS | 8 | 365.8 | 2926.4 | 8 | 365.8 | 2926.4 | 1 | 365.8 | 365.8 | 8 | 365.8 | 2926.4 | 6 | 365.8 | 2194.8 | 7 | 2 | 2560.6 | 731.6
1888 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)DOTTED HAND GLOVES | PAIR | 20 | 20.06 | 401.2 | 20 | 20.06 | 401.2 | 2 | 20.06 | 40.12 | 20 | 24.29 | 485.8 | 6 | 22.94 | 137.64 | 18 | 14 | 361.08 | 263.56
1889 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)DOUBLE LAYER SAFETY NET WITH OVERLAY | NOS | 54 | 4987.5 | 269325 | 54 | 4987.5 | 269325 | 5 | 4987.5 | 24937.5 | 54 | 5010.84 | 270585.09 | 54 | 5009.69 | 270523.5 | 49 | 0 | 244387.5 | -1198.5
1890 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Ear Plug | NOS | 10 | 29.5 | 295 | 10 | 29.5 | 295 | 1 | 29.5 | 29.5 | 10 | 13.8 | 138 | 0 | 0 | 0 | 9 | 10 | 265.5 | 295
1891 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Exercise Book (Big) | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 166.32 | 997.92 | 6 | 166.32 | 997.92 | 5 | 0 | 5.9 | -990.84
1892 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)FIRE BUCKET | NOS | 6 | 247.8 | 1486.8 | 6 | 247.8 | 1486.8 | 1 | 247.8 | 247.8 | 6 | 327.35 | 1964.1 | 0 | 0 | 0 | 5 | 6 | 1239 | 1486.8
1893 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)FULL BODY HARNES | NOS | 42 | 1652 | 69384 | 12 | 1652 | 19824 | 4 | 1652 | 6608 | 12 | 1503.96 | 18047.54 | 12 | 1499.03 | 17988.36 | 38 | 30 | 62776 | 51395.64
1894 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Garbage Bag | PKT | 4 | 29.5 | 118 | 4 | 29.5 | 118 | 0 | 29.5 | 0 | 4 | 53.1 | 212.4 | 0 | 0 | 0 | 4 | 4 | 118 | 118
1895 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)GIGABIT SWITCH | NOS | 1 | 1510.4 | 1510.4 | 1 | 1510.4 | 1510.4 | 0 | 1510.4 | 0 | 1 | 1504.5 | 1504.5 | 1 | 1504.5 | 1504.5 | 1 | 0 | 1510.4 | 5.9
1896 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)GLOVES | PAIR | 102 | 42 | 4284 | 102 | 42 | 4284 | 10 | 42 | 420 | 102 | 33.6 | 3427.2 | 101 | 33.6 | 3393.6 | 92 | 1 | 3864 | 890.4
1897 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)GRINDING WIRE BRUSH | NOS | 40 | 554.6 | 22184 | 40 | 554.6 | 22184 | 4 | 554.6 | 2218.4 | 40 | 141.6 | 5664 | 1 | 183.55 | 183.55 | 36 | 39 | 19965.6 | 22000.45
1898 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)GUM BOOT | PAIR | 40 | 425.6 | 17024 | 40 | 425.6 | 17024 | 4 | 425.6 | 1702.4 | 40 | 481.8 | 19272 | 28 | 481.74 | 13488.79 | 36 | 12 | 15321.6 | 3535.21
1899 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)INSTALLATION CHARGES | NOS | 1 | 625.4 | 625.4 | 1 | 625.4 | 625.4 | 0 | 625.4 | 0 | 1 | 590 | 590 | 1 | 826 | 826 | 1 | 0 | 625.4 | -200.6
1900 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)KEY BOARD | NOS | 1 | 1191.8 | 1191.8 | 1 | 1191.8 | 1191.8 | 0 | 1191.8 | 0 | 1 | 2065 | 2065 | 0 | 0 | 0 | 1 | 1 | 1191.8 | 1191.8
1901 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)LED STRIP LIGHT | MTR | 220 | 1180 | 259600 | 200 | 1180 | 236000 | 22 | 1180 | 25960 | 200 | 50.74 | 10148 | 200 | 50.74 | 10148 | 198 | 20 | 233640 | 249452
1902 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)LED STRIP LIGHT ADAPTER | NOS | 16 | 118 | 1888 | 16 | 118 | 1888 | 2 | 118 | 236 | 16 | 118 | 1888 | 16 | 118 | 1888 | 14 | 0 | 1652 | 0
1903 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)MAGNET | NOS | 1 | 106.2 | 106.2 | 1 | 106.2 | 106.2 | 0 | 106.2 | 0 | 1 | 118 | 118 | 1 | 118 | 118 | 1 | 0 | 106.2 | -11.8
1904 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)MASKING TAPE | PICS | 12 | 47.2 | 566.4 | 0 | 0 | 0 | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 12 | 20 | 240 | 11 | 0 | 519.2 | 326.4
1905 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)MOSQUITO OIL | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 409.98 | 4099.78 | 1 | -9 | 0 | -4099.78
1906 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)PATCH CHORD 2 MTRS | NOS | 2 | 153.4 | 306.8 | 2 | 153.4 | 306.8 | 0 | 153.4 | 0 | 2 | 151.04 | 302.08 | 2 | 151.04 | 302.08 | 2 | 0 | 306.8 | 4.72
1907 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)PHOTO FRAME | NOS | 1 | 5308.8 | 5308.8 | 1 | 5308.8 | 5308.8 | 0 | 5308.8 | 0 | 1 | 5310 | 5310 | 1 | 732.73 | 732.73 | 1 | 0 | 5308.8 | 4576.07
1908 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 45 | 110 | 4950 | 45 | 110 | 4950 | 5 | 110 | 550 | 45 | 141.6 | 6372 | 59.66 | 141.6 | 8447.86 | 40 | -14.66 | 4400 | -3497.86
1909 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Pressure Guage | SET | 2 | 159.3 | 318.6 | 2 | 159.3 | 318.6 | 0 | 159.3 | 0 | 2 | 159.3 | 318.6 | 2 | 159.3 | 318.6 | 2 | 0 | 318.6 | 0
1910 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)PVC SHOE | PAIR | 166 | 134.4 | 22310.4 | 129 | 134.4 | 17337.6 | 17 | 134.4 | 2284.8 | 129 | 156.35 | 20169.47 | 104 | 150.29 | 15629.72 | 149 | 62 | 20025.6 | 6680.68
1911 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)RAIN COAT (FREE SIZE) | NOS | 34 | 708 | 24072 | 34 | 708 | 24072 | 3 | 708 | 2124 | 34 | 576.4 | 19597.57 | 34 | 576.23 | 19591.86 | 31 | 0 | 21948 | 4480.14
1912 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)REFILLING OF TONER | NOS | 9 | 271.4 | 2442.6 | 9 | 271.4 | 2442.6 | 1 | 271.4 | 271.4 | 9 | 265.5 | 2389.5 | 9 | 265.5 | 2389.5 | 8 | 0 | 2171.2 | 53.1
1913 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)RJ 45 CONNECTOR | NOS | 2 | 11.8 | 23.6 | 2 | 11.8 | 23.6 | 0 | 11.8 | 0 | 2 | 5.9 | 11.8 | 2 | 5.9 | 11.8 | 2 | 0 | 23.6 | 11.8
1914 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)ROPE 26 MM (220 MTR) | MTR | 1 | 16874 | 16874 | 1 | 16874 | 16874 | 0 | 16874 | 0 | 1 | 16874 | 16874 | 1 | 16874 | 16874 | 1 | 0 | 16874 | 0
1915 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)RUBBER HAND GLOVES | PAIR | 70 | 70.8 | 4956 | 70 | 70.8 | 4956 | 7 | 70.8 | 495.6 | 70 | 33.77 | 2364.1 | 33 | 31.24 | 1031.02 | 63 | 37 | 4460.4 | 3924.98
1916 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY BELT | NOS | 30 | 1344 | 40320 | 30 | 1344 | 40320 | 3 | 1344 | 4032 | 30 | 1378.58 | 41357.4 | 23 | 1373.43 | 31588.96 | 27 | 7 | 36288 | 8731.04
1917 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY HELMET (BLUE) | NOS | 22 | 153.4 | 3374.8 | 22 | 153.4 | 3374.8 | 2 | 153.4 | 306.8 | 22 | 156.21 | 3436.66 | 21 | 156 | 3275.92 | 20 | 1 | 3068 | 98.88
1918 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY HELMET (GREY) | NOS | 31 | 118 | 3658 | 31 | 118 | 3658 | 3 | 118 | 354 | 31 | 122.94 | 3811.18 | 28 | 122.09 | 3418.62 | 28 | 3 | 3304 | 239.38
1919 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY HELMET (WHITE) | NOS | 51 | 153.4 | 7823.4 | 26 | 153.4 | 3988.4 | 5 | 153.4 | 767 | 26 | 155.03 | 4030.73 | 38 | 166.45 | 6325.18 | 46 | 13 | 7056.4 | 1498.22
1920 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY HELMET (YELLOW) | NOS | 340 | 94.4 | 32096 | 340 | 94.4 | 32096 | 34 | 94.4 | 3209.6 | 340 | 104.4 | 35496.9 | 318 | 103.1 | 32784.81 | 306 | 22 | 28886.4 | -688.81
1921 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY HELMET - ( GREEN) | NOS | 4 | 153.4 | 613.6 | 4 | 153.4 | 613.6 | 0 | 153.4 | 0 | 4 | 172.81 | 691.23 | 1 | 156.54 | 156.54 | 4 | 3 | 613.6 | 457.06
1922 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY HELMET - (RED) | NOS | 2 | 141.6 | 283.2 | 2 | 141.6 | 283.2 | 0 | 141.6 | 0 | 2 | 153.9 | 307.8 | 2 | 152.21 | 304.42 | 2 | 0 | 283.2 | -21.22
1923 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY JACKET (LIGHT GREEN) | NOS | 70 | 94.5 | 6615 | 70 | 94.5 | 6615 | 7 | 94.5 | 661.5 | 70 | 86.7 | 6069.2 | 62 | 83.24 | 5160.79 | 63 | 8 | 5953.5 | 1454.21
1924 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY JACKET (ORANGE) | NOS | 220 | 52.5 | 11550 | 220 | 52.5 | 11550 | 22 | 52.5 | 1155 | 220 | 47.25 | 10395 | 166 | 47.25 | 7843.5 | 198 | 54 | 10395 | 3706.5
1925 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY RIBBON | ROLL | 60 | 118 | 7080 | 60 | 118 | 7080 | 6 | 118 | 708 | 60 | 122.23 | 7333.5 | 48 | 121.76 | 5844.47 | 54 | 12 | 6372 | 1235.53
1926 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY SHOE | PAIR | 321 | 1030.4 | 330758.4 | 321 | 1030.4 | 330758.4 | 32 | 1030.4 | 32972.8 | 321 | 741.66 | 238071.43 | 221 | 816.4 | 180423.56 | 289 | 100 | 297785.6 | 150334.84
1927 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SAFETY SUNGLASS | NOS | 40 | 47.2 | 1888 | 40 | 47.2 | 1888 | 4 | 47.2 | 188.8 | 40 | 37.72 | 1508.6 | 40 | 41.92 | 1676.78 | 36 | 0 | 1699.2 | 211.22
1928 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Safety Sunglasses (Black) | NOS | 15 | 23.6 | 354 | 15 | 23.6 | 354 | 2 | 23.6 | 47.2 | 15 | 48.33 | 724.9 | 8 | 49.06 | 392.49 | 13 | 7 | 306.8 | -38.49
1929 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Safety Sunglasses (White) | NOS | 20 | 23.6 | 472 | 20 | 23.6 | 472 | 2 | 23.6 | 47.2 | 20 | 50.58 | 1011.6 | 20 | 50.18 | 1003.56 | 18 | 0 | 424.8 | -531.56
1930 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SERVICE CHARGES | NOS | 2 | 1817.2 | 3634.4 | 2 | 1817.2 | 3634.4 | 0 | 1817.2 | 0 | 2 | 649 | 1298 | 2 | 1856.85 | 3713.7 | 2 | 0 | 3634.4 | -79.3
1931 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)SPLENDOR GLOVES | PAIR | 324 | 59 | 19116 | 324 | 59 | 19116 | 32 | 59 | 1888 | 324 | 57.65 | 18677.64 | 319 | 56.34 | 17971.46 | 292 | 5 | 17228 | 1144.54
1932 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)STAND FAN (24") | NOS | 1 | 2832 | 2832 | 1 | 2832 | 2832 | 0 | 2832 | 0 | 1 | 11092 | 11092 | 1 | 11092 | 11092 | 1 | 0 | 2832 | -8260
1933 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)STAPLER NO 10 | PCS | 6 | 59 | 354 | 6 | 59 | 354 | 1 | 59 | 59 | 6 | 54.52 | 327.1002 | 6 | 54.52 | 327.1 | 5 | 0 | 295 | 26.9
1934 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)TARPAULIN (BIG SIZE) | NOS | 10 | 5699.4 | 56994 | 10 | 5699.4 | 56994 | 1 | 5699.4 | 5699.4 | 10 | 3670.65 | 36706.45 | 8 | 3610.8 | 28886.4 | 9 | 2 | 51294.6 | 28107.6
1935 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)TARPAULIN(MEDIUM SIZE) | NOS | 5 | 849.6 | 4248 | 5 | 849.6 | 4248 | 1 | 849.6 | 849.6 | 5 | 1393.07 | 6965.35 | 5 | 1387.91 | 6939.53 | 4 | 0 | 3398.4 | -2691.53
1936 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)TOILET PAPER ROLL | NOS | 12 | 306.8 | 3681.6 | 6 | 306.8 | 1840.8 | 1 | 306.8 | 306.8 | 6 | 584.1 | 3504.6 | 0 | 0 | 0 | 11 | 12 | 3374.8 | 3681.6
1937 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)Torchlight (Rechargeable Heavy Duty) | NOS | 2 | 2006 | 4012 | 2 | 2006 | 4012 | 0 | 2006 | 0 | 2 | 1994.2 | 3988.4 | 2 | 1994.2 | 3988.4 | 2 | 0 | 4012 | 23.6
1938 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)UPS | NOS | 1 | 2761.2 | 2761.2 | 1 | 2761.2 | 2761.2 | 0 | 2761.2 | 0 | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 1 | 0 | 2761.2 | -306.8
1939 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)UVC 35B MICROPHONE | NOS | 1 | 24780 | 24780 | 0 | 0 | 0 | 0 | 24780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 24780 | 24780
1940 | INFRA. SITE EXP. - Site Admin expenses | 10 | Started | Material | (M)WHITENER PEN | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 25.96 | 155.76 | 6 | 25.96 | 155.76 | 5 | 0 | 5.9 | -148.68
1941 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)DG Deployment Charges | NOS | 6 | 2360 | 14160 | 0 | 0 | 0 | 0 | 2360 | 0 | 6 | 2360 | 14160 | 6 | 2360 | 14160 | 6 | 0 | 14160 | 0
1942 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)DG Operator Hiring Charges | HRS | 36 | 2124 | 76464 | 0 | 0 | 0 | 0 | 2124 | 0 | 36 | 2124 | 76464 | 36 | 2124 | 76464 | 36 | 0 | 76464 | 0
1943 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)Hire Charges for 125KVA DG | DAYS | 9 | 7080 | 63720 | 0 | 0 | 0 | 0 | 7080 | 0 | 9 | 7080 | 63720 | 9 | 7080 | 63720 | 9 | 0 | 63720 | 0
1944 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)Hiring Charges for 125 KVA DG | MONTH | 12 | 38940 | 467280 | 0 | 0 | 0 | 0 | 38940 | 0 | 12 | 38940 | 467280 | 3 | 38940 | 116820 | 12 | 9 | 467280 | 350460
1945 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)Hiring Charges for JCB on Daily Basis (8hrs Shift) | DAYS | 8 | 7552 | 60416 | 0 | 0 | 0 | 0 | 7552 | 0 | 4 | 7552 | 30208 | 4 | 7552 | 30208 | 8 | 4 | 60416 | 30208
1946 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)HYDRA (FOR 4 HOURS) | DAYS | 6 | 3700 | 22200 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 22200 | 22200
1947 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)HYDRA (FOR 8 HOURS) | DAYS | 3 | 4500 | 13500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 13500 | 13500
1948 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Labour | (L)Operator Hiring Charges (8 hours shift) | MAN/DAY | 8 | 472 | 3776 | 0 | 0 | 0 | 0 | 472 | 0 | 4 | 472 | 1888 | 4 | 472 | 1888 | 8 | 4 | 3776 | 1888
1949 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)10/7 MIXER MACHINE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1950 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)2" SUCTION PIPE | FT | 100 | 59 | 5900 | 100 | 59 | 5900 | 0 | 59 | 0 | 100 | 41.3 | 4130 | 100 | 41.3 | 4130 | 100 | 0 | 5900 | 1770
1951 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)25 MM DRILL BIT | NOS | 12 | 377.6 | 4531.2 | 12 | 377.6 | 4531.2 | 0 | 377.6 | 0 | 12 | 397.27 | 4767.24 | 12 | 392.97 | 4715.66 | 12 | 0 | 4531.2 | -184.46
1952 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)25 MM VIBRATOR NOZZLE | NOS | 2 | 2950 | 5900 | 2 | 2950 | 5900 | 0 | 2950 | 0 | 2 | 3481 | 6962 | 0 | 0 | 0 | 2 | 2 | 5900 | 5900
1953 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM BARREL PIPE | NOS | 5 | 318.6 | 1593 | 5 | 318.6 | 1593 | 0 | 318.6 | 0 | 5 | 329.59 | 1647.95 | 5 | 324.29 | 1621.47 | 5 | 0 | 1593 | -28.47
1954 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM JOIN SOCKET | NOS | 16 | 153.4 | 2454.4 | 16 | 153.4 | 2454.4 | 0 | 153.4 | 0 | 16 | 273.88 | 4382.12 | 16 | 235.08 | 3761.29 | 16 | 0 | 2454.4 | -1306.89
1955 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM NOZZEL BEARING | NOS | 15 | 141.6 | 2124 | 15 | 141.6 | 2124 | 0 | 141.6 | 0 | 15 | 116.97 | 1754.6 | 15 | 115.63 | 1734.4 | 15 | 0 | 2124 | 389.6
1956 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM NOZZEL HEAD | NOS | 5 | 141.6 | 708 | 5 | 141.6 | 708 | 0 | 141.6 | 0 | 5 | 158.2 | 791 | 5 | 155.66 | 778.3 | 5 | 0 | 708 | -70.3
1957 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM NOZZEL OIL SEAL | NOS | 15 | 23.6 | 354 | 15 | 23.6 | 354 | 0 | 23.6 | 0 | 15 | 31.94 | 479.1 | 15 | 31.57 | 473.49 | 15 | 0 | 354 | -119.49
1958 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM NOZZEL ROTER | NOS | 4 | 318.6 | 1274.4 | 4 | 318.6 | 1274.4 | 0 | 318.6 | 0 | 4 | 315 | 1260 | 4 | 311.93 | 1247.73 | 4 | 0 | 1274.4 | 26.67
1959 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM NOZZEL ROTER END TIP | NOS | 6 | 23.6 | 141.6 | 6 | 23.6 | 141.6 | 0 | 23.6 | 0 | 6 | 31.43 | 188.58 | 6 | 31.14 | 186.81 | 6 | 0 | 141.6 | -45.21
1960 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM VIBRATOR NOZZLE | NOS | 2 | 2867.4 | 5734.8 | 2 | 2867.4 | 5734.8 | 0 | 2867.4 | 0 | 2 | 2520 | 5040 | 2 | 2495.47 | 4990.93 | 2 | 0 | 5734.8 | 743.87
1961 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40 MM VIBRATOR NOZZLE INNER CORD SET | NOS | 3 | 696.2 | 2088.6 | 3 | 696.2 | 2088.6 | 0 | 696.2 | 0 | 3 | 771.23 | 2313.69 | 3 | 758.85 | 2276.54 | 3 | 0 | 2088.6 | -187.94
1962 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40MM INNERCORD (SPRING) | NOS | 2 | 885 | 1770 | 2 | 885 | 1770 | 0 | 885 | 0 | 2 | 1003.53 | 2007.06 | 2 | 985.36 | 1970.72 | 2 | 0 | 1770 | -200.72
1963 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40MM RUBBER HOUSING NIPPLE ENDING | NOS | 2 | 236 | 472 | 2 | 236 | 472 | 0 | 236 | 0 | 2 | 267.61 | 535.22 | 2 | 262.76 | 525.52 | 2 | 0 | 472 | -53.52
1964 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)40MM RUBBER HOUSING NIPPLE STARTING | NOS | 2 | 259.6 | 519.2 | 2 | 259.6 | 519.2 | 0 | 259.6 | 0 | 2 | 294.37 | 588.74 | 2 | 289.04 | 578.08 | 2 | 0 | 519.2 | -58.88
1965 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM BARREL PIPE | NOS | 5 | 472 | 2360 | 5 | 472 | 2360 | 0 | 472 | 0 | 5 | 593.26 | 2966.3 | 5 | 583.73 | 2918.64 | 5 | 0 | 2360 | -558.64
1966 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM INERCORD (SPRING) | NOS | 2 | 885 | 1770 | 2 | 885 | 1770 | 0 | 885 | 0 | 2 | 1003.53 | 2007.06 | 2 | 985.36 | 1970.72 | 2 | 0 | 1770 | -200.72
1967 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM JOIN SOCKET | NOS | 16 | 153.4 | 2454.4 | 16 | 153.4 | 2454.4 | 0 | 153.4 | 0 | 16 | 281.74 | 4507.82 | 10 | 311.34 | 3113.43 | 16 | 6 | 2454.4 | -659.03
1968 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM NOZZEL BEARING | NOS | 15 | 177 | 2655 | 15 | 177 | 2655 | 0 | 177 | 0 | 15 | 164.09 | 2461.4 | 15 | 162.15 | 2432.31 | 15 | 0 | 2655 | 222.69
1969 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM NOZZEL HEAD | NOS | 5 | 295 | 1475 | 5 | 295 | 1475 | 0 | 295 | 0 | 5 | 329.59 | 1647.95 | 5 | 324.29 | 1621.47 | 5 | 0 | 1475 | -146.47
1970 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM NOZZEL OIL SEAL | NOS | 15 | 23.6 | 354 | 15 | 23.6 | 354 | 0 | 23.6 | 0 | 15 | 34.14 | 512.05 | 15 | 33.73 | 505.92 | 15 | 0 | 354 | -151.92
1971 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM NOZZEL ROTER | NOS | 10 | 483.8 | 4838 | 10 | 483.8 | 4838 | 0 | 483.8 | 0 | 10 | 566.24 | 5662.44 | 10 | 560.84 | 5608.42 | 10 | 0 | 4838 | -770.42
1972 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM NOZZEL ROTER END TIP | NOS | 10 | 23.6 | 236 | 10 | 23.6 | 236 | 0 | 23.6 | 0 | 10 | 31.43 | 314.3 | 10 | 31.13 | 311.34 | 10 | 0 | 236 | -75.34
1973 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM VIBRATOR NOZZLE | NOS | 4 | 3304 | 13216 | 2 | 3304 | 6608 | 0 | 3304 | 0 | 2 | 3150 | 6300 | 4 | 3514.31 | 14057.25 | 4 | 0 | 13216 | -841.25
1974 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60 MM VIBRATOR NOZZLE INNER CORD SET | NOS | 3 | 696.2 | 2088.6 | 3 | 696.2 | 2088.6 | 0 | 696.2 | 0 | 3 | 771.23 | 2313.69 | 3 | 758.85 | 2276.54 | 3 | 0 | 2088.6 | -187.94
1975 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60MM RUBBER HOUSING NIPPLE ENDING | NOS | 2 | 236 | 472 | 2 | 236 | 472 | 0 | 236 | 0 | 2 | 267.61 | 535.22 | 2 | 262.76 | 525.52 | 2 | 0 | 472 | -53.52
1976 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)60MM RUBBER HOUSING NIPPLE STARTING | NOS | 2 | 259.6 | 519.2 | 2 | 259.6 | 519.2 | 0 | 259.6 | 0 | 2 | 294.37 | 588.74 | 2 | 289.04 | 578.08 | 2 | 0 | 519.2 | -58.88
1977 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 13 | 460.2 | 5982.6 | 13 | 460.2 | 5982.6 | 0 | 460.2 | 0 | 13 | 505.33 | 6569.3 | 15 | 493.39 | 7400.87 | 13 | -2 | 5982.6 | -1418.27
1978 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)HEAD SHIELD | NOS | 1 | 413 | 413 | 1 | 413 | 413 | 0 | 413 | 0 | 1 | 568.85 | 568.85 | 1 | 568.85 | 568.85 | 1 | 0 | 413 | -155.85
1979 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)HESSIAN CLOTH | MTR | 20 | 2761.5 | 55230 | 9 | 2761.5 | 24853.5 | 0 | 2761.5 | 0 | 9 | 2863.99 | 25775.88 | 7 | 2861.8 | 20032.62 | 20 | 13 | 55230 | 35197.38
1980 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)NOZZLE VIBRATOR MACHINE 2HP 220V | NOS | 1 | 12980 | 12980 | 0 | 0 | 0 | 0 | 12980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12980 | 12980
1981 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)PVC DELIVERY PIPE 1" | FT | 100 | 35.4 | 3540 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 100 | 30.98 | 3098.39 | 100 | 0 | 3540 | 441.61
1982 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)PVC FOOT VALVE 1" | PCS | 1 | 177 | 177 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 1 | 185.9 | 185.9 | 1 | 0 | 177 | -8.9
1983 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)PVC SUCTION PIPE 1.1/4" | FT | 15 | 35.4 | 531 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 15 | 30.98 | 464.76 | 15 | 0 | 531 | 66.24
1984 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)TOOL BOX | NOS | 1 | 31624 | 31624 | 0 | 0 | 0 | 0 | 31624 | 0 | 0 | 0 | 0 | 1 | 26365.42 | 26365.42 | 1 | 0 | 31624 | 5258.58
1985 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)VICAT APPARATUS | NOS | 1 | 3068 | 3068 | 0 | 0 | 0 | 0 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3068 | 3068
1986 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)WEIGHING MACHINE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 23909.69 | 23909.69 | 1 | 0 | 0 | -23909.69
1987 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)WEIGHT MACHINE | SET | 1 | 8850 | 8850 | 0 | 0 | 0 | 0 | 8850 | 0 | 0 | 0 | 0 | 1 | 8950.89 | 8950.89 | 1 | 0 | 8850 | -100.89
1988 | INFRA. SITE EXP. - Tools And Equipments | 0 | Started | Material | (M)Welding Gloves | PAIR | 1 | 70.8 | 70.8 | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 1 | 89.39 | 89.39 | 1 | 89.39 | 89.39 | 1 | 0 | 70.8 | -18.59
1989 | INFRA. SITE EXP. - Firewood for Labours | 0 | Started | Material | (M)FIRE WOOD | KG | 71860 | 3.6 | 258696 | 67790 | 3.6 | 244044 | 0 | 3.6 | 0 | 66520 | 6.92 | 460330 | 77100 | 6.68 | 514781.72 | 71860 | -5240 | 258696 | -256085.72
1990 | INFRA. SITE EXP. - Laptop Rent | 10 | Started | Labour | (L)LAPTOP ON RENT | NOS | 1 | 1800 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1800 | 1800
1991 | INFRA. SITE EXP. - Laptop Rent | 10 | Started | Material | (M)Laptop For rent | MONTH | 4 | 3186 | 12744 | 4 | 3186 | 12744 | 0 | 3186 | 0 | 4 | 3186 | 12744 | 4 | 3186 | 12744 | 4 | 0 | 12744 | 0
1992 | INFRA. SITE EXP. - Construction and Repairing | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 0.238 | 1770 | 421.26 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 1.49 | 1429.8 | 2130.4 | 0.238 | -1.252 | 421.26 | -1709.14
1993 | INFRA. SITE EXP. - Construction and Repairing | 0 | Started | Material | (M)20 MM STONE CHIPS. | MT | 0.706 | 1750 | 1235.5 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 3.365 | 2057.96 | 6925.04 | 0.706 | -2.659 | 1235.5 | -5689.54
1994 | INFRA. SITE EXP. - Construction and Repairing | 0 | Started | Material | (M)2ND CLASS BRICKS | NOS | 6708 | 10 | 67080 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 7058 | 9 | 63522 | 6708 | -350 | 67080 | 3558
1995 | INFRA. SITE EXP. - Construction and Repairing | 0 | Started | Material | (M)M.C. SAND | MT | 8.586 | 1711.5 | 14694.94 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 11.963 | 1748.41 | 20916.21 | 8.586 | -3.377 | 14694.939 | -6221.271
1996 | INFRA. SITE EXP. - Construction and Repairing | 0 | Started | Material | (M)PPC CEMENT | BAG | 51 | 283.59 | 14463.09 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 49 | 286.16 | 14022 | 51 | 2 | 14463.09 | 441.09
1997 | INFRA. SITE EXP. - Construction and Repairing | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 5 | 78 | 390 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 5 | 156.93 | 784.65 | 5 | 0 | 390 | -394.65
1998 | INFRA. SITE EXP. - AMC For Concrete Pump | 10 | Started | Labour | (L)1NO SP1300HDRL Concrete Pump | NOS | 1 | 55000 | 55000 | 0 | 0 | 0 | 0 | 55000 | 0 | 1 | 64900 | 64900 | 1 | 64900 | 64900 | 1 | 0 | 55000 | -9900
1999 | INFRA. SITE EXP. - Motor and Hydraulic Pump | 10 | Started | Labour | (L)ELECTRIC MOTOR & HYDRAULIC PUMP REPAIR | LS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5500 | 5500 | 1 | 5500 | 5500 | 1 | 0 | 0 | -5500
2000 | INFRA. SITE EXP. - Mosquito Control | 10 | Started | Labour | (L)LABOUR CHARGES OF MOSQUITO CONTROL | NOS | 480 | 600 | 288000 | 0 | 0 | 0 | 48 | 600 | 28800 | 188 | 708 | 133104 | 112 | 708 | 79296 | 432 | 368 | 259200 | 208704
2001 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Labour | (L)Electricity Charges for Site | NOS | 1050000 | 1 | 1050000 | 0 | 0 | 0 | 0 | 1 | 0 | 1050000 | 1 | 1050000 | 126220 | 1 | 126220 | 1050000 | 923780 | 1050000 | 923780
2002 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)1.5 SQ MM 2 CORE CABLE (COPPER) | MTR | 1900 | 47.2 | 89680 | 1500 | 47.2 | 70800 | 0 | 47.2 | 0 | 1500 | 36.38 | 54575.34 | 1545 | 36.32 | 56113.29 | 1900 | 355 | 89680 | 33566.71
2003 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)1.5 SQ MM COPPER WIRE | MTR | 720 | 11.8 | 8496 | 720 | 11.8 | 8496 | 0 | 11.8 | 0 | 720 | 16.23 | 11683.854 | 720 | 16.23 | 11682.41 | 720 | 0 | 8496 | -3186.41
2004 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM 3 CORE CABLE | MTR | 1200 | 41.56 | 49872 | 800 | 41.56 | 33248 | 0 | 41.56 | 0 | 800 | 48.89 | 39112.4 | 1500 | 47.47 | 71202.59 | 1200 | -300 | 49872 | -21330.59
2005 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM COPPER CABLE 2 CORE | COIL | 3 | 3740.6 | 11221.8 | 3 | 3740.6 | 11221.8 | 0 | 3740.6 | 0 | 3 | 3761.17 | 11283.51 | 3 | 3757.31 | 11271.92 | 3 | 0 | 11221.8 | -50.12
2006 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)10 ' G1 EARTHING PIPE | NOS | 2 | 1333.4 | 2666.8 | 2 | 1333.4 | 2666.8 | 0 | 1333.4 | 0 | 2 | 1711 | 3422 | 0 | 0 | 0 | 2 | 2 | 2666.8 | 2666.8
2007 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)10 AMP PLUG TOP | NOS | 50 | 1.18 | 59 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 59 | 59
2008 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)10 AMP SINGLE POLE MCB | NOS | 10 | 236 | 2360 | 10 | 236 | 2360 | 0 | 236 | 0 | 10 | 157.41 | 1574.12 | 1 | 157.41 | 157.41 | 10 | 9 | 2360 | 2202.59
2009 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)100 AMP BUSBAR | NOS | 1 | 2380.06 | 2380.06 | 1 | 2380.06 | 2380.06 | 0 | 2380.06 | 0 | 1 | 2017.8 | 2017.8 | 1 | 2017.8 | 2017.8 | 1 | 0 | 2380.06 | 362.26
2010 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)1000W Halogen Bulb | NOS | 10 | 106.2 | 1062 | 10 | 106.2 | 1062 | 0 | 106.2 | 0 | 10 | 96.76 | 967.6 | 0 | 0 | 0 | 10 | 10 | 1062 | 1062
2011 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)12 MODULAR PVC BOARD | NOS | 2 | 507.4 | 1014.8 | 0 | 0 | 0 | 0 | 507.4 | 0 | 0 | 0 | 0 | 2 | 300.9 | 601.8 | 2 | 0 | 1014.8 | 413
2012 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)12 MODULER PLATE | NOS | 2 | 625.4 | 1250.8 | 0 | 0 | 0 | 0 | 625.4 | 0 | 0 | 0 | 0 | 2 | 175.11 | 350.22 | 2 | 0 | 1250.8 | 900.58
2013 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)150 W LED LIGHT | NOS | 50 | 1.18 | 59 | 50 | 1.18 | 59 | 0 | 1.18 | 0 | 50 | 2263.24 | 113162 | 32 | 2615.42 | 83693.53 | 50 | 18 | 59 | -83634.53
2014 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)16 AMP INDUSTRIAL SOCKET | NOS | 52 | 424.8 | 22089.6 | 10 | 424.8 | 4248 | 0 | 424.8 | 0 | 10 | 363.56 | 3635.58 | 22 | 263.99 | 5807.72 | 52 | 30 | 22089.6 | 16281.88
2015 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)16 AMP PLUG TOP | NOS | 20 | 1.18 | 23.6 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 73.16 | 731.6 | 0 | 0 | 0 | 20 | 20 | 23.6 | 23.6
2016 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)16 AMP SINGLE POLE MCB | NOS | 30 | 165.2 | 4956 | 30 | 165.2 | 4956 | 0 | 165.2 | 0 | 30 | 152.48 | 4574.52 | 8 | 158.36 | 1266.87 | 30 | 22 | 4956 | 3689.13
2017 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)16 AMP SOCKET | NOS | 8 | 413 | 3304 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 3304 | 3304
2018 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)16 MM TIE - ROD 1.50 MTR EACH | MTR | 195 | 118 | 23010 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 195 | 123.95 | 24169.7 | 195 | 0 | 23010 | -1159.7
2019 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)16 SQ MM CABLE FLAT SOCKET | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 8.26 | 82.6 | 4 | 8.26 | 33.04 | 10 | 6 | 11.8 | -21.24
2020 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2 MOD COVER | NOS | 1 | 62.65 | 62.65 | 0 | 0 | 0 | 0 | 62.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 62.65 | 62.65
2021 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ MM 4 CORE COPPER CABLE | MTR | 600 | 153.4 | 92040 | 600 | 153.4 | 92040 | 0 | 153.4 | 0 | 600 | 112.45 | 67468.2 | 725 | 109.68 | 79519.64 | 600 | -125 | 92040 | 12520.36
2022 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ MM 3 CORE CABLE(COPPER) | MTR | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 83.36 | 16671.48 | 200 | 0 | 0 | -16671.48
2023 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ MM COPPER FLEXIBLE SINGLE CORE WIRE(BLACK) | MTR | 180 | 33.04 | 5947.2 | 180 | 33.04 | 5947.2 | 0 | 33.04 | 0 | 180 | 26.43 | 4757.76 | 180 | 26.43 | 4757.76 | 180 | 0 | 5947.2 | 1189.44
2024 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ MM COPPER FLEXIBLE SINGLE CORE WIRE(GREEN) | MTR | 180 | 33.04 | 5947.2 | 180 | 33.04 | 5947.2 | 0 | 33.04 | 0 | 180 | 26.43 | 4757.76 | 180 | 26.43 | 4757.76 | 180 | 0 | 5947.2 | 1189.44
2025 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ MM COPPER FLEXIBLE SINGLE CORE WIRE(RED) | MTR | 180 | 33.04 | 5947.2 | 180 | 33.04 | 5947.2 | 0 | 33.04 | 0 | 180 | 26.43 | 4757.76 | 180 | 26.43 | 4757.76 | 180 | 0 | 5947.2 | 1189.44
2026 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ.MM COPPER WIRE (BLUE, 180 MTR) | COIL | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5900 | 5900
2027 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)2.5 SQ.MM. 2 CORE COPPER CABLE | MTR | 400 | 177 | 70800 | 400 | 177 | 70800 | 0 | 177 | 0 | 400 | 58.6 | 23441.88 | 0 | 0 | 0 | 400 | 400 | 70800 | 70800
2028 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)20 MM FLEXIBLE PIPE | MTR | 25 | 1 | 25 | 25 | 1 | 25 | 0 | 1 | 0 | 25 | 8.26 | 206.5 | 25 | 8.26 | 206.5 | 25 | 0 | 25 | -181.5
2029 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)200 WATT LED LIGHT | NOS | 36 | 1.18 | 42.48 | 15 | 1.18 | 17.7 | 0 | 1.18 | 0 | 15 | 3320.65 | 49809.8 | 32 | 3873.17 | 123941.45 | 36 | 4 | 42.48 | -123898.97
2030 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)20A INDUSTRIAL PLUG SOCKET | NOS | 60 | 236 | 14160 | 60 | 236 | 14160 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 14160 | 14160
2031 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)20MM PVC SADDLE | NOS | 150 | 1.18 | 177 | 150 | 1.18 | 177 | 0 | 1.18 | 0 | 150 | 4.72 | 708 | 150 | 4.72 | 708 | 150 | 0 | 177 | -531
2032 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)22 WATT YELLOW LED TUBE | NOS | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 205.29 | 4105.79 | 14 | -6 | 0 | -4105.79
2033 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)25 MM PVC FLEXIBLE PIPE 25 MTR ROLL | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 1 | 0 | 1.18 | -282.02
2034 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)25 SQ MM CABLE SOCKET | NOS | 8 | 23.6 | 188.8 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 8 | 21.24 | 169.92 | 8 | 0 | 188.8 | 18.88
2035 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)25 SQ.MM 4 CORE ALUMINIUM ARMOURED CABLE: | MTR | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 240.08 | 18005.89 | 75 | 0 | 0 | -18005.89
2036 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)25 SQ.MM ALUMINIUM FLAT TYPE SOCKET: | PICS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5.64 | 22.55 | 4 | 0 | 0 | -22.55
2037 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)25 SQMM AL FLAT SOCKET | NOS | 10 | 8.26 | 82.6 | 10 | 8.26 | 82.6 | 0 | 8.26 | 0 | 10 | 10.97 | 109.74 | 0 | 0 | 0 | 10 | 10 | 82.6 | 82.6
2038 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 MM CABLE LUGS | NOS | 4 | 11.8 | 47.2 | 4 | 11.8 | 47.2 | 0 | 11.8 | 0 | 4 | 14.68 | 58.72 | 4 | 14.6 | 58.41 | 4 | 0 | 47.2 | -11.21
2039 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 MM DEPTH PVC CIRCULAR BOX (1 WAY) | NOS | 15 | 14.16 | 212.4 | 15 | 14.16 | 212.4 | 0 | 14.16 | 0 | 15 | 14.16 | 212.4 | 15 | 14.16 | 212.4 | 15 | 0 | 212.4 | 0
2040 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 MM DEPTH PVC CIRCULAR BOX (2 WAY) | NOS | 20 | 14.16 | 283.2 | 20 | 14.16 | 283.2 | 0 | 14.16 | 0 | 20 | 14.16 | 283.2 | 20 | 14.16 | 283.2 | 20 | 0 | 283.2 | 0
2041 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 MM DEPTH PVC CIRCULAR BOX (3 WAY) | NOS | 15 | 21.24 | 318.6 | 15 | 21.24 | 318.6 | 0 | 21.24 | 0 | 15 | 14.16 | 212.4 | 15 | 14.16 | 212.4 | 15 | 0 | 318.6 | 106.2
2042 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 MM DEPTH PVC CIRCULAR BOX (4 WAY) | NOS | 30 | 21.24 | 637.2 | 30 | 21.24 | 637.2 | 0 | 21.24 | 0 | 30 | 14.16 | 424.8 | 30 | 14.16 | 424.8 | 30 | 0 | 637.2 | 212.4
2043 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 SQ.MM. BOTTLE TYPE ALUMINIUM LUGS | NOS | 4 | 2.96 | 11.84 | 4 | 2.96 | 11.84 | 0 | 2.96 | 0 | 4 | 15.34 | 61.36 | 4 | 15.34 | 61.36 | 4 | 0 | 11.84 | -49.52
2044 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35 SQMM CABLE FLAT SOCKET | NOS | 24 | 1.18 | 28.32 | 24 | 1.18 | 28.32 | 0 | 1.18 | 0 | 24 | 14.16 | 339.84 | 8 | 14.16 | 113.28 | 24 | 16 | 28.32 | -84.96
2045 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)35mm AL LUGS FLAT TYPE | NOS | 4 | 11.8 | 47.2 | 4 | 11.8 | 47.2 | 0 | 11.8 | 0 | 4 | 12.98 | 51.92 | 4 | 12.98 | 51.92 | 4 | 0 | 47.2 | -4.72
2046 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 Core X 16 Sqmm Aluminum Armoured Cable | MTR | 160 | 1.18 | 188.8 | 160 | 1.18 | 188.8 | 0 | 1.18 | 0 | 160 | 137 | 21919.68 | 57 | 137 | 7809 | 160 | 103 | 188.8 | -7620.2
2047 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 CORE X 35 SQ MM ALUMINIUM ARMOURED CABLE | MTR | 260 | 212.4 | 55224 | 260 | 212.4 | 55224 | 0 | 212.4 | 0 | 260 | 239.15 | 62179.08 | 260 | 238.87 | 62106.89 | 260 | 0 | 55224 | -6882.89
2048 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 MODULAR PVC BOARD | NOS | 5 | 212.4 | 1062 | 0 | 0 | 0 | 0 | 212.4 | 0 | 0 | 0 | 0 | 5 | 130.27 | 651.36 | 5 | 0 | 1062 | 410.64
2049 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 POLE 32 AMP MCB WITH COVER | NOS | 1 | 14396 | 14396 | 0 | 0 | 0 | 0 | 14396 | 0 | 0 | 0 | 0 | 1 | 1438.86 | 1438.86 | 1 | 0 | 14396 | 12957.14
2050 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 POLE 40 AMP MCB | NOS | 6 | 1463.2 | 8779.2 | 6 | 1463.2 | 8779.2 | 0 | 1463.2 | 0 | 6 | 1341.16 | 8046.9798 | 2 | 1341.16 | 2682.32 | 6 | 4 | 8779.2 | 6096.88
2051 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 POLE 63 AMP MCB | NOS | 2 | 4618.52 | 9237.04 | 0 | 0 | 0 | 0 | 4618.52 | 0 | 0 | 0 | 0 | 2 | 1392.23 | 2784.46 | 2 | 0 | 9237.04 | 6452.58
2052 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 POLE MCB ENCLOSER | NOS | 1 | 2478 | 2478 | 1 | 2478 | 2478 | 0 | 2478 | 0 | 1 | 411.53 | 411.53 | 2 | 1079.95 | 2159.89 | 1 | -1 | 2478 | 318.11
2053 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)4 SQ MM 4 CORE COPPER CABLE | COIL | 4 | 17841.6 | 71366.4 | 4 | 17841.6 | 71366.4 | 0 | 17841.6 | 0 | 4 | 17651.12 | 70604.48 | 2 | 18197.19 | 36394.38 | 4 | 2 | 71366.4 | 34972.02
2054 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)40 AMP 4 POLE RCCB COVER BOX | NOS | 3 | 1.18 | 3.54 | 3 | 1.18 | 3.54 | 0 | 1.18 | 0 | 3 | 2443.07 | 7329.2199 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54
2055 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)40 AMP RCCB | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 2020.16 | 8080.64 | 2 | 2020.16 | 4040.32 | 4 | 2 | 4.72 | -4035.6
2056 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)40 AMP. 4 POLE ISOLATOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 944.74 | 944.74 | 1 | 0 | 0 | -944.74
2057 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)5 WAY PVC BOX SURFACE TYPE (FOR 3 NOS SWITCH & 2 NOS SOCKET | NOS | 28 | 554.6 | 15528.8 | 28 | 554.6 | 15528.8 | 0 | 554.6 | 0 | 28 | 555.51 | 15554.28 | 28 | 555.32 | 15549.02 | 28 | 0 | 15528.8 | -20.22
2058 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)50 SQMM AL FLAT SOCKET | NOS | 24 | 12.4 | 297.6 | 24 | 12.4 | 297.6 | 0 | 12.4 | 0 | 24 | 20.77 | 498.4392 | 0 | 0 | 0 | 24 | 24 | 297.6 | 297.6
2059 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)50/6 STRIP SADDLE | PICS | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 10.03 | 200.6 | 20 | 0 | 0 | -200.6
2060 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)6 AMP 5 PIN SOCKET | NOS | 90 | 35.4 | 3186 | 60 | 35.4 | 2124 | 0 | 35.4 | 0 | 60 | 29.5 | 1770 | 22 | 29.5 | 649 | 90 | 68 | 3186 | 2537
2061 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)6 AMP SOCKET | NOS | 48 | 274.94 | 13197.12 | 40 | 274.94 | 10997.6 | 0 | 274.94 | 0 | 40 | 29.03 | 1161.12 | 28 | 44.71 | 1251.94 | 48 | 20 | 13197.12 | 11945.18
2062 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)6 AMP SWITCH | NOS | 150 | 142.78 | 21417 | 150 | 142.78 | 21417 | 0 | 142.78 | 0 | 150 | 15.15 | 2272.68 | 42 | 15.16 | 636.65 | 150 | 108 | 21417 | 20780.35
2063 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)6 MM CHINA CLAMP | PKT | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 1 | 153.94 | 153.94 | 1 | 0 | 141.6 | -12.34
2064 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)6 WAY TPN DB BOX | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 2782.38 | 11129.52 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
2065 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)63 A, 16KA, TPN, MCCB (TMR) with Enclosure | NOS | 1 | 6565.52 | 6565.52 | 1 | 6565.52 | 6565.52 | 0 | 6565.52 | 0 | 1 | 6565.52 | 6565.52 | 0 | 0 | 0 | 1 | 1 | 6565.52 | 6565.52
2066 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)63 AMP 4 POLE MCCB | NOS | 5 | 10561 | 52805 | 5 | 10561 | 52805 | 0 | 10561 | 0 | 5 | 3221.39 | 16106.96 | 4 | 3221.39 | 12885.57 | 5 | 1 | 52805 | 39919.43
2067 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)63 AMP BUSBAR | NOS | 5 | 1 | 5 | 5 | 1 | 5 | 0 | 1 | 0 | 5 | 1587.1 | 7935.5 | 2 | 1587.1 | 3174.2 | 5 | 3 | 5 | -3169.2
2068 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)63 AMP-30 MA 4 POLE RCCB WITH COVER BOX | NOS | 1 | 4189 | 4189 | 1 | 4189 | 4189 | 0 | 4189 | 0 | 1 | 2687.75 | 2687.75 | 1 | 2687.75 | 2687.75 | 1 | 0 | 4189 | 1501.25
2069 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)63 AMPS.,30 MA, 4 POLE RCCB WITH COVER BOX. | NOS | 2 | 3180.1 | 6360.2 | 2 | 3180.1 | 6360.2 | 0 | 3180.1 | 0 | 2 | 2978.91 | 5957.82 | 0 | 0 | 0 | 2 | 2 | 6360.2 | 6360.2
2070 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)63AMP MCCB (TMR) WITH ENCLOSURE | NOS | 1 | 6565.52 | 6565.52 | 1 | 6565.52 | 6565.52 | 0 | 6565.52 | 0 | 1 | 6565.52 | 6565.52 | 0 | 0 | 0 | 1 | 1 | 6565.52 | 6565.52
2071 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)8' 0" LONG ALUMINIUM LADER (DOUBLE STAND) | NOS | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 0 | 7080 | 0 | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 1 | 0 | 7080 | 0
2072 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)ADAPTOR 12V2AMP | NOS | 9 | 767 | 6903 | 0 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 9 | 322.57 | 2903.13 | 9 | 0 | 6903 | 3999.87
2073 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)BATTERY CHARGER | NOS | 1 | 4991.4 | 4991.4 | 0 | 0 | 0 | 0 | 4991.4 | 0 | 0 | 0 | 0 | 1 | 4989.01 | 4989.01 | 1 | 0 | 4991.4 | 2.39
2074 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)BROWN TAPE | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 5 | 41.3 | 206.5 | 1 | -4 | 47.2 | -159.3
2075 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)CASSING | NOS | 25 | 82.6 | 2065 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 20 | 82.6 | 1652 | 25 | 5 | 2065 | 413
2076 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)CAT 6 WIRE | MTR | 305 | 23.6 | 7198 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 305 | 27.14 | 8277.7 | 305 | 0 | 7198 | -1079.7
2077 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)CAT 6 WIRE FINOLEX | MTR | 80 | 23.6 | 1888 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 80 | 25.96 | 2076.8 | 80 | 0 | 1888 | -188.8
2078 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)DIGITAL AC/DC CLAMP METER | NOS | 1 | 22968.7 | 22968.7 | 1 | 22968.7 | 22968.7 | 0 | 22968.7 | 0 | 1 | 3481 | 3481 | 0 | 0 | 0 | 1 | 1 | 22968.7 | 22968.7
2079 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)Digital insulation megger (Calibrated) | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 7857.62 | 7857.62 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2080 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)DOUBLE POLE 32 AMP MCB | NOS | 18 | 525.1 | 9451.8 | 18 | 525.1 | 9451.8 | 0 | 525.1 | 0 | 18 | 427.87 | 7701.62 | 4 | 429.31 | 1717.25 | 18 | 14 | 9451.8 | 7734.55
2081 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)DOUBLE POLE ENCLOSER BOX | NOS | 6 | 413 | 2478 | 6 | 413 | 2478 | 0 | 413 | 0 | 6 | 435.72 | 2614.3002 | 3 | 435.72 | 1307.15 | 6 | 3 | 2478 | 1170.85
2082 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)ELBOW | NOS | 50 | 1.18 | 59 | 50 | 1.18 | 59 | 0 | 1.18 | 0 | 50 | 5.9 | 295 | 50 | 5.9 | 295 | 50 | 0 | 59 | -236
2083 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)ENCLOSER BOX | NOS | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 0 | 1.18 | 0 | 8 | 460.61 | 3684.9 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
2084 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)FLOOD LIGHT | NOS | 26 | 3540 | 92040 | 26 | 3540 | 92040 | 0 | 3540 | 0 | 26 | 3803.32 | 98886.19 | 26 | 2285.95 | 59434.82 | 26 | 0 | 92040 | 32605.18
2085 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)G.I Earthing Rod | NOS | 10 | 212.4 | 2124 | 10 | 212.4 | 2124 | 0 | 212.4 | 0 | 10 | 212.4 | 2124 | 10 | 212.4 | 2124 | 10 | 0 | 2124 | 0
2086 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)GIGABIT SWITCH | NOS | 1 | 1510.4 | 1510.4 | 1 | 1510.4 | 1510.4 | 0 | 1510.4 | 0 | 1 | 2242 | 2242 | 0 | 0 | 0 | 1 | 1 | 1510.4 | 1510.4
2087 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)GYPSUM SCREW | NOS | 200 | 23.6 | 4720 | 200 | 23.6 | 4720 | 0 | 23.6 | 0 | 200 | 1.18 | 236 | 200 | 1.18 | 236 | 200 | 0 | 4720 | 4484
2088 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)INDUSTRIAL SOCKET | NOS | 104 | 188.8 | 19635.2 | 104 | 188.8 | 19635.2 | 0 | 188.8 | 0 | 104 | 186.86 | 19433.32 | 77 | 186.7 | 14375.69 | 104 | 27 | 19635.2 | 5259.51
2089 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)INDUSTRIAL TOP | NOS | 121 | 141.6 | 17133.6 | 89 | 141.6 | 12602.4 | 0 | 141.6 | 0 | 64 | 134.51 | 8608.64 | 32 | 164.21 | 5254.73 | 121 | 89 | 17133.6 | 11878.87
2090 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)LED TUBE LIGHT | NOS | 70 | 263.39 | 18437.3 | 50 | 263.39 | 13169.5 | 0 | 263.39 | 0 | 50 | 157.06 | 7853.2 | 68 | 181.06 | 12312.32 | 70 | 2 | 18437.3 | 6124.98
2091 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)MCB 4 POLE 32 AMP WITH EXTERNAL COVER | NOS | 6 | 1416 | 8496 | 6 | 1416 | 8496 | 0 | 1416 | 0 | 6 | 1443.41 | 8660.4402 | 6 | 1440.03 | 8640.16 | 6 | 0 | 8496 | -144.16
2092 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)MCCB 125A (TMR) WITH ENCLOSURE | NOS | 1 | 7831.66 | 7831.66 | 1 | 7831.66 | 7831.66 | 0 | 7831.66 | 0 | 1 | 7831.08 | 7831.08 | 0 | 0 | 0 | 1 | 1 | 7831.66 | 7831.66
2093 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)MOTOR STARTER | NOS | 3 | 1 | 3 | 3 | 1 | 3 | 0 | 1 | 0 | 3 | 2515.76 | 7547.28 | 0 | 0 | 0 | 3 | 3 | 3 | 3
2094 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PATCH CORD (3 MTR) | NOS | 1 | 324.5 | 324.5 | 1 | 324.5 | 324.5 | 0 | 324.5 | 0 | 1 | 324.5 | 324.5 | 1 | 324.5 | 324.5 | 1 | 0 | 324.5 | 0
2095 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)Patch Cord (5 Mtr) | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 413 | 826 | 2 | 413 | 826 | 2 | 0 | 2.36 | -823.64
2096 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PLUG TOP (16 AMP 3 PIN) | NOS | 10 | 63.72 | 637.2 | 10 | 63.72 | 637.2 | 0 | 63.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 637.2 | 637.2
2097 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PLUG TOP (6 AMP 2 PIN) | NOS | 50 | 40.12 | 2006 | 50 | 40.12 | 2006 | 0 | 40.12 | 0 | 50 | 14.16 | 708 | 4 | 14.16 | 56.64 | 50 | 46 | 2006 | 1949.36
2098 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PVC TAPE BLACK | NOS | 21 | 41.3 | 867.3 | 20 | 41.3 | 826 | 0 | 41.3 | 0 | 20 | 41.3 | 826 | 27 | 31.93 | 862.17 | 21 | -6 | 867.3 | 5.13
2099 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PVC TAPE BLUE | NOS | 20 | 35 | 700 | 20 | 35 | 700 | 0 | 35 | 0 | 20 | 41.3 | 826 | 20 | 40.95 | 819.07 | 20 | 0 | 700 | -119.07
2100 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PVC TAPE GREEN | NOS | 20 | 41.3 | 826 | 20 | 41.3 | 826 | 0 | 41.3 | 0 | 20 | 41.3 | 826 | 20 | 41.18 | 823.61 | 20 | 0 | 826 | 2.39
2101 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PVC TAPE RED | NOS | 20 | 41.3 | 826 | 20 | 41.3 | 826 | 0 | 41.3 | 0 | 20 | 41.3 | 826 | 19 | 40.54 | 770.2 | 20 | 1 | 826 | 55.8
2102 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PVC TAPE YELLOW | NOS | 20 | 41.3 | 826 | 20 | 41.3 | 826 | 0 | 41.3 | 0 | 20 | 41.3 | 826 | 20 | 41.42 | 828.39 | 20 | 0 | 826 | -2.39
2103 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)PVC TAPE. | NOS | 46 | 1.18 | 54.28 | 45 | 1.18 | 53.1 | 0 | 1.18 | 0 | 45 | 25.57 | 1150.5 | 53 | 27.42 | 1453.32 | 46 | -7 | 54.28 | -1399.04
2104 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)RCCB 32 AMP 220 VOLT 2POL | PICS | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4
2105 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)SINGLE POLE 10 AMP MCB | NOS | 10 | 130.98 | 1309.8 | 10 | 130.98 | 1309.8 | 0 | 130.98 | 0 | 10 | 159.56 | 1595.6 | 10 | 159.51 | 1595.07 | 10 | 0 | 1309.8 | -285.27
2106 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)SINGLE POLE 20 AMP MCB | NOS | 10 | 446.04 | 4460.4 | 0 | 0 | 0 | 0 | 446.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 4460.4 | 4460.4
2107 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)SINGLE POLE 25 AMP MCB | NOS | 24 | 1.18 | 28.32 | 24 | 1.18 | 28.32 | 0 | 1.18 | 0 | 24 | 148.95 | 3574.6992 | 0 | 0 | 0 | 24 | 24 | 28.32 | 28.32
2108 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)STARTER 3 PHASE 7.5 HP | NOS | 2 | 3658 | 7316 | 2 | 3658 | 7316 | 0 | 3658 | 0 | 2 | 4269.12 | 8538.24 | 2 | 4267.7 | 8535.4 | 2 | 0 | 7316 | -1219.4
2109 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)SURFACE TYPE PVC SWITCH BOX | NOS | 45 | 300.9 | 13540.5 | 45 | 300.9 | 13540.5 | 0 | 300.9 | 0 | 45 | 159.82 | 7192.1 | 15 | 64.9 | 973.5 | 45 | 30 | 13540.5 | 12567
2110 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)TEFLON TAPE | NOS | 6 | 23.6 | 141.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 6 | 18.88 | 113.28 | 6 | 0 | 141.6 | 28.32
2111 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)TUBELIGHT | NOS | 30 | 1 | 30 | 30 | 1 | 30 | 0 | 1 | 0 | 30 | 112.1 | 3363 | 2 | 112.1 | 224.2 | 30 | 28 | 30 | -194.2
2112 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)WATERPROOF INDUSTRIAL TOP 220 V | NOS | 5 | 208.86 | 1044.3 | 5 | 208.86 | 1044.3 | 0 | 208.86 | 0 | 5 | 203.55 | 1017.76 | 0 | 0 | 0.01 | 5 | 5 | 1044.3 | 1044.29
2113 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)WATERPROOF INDUSTRIAL SOCKET 220 V | NOS | 5 | 195.88 | 979.4 | 5 | 195.88 | 979.4 | 0 | 195.88 | 0 | 5 | 224.79 | 1123.96 | 5 | 224.79 | 1123.96 | 5 | 0 | 979.4 | -144.56
2114 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)WATERPROOF INDUSTRIAL SOCKET 3 PHASE ( 5 PIN) | NOS | 5 | 508 | 2540 | 5 | 508 | 2540 | 0 | 508 | 0 | 5 | 507.99 | 2539.96 | 0 | 0 | 0 | 5 | 5 | 2540 | 2540
2115 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)WATERPROOF INDUSTRIAL TOP 3 PHASE ( 5 PIN) | NOS | 5 | 189.98 | 949.9 | 5 | 189.98 | 949.9 | 0 | 189.98 | 0 | 5 | 507.99 | 2539.96 | 0 | 0 | 0 | 5 | 5 | 949.9 | 949.9
2116 | INFRA. SITE EXP. - Electrical Work | 0 | Started | Material | (M)WATERPROOF TAPE | NOS | 5 | 342.2 | 1711 | 5 | 342.2 | 1711 | 0 | 342.2 | 0 | 5 | 389.4 | 1947 | 1 | 389.4 | 389.4 | 5 | 4 | 1711 | 1321.6
2117 | INFRA. SITE EXP. - Garden Maintenance | 10 | Started | Labour | (L)GARDEN MAINTENANCE WITHIN OUTSIDE PROJECT | Monthly | 23.5 | 15000 | 352500 | 0 | 0 | 0 | 2 | 15000 | 30000 | 12.5 | 15000 | 187500 | 12.5 | 15000 | 187500 | 21.5 | 11 | 322500 | 165000
2118 | INFRA. SITE EXP. - Garden Maintenance | 10 | Started | Material | (M)ARICA PALMS W/18" POT | NOS | 30 | 1500 | 45000 | 30 | 1500 | 45000 | 3 | 1500 | 4500 | 30 | 1500 | 45000 | 30 | 1500 | 45000 | 27 | 0 | 40500 | 0
2119 | INFRA. SITE EXP. - Garden Maintenance | 10 | Started | Material | (M)WHITE PEBBLES | NOS | 400 | 63 | 25200 | 400 | 63 | 25200 | 40 | 63 | 2520 | 400 | 50 | 20000 | 400 | 50 | 20000 | 360 | 0 | 22680 | 5200
2120 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Labour | (L)Mirror with Fixing | NOS | 340 | 300.9 | 102306 | 0 | 0 | 0 | 34 | 300.9 | 10230.6 | 340 | 300.9 | 102306 | 340 | 300.9 | 102306 | 306 | 0 | 92075.4 | 0
2121 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Labour | (L)TOP CONCRETE SLAB FOR WELL COVER | LS | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1770 | 1770
2122 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Labour | (L)WELL MATERIALS & LABOUR COST | LS | 2 | 24780 | 49560 | 0 | 0 | 0 | 0 | 24780 | 0 | 1 | 20000 | 20000 | 1 | 20000 | 20000 | 2 | 1 | 49560 | 29560
2123 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)12 MM PLY | NOS | 512 | 48 | 24576 | 0 | 0 | 0 | 51 | 48 | 2448 | 0 | 0 | 0 | 512 | 54.86 | 28087.09 | 461 | 0 | 22128 | -3511.09
2124 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)12 MM PLY 8' X 4' | NOS | 384 | 48 | 18432 | 384 | 48 | 18432 | 38 | 48 | 1824 | 384 | 78.62 | 30189.0048 | 384 | 78.24 | 30042.74 | 346 | 0 | 16608 | -11610.74
2125 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 12 | 2194.8 | 26337.6 | 0 | 0 | 0 | 1 | 2194.8 | 2194.8 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 24142.8 | 26337.6
2126 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 1 | 1750 | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0.4 | 2000 | 800 | 1 | 0.6 | 1750 | 950
2127 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 5000 | 10 | 50000 | 5000 | 10 | 50000 | 500 | 10 | 5000 | 5000 | 10.2 | 51000 | 2025 | 10.75 | 21771.77 | 4500 | 2975 | 45000 | 28228.23
2128 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)GANESH JI IDOL | NOS | 1 | 6500 | 6500 | 1 | 6500 | 6500 | 0 | 6500 | 0 | 1 | 6500 | 6500 | 1 | 6500 | 6500 | 1 | 0 | 6500 | 0
2129 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)M.C. SAND | MT | 4 | 1711.5 | 6846 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 3.56 | 1652.57 | 5883.16 | 4 | 0.44 | 6846 | 962.84
2130 | INFRA. SITE EXP. - Vastu Materials and Labour | 10 | Started | Material | (M)PPC CEMENT | BAG | 10 | 283.59 | 2835.9 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 9 | 307.57 | 2768.09 | 9 | 1 | 2552.31 | 67.81
2131 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)AMC FOR CP-18 BATCHING PLANT | JOB | 1 | 82600 | 82600 | 0 | 0 | 0 | 0 | 82600 | 0 | 1 | 82600 | 82600 | 1 | 82600 | 82600 | 1 | 0 | 82600 | 0
2132 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)AMC for Weigh Bridge | Yearly | 1 | 46020 | 46020 | 0 | 0 | 0 | 0 | 46020 | 0 | 1 | 46020 | 46020 | 0 | 0 | 0 | 1 | 1 | 46020 | 46020
2133 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Charges for Starter & Fld. Coil Heating & red oxide | NOS | 1 | 3540 | 3540 | 0 | 0 | 0 | 0 | 3540 | 0 | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 1 | 0 | 3540 | 0
2134 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)FREIGHT CHARGES | TRIP | 2 | 7080 | 14160 | 0 | 0 | 0 | 0 | 7080 | 0 | 1 | 1888 | 1888 | 1 | 1888 | 1888 | 2 | 1 | 14160 | 12272
2135 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Diode assembly Removal & fitting | NOS | 6 | 1239 | 7434 | 0 | 0 | 0 | 0 | 1239 | 0 | 6 | 1239 | 7434 | 6 | 1239 | 7434 | 6 | 0 | 7434 | 0
2136 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Dismantling & Relocation of Labor Hutment 80'X16' | PER/SQFT | 1280 | 60 | 76800 | 0 | 0 | 0 | 0 | 60 | 0 | 1280 | 60 | 76800 | 1280 | 60 | 76800 | 1280 | 0 | 76800 | 0
2137 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Dismantling & Relocation of Labour Hutment 70' X 16' | PER/SQFT | 1120 | 60 | 67200 | 0 | 0 | 0 | 0 | 60 | 0 | 1120 | 60 | 67200 | 1098 | 60 | 65880 | 1120 | 22 | 67200 | 1320
2138 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Dismantling & Relocation of Labour Hutment 75' X 20' | PER/SQFT | 1500 | 60 | 90000 | 0 | 0 | 0 | 0 | 60 | 0 | 1351 | 60 | 81060 | 1351 | 60 | 81060 | 1500 | 149 | 90000 | 8940
2139 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Dismantling of Existing Labour Hutment | NOS | 630 | 15 | 9450 | 0 | 0 | 0 | 0 | 15 | 0 | 630 | 15 | 9450 | 630 | 15 | 9450 | 630 | 0 | 9450 | 0
2140 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for installation & repair of 5HP Monoblock Pump | NOS | 1 | 5310 | 5310 | 0 | 0 | 0 | 0 | 5310 | 0 | 1 | 5310 | 5310 | 1 | 5310 | 5310 | 1 | 0 | 5310 | 0
2141 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for laying 160mm Dia DWC Pipe | RMT | 75 | 1298 | 97350 | 0 | 0 | 0 | 0 | 1298 | 0 | 58.9 | 1298 | 76452.2 | 58.9 | 1298 | 76452.2 | 75 | 16.1 | 97350 | 20897.8
2142 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for laying 200mm dia DWC Pipe | RMT | 15 | 1298 | 19470 | 0 | 0 | 0 | 0 | 1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 19470 | 19470
2143 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for laying 40mm/32mm dia UPVC pipeline | RMT | 60 | 200.6 | 12036 | 0 | 0 | 0 | 0 | 200.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 12036 | 12036
2144 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for laying 50mm Dia UPVC pipeline | RMT | 140 | 212.4 | 29736 | 0 | 0 | 0 | 0 | 212.4 | 0 | 25 | 212.4 | 5310 | 25 | 212.4 | 5310 | 140 | 115 | 29736 | 24426
2145 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for making Labour Hutment 30'X60' | SQFT | 1800 | 75 | 135000 | 0 | 0 | 0 | 0 | 75 | 0 | 1800 | 75 | 135000 | 587.4 | 75 | 44055 | 1800 | 1212.6 | 135000 | 90945
2146 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Paint work in M.E. P Hoist & Rebar Cage | LS | 1 | 47200 | 47200 | 0 | 0 | 0 | 0 | 47200 | 0 | 1 | 47200 | 47200 | 1 | 47200 | 47200 | 1 | 0 | 47200 | 0
2147 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Paver Block Laying at Customer Walkway | SQFT | 1700 | 20 | 34000 | 0 | 0 | 0 | 0 | 20 | 0 | 1303 | 20 | 26060 | 1303 | 20 | 26060 | 1700 | 397 | 34000 | 7940
2148 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Pit Connection w/100mm dia PVC pipe | RMT | 90 | 1298 | 116820 | 0 | 0 | 0 | 0 | 1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 116820 | 116820
2149 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for placing Bricks on both sides of Customers Walkway | RFT | 800 | 23.6 | 18880 | 0 | 0 | 0 | 0 | 23.6 | 0 | 782 | 20 | 15640 | 782 | 20 | 15640 | 800 | 18 | 18880 | 3240
2150 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)L/C for Str. Wall Barrication incl. metal primer (12'X70'') | PER/SQFT | 956 | 200.6 | 191773.6 | 0 | 0 | 0 | 0 | 200.6 | 0 | 956 | 200.6 | 191773.6 | 840 | 200.6 | 168504 | 956 | 116 | 191773.6 | 23269.6
2151 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Main Alternator Removal & Fitting Charges | NOS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
2152 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)MAINTENANCE & REPAIR SERVICE | JOB | 1 | 8024 | 8024 | 0 | 0 | 0 | 0 | 8024 | 0 | 1 | 8024 | 8024 | 1 | 8024 | 8024 | 1 | 0 | 8024 | 0
2153 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Repairing Charges for Porta Cabin | LS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
2154 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)S/C for 125 KVA DG (Q.No.-EEC/SQTN/051/24-25) | LS | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 1 | 0 | 4130 | 0
2155 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)S/C for repair of 125 KVA DG (Quot. -EEC/SQTN/597/24-25) | LS | 1 | 29500 | 29500 | 0 | 0 | 0 | 0 | 29500 | 0 | 1 | 29500 | 29500 | 1 | 29500 | 29500 | 1 | 0 | 29500 | 0
2156 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)S/C for repair of Charging Alternator | LS | 1 | 3776 | 3776 | 0 | 0 | 0 | 0 | 3776 | 0 | 1 | 3776 | 3776 | 1 | 3776 | 3776 | 1 | 0 | 3776 | 0
2157 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)S/C for repair of Starting Prob. in Conc. Pump & Ch. Alt. | NOS | 2 | 1770 | 3540 | 0 | 0 | 0 | 0 | 1770 | 0 | 2 | 1770 | 3540 | 2 | 1770 | 3540 | 2 | 0 | 3540 | 0
2158 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Service Charges( 01 Main Alternator & Main Coil Rewinding) | NOS | 1 | 49560 | 49560 | 0 | 0 | 0 | 0 | 49560 | 0 | 1 | 49560 | 49560 | 1 | 49560 | 49560 | 1 | 0 | 49560 | 0
2159 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Service Charges( 01 Main Alternator Excitor Rotter) | NOS | 1 | 25960 | 25960 | 0 | 0 | 0 | 0 | 25960 | 0 | 1 | 25960 | 25960 | 1 | 25960 | 25960 | 1 | 0 | 25960 | 0
2160 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Supply of Plumber on Daily Basis | NOS | 60 | 826 | 49560 | 0 | 0 | 0 | 0 | 826 | 0 | 60 | 826 | 49560 | 11 | 826 | 9086 | 60 | 49 | 49560 | 40474
2161 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Supply of Plumbing Helper on Daily Basis | NOS | 60 | 590 | 35400 | 0 | 0 | 0 | 0 | 590 | 0 | 60 | 590 | 35400 | 5 | 590 | 2950 | 60 | 55 | 35400 | 32450
2162 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)SUPPLY OF SKILLED MASON-11 HRS | MAN/DAY | 90 | 802.4 | 72216 | 0 | 0 | 0 | 0 | 802.4 | 0 | 3 | 750 | 2250 | 3 | 750 | 2250 | 90 | 87 | 72216 | 69966
2163 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 2760 | 535 | 1476600 | 0 | 0 | 0 | 0 | 535 | 0 | 1729.66 | 544.91 | 942513.1 | 1729.66 | 544.91 | 942513.1 | 2760 | 1030.34 | 1476600 | 534086.9
2164 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)Supplying, making & Fixing of 2-Tier Labour Hutment | NOS | 800 | 123.9 | 99120 | 0 | 0 | 0 | 0 | 123.9 | 0 | 800 | 105 | 84000 | 800 | 105 | 84000 | 800 | 0 | 99120 | 15120
2165 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Labour | (L)To & Fro Trip Charges | NOS | 2 | 3540 | 7080 | 0 | 0 | 0 | 0 | 3540 | 0 | 2 | 3540 | 7080 | 2 | 3540 | 7080 | 2 | 0 | 7080 | 0
2166 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)1" X 3/4" REDUCER (UPVC) | NOS | 4 | 23.6 | 94.4 | 4 | 23.6 | 94.4 | 0 | 23.6 | 0 | 4 | 18.48 | 73.92 | 0 | 0 | 0 | 4 | 4 | 94.4 | 94.4
2167 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)10 MM DRILL BIT | NOS | 5 | 129.8 | 649 | 5 | 129.8 | 649 | 0 | 129.8 | 0 | 5 | 135.7 | 678.5 | 0 | 0 | 0 | 5 | 5 | 649 | 649
2168 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)10 MM STONE CHIPS. | MT | 5.729 | 1770 | 10140.33 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 18.188 | 1452.7 | 26421.64 | 5.729 | -12.459 | 10140.33 | -16281.31
2169 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)100 NB RUBBER HOSE | NOS | 1 | 21830 | 21830 | 1 | 21830 | 21830 | 0 | 21830 | 0 | 1 | 18880 | 18880 | 0 | 0 | 0 | 1 | 1 | 21830 | 21830
2170 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)12 MM DRILL BIT | NOS | 3 | 140.42 | 421.26 | 3 | 140.42 | 421.26 | 0 | 140.42 | 0 | 3 | 147.5 | 442.5 | 0 | 0 | 0 | 3 | 3 | 421.26 | 421.26
2171 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)12" CHANNEL LOCK PLIER | NOS | 1 | 519.2 | 519.2 | 1 | 519.2 | 519.2 | 0 | 519.2 | 0 | 1 | 522.74 | 522.74 | 1 | 522.74 | 522.74 | 1 | 0 | 519.2 | -3.54
2172 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)150 NB RUBBER HOSE | NOS | 1 | 42126 | 42126 | 1 | 42126 | 42126 | 0 | 42126 | 0 | 1 | 31860 | 31860 | 0 | 0 | 0 | 1 | 1 | 42126 | 42126
2173 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2" ELBOW (UPVC) | NOS | 17 | 82.6 | 1404.2 | 17 | 82.6 | 1404.2 | 0 | 82.6 | 0 | 17 | 66.8 | 1135.5898 | 17 | 66.59 | 1132.07 | 17 | 0 | 1404.2 | 272.13
2174 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2" END CAP (UPVC) | NOS | 2 | 35.4 | 70.8 | 2 | 35.4 | 70.8 | 0 | 35.4 | 0 | 2 | 30.92 | 61.84 | 2 | 30.92 | 61.84 | 2 | 0 | 70.8 | 8.96
2175 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2" G.I SADDLE CLAMP | NOS | 30 | 23.6 | 708 | 30 | 23.6 | 708 | 0 | 23.6 | 0 | 30 | 35.4 | 1062 | 0 | 0 | 0 | 30 | 30 | 708 | 708
2176 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2" MTA (BRASS) UPVC | NOS | 6 | 495.6 | 2973.6 | 0 | 0 | 0 | 0 | 495.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 2973.6 | 2973.6
2177 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2" UPVC MTA (METAL) | NOS | 6 | 519.2 | 3115.2 | 6 | 519.2 | 3115.2 | 0 | 519.2 | 0 | 6 | 523.35 | 3140.1198 | 5 | 523.35 | 2616.77 | 6 | 1 | 3115.2 | 498.43
2178 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2" UPVC TEE | NOS | 4 | 94.4 | 377.6 | 4 | 94.4 | 377.6 | 0 | 94.4 | 0 | 4 | 97.71 | 390.82 | 0 | 0 | 0 | 4 | 4 | 377.6 | 377.6
2179 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)20 MM CHINA CLIP | PKT | 11 | 118 | 1298 | 11 | 118 | 1298 | 0 | 118 | 0 | 11 | 46.45 | 510.94 | 11 | 46.96 | 516.51 | 11 | 0 | 1298 | 781.49
2180 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)20 MM PVC PIPE | NOS | 15 | 76.7 | 1150.5 | 15 | 76.7 | 1150.5 | 0 | 76.7 | 0 | 15 | 74.34 | 1115.1 | 15 | 75.57 | 1133.52 | 15 | 0 | 1150.5 | 16.98
2181 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)20 MM UPVC PIPE (SCHEDULE 40) | MTR | 18 | 165.2 | 2973.6 | 10 | 165.2 | 1652 | 0 | 165.2 | 0 | 10 | 167.3 | 1673 | 10 | 167.3 | 1673 | 18 | 8 | 2973.6 | 1300.6
2182 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)200 AMP 3 POLE MCCB | NOS | 1 | 9515.52 | 9515.52 | 1 | 9515.52 | 9515.52 | 0 | 9515.52 | 0 | 1 | 10105.52 | 10105.52 | 1 | 10015.08 | 10015.08 | 1 | 0 | 9515.52 | -499.56
2183 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)200 MM DIA DWC PIPE (6 MTR LENGTH) | NOS | 11 | 2678.6 | 29464.6 | 11 | 2678.6 | 29464.6 | 0 | 2678.6 | 0 | 11 | 2826.42 | 31090.62 | 10 | 2803.36 | 28033.62 | 11 | 1 | 29464.6 | 1430.98
2184 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)25 MM FLEXIBLE PIPE | MTR | 140 | 430.7 | 60298 | 0 | 0 | 0 | 0 | 430.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 60298 | 60298
2185 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)25 MM FLEXIBLE PIPE. | ROLL | 1 | 507.4 | 507.4 | 1 | 507.4 | 507.4 | 0 | 507.4 | 0 | 1 | 507.4 | 507.4 | 1 | 507.4 | 507.4 | 1 | 0 | 507.4 | 0
2186 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)25 MM PVC PIPE | NOS | 30 | 82.6 | 2478 | 20 | 82.6 | 1652 | 0 | 82.6 | 0 | 20 | 85.1 | 1702 | 20 | 82.82 | 1656.3 | 30 | 10 | 2478 | 821.7
2187 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)25MM HOOK CHINA CLIP | PKT | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 540.34 | 540.34 | 1 | 525.81 | 525.81 | 1 | 0 | 1 | -524.81
2188 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)2ND CLASS BRICKS | NOS | 650 | 10 | 6500 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 650 | 9.75 | 6334.77 | 650 | 0 | 6500 | 165.23
2189 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)3" SUCTION PIPE | FT | 120 | 283.2 | 33984 | 120 | 283.2 | 33984 | 0 | 283.2 | 0 | 120 | 82.6 | 9912 | 120 | 82.6 | 9912 | 120 | 0 | 33984 | 24072
2190 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)3+1 CCTV CABLE | MTR | 180 | 14.4 | 2592 | 180 | 14.4 | 2592 | 0 | 14.4 | 0 | 180 | 14.42 | 2595.528 | 180 | 14.42 | 2595.53 | 180 | 0 | 2592 | -3.53
2191 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)3/4" UPVC BALL VALVE | NOS | 17 | 212.4 | 3610.8 | 17 | 212.4 | 3610.8 | 0 | 212.4 | 0 | 17 | 115.12 | 1957.0604 | 7 | 115.12 | 805.85 | 17 | 10 | 3610.8 | 2804.95
2192 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)3/4" UPVC ELBOW | NOS | 15 | 23.6 | 354 | 15 | 23.6 | 354 | 0 | 23.6 | 0 | 15 | 15.28 | 229.2105 | 15 | 15.28 | 229.21 | 15 | 0 | 354 | 124.79
2193 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)3/4" UPVC SOCKET | NOS | 8 | 12.98 | 103.84 | 8 | 12.98 | 103.84 | 0 | 12.98 | 0 | 8 | 9.95 | 79.58 | 2 | 9.95 | 19.9 | 8 | 6 | 103.84 | 83.94
2194 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)3/4" UPVC TEE | NOS | 8 | 22.42 | 179.36 | 8 | 22.42 | 179.36 | 0 | 22.42 | 0 | 8 | 18.48 | 147.84 | 2 | 18.48 | 36.96 | 8 | 6 | 179.36 | 142.4
2195 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)40 MM VIBRATOR NOZZLE | NOS | 2 | 2867.4 | 5734.8 | 0 | 0 | 0 | 0 | 2867.4 | 0 | 0 | 0 | 0 | 2 | 3420.63 | 6841.26 | 2 | 0 | 5734.8 | -1106.46
2196 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)50 MM UPVC PIPE SCH-80 (3 mtr length) | NOS | 18 | 696.2 | 12531.6 | 18 | 696.2 | 12531.6 | 0 | 696.2 | 0 | 18 | 700.92 | 12616.56 | 18 | 700.92 | 12616.56 | 18 | 0 | 12531.6 | -84.96
2197 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)50 MM UPVC UNION SCH-80 | NOS | 4 | 141.6 | 566.4 | 4 | 141.6 | 566.4 | 0 | 141.6 | 0 | 4 | 146.03 | 584.1 | 4 | 146.03 | 584.1 | 4 | 0 | 566.4 | -17.7
2198 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)50 MM X 20 MM TEE UPVC | NOS | 13 | 94.4 | 1227.2 | 13 | 94.4 | 1227.2 | 0 | 94.4 | 0 | 13 | 90.6 | 1177.8 | 7 | 90.6 | 634.2 | 13 | 6 | 1227.2 | 593
2199 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)6/6 PVC BOX | NOS | 1 | 295 | 295 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 295 | 295
2200 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)75 mm X 10 MM bullet fastener | NOS | 30 | 23.6 | 708 | 30 | 23.6 | 708 | 0 | 23.6 | 0 | 30 | 22.42 | 672.6 | 0 | 0 | 0 | 30 | 30 | 708 | 708
2201 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)ABC Powder Type Stored Pressure Fire Extinguisher of 6Kg | NOS | 4 | 2773 | 11092 | 0 | 0 | 0 | 0 | 2773 | 0 | 0 | 0 | 0 | 4 | 2837.61 | 11350.44 | 4 | 0 | 11092 | -258.44
2202 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)ANCHOR SAFETY BOLT HST M20 X 184/30 | NOS | 10 | 885 | 8850 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 10 | 737.95 | 7379.48 | 10 | 0 | 8850 | 1470.52
2203 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)ANCHORING FASTNER M12(R &P) | NOS | 96 | 507.4 | 48710.4 | 0 | 0 | 0 | 0 | 507.4 | 0 | 0 | 0 | 0 | 96 | 418.17 | 40144.39 | 96 | 0 | 48710.4 | 8566.01
2204 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)BENCH VICE | NOS | 1 | 2643.2 | 2643.2 | 1 | 2643.2 | 2643.2 | 0 | 2643.2 | 0 | 1 | 2643.2 | 2643.2 | 1 | 2643.2 | 2643.2 | 1 | 0 | 2643.2 | 0
2205 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)BOLT (1037202) | NOS | 1 | 23.6 | 23.6 | 1 | 23.6 | 23.6 | 0 | 23.6 | 0 | 1 | 19.6 | 19.6 | 1 | 19.6 | 19.6 | 1 | 0 | 23.6 | 4
2206 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)BOLT FOR GUIDE PLATE (PART NO 1035101) | NOS | 4 | 17.7 | 70.8 | 4 | 17.7 | 70.8 | 0 | 17.7 | 0 | 4 | 14.16 | 56.64 | 4 | 14.16 | 56.64 | 4 | 0 | 70.8 | 14.16
2207 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)BRAKE LINERS 31 T | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19186.66 | 38373.32 | 2 | 0 | 0 | -38373.32
2208 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)BREAK LINEAR 5.19 KW | NOS | 2 | 24780 | 49560 | 2 | 24780 | 49560 | 0 | 24780 | 0 | 2 | 20815.2 | 41630.4 | 2 | 20662.56 | 41325.11 | 2 | 0 | 49560 | 8234.89
2209 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CABLE LAYING | MTR | 140 | 11.8 | 1652 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 1652 | 1652
2210 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CAT 6 CABLE | MTR | 210 | 35.4 | 7434 | 210 | 35.4 | 7434 | 0 | 35.4 | 0 | 210 | 30.92 | 6493.9 | 70 | 32.86 | 2300.41 | 210 | 140 | 7434 | 5133.59
2211 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 1.527 | 8200.01 | 12521.42 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 4.185 | 7669.26 | 32095.86 | 1.527 | -2.658 | 12521.415 | -19574.4447
2212 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CHISEL | NOS | 2 | 354 | 708 | 2 | 354 | 708 | 0 | 354 | 0 | 2 | 348.1 | 696.2 | 0 | 0 | 0 | 2 | 2 | 708 | 708
2213 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CO2 Type Fire Extinguisher of 4.5Kg capacity | NOS | 2 | 7316 | 14632 | 0 | 0 | 0 | 0 | 7316 | 0 | 0 | 0 | 0 | 2 | 7486.47 | 14972.93 | 2 | 0 | 14632 | -340.93
2214 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)COLOURED CORRUGATED SHEET (10' FOOT LONG) | NOS | 10 | 2832 | 28320 | 0 | 0 | 0 | 0 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 28320 | 28320
2215 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CONECTION TUBE DN-125 | PICS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8300.86 | 16601.72 | 2 | 0 | 0 | -16601.72
2216 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)CORRUGATED SHEET | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 0 | 1.18 | 0 | 10 | 1510.4 | 15104 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
2217 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)COUPLING NIB (PART NO 1021204) | NOS | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 0 | 2065 | 0 | 1 | 1652 | 1652 | 1 | 1652 | 1652 | 1 | 0 | 2065 | 413
2218 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Coupling Nib Guide Plate (part no - 1014133) | NOS | 1 | 1917.5 | 1917.5 | 1 | 1917.5 | 1917.5 | 0 | 1917.5 | 0 | 1 | 1534 | 1534 | 1 | 1534 | 1534 | 1 | 0 | 1917.5 | 383.5
2219 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)COUPLING NIB RET. SPRING (1044101) | NOS | 2 | 194.7 | 389.4 | 2 | 194.7 | 389.4 | 0 | 194.7 | 0 | 2 | 161.74 | 323.48 | 2 | 161.74 | 323.47 | 2 | 0 | 389.4 | 65.93
2220 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Coupling Nib Trust Spring(PART NO - 1044101) | NOS | 2 | 194.7 | 389.4 | 2 | 194.7 | 389.4 | 0 | 194.7 | 0 | 2 | 155.76 | 311.52 | 2 | 155.76 | 311.52 | 2 | 0 | 389.4 | 77.88
2221 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)D-LINK CAT 6 I/O | NOS | 1 | 186.44 | 186.44 | 1 | 186.44 | 186.44 | 0 | 186.44 | 0 | 1 | 213.43 | 213.43 | 1 | 207.69 | 207.69 | 1 | 0 | 186.44 | -21.25
2222 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)DELTA HMI (MODEL NO - TP02) | NOS | 1 | 77880 | 77880 | 0 | 0 | 0 | 0 | 77880 | 0 | 0 | 0 | 0 | 1 | 64939.46 | 64939.46 | 1 | 0 | 77880 | 12940.54
2223 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)ELEMENT - NC MAKE TEKNIC 240 V - 3A | NOS | 1 | 495.6 | 495.6 | 0 | 0 | 0 | 0 | 495.6 | 0 | 0 | 0 | 0 | 3 | 413.25 | 1239.75 | 1 | -2 | 495.6 | -744.15
2224 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)ELEMENT - NO MAKE TEKNIC 240 V -3A | NOS | 1 | 495.6 | 495.6 | 0 | 0 | 0 | 0 | 495.6 | 0 | 0 | 0 | 0 | 3 | 413.25 | 1239.75 | 1 | -2 | 495.6 | -744.15
2225 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)END HOSE DN125 - 4 M | NOS | 1 | 49571.75 | 49571.75 | 1 | 49571.75 | 49571.75 | 0 | 49571.75 | 0 | 1 | 47296.65 | 47296.65 | 0 | 0 | 0 | 1 | 1 | 49571.75 | 49571.75
2226 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Expandable Road Barrier on Wheel | NOS | 1 | 10030 | 10030 | 0 | 0 | 0 | 0 | 10030 | 0 | 0 | 0 | 0 | 3 | 10295.8 | 30887.39 | 1 | -2 | 10030 | -20857.39
2227 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)EXTERIOR WATER BASE PRIMER | NOS | 20 | 224.2 | 4484 | 20 | 224.2 | 4484 | 0 | 224.2 | 0 | 20 | 250 | 5000.008 | 20 | 250 | 5000.01 | 20 | 0 | 4484 | -516.01
2228 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Fire Extinguisher | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2006 | 2006 | 1 | 0 | 0 | -2006
2229 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)FLY ASH | MT | 0.594 | 1396.5 | 829.52 | 0 | 0 | 0 | 0 | 1396.5 | 0 | 0 | 0 | 0 | 1.788 | 1396.5 | 2496.94 | 0.594 | -1.194 | 829.521 | -1667.419
2230 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Gear Oil - 90 Grade | LTR | 10 | 153.4 | 1534 | 10 | 153.4 | 1534 | 0 | 153.4 | 0 | 10 | 246.62 | 2466.2 | 10 | 246.62 | 2466.2 | 10 | 0 | 1534 | -932.2
2231 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)GEAR OIL 15W-40 | NOS | 20 | 224.2 | 4484 | 20 | 224.2 | 4484 | 0 | 224.2 | 0 | 20 | 221.84 | 4436.8 | 20 | 221.84 | 4436.8 | 20 | 0 | 4484 | 47.2
2232 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Gear Oil VG 220 | LTR | 90 | 261.96 | 23576.4 | 20 | 261.96 | 5239.2 | 0 | 261.96 | 0 | 20 | 233.64 | 4672.8 | 20 | 233.64 | 4672.8 | 90 | 70 | 23576.4 | 18903.6
2233 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)GI RACK | NOS | 1 | 7080 | 7080 | 0 | 0 | 0 | 0 | 7080 | 0 | 0 | 0 | 0 | 12 | 7146.55 | 85758.62 | 1 | -11 | 7080 | -78678.62
2234 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)HAMMER (1 KG) | NOS | 1 | 247.8 | 247.8 | 1 | 247.8 | 247.8 | 0 | 247.8 | 0 | 1 | 241.9 | 241.9 | 0 | 0 | 0 | 1 | 1 | 247.8 | 247.8
2235 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)HAND LEVER RETURN SPRING (PART NO. 1044103) | NOS | 2 | 200.6 | 401.2 | 2 | 200.6 | 401.2 | 0 | 200.6 | 0 | 2 | 161.74 | 323.48 | 2 | 161.74 | 323.47 | 2 | 0 | 401.2 | 77.73
2236 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)HIGH RANGE VIDEO BALOON CONNECTOR | NOS | 1 | 224.2 | 224.2 | 1 | 224.2 | 224.2 | 0 | 224.2 | 0 | 1 | 224.2 | 224.2 | 1 | 224.2 | 224.2 | 1 | 0 | 224.2 | 0
2237 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)HYDRAULIC OIL 68 GRADE | LTR | 20 | 141.6 | 2832 | 20 | 141.6 | 2832 | 0 | 141.6 | 0 | 20 | 139.24 | 2784.8 | 20 | 139.24 | 2784.8 | 20 | 0 | 2832 | 47.2
2238 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)I CONNECTORS | NOS | 3 | 236 | 708 | 3 | 236 | 708 | 0 | 236 | 0 | 3 | 270.17 | 810.51 | 3 | 262.9 | 788.71 | 3 | 0 | 708 | -80.71
2239 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Limit Switch | NOS | 3 | 5425.64 | 16276.92 | 3 | 5425.64 | 16276.92 | 0 | 5425.64 | 0 | 3 | 3850.68 | 11552.04 | 2 | 3063.2 | 6126.39 | 3 | 1 | 16276.92 | 10150.53
2240 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)M.C SAND | CFT | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0.48 | 0 | 0
2241 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)M.C. SAND | MT | 24 | 1711.5 | 41076 | 24 | 1711.5 | 41076 | 0 | 1711.5 | 0 | 24 | 1890 | 45360 | 14.273 | 1822.57 | 26013.48 | 24 | 9.727 | 41076 | 15062.52
2242 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)MASKING TAPE | PICS | 60 | 47.2 | 2832 | 60 | 47.2 | 2832 | 0 | 47.2 | 0 | 60 | 80 | 4799.994 | 2 | 80 | 160 | 60 | 58 | 2832 | 2672
2243 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)New Handle Bolt with washer(PART NO - 1014411) | NOS | 1 | 206.5 | 206.5 | 1 | 206.5 | 206.5 | 0 | 206.5 | 0 | 1 | 165.2 | 165.2 | 1 | 165.2 | 165.2 | 1 | 0 | 206.5 | 41.3
2244 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)NOSE PLIER | NOS | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 0 | 283.2 | 0 | 1 | 277.3 | 277.3 | 1 | 277.3 | 277.3 | 1 | 0 | 283.2 | 5.9
2245 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)NUT , BOLT, & WASHER | SET | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 5.31 | 106.2 | 1 | -19 | 0 | -106.2
2246 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)PLIER | NOS | 1 | 318.6 | 318.6 | 1 | 318.6 | 318.6 | 0 | 318.6 | 0 | 1 | 318.6 | 318.6 | 1 | 318.6 | 318.6 | 1 | 0 | 318.6 | 0
2247 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)POLYTHENE SHEET | KG | 30 | 110 | 3300 | 30 | 110 | 3300 | 0 | 110 | 0 | 30 | 141.6 | 4248 | 113.85 | 141.6 | 16121.16 | 30 | -83.85 | 3300 | -12821.16
2248 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Polythene Sheets | KG | 40 | 82.6 | 3304 | 40 | 82.6 | 3304 | 0 | 82.6 | 0 | 40 | 141.6 | 5664 | 80 | 141.6 | 11328 | 40 | -40 | 3304 | -8024
2249 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)POWER SPIKE BUSTER | NOS | 1 | 560.5 | 560.5 | 1 | 560.5 | 560.5 | 0 | 560.5 | 0 | 1 | 560.5 | 560.5 | 1 | 560.5 | 560.5 | 1 | 0 | 560.5 | 0
2250 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)PPC CEMENT | BAG | 2 | 283.59 | 567.18 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 2 | 298.9 | 597.8 | 2 | 0 | 567.18 | -30.62
2251 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)PVC BOX 4 X 4 | NOS | 3 | 47.2 | 141.6 | 3 | 47.2 | 141.6 | 0 | 47.2 | 0 | 3 | 54.03 | 162.09 | 3 | 52.58 | 157.74 | 3 | 0 | 141.6 | -16.14
2252 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)PVC- TAPE | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2253 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)RCPC GRATINGS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1731.96 | 43298.92 | 1 | -24 | 0 | -43298.92
2254 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)RJ 45 CONNECTOR | NOS | 1 | 11.8 | 11.8 | 1 | 11.8 | 11.8 | 0 | 11.8 | 0 | 1 | 11.8 | 11.8 | 1 | 11.8 | 11.8 | 1 | 0 | 11.8 | 0
2255 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)RUBBISH | CFT | 35534.01 | 29.5 | 1048253.3 | 35534.01 | 29.5 | 1048253.3 | 0 | 29.5 | 0 | 35534.01 | 24 | 852816.24 | 32309.44 | 24 | 775426.56 | 35534.01 | 3224.57 | 1048253.295 | 272826.735
2256 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SCREW DRIVER (BIG) | NOS | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 0 | 283.2 | 0 | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 1 | 0 | 283.2 | 0
2257 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SCREW DRIVER SET | SET | 1 | 224.2 | 224.2 | 1 | 224.2 | 224.2 | 0 | 224.2 | 0 | 1 | 224.2 | 224.2 | 1 | 224.2 | 224.2 | 1 | 0 | 224.2 | 0
2258 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SERVICE CHARGES | NOS | 4 | 1817.2 | 7268.8 | 4 | 1817.2 | 7268.8 | 0 | 1817.2 | 0 | 4 | 2088.35 | 8353.4 | 1 | 5258.08 | 5258.08 | 4 | 3 | 7268.8 | 2010.72
2259 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SERVO LITHIUM BASE SERVO GREASE | KG | 20 | 1 | 20 | 20 | 1 | 20 | 0 | 1 | 0 | 20 | 416.54 | 8330.8 | 20 | 416.54 | 8330.8 | 20 | 0 | 20 | -8310.8
2260 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Shearing Blade | NOS | 2 | 2301 | 4602 | 2 | 2301 | 4602 | 0 | 2301 | 0 | 2 | 1911.44 | 3822.88 | 2 | 1911.44 | 3822.87 | 2 | 0 | 4602 | 779.13
2261 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SIKA HIBOND | PKT | 6 | 507.4 | 3044.4 | 6 | 507.4 | 3044.4 | 0 | 507.4 | 0 | 6 | 570.33 | 3421.98 | 18 | 522.43 | 9403.76 | 6 | -12 | 3044.4 | -6359.36
2262 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SIKA LATEX POWER | KG | 30 | 212.4 | 6372 | 30 | 212.4 | 6372 | 0 | 212.4 | 0 | 30 | 228.13 | 6844 | 20 | 225.42 | 4508.37 | 30 | 10 | 6372 | 1863.63
2263 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Sika Viscocrete 4021 NS | KG | 9 | 120.36 | 1083.24 | 0 | 0 | 0 | 0 | 120.36 | 0 | 0 | 0 | 0 | 27 | 112.03 | 3024.92 | 9 | -18 | 1083.24 | -1941.68
2264 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)Small Relay with Base | NOS | 1 | 1770 | 1770 | 1 | 1770 | 1770 | 0 | 1770 | 0 | 1 | 1470.34 | 1470.34 | 1 | 1470.33 | 1470.33 | 1 | 0 | 1770 | 299.67
2265 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)SPARE PARTS OF 125 KVA DG (Q.NO.-EEC/QTN/596/24-25) | LS | 1 | 24201.8 | 24201.8 | 1 | 24201.8 | 24201.8 | 0 | 24201.8 | 0 | 1 | 24202.01 | 24202.01 | 1 | 24202.01 | 24202.01 | 1 | 0 | 24201.8 | -0.21
2266 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)TARPAULIN (BIG SIZE) | NOS | 1 | 5699.4 | 5699.4 | 0 | 0 | 0 | 0 | 5699.4 | 0 | 0 | 0 | 0 | 12 | 7374.31 | 88491.69 | 1 | -11 | 5699.4 | -82792.29
2267 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)TWO WAY SPRING SL SWITCH (7047102) | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 686.16 | 686.16 | 1 | 686.16 | 686.16 | 1 | 0 | 826 | 139.84
2268 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)UPVC SOLVENT | NOS | 4 | 384 | 1536 | 4 | 384 | 1536 | 0 | 384 | 0 | 4 | 453.12 | 1812.48 | 4 | 453.12 | 1812.48 | 4 | 0 | 1536 | -276.48
2269 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)UPVC 50 MM PIPE 3 MTR LONG | NOS | 6 | 779 | 4674 | 6 | 779 | 4674 | 0 | 779 | 0 | 6 | 507.31 | 3043.8402 | 6 | 507.31 | 3043.84 | 6 | 0 | 4674 | 1630.16
2270 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)VERTICAL CUP-LOCK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1018.87 | 12226.44 | 1 | -11 | 0 | -12226.44
2271 | INFRA. SITE EXP. - Maintenance and Repair Service | 0 | Started | Material | (M)WEATHER GUARD EXTERIOR PAINT (NATURAL WHITE) | NOS | 30 | 389.4 | 11682 | 30 | 389.4 | 11682 | 0 | 389.4 | 0 | 30 | 500 | 15000.003 | 30 | 500 | 15000 | 30 | 0 | 11682 | -3318
2272 | INFRA. SITE EXP. - Tiles Fixing and Marble Temple | 10 | Started | Labour | (L)3' 0" MARBLE TEMPLE | NOS | 1 | 24500 | 24500 | 0 | 0 | 0 | 0 | 24500 | 0 | 1 | 24500 | 24500 | 1 | 24500 | 24500 | 1 | 0 | 24500 | 0
2273 | INFRA. SITE EXP. - Tiles Fixing and Marble Temple | 10 | Started | Labour | (L)LABOUR CHARGS OF TILES FIXING AT TEMPLE BASE & SIDE | LS | 1 | 2360 | 2360 | 0 | 0 | 0 | 0 | 2360 | 0 | 1 | 2000 | 2000 | 1 | 2000 | 2000 | 1 | 0 | 2360 | 360
2274 | INFRA. SITE EXP. - Tiles Fixing and Marble Temple | 10 | Started | Labour | (L)TEMPLE TRANSPORT CHARGE | LS | 1 | 1298 | 1298 | 0 | 0 | 0 | 0 | 1298 | 0 | 1 | 1100 | 1100 | 1 | 1100 | 1100 | 1 | 0 | 1298 | 198
2275 | INFRA. SITE EXP. - Round Table | 10 | Started | Material | (M)10MM ROUND GLASS TOP | NOS | 1 | 9440 | 9440 | 1 | 9440 | 9440 | 0 | 9440 | 0 | 1 | 9440 | 9440 | 0 | 0 | 0 | 1 | 1 | 9440 | 9440
2276 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 0.344 | 1770 | 608.88 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0.688 | 1574.62 | 1083.34 | 0.344 | -0.344 | 608.88 | -474.46
2277 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 256 | 10 | 2560 | 0 | 0 | 0 | 26 | 10 | 260 | 0 | 0 | 0 | 256 | 9.75 | 2494.92 | 230 | 0 | 2300 | 65.08
2278 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)3/4" BALL VALVE | NOS | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 1 | 122.12 | 122.12 | 1 | 120.88 | 120.88 | 1 | 0 | 118 | -2.88
2279 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)3/4" UPVC PLAIN ELBOW | NOS | 1 | 23.6 | 23.6 | 1 | 23.6 | 23.6 | 0 | 23.6 | 0 | 1 | 16.19 | 16.19 | 1 | 16.03 | 16.03 | 1 | 0 | 23.6 | 7.57
2280 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)M.C. SAND | MT | 1.8 | 1711.5 | 3080.7 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 1.88 | 1668.11 | 3136.05 | 1.8 | -0.08 | 3080.7 | -55.35
2281 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 5 | 283.59 | 1417.95 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 6 | 307.75 | 1846.51 | 4 | -1 | 1134.36 | -428.56
2282 | INFRA. SITE EXP. - Vat Work | 10 | Started | Material | (M)SOLVENT CEMENT.(UPVC) | NOS | 2 | 236 | 472 | 2 | 236 | 472 | 0 | 236 | 0 | 2 | 253.06 | 506.12 | 2 | 250.5 | 501 | 2 | 0 | 472 | -29
2283 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)10 MM DIA TMT STAIGHTENING, CUTTING, BENDING, BINDING | MT | 1.22 | 8250 | 10065 | 0 | 0 | 0 | 0 | 8250 | 0 | 1.214 | 5250 | 6373.5 | 1.214 | 5250 | 6373.5 | 1.22 | 0.006 | 10065 | 3691.5
2284 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)12 MM DIA TMT STAIGHTING, CUTTING, BENDING & BINDING | MT | 0.9 | 9735 | 8761.5 | 0 | 0 | 0 | 0 | 9735 | 0 | 0.877 | 5250 | 4604.25 | 0.877 | 5250 | 4604.25 | 0.9 | 0.023 | 8761.5 | 4157.25
2285 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)16 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.971 | 5250 | 5097.75 | 0.971 | 5250 | 5097.75 | 1 | 0.029 | 8250 | 3152.25
2286 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)20 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 0.7 | 8250 | 5775 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.676 | 5250 | 3549 | 0.676 | 5250 | 3549 | 0.7 | 0.024 | 5775 | 2226
2287 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)250/230/200 MM BRICK WORK | CUM | 10 | 700 | 7000 | 0 | 0 | 0 | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 6300 | 7000
2288 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)375 MM / 250 MM / 200 MM TH. BRICK WORK | CUM | 10 | 700 | 7000 | 0 | 0 | 0 | 1 | 700 | 700 | 7.98 | 700 | 5586 | 7.98 | 700 | 5586 | 9 | 2.02 | 6300 | 1414
2289 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)8 MM DIA TMT CUTTING, BENDING, BINDING | MT | 0.7 | 8250 | 5775 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.694 | 5250 | 3643.5 | 0.694 | 5250 | 3643.5 | 0.7 | 0.006 | 5775 | 2131.5
2290 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 420 | 141.6 | 59472 | 0 | 0 | 0 | 42 | 141.6 | 5947.2 | 412.09 | 125 | 51511.25 | 412.09 | 125 | 51511.25 | 378 | 7.91 | 53524.8 | 7960.75
2291 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 235 | 82.6 | 19411 | 0 | 0 | 0 | 24 | 82.6 | 1982.4 | 226.16 | 75 | 16962 | 226.16 | 75 | 16962 | 211 | 8.84 | 17428.6 | 2449
2292 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 122 | 50 | 6100 | 0 | 0 | 0 | 12 | 50 | 600 | 120.42 | 55 | 6623.1 | 120.42 | 55 | 6623.1 | 110 | 1.58 | 5500 | -523.1
2293 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)DEWATERING | HP-HR | 300 | 10 | 3000 | 0 | 0 | 0 | 30 | 10 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 300 | 2700 | 3000
2294 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)DISPOSAL OF EARTH WITHIN PROJECT SITE, MORE THAN 50'0" LEAD | CUM | 70 | 90 | 6300 | 0 | 0 | 0 | 7 | 90 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 70 | 5670 | 6300
2295 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)EARTH WORK IN EXCAVATION MANUALLY UP TO 3.0 MTR. | CUM | 70 | 150 | 10500 | 0 | 0 | 0 | 7 | 150 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 70 | 9450 | 10500
2296 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MANUAL SHIFTING OF BRICKS | NOS | 7600 | 1.18 | 8968 | 0 | 0 | 0 | 760 | 1.18 | 896.8 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 7600 | 8071.2 | 8968
2297 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MANUAL SHIFTING OF SAND IN BAGS | NOS | 3500 | 2.5 | 8750 | 0 | 0 | 0 | 350 | 2.5 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3500 | 7875 | 8750
2298 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MANUAL SHIFTING OF STONECHIP IN BAGS | NOS | 7000 | 2.5 | 17500 | 0 | 0 | 0 | 700 | 2.5 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 7000 | 15750 | 17500
2299 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MECH. EXCAVATION (EGL-FDN. BOTT.)& STACKING IN SITE | CUM | 460 | 188.8 | 86848 | 0 | 0 | 0 | 46 | 188.8 | 8684.8 | 458.39 | 188.8 | 86544.04 | 458.39 | 188.8 | 86544.04 | 414 | 1.61 | 78163.2 | 303.96
2300 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 52 | 885 | 46020 | 0 | 0 | 0 | 5 | 885 | 4425 | 51.9 | 750 | 38925 | 51.9 | 750 | 38925 | 47 | 0.1 | 41595 | 7095
2301 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 10 | 700 | 7000 | 0 | 0 | 0 | 1 | 700 | 700 | 9.74 | 750 | 7305 | 9.74 | 750 | 7305 | 9 | 0.26 | 6300 | -305
2302 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)MIXING & POURING OF RCC M- 25 FOR WALL CASTING | CUM | 3.5 | 1062 | 3717 | 0 | 0 | 0 | 0 | 1062 | 0 | 3.36 | 1000 | 3360 | 3.36 | 1000 | 3360 | 3.5 | 0.14 | 3717 | 357
2303 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)Paint work for Batching Plant & 2 nos Silo | JOB | 1 | 112100 | 112100 | 0 | 0 | 0 | 0 | 112100 | 0 | 1 | 112100 | 112100 | 1 | 112100 | 112100 | 1 | 0 | 112100 | 0
2304 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING & DE SHUTTERING. | RMT | 15 | 64.9 | 973.5 | 0 | 0 | 0 | 2 | 64.9 | 129.8 | 12.8 | 56 | 716.8 | 12.8 | 56 | 716.8 | 13 | 2.2 | 843.7 | 256.7
2305 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 220 | 295 | 64900 | 0 | 0 | 0 | 22 | 295 | 6490 | 145.57 | 257.5 | 37484.275 | 145.57 | 257.5 | 37484.28 | 198 | 74.43 | 58410 | 27415.72
2306 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)SKILLED MASON (12 HRS) | NOS | 15 | 675 | 10125 | 0 | 0 | 0 | 2 | 675 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 15 | 8775 | 10125
2307 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 15 | 885 | 13275 | 0 | 0 | 0 | 2 | 885 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 15 | 11505 | 13275
2308 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 50 | 535 | 26750 | 0 | 0 | 0 | 5 | 535 | 2675 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 24075 | 26750
2309 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)UNSKILLED LABOUR (12 HRS) | NOS | 50 | 525 | 26250 | 0 | 0 | 0 | 5 | 525 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 23625 | 26250
2310 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 125 | 82.6 | 10325 | 0 | 0 | 0 | 13 | 82.6 | 1073.8 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 125 | 9251.2 | 10325
2311 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)1.5" NAIL | KG | 22.65 | 100 | 2265 | 20 | 100 | 2000 | 2 | 100 | 200 | 20 | 75.52 | 1510.4 | 0 | 0 | 0 | 20.65 | 22.65 | 2065 | 2265
2312 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)10 MM DIA TMT | MT | 1.29 | 55000 | 70950 | 1.29 | 55000 | 70950 | 0 | 55000 | 0 | 1.29 | 55755.01 | 71923.9682 | 1.29 | 55637.95 | 71772.95 | 1.29 | 0 | 70950 | -822.95
2313 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 30.77 | 1770 | 54462.9 | 30.77 | 1770 | 54462.9 | 3 | 1770 | 5310 | 30.77 | 1522.5 | 46847.3281 | 26.386 | 1519.03 | 40081.04 | 27.77 | 4.384 | 49152.9 | 14381.86
2314 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)12 MM DIA TMT | MT | 0.79 | 54500 | 43055 | 0.79 | 54500 | 43055 | 0 | 54500 | 0 | 0.79 | 55755 | 44046.45 | 0.7902 | 55921.12 | 44188.87 | 0.79 | -0.0002 | 43055 | -1133.87
2315 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)16 MM DIA TMT | MT | 0.73 | 54500 | 39785 | 0.73 | 54500 | 39785 | 0 | 54500 | 0 | 0.73 | 55755.01 | 40701.1548 | 0.73 | 55237.58 | 40323.43 | 0.73 | 0 | 39785 | -538.43
2316 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)20 MM DIA TMT. | MT | 0.7 | 50000 | 35000 | 0.7 | 50000 | 35000 | 0 | 50000 | 0 | 0.7 | 55755.03 | 39028.52 | 0.7 | 55239.36 | 38667.55 | 0.7 | 0 | 35000 | -3667.55
2317 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 75 | 1750 | 131250 | 57.82 | 1750 | 101185 | 8 | 1750 | 14000 | 57.82 | 2052.93 | 118700.6404 | 64.323 | 2035.45 | 130926.04 | 67 | 10.677 | 117250 | 323.96
2318 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 41.76 | 55.6 | 2321.86 | 0 | 0 | 0 | 4 | 55.6 | 222.4 | 0 | 0 | 0 | 0 | 0 | 0 | 37.76 | 41.76 | 2099.456 | 2321.856
2319 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 4511 | 10 | 45110 | 4511 | 10 | 45110 | 451 | 10 | 4510 | 4511 | 9.5 | 42854.5 | 2296 | 9.6 | 22040.15 | 4060 | 2215 | 40600 | 23069.85
2320 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)3" NAIL | KG | 15.86 | 51 | 808.86 | 15.86 | 51 | 808.86 | 2 | 51 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 13.86 | 15.86 | 706.86 | 808.86
2321 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)4" NAIL | KG | 11.33 | 51 | 577.83 | 11.33 | 51 | 577.83 | 1 | 51 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 10.33 | 11.33 | 526.83 | 577.83
2322 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)8 MM DIA TMT | MT | 0.89 | 56000.01 | 49840.01 | 0.89 | 56000.01 | 49840.01 | 0 | 56000.01 | 0 | 0.89 | 57525.01 | 51197.26 | 0.89 | 57591.3 | 51256.26 | 0.89 | 0 | 49840.009 | -1416.2511
2323 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 101.31 | 36.58 | 3705.92 | 101.31 | 36.58 | 3705.92 | 10 | 36.58 | 365.8 | 101.31 | 53.1 | 5379.561 | 139.3 | 55.46 | 7725.02 | 91.31 | -37.99 | 3340.12 | -4019.1002
2324 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)M.C. SAND | MT | 55.64 | 1711.5 | 95227.86 | 0 | 0 | 0 | 6 | 1711.5 | 10269 | 0 | 0 | 0 | 52.006 | 1690.01 | 87890.69 | 49.64 | 3.634 | 84958.86 | 7337.17
2325 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 4536 | 11 | 49896 | 3180 | 11 | 34980 | 454 | 11 | 4994 | 3180 | 8.94 | 28430 | 3180 | 9.21 | 29300 | 4082 | 1356 | 44902 | 20596
2326 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 47 | 47.2 | 2218.4 | 47 | 47.2 | 2218.4 | 5 | 47.2 | 236 | 47 | 138.66 | 6517.14 | 4 | 143.22 | 572.89 | 42 | 43 | 1982.4 | 1645.51
2327 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 19 | 110 | 2090 | 19 | 110 | 2090 | 2 | 110 | 220 | 19 | 141.6 | 2690.4019 | 6 | 141.6 | 849.6 | 17 | 13 | 1870 | 1240.4
2328 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)PPC CEMENT | BAG | 550 | 283.59 | 155974.5 | 466 | 283.59 | 132152.94 | 55 | 283.59 | 15597.45 | 401 | 305.64 | 122560.3328 | 479 | 326.22 | 156257.07 | 495 | 71 | 140377.05 | -282.57
2329 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 25 | 78 | 1950 | 25 | 78 | 1950 | 3 | 78 | 234 | 25 | 155.76 | 3894 | 25 | 155.76 | 3894 | 22 | 0 | 1716 | -1944
2330 | INFRA. SITE EXP. - B. Plant and Sylo Foundation | 10 | Started | Material | (M)SILVER SAND | CFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2331 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)10 MM DIA TMT STAIGHTENING, CUTTING, BENDING, BINDING | MT | 0.72 | 8250 | 5940 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.716 | 5250 | 3759 | 0.716 | 5250 | 3759 | 0.72 | 0.004 | 5940 | 2181
2332 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)10/15/20 MM PLASTERING | SQM | 99.242 | 150 | 14886.3 | 0 | 0 | 0 | 10 | 150 | 1500 | 90.22 | 150 | 13533 | 90.22 | 150 | 13533 | 89.242 | 9.022 | 13386.3 | 1353.3
2333 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)16 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 0.2 | 8250 | 1650 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 1650 | 1650
2334 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)375 MM / 250 MM / 200 MM TH. BRICK WORK | CUM | 30.412 | 700 | 21288.4 | 0 | 0 | 0 | 3 | 700 | 2100 | 27.648 | 700 | 19353.6 | 27.648 | 700 | 19353.6 | 27.412 | 2.764 | 19188.4 | 1934.8
2335 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)8 MM DIA TMT CUTTING, BENDING, BINDING | MT | 0.34 | 8250 | 2805 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.335 | 5250 | 1758.75 | 0.335 | 5250 | 1758.75 | 0.34 | 0.005 | 2805 | 1046.25
2336 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 200 | 141.6 | 28320 | 0 | 0 | 0 | 20 | 141.6 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 200 | 25488 | 28320
2337 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 36.894 | 82.6 | 3047.44 | 0 | 0 | 0 | 4 | 82.6 | 330.4 | 33.54 | 75 | 2515.5 | 33.54 | 75 | 2515.5 | 32.894 | 3.354 | 2717.044 | 531.9444
2338 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 36.894 | 50 | 1844.7 | 0 | 0 | 0 | 4 | 50 | 200 | 33.54 | 55 | 1844.7 | 33.54 | 55 | 1844.7 | 32.894 | 3.354 | 1644.7 | 0
2339 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)DISPOSAL OF EARTH WITHIN PROJECT SITE, MORE THAN 50'0" LEAD | CUM | 300 | 90 | 27000 | 0 | 0 | 0 | 30 | 90 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 300 | 24300 | 27000
2340 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)EARTH WORK IN EXCAVATION MANUALLY UP TO 3.0 MTR. | CUM | 415 | 150 | 62250 | 0 | 0 | 0 | 42 | 150 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 415 | 55950 | 62250
2341 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for 20mm Dia Ball Valve | NOS | 16 | 177 | 2832 | 0 | 0 | 0 | 2 | 177 | 354 | 5 | 177 | 885 | 5 | 177 | 885 | 14 | 11 | 2478 | 1947
2342 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for 50mm Dia GI main line to Batching Plant | RMT | 90 | 324.5 | 29205 | 0 | 0 | 0 | 9 | 324.5 | 2920.5 | 55 | 324.5 | 17847.5 | 55 | 324.5 | 17847.5 | 81 | 35 | 26284.5 | 11357.5
2343 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for fab. & erection of Sides Gabbling of Str. Shed | SQFT | 2010 | 53.1 | 106731 | 0 | 0 | 0 | 201 | 53.1 | 10673.1 | 2010 | 53.1 | 106731 | 1803.07 | 53.1 | 95743.01 | 1809 | 206.93 | 96057.9 | 10987.99
2344 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for Fabrication & Erection of Structural Shed | SQFT | 1643 | 70.8 | 116324.4 | 0 | 0 | 0 | 164 | 70.8 | 11611.2 | 1643 | 70.8 | 116324.4 | 1630 | 70.8 | 115404 | 1479 | 13 | 104713.2 | 920.4
2345 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for fixing 50mm Dia Non return valve | NOS | 4 | 354 | 1416 | 0 | 0 | 0 | 0 | 354 | 0 | 3 | 354 | 1062 | 3 | 354 | 1062 | 4 | 1 | 1416 | 354
2346 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for fixing 50mm Dua Ball Valve | NOS | 12 | 354 | 4248 | 0 | 0 | 0 | 1 | 354 | 354 | 3 | 354 | 1062 | 3 | 354 | 1062 | 11 | 9 | 3894 | 3186
2347 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for mixing & pouring M25 Gr. Conc. (RMC w/ head load) | CUM | 6.05 | 531 | 3212.55 | 0 | 0 | 0 | 1 | 531 | 531 | 5.5 | 450 | 2475 | 5.5 | 450 | 2475 | 5.05 | 0.55 | 2681.55 | 737.55
2348 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for repair & fixing of 2HP monoblock pump | NOS | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 1 | 0 | 4130 | 0
2349 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for repair & placing iof 3HP mono block pump | NOS | 1 | 4720 | 4720 | 0 | 0 | 0 | 0 | 4720 | 0 | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 1 | 0 | 4720 | 0
2350 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)L/C for RMC Concreting in RCC Walls | CUM | 7.7 | 354 | 2725.8 | 0 | 0 | 0 | 1 | 354 | 354 | 7 | 300 | 2100 | 7 | 300 | 2100 | 6.7 | 0.7 | 2371.8 | 625.8
2351 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MANUAL SHIFTING OF BRICKS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2352 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MANUAL SHIFTING OF SAND IN BAGS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2353 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MANUAL SHIFTING OF STONECHIP IN BAGS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2354 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2355 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C(1:2:4) | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2356 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 26.133 | 700 | 18293.1 | 0 | 0 | 0 | 3 | 700 | 2100 | 23.757 | 750 | 17817.75 | 23.757 | 750 | 17817.75 | 23.133 | 2.376 | 16193.1 | 475.35
2357 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)MIXING & POURING OF RCC M- 25 FOR WALL CASTING | CUM | 3.454 | 1062 | 3668.15 | 0 | 0 | 0 | 0 | 1062 | 0 | 3.14 | 750 | 2355 | 3.14 | 750 | 2355 | 3.454 | 0.314 | 3668.148 | 1313.148
2358 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)NEAT CEMENT FINISH | SQM | 40 | 55 | 2200 | 0 | 0 | 0 | 4 | 55 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 40 | 1980 | 2200
2359 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING & DE SHUTTERING. | RMT | 810 | 64.9 | 52569 | 0 | 0 | 0 | 81 | 64.9 | 5256.9 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 810 | 47312.1 | 52569
2360 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 208.2 | 295 | 61419 | 0 | 0 | 0 | 21 | 295 | 6195 | 208.18 | 257.5 | 53606.35 | 208.18 | 257.5 | 53606.35 | 187.2 | 0.02 | 55224 | 7812.65
2361 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)SKILLED MASON (12 HRS) | NOS | 30 | 675 | 20250 | 0 | 0 | 0 | 3 | 675 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 30 | 18225 | 20250
2362 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)UNSKILLED LABOUR (12 HRS) | NOS | 100 | 525 | 52500 | 0 | 0 | 0 | 10 | 525 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 100 | 47250 | 52500
2363 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 300 | 82.6 | 24780 | 0 | 0 | 0 | 30 | 82.6 | 2478 | 272.04 | 50 | 13602 | 272.04 | 50 | 13602 | 270 | 27.96 | 22302 | 11178
2364 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)1.5 TON AC | NOS | 1 | 33500.2 | 33500.2 | 1 | 33500.2 | 33500.2 | 0 | 33500.2 | 0 | 1 | 37000.01 | 37000.01 | 1 | 37000.01 | 37000.01 | 1 | 0 | 33500.2 | -3499.81
2365 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)1.5" NAIL | KG | 87.23 | 100 | 8723 | 87.23 | 100 | 8723 | 9 | 100 | 900 | 80 | 75.52 | 6041.6 | 2 | 78.83 | 157.66 | 78.23 | 85.23 | 7823 | 8565.34
2366 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)10 MM DIA TMT | MT | 0.23 | 55000 | 12650 | 0.23 | 55000 | 12650 | 0 | 55000 | 0 | 0.23 | 55755.01 | 12823.6517 | 0.23 | 53067.09 | 12205.43 | 0.23 | 0 | 12650 | 444.57
2367 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 3.89 | 1770 | 6885.3 | 3.89 | 1770 | 6885.3 | 0 | 1770 | 0 | 3.89 | 1522.5 | 5922.5254 | 4.858 | 1524 | 7403.58 | 3.89 | -0.968 | 6885.3 | -518.28
2368 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)16 MM DIA TMT | MT | 0.16 | 54500 | 8720 | 0.16 | 54500 | 8720 | 0 | 54500 | 0 | 0.16 | 55755.01 | 8920.8011 | 0.16 | 52874.44 | 8459.91 | 0.16 | 0 | 8720 | 260.09
2369 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2 HP Centrifugal Pump | NOS | 1 | 16520 | 16520 | 1 | 16520 | 16520 | 0 | 16520 | 0 | 1 | 19225.74 | 19225.74 | 1 | 19126.61 | 19126.61 | 1 | 0 | 16520 | -2606.61
2370 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" ELBOW (UPVC) | NOS | 10 | 82.6 | 826 | 10 | 82.6 | 826 | 1 | 82.6 | 82.6 | 10 | 65.21 | 652.08 | 10 | 65.18 | 651.82 | 9 | 0 | 743.4 | 174.18
2371 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" G.I. Elbow | NOS | 20 | 29.5 | 590 | 20 | 29.5 | 590 | 2 | 29.5 | 59 | 20 | 197.01 | 3940.16 | 20 | 195.86 | 3917.13 | 18 | 0 | 531 | -3327.13
2372 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" G.I. Socket | NOS | 10 | 59 | 590 | 10 | 59 | 590 | 1 | 59 | 59 | 10 | 130.37 | 1303.7 | 10 | 129.61 | 1296.11 | 9 | 0 | 531 | -706.11
2373 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" G.I. Tee | NOS | 6 | 59 | 354 | 6 | 59 | 354 | 1 | 59 | 59 | 6 | 266.14 | 1596.8598 | 6 | 264.59 | 1587.54 | 5 | 0 | 295 | -1233.54
2374 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" G.I. Union | NOS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 2 | 377.49 | 754.98 | 2 | 375.29 | 750.57 | 2 | 0 | 118 | -632.57
2375 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" GM GATE VALVE | NOS | 2 | 3929.4 | 7858.8 | 2 | 3929.4 | 7858.8 | 0 | 3929.4 | 0 | 2 | 3932.29 | 7864.58 | 0 | 0 | 0 | 2 | 2 | 7858.8 | 7858.8
2376 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" MTA (BRASS) UPVC | NOS | 6 | 495.6 | 2973.6 | 6 | 495.6 | 2973.6 | 1 | 495.6 | 495.6 | 6 | 510.91 | 3065.4402 | 5 | 507.92 | 2539.6 | 5 | 1 | 2478 | 434
2377 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" NAIL | KG | 61 | 51 | 3111 | 0 | 0 | 0 | 6 | 51 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 61 | 2805 | 3111
2378 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" SOCKET | NOS | 4 | 59 | 236 | 4 | 59 | 236 | 0 | 59 | 0 | 4 | 39.54 | 158.16 | 4 | 39.31 | 157.22 | 4 | 0 | 236 | 78.78
2379 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" UPVC PIPE (10' LENTH) | NOS | 3 | 460.2 | 1380.6 | 3 | 460.2 | 1380.6 | 0 | 460.2 | 0 | 3 | 482.28 | 1446.8301 | 3 | 479.46 | 1438.37 | 3 | 0 | 1380.6 | -57.77
2380 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" UPVC TEE | NOS | 4 | 94.4 | 377.6 | 4 | 94.4 | 377.6 | 0 | 94.4 | 0 | 4 | 95.39 | 381.54 | 0 | 0 | 0 | 4 | 4 | 377.6 | 377.6
2381 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" X 4" G.I. Nipple | NOS | 6 | 59 | 354 | 6 | 59 | 354 | 1 | 59 | 59 | 6 | 95.68 | 574.08 | 6 | 95.12 | 570.74 | 5 | 0 | 295 | -216.74
2382 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2" X 6" G.I. Nipple | NOS | 8 | 59 | 472 | 8 | 59 | 472 | 1 | 59 | 59 | 8 | 142.3 | 1138.4 | 8 | 141.47 | 1131.72 | 7 | 0 | 413 | -659.72
2383 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 30.985 | 1750 | 54223.75 | 30.985 | 1750 | 54223.75 | 3 | 1750 | 5250 | 30.985 | 2050 | 63519.25 | 40.797 | 2109.57 | 86064.24 | 27.985 | -9.812 | 48973.75 | -31840.49
2384 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 17820 | 10 | 178200 | 11322 | 10 | 113220 | 1782 | 10 | 17820 | 11322 | 9.06 | 102559 | 6249 | 12.14 | 75839.54 | 16038 | 11571 | 160380 | 102360.46
2385 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)3" NAIL | KG | 61 | 51 | 3111 | 50 | 51 | 2550 | 6 | 51 | 306 | 50 | 70.8 | 3540 | 5 | 81.94 | 409.72 | 55 | 56 | 2805 | 2701.28
2386 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)4" NAIL | KG | 43.62 | 51 | 2224.62 | 43.62 | 51 | 2224.62 | 4 | 51 | 204 | 43 | 70.8 | 3044.4 | 0 | 0 | 0 | 39.62 | 43.62 | 2020.62 | 2224.62
2387 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)50 MM UPVC SOCKET | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
2388 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)8 MM DIA TMT | MT | 0.18 | 56000.01 | 10080 | 0.18 | 56000.01 | 10080 | 0 | 56000.01 | 0 | 0.18 | 57525 | 10354.5 | 0.18 | 55050.44 | 9909.08 | 0.18 | 0 | 10080.002 | 170.9218
2389 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)CAST IRON GATE VALVE | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2390 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)CAT 6 CABLE | MTR | 100 | 35.4 | 3540 | 100 | 35.4 | 3540 | 10 | 35.4 | 354 | 100 | 29.5 | 2950 | 100 | 29.5 | 2950 | 90 | 0 | 3186 | 590
2391 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)CEMENT - OPC 53 GRADE | MT | 0.594 | 8200.01 | 4870.81 | 0 | 0 | 0 | 0 | 8200.01 | 0 | 0 | 0 | 0 | 0.594 | 7777.95 | 4620.1 | 0.594 | 0 | 4870.806 | 250.7059
2392 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)COLOURED CORRUGATED SHEET (10' FOOT LONG) | NOS | 12 | 2832 | 33984 | 12 | 2832 | 33984 | 1 | 2832 | 2832 | 12 | 1382.58 | 16590.96 | 12 | 1369.13 | 16429.52 | 11 | 0 | 31152 | 17554.48
2393 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)COLOURED CORRUGATED SHEET (11' FOOT LONG) | NOS | 6 | 2832 | 16992 | 6 | 2832 | 16992 | 1 | 2832 | 2832 | 6 | 1520.84 | 9125.0202 | 6 | 1506.04 | 9036.25 | 5 | 0 | 14160 | 7955.75
2394 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)COLOURED CORRUGATED SHEET (12' FOOT LONG) | NOS | 31 | 1840.8 | 57064.8 | 31 | 1840.8 | 57064.8 | 3 | 1840.8 | 5522.4 | 31 | 2019.02 | 62589.63 | 31 | 2015.38 | 62476.67 | 28 | 0 | 51542.4 | -5411.87
2395 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)COLOURED CORRUGATED SHEET (13' FOOT LONG) | NOS | 4 | 2832 | 11328 | 4 | 2832 | 11328 | 0 | 2832 | 0 | 4 | 1797.36 | 7189.42 | 4 | 1779.87 | 7119.46 | 4 | 0 | 11328 | 4208.54
2396 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)COLOURED CORRUGATED SHEET (14' FOOT LONG) | NOS | 10 | 2147.6 | 21476 | 10 | 2147.6 | 21476 | 1 | 2147.6 | 2147.6 | 10 | 2315.28 | 23152.8399 | 10 | 2309.63 | 23096.34 | 9 | 0 | 19328.4 | -1620.34
2397 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)COLOURED CORRUGATED SHEET (16' FOOT LONG) | NOS | 21 | 2832 | 59472 | 21 | 2832 | 59472 | 2 | 2832 | 5664 | 21 | 2832 | 59472 | 21 | 2832 | 59472 | 19 | 0 | 53808 | 0
2398 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)FLY ASH | MT | 0.271 | 1396.5 | 378.45 | 0 | 0 | 0 | 0 | 1396.5 | 0 | 0 | 0 | 0 | 0.273 | 1396.48 | 381.24 | 0.271 | -0.002 | 378.452 | -2.7885
2399 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 12.8 | 36.58 | 468.22 | 12.8 | 36.58 | 468.22 | 1 | 36.58 | 36.58 | 12.8 | 53.1 | 679.68 | 8.05 | 54.41 | 438.01 | 11.8 | 4.75 | 431.644 | 30.214
2400 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)JHAMA BATS | CFT | 18209.37 | 50 | 910468.5 | 0 | 0 | 0 | 1821 | 50 | 91050 | 0 | 0 | 0 | 0 | 0 | 0 | 16388.37 | 18209.37 | 819418.5 | 910468.5
2401 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)JUTE | KG | 1 | 106.2 | 106.2 | 1 | 106.2 | 106.2 | 0 | 106.2 | 0 | 1 | 104.27 | 104.27 | 1 | 103.66 | 103.66 | 1 | 0 | 106.2 | 2.54
2402 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)M.C. SAND | MT | 42.75 | 1711.5 | 73166.63 | 0 | 0 | 0 | 4 | 1711.5 | 6846 | 0 | 0 | 0 | 54.438 | 1684.41 | 91695.72 | 38.75 | -11.688 | 66320.625 | -18529.095
2403 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 6606 | 11 | 72666 | 5300 | 11 | 58300 | 661 | 11 | 7271 | 5300 | 8.75 | 46375 | 15300 | 8.92 | 136441.6 | 5945 | -8694 | 65395 | -63775.6
2404 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 192 | 47.2 | 9062.4 | 192 | 47.2 | 9062.4 | 19 | 47.2 | 896.8 | 192 | 112.1 | 21523.2 | 5 | 143.22 | 716.12 | 173 | 187 | 8165.6 | 8346.28
2405 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 21.74 | 110 | 2391.4 | 21.74 | 110 | 2391.4 | 2 | 110 | 220 | 21.74 | 141.6 | 3078.3862 | 10 | 141.6 | 1416 | 19.74 | 11.74 | 2171.4 | 975.4
2406 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 207 | 283.59 | 58703.13 | 207 | 283.59 | 58703.13 | 21 | 283.59 | 5955.39 | 200 | 309.99 | 61998.08 | 234 | 299.6 | 70106.58 | 186 | -27 | 52747.74 | -11403.45
2407 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 12.5 | 7257 | 90712.5 | 12.5 | 7257 | 90712.5 | 1 | 7257 | 7257 | 12.5 | 7199.99 | 89999.925 | 12.5 | 7200 | 89999.95 | 11.5 | 0 | 83455.5 | 712.55
2408 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)ROUTER | NOS | 1 | 2419 | 2419 | 1 | 2419 | 2419 | 0 | 2419 | 0 | 1 | 2419 | 2419 | 1 | 2419 | 2419 | 1 | 0 | 2419 | 0
2409 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)SERVICE CHARGES | NOS | 1 | 1817.2 | 1817.2 | 1 | 1817.2 | 1817.2 | 0 | 1817.2 | 0 | 1 | 3540 | 3540 | 1 | 944 | 944 | 1 | 0 | 1817.2 | 873.2
2410 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 96 | 78 | 7488 | 96 | 78 | 7488 | 10 | 78 | 780 | 96 | 155.76 | 14952.96 | 0 | 0 | 0 | 86 | 96 | 6708 | 7488
2411 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)SILVER SAND | CFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2412 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)TP Link 8 PORT Gigabyte Switch (TL-SG1008D) | NOS | 1 | 1882.1 | 1882.1 | 1 | 1882.1 | 1882.1 | 0 | 1882.1 | 0 | 1 | 1882.1 | 1882.1 | 1 | 1882.1 | 1882.1 | 1 | 0 | 1882.1 | 0
2413 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)TP-LINK CPE710 5 GHZ WIRELESS-AC867 | NOS | 2 | 6962 | 13924 | 2 | 6962 | 13924 | 0 | 6962 | 0 | 2 | 6962 | 13924 | 2 | 6962 | 13924 | 2 | 0 | 13924 | 0
2414 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)UPVC SOLVENT | NOS | 1 | 384 | 384 | 1 | 384 | 384 | 0 | 384 | 0 | 1 | 471.05 | 471.05 | 1 | 468.3 | 468.3 | 1 | 0 | 384 | -84.3
2415 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)UPVC 50 MM BALL VALVE. | NOS | 4 | 765 | 3060 | 4 | 765 | 3060 | 0 | 765 | 0 | 4 | 645.15 | 2580.58 | 1 | 641.38 | 641.38 | 4 | 3 | 3060 | 2418.62
2416 | INFRA. SITE EXP. - Batching Plant Area Work | 10 | Started | Material | (M)WHITE ZINC | GRAM | 1000 | 0 | 0 | 1000 | 0 | 0 | 100 | 0 | 0 | 1000 | 0.43 | 433 | 1000 | 0.43 | 426.8 | 900 | 0 | 0 | -426.8
2417 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)6" DIA 20' LONG UCALYPTUS BALLAH DRIVING INCLUDING 2 COATS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2418 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)DRUM SHEET FIXING | NOS | 131 | 50 | 6550 | 0 | 0 | 0 | 13 | 50 | 650 | 131 | 50 | 6550 | 131 | 50 | 6550 | 118 | 0 | 5900 | 0
2419 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)DRUM SHEET SUPPLYING & FIXING INCLUDING BITUMINOUS PAINT. | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2420 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)LABOUR CHARGES FOR DRIVING 6" DIA 20'0" LONG UC BALLAH. | NOS | 1365 | 300 | 409500 | 0 | 0 | 0 | 137 | 300 | 41100 | 1165 | 300 | 349500 | 1165 | 300 | 349500 | 1228 | 200 | 368400 | 60000
2421 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)LIFTING | NOS | 200 | 200 | 40000 | 0 | 0 | 0 | 20 | 200 | 4000 | 35 | 200 | 7000 | 35 | 200 | 7000 | 180 | 165 | 36000 | 33000
2422 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)Site Expenses | NOS | 275000 | 1.18 | 324500 | 0 | 0 | 0 | 27500 | 1.18 | 32450 | 0 | 0 | 0 | 0 | 0 | 0 | 247500 | 275000 | 292050 | 324500
2423 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Labour | (L)SUPPLYING & INSTALLATION OF UC BALLAH 5" DIA (TOP) AND 16'0" | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2424 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)6" DIA 20FT LONG UCALYPTUS BALLAH | PICS | 1550 | 914.5 | 1417475 | 1150 | 914.5 | 1051675 | 155 | 914.5 | 141747.5 | 650 | 893.17 | 580560 | 1050 | 912.53 | 958160 | 1395 | 500 | 1275727.5 | 459315
2425 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)BITUMEN DRUM SHEET (5' 0" X 3' 3") | NOS | 160 | 483.8 | 77408 | 60 | 483.8 | 29028 | 16 | 483.8 | 7740.8 | 60 | 489.7 | 29382 | 160 | 494.29 | 79086.9 | 144 | 0 | 69667.2 | -1678.9
2426 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)COL - TAR | NOS | 45 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 45 | 242.44 | 10909.93 | 40 | 0 | 0 | -10909.93
2427 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)DRUM | NOS | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 20 | 236 | 4720 | 1 | -19 | 236 | -4484
2428 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)FOLDING SCREW DRIVER 12" | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 131.02 | 131.02 | 1 | 0 | 0 | -131.02
2429 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)PLUS 8" | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 315.64 | 315.64 | 1 | 0 | 0 | -315.64
2430 | INFRA. SITE EXP. - UC Ballah Piling | 10 | Started | Material | (M)RED OXIDE | NOS | 1 | 3917.6 | 3917.6 | 0 | 0 | 0 | 0 | 3917.6 | 0 | 0 | 0 | 0 | 4 | 3985.89 | 15943.55 | 1 | -3 | 3917.6 | -12025.95
2431 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)10 MM CHINA CLIP | PKT | 1 | 245.01 | 245.01 | 1 | 245.01 | 245.01 | 0 | 245.01 | 0 | 1 | 289.1 | 289.1 | 0 | 0 | 0 | 1 | 1 | 245.01 | 245.01
2432 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)10TB HDD INTERNAL | NOS | 2 | 35400 | 70800 | 2 | 35400 | 70800 | 0 | 35400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 70800 | 70800
2433 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)12V 2AMP CCTV ADAPTER | NOS | 2 | 531 | 1062 | 2 | 531 | 1062 | 0 | 531 | 0 | 2 | 413 | 826 | 1 | 413 | 413 | 2 | 1 | 1062 | 649
2434 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)20 MM CHINA CLIP | PKT | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 1 | 485.15 | 485.15 | 1 | 477.57 | 477.57 | 1 | 0 | 118 | -359.57
2435 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)20 MM PVC PIPE | NOS | 35 | 76.7 | 2684.5 | 35 | 76.7 | 2684.5 | 0 | 76.7 | 0 | 35 | 76.41 | 2674.35 | 35 | 75.57 | 2644.88 | 35 | 0 | 2684.5 | 39.62
2436 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)25 MM FLEXIBLE PIPE | MTR | 30 | 430.7 | 12921 | 30 | 430.7 | 12921 | 0 | 430.7 | 0 | 30 | 19.41 | 582.3 | 30 | 19.33 | 579.77 | 30 | 0 | 12921 | 12341.23
2437 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)250 mm Cable Tie | PKT | 4 | 413 | 1652 | 3 | 413 | 1239 | 0 | 413 | 0 | 3 | 424.51 | 1273.53 | 3 | 422.75 | 1268.24 | 4 | 1 | 1652 | 383.76
2438 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)3 CORE CABLE | MTR | 400 | 41.3 | 16520 | 400 | 41.3 | 16520 | 0 | 41.3 | 0 | 400 | 41.3 | 16520 | 0 | 0 | 0 | 400 | 400 | 16520 | 16520
2439 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)3+1 CCTV CABLE | MTR | 90 | 14.4 | 1296 | 90 | 14.4 | 1296 | 0 | 14.4 | 0 | 90 | 15.34 | 1380.6 | 0 | 0 | 0 | 90 | 90 | 1296 | 1296
2440 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)6/6 PVC BOX | NOS | 1 | 295 | 295 | 1 | 295 | 295 | 0 | 295 | 0 | 1 | 70.8 | 70.8 | 1 | 70.8 | 70.8 | 1 | 0 | 295 | 224.2
2441 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)ADAPTOR 12V2AMP | NOS | 1 | 767 | 767 | 0 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 767 | 767
2442 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)BNC CONNECTOR | NOS | 18 | 47.2 | 849.6 | 14 | 47.2 | 660.8 | 0 | 47.2 | 0 | 14 | 69.54 | 973.5 | 8 | 90.71 | 725.7 | 18 | 10 | 849.6 | 123.9
2443 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)BULLET CAMERA D12 HIKVISION | NOS | 3 | 1.18 | 3.54 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 1622.5 | 1622.5 | 3 | 2587.35 | 7762.06 | 3 | 0 | 3.54 | -7758.52
2444 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CABLE 3+1 | MTR | 180 | 11.8 | 2124 | 180 | 11.8 | 2124 | 0 | 11.8 | 0 | 180 | 14.42 | 2595.528 | 810 | 14.42 | 11679.88 | 180 | -630 | 2124 | -9555.88
2445 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CABLE DLINK CAT-6 | MTR | 20 | 23.6 | 472 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 20 | 25.96 | 519.2 | 20 | 0 | 472 | -47.2
2446 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CABLE LAYING | MTR | 597 | 11.8 | 7044.6 | 547 | 11.8 | 6454.6 | 0 | 11.8 | 0 | 547 | 11.92 | 6522.91 | 507 | 11.91 | 6040.25 | 597 | 90 | 7044.6 | 1004.35
2447 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CABLE TIE 250MM | PKT | 6 | 389.4 | 2336.4 | 4 | 389.4 | 1557.6 | 0 | 389.4 | 0 | 4 | 410.05 | 1640.2 | 6 | 387.43 | 2324.6 | 6 | 0 | 2336.4 | 11.8
2448 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CAT 6 CABLE | MTR | 777 | 35.4 | 27505.8 | 727 | 35.4 | 25735.8 | 0 | 35.4 | 0 | 727 | 38.17 | 27752.24 | 772 | 35.75 | 27596.81 | 777 | 5 | 27505.8 | -91.01
2449 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CHINA CLIP 6MM | PKT | 5 | 271.4 | 1357 | 4 | 271.4 | 1085.6 | 0 | 271.4 | 0 | 4 | 252.23 | 1008.9 | 3 | 253.7 | 761.1 | 5 | 2 | 1357 | 595.9
2450 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CMOS BATTERRY | NOS | 1 | 177 | 177 | 1 | 177 | 177 | 0 | 177 | 0 | 1 | 177 | 177 | 1 | 177 | 177 | 1 | 0 | 177 | 0
2451 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CONNECTOR | NOS | 10 | 177 | 1770 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 10 | 175.82 | 1758.2 | 10 | 0 | 1770 | 11.8
2452 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)CONNECTOR DLINK RJ-45 | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11.8 | 23.6 | 2 | 0 | 0 | -23.6
2453 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)D-LINK POE SWITCH 4 PORT | NOS | 1 | 2950 | 2950 | 1 | 2950 | 2950 | 0 | 2950 | 0 | 1 | 2031.57 | 2031.57 | 1 | 2023.15 | 2023.15 | 1 | 0 | 2950 | 926.85
2454 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)D-LINK POE SWITCH 8 PORT | NOS | 1 | 4543 | 4543 | 1 | 4543 | 4543 | 0 | 4543 | 0 | 1 | 4543 | 4543 | 1 | 4543 | 4543 | 1 | 0 | 4543 | 0
2455 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)DC CONNECTOR | NOS | 53 | 35.4 | 1876.2 | 6 | 35.4 | 212.4 | 0 | 35.4 | 0 | 6 | 35.73 | 214.38 | 20 | 35.48 | 709.67 | 53 | 33 | 1876.2 | 1166.53
2456 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)DVR 32 PORT (MODEL-iDS-7232HQHI-M2/S) | NOS | 1 | 30243.4 | 30243.4 | 0 | 0 | 0 | 0 | 30243.4 | 0 | 0 | 0 | 0 | 1 | 30237.5 | 30237.5 | 1 | 0 | 30243.4 | 5.9
2457 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)DVR TO INTRUTION CONNECTOR | NOS | 1 | 3245 | 3245 | 1 | 3245 | 3245 | 0 | 3245 | 0 | 1 | 3245 | 3245 | 0 | 0 | 0 | 1 | 1 | 3245 | 3245
2458 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)ELECTRIC SIREN | NOS | 4 | 3776 | 15104 | 4 | 3776 | 15104 | 0 | 3776 | 0 | 4 | 3776 | 15104 | 0 | 0 | 0 | 4 | 4 | 15104 | 15104
2459 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)GIGABIT SWITCH | NOS | 2 | 1510.4 | 3020.8 | 2 | 1510.4 | 3020.8 | 0 | 1510.4 | 0 | 2 | 4441.72 | 8883.43 | 2 | 4986.12 | 9972.23 | 2 | 0 | 3020.8 | -6951.43
2460 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HARD DISK 2 TB | NOS | 1 | 5369 | 5369 | 1 | 5369 | 5369 | 0 | 5369 | 0 | 1 | 5369 | 5369 | 1 | 5369 | 5369 | 1 | 0 | 5369 | 0
2461 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HD DOME CAMERA 2 MP WITH AUDIO | NOS | 12 | 1746.4 | 20956.8 | 2 | 1746.4 | 3492.8 | 0 | 1746.4 | 0 | 2 | 1622.5 | 3245 | 10 | 1741.68 | 17416.8 | 12 | 2 | 20956.8 | 3540
2462 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HDMI CABLE | MTR | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 236 | 236
2463 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HDMI CABLE . | NOS | 3 | 472 | 1416 | 1 | 472 | 472 | 0 | 472 | 0 | 1 | 2124 | 2124 | 3 | 963.67 | 2891 | 3 | 0 | 1416 | -1475
2464 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HIGH RANGE VIDEO BALOON CONNECTOR | NOS | 5 | 224.2 | 1121 | 4 | 224.2 | 896.8 | 0 | 224.2 | 0 | 4 | 227.33 | 909.3 | 4 | 226.85 | 907.38 | 5 | 1 | 1121 | 213.62
2465 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HIKVISION 30MTRS BULLET CAMERA 2MP | NOS | 1 | 2891 | 2891 | 0 | 0 | 0 | 0 | 2891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2891 | 2891
2466 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HIKVISION HD BULLET CAMERA 2 MP(40 mtrs) | NOS | 2 | 2891 | 5782 | 2 | 2891 | 5782 | 0 | 2891 | 0 | 2 | 2822.12 | 5644.24 | 2 | 2816.41 | 5632.81 | 2 | 0 | 5782 | 149.19
2467 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)HIKVISION HD DOME CAMERA 2 MP(20 mtrs) | NOS | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 0 | 1416 | 0 | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 1 | 0 | 1416 | 0
2468 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)INSPECTION AND TESTING CHARGES | NOS | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 590 | 590
2469 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)INSTALLATION | PICS | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 590 | 590
2470 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)INSTALLATION CHARGES | NOS | 9 | 625.4 | 5628.6 | 8 | 625.4 | 5003.2 | 0 | 625.4 | 0 | 8 | 472 | 3776 | 2 | 590 | 1180 | 9 | 7 | 5628.6 | 4448.6
2471 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)INTRUTION ALARM | NOS | 1 | 15930 | 15930 | 1 | 15930 | 15930 | 0 | 15930 | 0 | 1 | 15930 | 15930 | 0 | 0 | 0 | 1 | 1 | 15930 | 15930
2472 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)IP BULLET CAMERA | NOS | 11 | 2596 | 28556 | 10 | 2596 | 25960 | 0 | 2596 | 0 | 10 | 2953 | 29529.96 | 10 | 2950.73 | 29507.32 | 11 | 1 | 28556 | -951.32
2473 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)JUNCTION BOX IP 65 | NOS | 10 | 448.4 | 4484 | 10 | 448.4 | 4484 | 0 | 448.4 | 0 | 10 | 448.4 | 4484 | 9 | 448.4 | 4035.6 | 10 | 1 | 4484 | 448.4
2474 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)MEDIA CONVERTER | NOS | 2 | 2596 | 5192 | 2 | 2596 | 5192 | 0 | 2596 | 0 | 2 | 2596 | 5192 | 2 | 2596 | 5192 | 2 | 0 | 5192 | 0
2475 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)MONITOR | NOS | 1 | 22951 | 22951 | 1 | 22951 | 22951 | 0 | 22951 | 0 | 1 | 4130 | 4130 | 0 | 0 | 0 | 1 | 1 | 22951 | 22951
2476 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)NVR 16 CHANNEL | NOS | 1 | 7670 | 7670 | 0 | 0 | 0 | 0 | 7670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7670 | 7670
2477 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)NVR 32 PORT | NOS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 17464 | 17464 | 1 | 17464 | 17464 | 1 | 0 | 1 | -17463
2478 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)OPTICAL FIBER CABLE 4 CORE | MTR | 400 | 29.5 | 11800 | 400 | 29.5 | 11800 | 0 | 29.5 | 0 | 400 | 29.5 | 11800 | 272 | 29.5 | 8024 | 400 | 128 | 11800 | 3776
2479 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)PATCH CORD (1.5 MTR) | NOS | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 236 | 236
2480 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)POWER CABLE | MTR | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 90 | 40.12 | 3611.14 | 1 | -89 | 35.4 | -3575.74
2481 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)Power Cable Imported | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 236 | 472 | 1 | -1 | 0 | -472
2482 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)POWER SPIKE BUSTER | NOS | 2 | 560.5 | 1121 | 1 | 560.5 | 560.5 | 0 | 560.5 | 0 | 1 | 576.12 | 576.12 | 2 | 567.12 | 1134.23 | 2 | 0 | 1121 | -13.23
2483 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)Power Supply | LS | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 1 | 885 | 885 | 1 | 0 | 885 | 0
2484 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)PVC BOX | NOS | 5 | 64.9 | 324.5 | 5 | 64.9 | 324.5 | 0 | 64.9 | 0 | 5 | 64.9 | 324.5 | 0 | 0 | 0 | 5 | 5 | 324.5 | 324.5
2485 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)PVC BOX 4 X 4 | NOS | 10 | 47.2 | 472 | 7 | 47.2 | 330.4 | 0 | 47.2 | 0 | 7 | 47.77 | 334.36 | 8 | 47.62 | 380.94 | 10 | 2 | 472 | 91.06
2486 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)RACK 4U | NOS | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 0 | 3068 | 0 | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 1 | 0 | 3068 | 0
2487 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)RJ 45 CONNECTOR | NOS | 55 | 11.8 | 649 | 53 | 11.8 | 625.4 | 0 | 11.8 | 0 | 53 | 11.95 | 633.32 | 49 | 11.94 | 584.88 | 55 | 6 | 649 | 64.12
2488 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)SERVICE CHARGES | NOS | 35 | 1817.2 | 63602 | 10 | 1817.2 | 18172 | 0 | 1817.2 | 0 | 9 | 1522.39 | 13701.52 | 32 | 1436.79 | 45977.19 | 35 | 3 | 63602 | 17624.81
2489 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)SERVICE CHARGES FOR CABLE LAYING | MTR | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 530 | 11.8 | 6254 | 1 | -529 | 11.8 | -6242.2
2490 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)SINGLE FACE PLATE | NOS | 1 | 153.4 | 153.4 | 0 | 0 | 0 | 0 | 153.4 | 0 | 0 | 0 | 0 | 10 | 152.22 | 1522.2 | 1 | -9 | 153.4 | -1368.8
2491 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)SMPS 12 VOLT 10 AMP | NOS | 1 | 944 | 944 | 1 | 944 | 944 | 0 | 944 | 0 | 1 | 970.3 | 970.3 | 1 | 966.28 | 966.28 | 1 | 0 | 944 | -22.28
2492 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)SMPS 12 VOLT 20 AMP | NOS | 1 | 2950 | 2950 | 1 | 2950 | 2950 | 0 | 2950 | 0 | 1 | 2950 | 2950 | 1 | 2950 | 2950 | 1 | 0 | 2950 | 0
2493 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)UPS | NOS | 1 | 2761.2 | 2761.2 | 1 | 2761.2 | 2761.2 | 0 | 2761.2 | 0 | 1 | 2183 | 2183 | 1 | 2183 | 2183 | 1 | 0 | 2761.2 | 578.2
2494 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)VIDEO BALOON | NOS | 1 | 271.4 | 271.4 | 0 | 0 | 0 | 0 | 271.4 | 0 | 0 | 0 | 0 | 7 | 271.4 | 1899.8 | 1 | -6 | 271.4 | -1628.4
2495 | INFRA. SITE EXP. - CC TV Work | 0 | Started | Material | (M)WALL MOUNT KIT | NOS | 1 | 560.5 | 560.5 | 1 | 560.5 | 560.5 | 0 | 560.5 | 0 | 1 | 413 | 413 | 0 | 0 | 0 | 1 | 1 | 560.5 | 560.5
2496 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)CALIBRATION & MAINTANACE OF DIGTAL CUBE TESTING MACHINE | NOS | 1 | 8500 | 8500 | 0 | 0 | 0 | 0 | 8500 | 0 | 1 | 8500 | 8500 | 1 | 8500 | 8500 | 1 | 0 | 8500 | 0
2497 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)Calibration & Servicing of Auto Level machine | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 0 | 0 | -2500
2498 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)Calibration of Digital Weigh Balance | NOS | 2 | 1600 | 3200 | 0 | 0 | 0 | 0 | 1600 | 0 | 2 | 1600 | 3200 | 2 | 1600 | 3200 | 2 | 0 | 3200 | 0
2499 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)Calibration of HOT AIR Oven 300 Deg. Cel. | NOS | 1 | 1600 | 1600 | 0 | 0 | 0 | 0 | 1600 | 0 | 1 | 1600 | 1600 | 1 | 1600 | 1600 | 1 | 0 | 1600 | 0
2500 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)Calibration of IS seives | NOS | 12 | 600 | 7200 | 0 | 0 | 0 | 1 | 600 | 600 | 12 | 550 | 6600 | 12 | 550 | 6600 | 11 | 0 | 6600 | 600
2501 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)HEATER COIL | NOS | 1 | 1800 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1 | 1800 | 1800 | 1 | 1800 | 1800 | 1 | 0 | 1800 | 0
2502 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)Repairing of Digital Weigh Balance (Capacity - 1000 Kg) | NOS | 1 | 3068 | 3068 | 0 | 0 | 0 | 0 | 3068 | 0 | 1 | 2600 | 2600 | 1 | 2600 | 2600 | 1 | 0 | 3068 | 468
2503 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)SERVICE CHARGE | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 1 | 0 | 1416 | 216
2504 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)Supply & Fitting of New Battery DC | NOS | 1 | 1711 | 1711 | 0 | 0 | 0 | 0 | 1711 | 0 | 1 | 1450 | 1450 | 1 | 1450 | 1450 | 1 | 0 | 1711 | 261
2505 | INFRA. SITE EXP. - Calibration of Tools | 10 | Started | Labour | (L)THERMOSTAT SENSOR | NOS | 1 | 2950 | 2950 | 0 | 0 | 0 | 0 | 2950 | 0 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 0 | 2950 | 450
2506 | INFRA. SITE EXP. - TPI for Materials | 10 | Started | Labour | (L)Physical & Chemical Test | NOS | 84 | 1416 | 118944 | 0 | 0 | 0 | 8 | 1416 | 11328 | 84 | 1416 | 118944 | 60 | 1416 | 84960 | 76 | 24 | 107616 | 33984
2507 | INFRA. SITE EXP. - Freight Charges for Shifting | 10 | Started | Labour | (L)ORCHARD RESIDENCY TO AMRITYA | TRIP | 1 | 3800 | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | 3800 | 3800 | 1 | 3800 | 3800 | 1 | 0 | 3800 | 0
2508 | INFRA. SITE EXP. - Freight Charges for Shifting | 10 | Started | Labour | (L)Rental for 30MT Heavy Crane for Cement Bulker Towing | DAYS | 5 | 11800 | 59000 | 0 | 0 | 0 | 1 | 11800 | 11800 | 5 | 11800 | 59000 | 3 | 11800 | 35400 | 4 | 2 | 47200 | 23600
2509 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)AGARPARA TO KASHIPUR (10 WHEELER) | TRIP | 10 | 10266 | 102660 | 0 | 0 | 0 | 1 | 10266 | 10266 | 10 | 8700 | 87000 | 10 | 8700 | 87000 | 9 | 0 | 92394 | 15660
2510 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)AGARPARA TO KASHIPUR (6WHEELER) | TRIP | 11 | 7300 | 80300 | 0 | 0 | 0 | 1 | 7300 | 7300 | 11 | 7300 | 80300 | 11 | 7300 | 80300 | 10 | 0 | 73000 | 0
2511 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)AMRITAYA TO NAVKAAR WORKSHOP (TATA-407) | TRIP | 27 | 4720 | 127440 | 0 | 0 | 0 | 3 | 4720 | 14160 | 27 | 4720 | 127440 | 23 | 4720 | 108560 | 24 | 4 | 113280 | 18880
2512 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)AMRITAYA TO NAVKAR WORKSHOP (TATA-1109) | TRIP | 8 | 9440 | 75520 | 0 | 0 | 0 | 1 | 9440 | 9440 | 8 | 9440 | 75520 | 5 | 9440 | 47200 | 7 | 3 | 66080 | 28320
2513 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)BATANAGAR TO KASHIPUR (10 WHEELER) | TRIP | 3 | 13350 | 40050 | 0 | 0 | 0 | 0 | 13350 | 0 | 3 | 12700 | 38100 | 3 | 12700 | 38100 | 3 | 0 | 40050 | 1950
2514 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)BATANAGAR TO KASHIPUR (6 WHEELER) | TRIP | 3 | 11500 | 34500 | 0 | 0 | 0 | 0 | 11500 | 0 | 3 | 11500 | 34500 | 3 | 11500 | 34500 | 3 | 0 | 34500 | 0
2515 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)BATANAGAR TO RAJARHAT (6 WHEELER) | TRIP | 5 | 18290 | 91450 | 0 | 0 | 0 | 1 | 18290 | 18290 | 5 | 15500 | 77500 | 5 | 15500 | 77500 | 4 | 0 | 73160 | 13950
2516 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)COSSIPORE TO RAJARHAT (407) | NOS | 10 | 4484 | 44840 | 0 | 0 | 0 | 1 | 4484 | 4484 | 10 | 4484 | 44840 | 0 | 0 | 0 | 9 | 10 | 40356 | 44840
2517 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)COSSIPORE TO RAJARHAT BOLERO | NOS | 17 | 3186 | 54162 | 0 | 0 | 0 | 2 | 3186 | 6372 | 17 | 3186 | 54162 | 8 | 3186 | 25488 | 15 | 9 | 47790 | 28674
2518 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)FREIGHT CHARGES | TRIP | 1 | 7080 | 7080 | 0 | 0 | 0 | 0 | 7080 | 0 | 1 | 28320 | 28320 | 1 | 28320 | 28320 | 1 | 0 | 7080 | -21240
2519 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)Hire Charges for TATA 1109(Dankuni to Cossipore) | TRIP | 3 | 10030 | 30090 | 0 | 0 | 0 | 0 | 10030 | 0 | 3 | 10030 | 30090 | 2 | 10030 | 20060 | 3 | 1 | 30090 | 10030
2520 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)Hire Charges for TATA 407(Dankuni to Cossipore) | TRIP | 3 | 5900 | 17700 | 0 | 0 | 0 | 0 | 5900 | 0 | 3 | 5900 | 17700 | 3 | 5900 | 17700 | 3 | 0 | 17700 | 0
2521 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)RAJARHAT TO COSSIPORE (407) | NOS | 10 | 4484 | 44840 | 0 | 0 | 0 | 1 | 4484 | 4484 | 10 | 4484 | 44840 | 5 | 4484 | 22420 | 9 | 5 | 40356 | 22420
2522 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)RAJARHAT TO COSSIPORE (TATA ACE) | NOS | 8 | 2596 | 20768 | 0 | 0 | 0 | 1 | 2596 | 2596 | 8 | 2596 | 20768 | 0 | 0 | 0 | 7 | 8 | 18172 | 20768
2523 | INFRA. SITE EXP. - Freight Charges | 10 | Started | Labour | (L)ROAD ROLLER | LS | 1 | 8850 | 8850 | 0 | 0 | 0 | 0 | 8850 | 0 | 1 | 8850 | 8850 | 1 | 8850 | 8850 | 1 | 0 | 8850 | 0
2524 | INFRA. SITE EXP. - Freight Charges for Trailor | 0 | Started | Labour | (L)TRAILER FOR PORTA CABIN FROM BAIDYABATI TO AMRITAYA | NOS | 4 | 21240 | 84960 | 0 | 0 | 0 | 0 | 21240 | 0 | 4 | 20160 | 80640 | 4 | 20160 | 80640 | 4 | 0 | 84960 | 4320
2525 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)10/15/20 MM PLASTERING | SQM | 25 | 150 | 3750 | 0 | 0 | 0 | 3 | 150 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25 | 3300 | 3750
2526 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)12 MM DIA TMT STAIGHTING, CUTTING, BENDING & BINDING | MT | 2.81 | 9735 | 27355.35 | 0 | 0 | 0 | 0 | 9735 | 0 | 1.599 | 5250 | 8394.75 | 1.599 | 5250 | 8394.75 | 2.81 | 1.211 | 27355.35 | 18960.6
2527 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)16 MM DIA TMT STRAIGHTING, CUTTING, BENDING & BINDING | MT | 0.6 | 8250 | 4950 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.591 | 5250 | 3102.75 | 0.591 | 5250 | 3102.75 | 0.6 | 0.009 | 4950 | 1847.25
2528 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)250/230/200 MM BRICK WORK | CUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2529 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)375 MM / 250 MM / 200 MM TH. BRICK WORK | CUM | 12 | 700 | 8400 | 0 | 0 | 0 | 1 | 700 | 700 | 7.065 | 700 | 4945.5 | 7.065 | 700 | 4945.5 | 11 | 4.935 | 7700 | 3454.5
2530 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)8 MM DIA TMT CUTTING, BENDING, BINDING | MT | 0.65 | 8250 | 5362.5 | 0 | 0 | 0 | 0 | 8250 | 0 | 0.612 | 5250 | 3213 | 0.612 | 5250 | 3213 | 0.65 | 0.038 | 5362.5 | 2149.5
2531 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 112 | 141.6 | 15859.2 | 0 | 0 | 0 | 11 | 141.6 | 1557.6 | 111.78 | 125 | 13972.5 | 111.78 | 125 | 13972.5 | 101 | 0.22 | 14301.6 | 1886.7
2532 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)BED PREPARATION/ EARTH DRESSING | SQM | 75.9 | 82.6 | 6269.34 | 0 | 0 | 0 | 8 | 82.6 | 660.8 | 48.18 | 75 | 3613.5 | 48.18 | 75 | 3613.5 | 67.9 | 27.72 | 5608.54 | 2655.84
2533 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 70 | 50 | 3500 | 0 | 0 | 0 | 7 | 50 | 350 | 48.529 | 55 | 2669.095 | 48.529 | 55 | 2669.1 | 63 | 21.471 | 3150 | 830.9
2534 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)DISPOSAL OF EARTH WITHIN PROJECT SITE, MORE THAN 50'0" LEAD | CUM | 180 | 90 | 16200 | 0 | 0 | 0 | 18 | 90 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 180 | 14580 | 16200
2535 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)EARTH WORK IN EXCAVATION MECHANICALLY UPTO 3M FROM EGL | CUM | 235 | 188.8 | 44368 | 0 | 0 | 0 | 24 | 188.8 | 4531.2 | 116.6 | 160 | 18656 | 116.6 | 160 | 18656 | 211 | 118.4 | 39836.8 | 25712
2536 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)L/C for Mixing and Pouring M-25 Grade Concrete | CUM | 6 | 750 | 4500 | 0 | 0 | 0 | 1 | 750 | 750 | 4.38 | 885 | 3876.3 | 4.38 | 750 | 3285 | 5 | 1.62 | 3750 | 1215
2537 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MANUAL EXCAVATION | CUM | 40 | 206.5 | 8260 | 0 | 0 | 0 | 4 | 206.5 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 40 | 7434 | 8260
2538 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MANUAL SHIFTING OF BRICKS | NOS | 2695 | 1.18 | 3180.1 | 0 | 0 | 0 | 270 | 1.18 | 318.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2425 | 2695 | 2861.5 | 3180.1
2539 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MANUAL SHIFTING OF SAND IN BAGS | NOS | 1060.94 | 2.5 | 2652.35 | 0 | 0 | 0 | 106 | 2.5 | 265 | 520 | 2.5 | 1300 | 520 | 2.5 | 1300 | 954.94 | 540.94 | 2387.35 | 1352.35
2540 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MANUAL SHIFTING OF STONECHIP IN BAGS | NOS | 1698.36 | 2.5 | 4245.9 | 0 | 0 | 0 | 170 | 2.5 | 425 | 810 | 2.5 | 2025 | 810 | 2.5 | 2025 | 1528.36 | 888.36 | 3820.9 | 2220.9
2541 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MIXING & POURING OF CONCRETE M-25 , SLAB | CUM | 17.2 | 885 | 15222 | 0 | 0 | 0 | 2 | 885 | 1770 | 15.979 | 750 | 11984.25 | 15.979 | 750 | 11984.25 | 15.2 | 1.221 | 13452 | 3237.75
2542 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 13.42 | 700 | 9394 | 0 | 0 | 0 | 1 | 700 | 700 | 12.125 | 750 | 9093.75 | 12.125 | 750 | 9093.75 | 12.42 | 1.295 | 8694 | 300.25
2543 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)MIXING & POURING OF RCC M- 25 FOR WALL CASTING | CUM | 26.5 | 1062 | 28143 | 0 | 0 | 0 | 3 | 1062 | 3186 | 3.466 | 1000 | 3466 | 3.466 | 1000 | 3466 | 23.5 | 23.034 | 24957 | 24677
2544 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING & DE SHUTTERING. | RMT | 55 | 64.9 | 3569.5 | 0 | 0 | 0 | 6 | 64.9 | 389.4 | 51.28 | 56 | 2871.68 | 51.28 | 56 | 2871.68 | 49 | 3.72 | 3180.1 | 697.82
2545 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 172 | 295 | 50740 | 0 | 0 | 0 | 17 | 295 | 5015 | 98.08 | 257.5 | 25255.6 | 98.08 | 257.5 | 25255.6 | 155 | 73.92 | 45725 | 25484.4
2546 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)POCKET MAKING400 X 125X 300 | NOS | 16 | 472 | 7552 | 0 | 0 | 0 | 2 | 472 | 944 | 16 | 400 | 6400 | 16 | 400 | 6400 | 14 | 0 | 6608 | 1152
2547 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)SKILLED MASON (12 HRS) | NOS | 20 | 675 | 13500 | 0 | 0 | 0 | 2 | 675 | 1350 | 7.166 | 750 | 5374.5 | 7.166 | 750 | 5374.5 | 18 | 12.834 | 12150 | 8125.5
2548 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)UNSKILLED LABOUR (12 HRS) | NOS | 50 | 525 | 26250 | 0 | 0 | 0 | 5 | 525 | 2625 | 21.253 | 535 | 11370.355 | 21.253 | 535 | 11370.36 | 45 | 28.747 | 23625 | 14879.64
2549 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Labour | (L)VAPOUR BARRIER | SQM | 96.529 | 82.6 | 7973.3 | 0 | 0 | 0 | 10 | 82.6 | 826 | 95.969 | 50 | 4798.45 | 95.969 | 50 | 4798.45 | 86.529 | 0.56 | 7147.295 | 3174.8454
2550 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)1-1/2 NAIL | KG | 18.92 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.92 | 18.92 | 0 | 0
2551 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)1.5" NAIL | KG | 16.182 | 100 | 1618.2 | 0 | 0 | 0 | 2 | 100 | 200 | 0 | 0 | 0 | 10.7 | 76.88 | 822.6 | 14.182 | 5.482 | 1418.2 | 795.6
2552 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)10 ' G1 EARTHING PIPE | NOS | 2 | 1333.4 | 2666.8 | 2 | 1333.4 | 2666.8 | 0 | 1333.4 | 0 | 2 | 1461.64 | 2923.28 | 2 | 1441.14 | 2882.27 | 2 | 0 | 2666.8 | -215.47
2553 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 28.3 | 1770 | 50091 | 12.81 | 1770 | 22673.7 | 3 | 1770 | 5310 | 12.81 | 1522.5 | 19503.2263 | 12.724 | 1486.93 | 18919.72 | 25.3 | 15.576 | 44781 | 31171.28
2554 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)12 MM DIA TMT | MT | 2.9 | 54500 | 158050 | 1.61 | 54500 | 87745 | 0 | 54500 | 0 | 1.61 | 55755 | 89765.55 | 1.61 | 57100.09 | 91931.14 | 2.9 | 1.29 | 158050 | 66118.86
2555 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)16 MM DIA TMT | MT | 0.62 | 54500 | 33790 | 0.59 | 54500 | 32155 | 0 | 54500 | 0 | 0.59 | 55755.01 | 32895.4539 | 0.59 | 55599.19 | 32803.52 | 0.62 | 0.03 | 33790 | 986.48
2556 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)2.5 SQ.MM COPPER WIRE (GREEN, 90 MTR) | COIL | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 0 | 3540 | 0 | 1 | 2680.06 | 2680.06 | 1 | 2642.46 | 2642.46 | 1 | 0 | 3540 | 897.54
2557 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 39.65 | 1750 | 69387.5 | 23.66 | 1750 | 41405 | 4 | 1750 | 7000 | 23.66 | 2050 | 48503 | 35.089 | 2058.6 | 72234.3 | 35.65 | 4.561 | 62387.5 | -2846.8
2558 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)22 GAUGE BINDING WIRE | KG | 28.54 | 55.6 | 1586.82 | 0 | 0 | 0 | 3 | 55.6 | 166.8 | 0 | 0 | 0 | 44 | 81.37 | 3580.43 | 25.54 | -15.46 | 1420.024 | -1993.606
2559 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)25 MM PVC PIPE | NOS | 25 | 82.6 | 2065 | 25 | 82.6 | 2065 | 3 | 82.6 | 247.8 | 25 | 84.45 | 2111.25 | 25 | 83.27 | 2081.64 | 22 | 0 | 1817.2 | -16.64
2560 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 4167 | 10 | 41670 | 4167 | 10 | 41670 | 417 | 10 | 4170 | 4167 | 9.5 | 39586.5 | 3284 | 10.11 | 33214.38 | 3750 | 883 | 37500 | 8455.62
2561 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)3" NAIL | KG | 13.24 | 51 | 675.24 | 0 | 0 | 0 | 1 | 51 | 51 | 0 | 0 | 0 | 11.3 | 74.06 | 836.92 | 12.24 | 1.94 | 624.24 | -161.68
2562 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)300 MM X 300 MM C.I COVER | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 536.9 | 1073.8 | 1 | -1 | 0 | -1073.8
2563 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)4" NAIL | KG | 13.24 | 51 | 675.24 | 7 | 51 | 357 | 1 | 51 | 51 | 7 | 70.8 | 495.6 | 0 | 0 | 0 | 12.24 | 13.24 | 624.24 | 675.24
2564 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)8 MM DIA TMT | MT | 0.44 | 56000.01 | 24640 | 0.44 | 56000.01 | 24640 | 0 | 56000.01 | 0 | 0.44 | 57525 | 25311 | 0.44 | 57934.3 | 25491.09 | 0.44 | 0 | 24640.004 | -851.0856
2565 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)CYBERPOWER 1 KVA UPS | NOS | 1 | 4873.4 | 4873.4 | 1 | 4873.4 | 4873.4 | 0 | 4873.4 | 0 | 1 | 5015 | 5015 | 1 | 5015 | 5015 | 1 | 0 | 4873.4 | -141.6
2566 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)Dot Matrix Printer (W.Bridge) | NOS | 1 | 13806 | 13806 | 1 | 13806 | 13806 | 0 | 13806 | 0 | 1 | 13806 | 13806 | 1 | 13806 | 13806 | 1 | 0 | 13806 | 0
2567 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)GP-2 Grout Cement (FOSROC) | BAG | 16 | 424.8 | 6796.8 | 16 | 424.8 | 6796.8 | 2 | 424.8 | 849.6 | 16 | 553.13 | 8850.08 | 16 | 536.22 | 8579.54 | 14 | 0 | 5947.2 | -1782.74
2568 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 93.16 | 36.58 | 3407.79 | 42.16 | 36.58 | 1542.21 | 9 | 36.58 | 329.22 | 42.16 | 53.1 | 2238.696 | 44.75 | 53.67 | 2401.68 | 84.16 | 48.41 | 3078.573 | 1006.1128
2569 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)LOAD CELL CABLE 10 GA 16 GAUGE | MTR | 40 | 177 | 7080 | 40 | 177 | 7080 | 4 | 177 | 708 | 40 | 180.54 | 7221.6 | 40 | 179.99 | 7199.65 | 36 | 0 | 6372 | -119.65
2570 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)M.C. SAND | MT | 42.5 | 1711.5 | 72738.75 | 0 | 0 | 0 | 4 | 1711.5 | 6846 | 0 | 0 | 0 | 35.699 | 1689.98 | 60330.75 | 38.5 | 6.801 | 65892.75 | 12408
2571 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 2695 | 11 | 29645 | 2580 | 11 | 28380 | 270 | 11 | 2970 | 2580 | 9 | 23220 | 1600 | 9 | 14400 | 2425 | 1095 | 26675 | 15245
2572 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)PLY SHUTTERING OIL | LTR | 43 | 47.2 | 2029.6 | 31 | 47.2 | 1463.2 | 4 | 47.2 | 188.8 | 31 | 124.36 | 3855.06 | 10 | 143.22 | 1432.23 | 39 | 33 | 1840.8 | 597.37
2573 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 10.72 | 110 | 1179.2 | 10.72 | 110 | 1179.2 | 1 | 110 | 110 | 10.72 | 141.6 | 1517.9531 | 21.5 | 141.6 | 3044.4 | 9.72 | -10.78 | 1069.2 | -1865.2
2574 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)PPC CEMENT | BAG | 371 | 283.59 | 105211.89 | 271 | 283.59 | 76852.89 | 37 | 283.59 | 10492.83 | 271 | 297.68 | 80670.2848 | 271 | 324.38 | 87907.08 | 334 | 100 | 94719.06 | 17304.81
2575 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)RMC M-25 GRADE | CUM | 1.5 | 7257 | 10885.5 | 1.5 | 7257 | 10885.5 | 0 | 7257 | 0 | 1.5 | 7199.99 | 10799.9913 | 1.5 | 7300 | 10950 | 1.5 | 0 | 10885.5 | -64.5
2576 | INFRA. SITE EXP. - Weighment Briedge Civil | 10 | Started | Material | (M)SHUTTERING GREASE | KG | 17.8 | 78 | 1388.4 | 5 | 78 | 390 | 2 | 78 | 156 | 5 | 155.76 | 778.8 | 17.8 | 155.76 | 2772.53 | 15.8 | 0 | 1232.4 | -1384.13
2577 | INFRA. SITE EXP. - Weighment Briedge Anti Termite | 0 | Tentative | Labour | (L)ANTI- TERMITE Imidacloprid 30.50 SC | SQM | 70 | 64.9 | 4543 | 0 | 0 | 0 | 0 | 64.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 4543 | 4543
2578 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Labour | (L)SKILLED LABOUR | NOS | 36 | 796.5 | 28674 | 0 | 0 | 0 | 4 | 796.5 | 3186 | 26 | 675 | 17550 | 26 | 749.77 | 19494 | 32 | 10 | 25488 | 9180
2579 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Labour | (L)UNSKILLED LABOUR | NOS | 1215.32 | 525 | 638043 | 0 | 0 | 0 | 122 | 525 | 64050 | 1215.32 | 525 | 638043 | 1215.32 | 564.05 | 685497.12 | 1093.32 | 0 | 573993 | -47454.12
2580 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)1.5" NAIL | KG | 0.3 | 100 | 30 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 7.8 | 78.46 | 611.99 | 0.3 | -7.5 | 30 | -581.99
2581 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 0.568 | 1770 | 1005.36 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0.568 | 1574.63 | 894.39 | 0.568 | 0 | 1005.36 | 110.97
2582 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 0.123 | 1750 | 215.25 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0.123 | 2000 | 246 | 0.123 | 0 | 215.25 | -30.75
2583 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 2147 | 10 | 21470 | 0 | 0 | 0 | 215 | 10 | 2150 | 0 | 0 | 0 | 3647 | 9.9 | 36095.38 | 1932 | -1500 | 19320 | -14625.38
2584 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)3" NAIL | KG | 2.5 | 51 | 127.5 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 2.5 | 73.55 | 183.87 | 2.5 | 0 | 127.5 | -56.37
2585 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)GLOVES | PAIR | 11 | 42 | 462 | 0 | 0 | 0 | 1 | 42 | 42 | 0 | 0 | 0 | 26 | 37.16 | 966.1 | 10 | -15 | 420 | -504.1
2586 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)M.C. SAND | MT | 4.952 | 1711.5 | 8475.35 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 5.062 | 1653.39 | 8369.45 | 4.952 | -0.11 | 8475.348 | 105.898
2587 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)PPC CEMENT | BAG | 9 | 283.59 | 2552.31 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 11 | 314.25 | 3456.76 | 8 | -2 | 2268.72 | -904.45
2588 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)PSC CEMENT | BAG | 22 | 307.2 | 6758.4 | 0 | 0 | 0 | 2 | 307.2 | 614.4 | 0 | 0 | 0 | 22 | 308 | 6775.89 | 20 | 0 | 6144 | -17.49
2589 | INFRA. SITE EXP. - Unskilled Labour | 10 | Started | Material | (M)SPLENDOR GLOVES | PAIR | 2 | 59 | 118 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 21 | 64.57 | 1355.9 | 2 | -19 | 118 | -1237.9
2590 | INFRA. SITE EXP. - Transfer to O126 | 10 | Started | Material | (M)M.C. SAND | MT | 1 | 1711.5 | 1711.5 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 1 | 1690.01 | 1690.01 | 1 | 0 | 1711.5 | 21.49
2591 | INFRA. SITE EXP. - Transfer to O126 | 10 | Started | Material | (M)PPC CEMENT | BAG | 10 | 283.59 | 2835.9 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 10 | 306.18 | 3061.82 | 9 | 0 | 2552.31 | -225.92
2592 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)125 KVA SILENT D.G. SET HIRE | SET | 1 | 59000 | 59000 | 0 | 0 | 0 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 59000 | 0 | INFRA
2593 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)HIRE CH. FOR DUMPER | DAYS | 10 | 11210 | 112100 | 0 | 0 | 0 | 1 | 11210 | 11210 | 10 | 8850 | 88500 | 6 | 8850 | 53100 | 9 | 4 | 100890 | 59000 | INFRA
2594 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)Hire Ch.for Pocklain (8hrs Shift) | DAYS | 5 | 14160 | 70800 | 0 | 0 | 0 | 1 | 14160 | 14160 | 5 | 14160 | 70800 | 5 | 14160 | 70800 | 4 | 0 | 56640 | 0 | INFRA
2595 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)Hire Charges for 3HP Submersible Pump | MONTH | 3 | 4000 | 12000 | 0 | 0 | 0 | 0 | 4000 | 0 | 3 | 4000 | 12000 | 2 | 4000 | 8000 | 3 | 1 | 12000 | 4000 | INFRA
2596 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)Hiring Charges for JCB on Daily Basis (8hrs Shift) | DAYS | 245 | 7552 | 1850240 | 0 | 0 | 0 | 25 | 7552 | 188800 | 245 | 7552 | 1850240 | 158 | 7552 | 1193216 | 220 | 87 | 1661440 | 657024 | INFRA
2597 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)HYDRA (FOR 4 HOURS) | DAYS | 171 | 3700 | 632700 | 0 | 0 | 0 | 17 | 3700 | 62900 | 171 | 4366 | 746586 | 65 | 4366 | 283790 | 154 | 106 | 569800 | 348910 | INFRA
2598 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)HYDRA (FOR 8 HOURS) | DAYS | 240 | 4500 | 1080000 | 0 | 0 | 0 | 24 | 4500 | 108000 | 240 | 5310 | 1274400 | 105 | 5310 | 557550 | 216 | 135 | 972000 | 522450 | INFRA
2599 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)Monthly Hire Ch. for JCB with Operator & Fuel | MONTH | 5 | 194700 | 973500 | 0 | 0 | 0 | 1 | 194700 | 194700 | 5 | 194700 | 973500 | 4 | 194700 | 778800 | 4 | 1 | 778800 | 194700 | INFRA
2600 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)Operator Hiring Charges (8 hours shift) | MAN/DAY | 245 | 472 | 115640 | 0 | 0 | 0 | 25 | 472 | 11800 | 245 | 472 | 115640 | 158 | 472 | 74576 | 220 | 87 | 103840 | 41064 | INFRA
2601 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)POCKLAIN TRANSPORTATION CHARGE ONE SIDE | LS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 1 | 17110 | 17110 | 1 | 17110 | 17110 | 1 | 0 | 17700 | 590 | INFRA
2602 | INFRA. SITE EXP. - Equipment and Machine Hire | 10 | Started | Labour | (L)TRANSPORTATION CHARGES | NOS | 2 | 25.96 | 51.92 | 0 | 0 | 0 | 0 | 25.96 | 0 | 2 | 6490 | 12980 | 2 | 6490 | 12980 | 2 | 0 | 51.92 | -12928.08 | INFRA
2603 | INFRA. SITE EXP. - Batching Plant Rent | 0 | Started | Labour | (L)Rent for Batching Plant | Monthly | 12 | 51330 | 615960 | 0 | 0 | 0 | 0 | 51330 | 0 | 12 | 51330 | 615960 | 8 | 51330 | 410640 | 12 | 4 | 615960 | 205320 | INFRA | ABOVE ROOF
2604 | INFRA. SITE EXP. - Materials Transfer to Avaasa | 0 | Started | Material | (M)10 MM DIA TMT | MT | 0.499 | 55000 | 27445 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0.16 | 58310.06 | 9329.61 | 0.499 | 0.339 | 27445 | 18115.39
2605 | INFRA. SITE EXP. - Materials Transfer to Avaasa | 0 | Started | Material | (M)12 MM DIA TMT | MT | 0.291 | 54500 | 15859.5 | 0 | 0 | 0 | 0 | 54500 | 0 | 0 | 0 | 0 | 0.291 | 55781 | 16232.27 | 0.291 | 0 | 15859.5 | -372.77
2606 | INFRA. SITE EXP. - Materials Transfer to Avaasa | 0 | Started | Material | (M)8 MM DIA TMT | MT | 0.303 | 56000.01 | 16968 | 0 | 0 | 0 | 0 | 56000.01 | 0 | 0 | 0 | 0 | 0.303 | 59505.08 | 18030.04 | 0.303 | 0 | 16968.003 | -1062.037
2607 | INFRA. SITE EXP. - Materials Transfer to Avaasa | 0 | Started | Material | (M)PPC CEMENT | BAG | 130 | 283.59 | 36866.7 | 0 | 0 | 0 | 0 | 283.59 | 0 | 0 | 0 | 0 | 280 | 286.63 | 80255.72 | 130 | -150 | 36866.7 | -43389.02
2608 | INFRA. SITE EXP. - Skilled and Unskilled Labour | 10 | Started | Labour | (L)SKILLED LABOUR | NOS | 115 | 796.5 | 91597.5 | 0 | 0 | 0 | 12 | 796.5 | 9558 | 109.07 | 717.26 | 78231.78 | 89.07 | 709.91 | 63231.78 | 103 | 25.93 | 82039.5 | 28365.72
2609 | INFRA. SITE EXP. - Skilled and Unskilled Labour | 10 | Started | Labour | (L)UNSKILLED LABOUR | NOS | 2912 | 525 | 1528800 | 0 | 0 | 0 | 291 | 525 | 152775 | 2669.423 | 548.7 | 1464707.965 | 2127.423 | 540.72 | 1150347.97 | 2621 | 784.577 | 1376025 | 378452.03
2610 | INFRA. SITE EXP. - Skilled and Unskilled Labour | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 0.54 | 1750 | 945 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0.54 | 2000 | 1080 | 0.54 | 0 | 945 | -135
2611 | INFRA. SITE EXP. - Skilled and Unskilled Labour | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 50 | 10 | 500 | 0 | 0 | 0 | 5 | 10 | 50 | 0 | 0 | 0 | 50 | 9.75 | 487.29 | 45 | 0 | 450 | 12.71
2612 | INFRA. SITE EXP. - Skilled and Unskilled Labour | 10 | Started | Material | (M)M.C. SAND | MT | 0.8 | 1711.5 | 1369.2 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0.8 | 1652.58 | 1322.06 | 0.8 | 0 | 1369.2 | 47.14
2613 | INFRA. SITE EXP. - Skilled and Unskilled Labour | 10 | Started | Material | (M)PPC CEMENT | BAG | 6 | 283.59 | 1701.54 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 6 | 307.76 | 1846.55 | 5 | 0 | 1417.95 | -145.01
2614 | CONSULTANT - Micro Climate Charges | 10 | Started | Labour | (L)Micro Climate Analysis | LS | 1 | 106200 | 106200 | 0 | 0 | 0 | 0 | 106200 | 0 | 1 | 106200 | 106200 | 1 | 106200 | 106200 | 1 | 0 | 106200 | 0
2615 | CONSULTANT - Environmental Clearance | 10 | Started | Labour | (L)SUBMISSION OF FILLED IN FORM 1 AND FORM 1A AS PER NEW MOEF | LS | 1 | 650000 | 650000 | 0 | 0 | 0 | 0 | 650000 | 0 | 1 | 767000 | 767000 | 1 | 767000 | 767000 | 1 | 0 | 650000 | -117000
2616 | CONSULTANT - Consultancy Charges | 10 | Started | Labour | (L)CALIBRATION & MAINTANACE CUBE TESTING MACHINE | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 10030 | 10030 | 1 | 10030 | 10030 | 1 | 0 | 1 | -10029
2617 | CONSULTANT - Consultancy Charges | 10 | Started | Labour | (L)Fees for Structural Review | NOS | 4 | 236000 | 944000 | 0 | 0 | 0 | 0 | 236000 | 0 | 2 | 236000 | 472000 | 1.5 | 236000 | 354000 | 4 | 2.5 | 944000 | 590000
2618 | CONSULTANT - Consultancy Charges | 10 | Started | Labour | (L)FIRE CONSULTANCY CHARGE | NOS | 12 | 53100 | 637200 | 0 | 0 | 0 | 1 | 53100 | 53100 | 12 | 110133.33 | 1321600 | 12 | 110133.33 | 1321600 | 11 | 0 | 584100 | -684400
2619 | CONSULTANT - Consultancy Charges | 10 | Started | Labour | (L)Landscape Design Consultancy | LS | 1 | 767000 | 767000 | 0 | 0 | 0 | 0 | 767000 | 0 | 1 | 767000 | 767000 | 0 | 0 | 0 | 1 | 1 | 767000 | 767000
2620 | CONSULTANT - Consultancy Charges | 10 | Started | Labour | (L)Professional Charges for Arch. Consultancy at Amritaya | PER/SQFT | 493451.61 | 25.96 | 12810003.8 | 0 | 0 | 0 | 49345 | 25.96 | 1280996.2 | 493451.61 | 25.96 | 12810003.8 | 246725.805 | 25.96 | 6405001.91 | 444106.61 | 246725.805 | 11529007.596 | 6405001.8856
2621 | CONSULTANT - Structural Drawings | 10 | Started | Labour | (L)structural design | NOS | 438000 | 5.32 | 2330160 | 0 | 0 | 0 | 43800 | 5.32 | 233016 | 438000 | 5.31 | 2325780 | 175200 | 5.31 | 930312 | 394200 | 262800 | 2097144 | 1399848
2622 | CONSULTANT - Tower Pressurisation | 10 | Started | Labour | (L)FIRE TOWER PRESSURISATION | NOS | 4 | 17700 | 70800 | 0 | 0 | 0 | 0 | 17700 | 0 | 4 | 17700 | 70800 | 3.6 | 17700 | 63720 | 4 | 0.4 | 70800 | 7080
2623 | CONSULTANT - Professional Charges | 10 | Started | Labour | (L)Prepare Half-yearly compliance | LS | 1 | 129800 | 129800 | 0 | 0 | 0 | 0 | 129800 | 0 | 1 | 129800 | 129800 | 1 | 129800 | 129800 | 1 | 0 | 129800 | 0
2624 | CONSULTANT - Professional Charges | 10 | Started | Labour | (L)Prof. Ch. for certifying means of funds & exp. at Amritaya | LS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 1 | 15000 | 15000 | 0 | 0 | 0 | 1 | 1 | 17700 | 17700
2625 | CONSULTANT - Professional Charges | 10 | Started | Labour | (L)Prof. Ch. for GST & A/c's related services | LS | 1 | 59000 | 59000 | 0 | 0 | 0 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 59000 | 0
2626 | CONSULTANT - Professional Charges | 10 | Started | Labour | (L)Regular Half-yearly compliance | LS | 1 | 129800 | 129800 | 0 | 0 | 0 | 0 | 129800 | 0 | 1 | 129800 | 129800 | 1 | 129800 | 129800 | 1 | 0 | 129800 | 0
2627 | CONSULTANT - Survey Consultancy | 10 | Started | Labour | (L)Hire Charges of Total Station | Monthly | 1 | 20060 | 20060 | 0 | 0 | 0 | 0 | 20060 | 0 | 1 | 20060 | 20060 | 1 | 20060 | 20060 | 1 | 0 | 20060 | 0
2628 | CONSULTANT - Survey Consultancy | 10 | Started | Labour | (L)L/C for Survey Helper | MAN/DAY | 14 | 708 | 9912 | 0 | 0 | 0 | 1 | 708 | 708 | 14 | 708 | 9912 | 14 | 708 | 9912 | 13 | 0 | 9204 | 0
2629 | CONSULTANT - Survey Consultancy | 10 | Started | Labour | (L)LEVELLING, BLOCK LAY OUT, GRID LINE ETC. | NOS | 80 | 3200 | 256000 | 0 | 0 | 0 | 8 | 3200 | 25600 | 39 | 3262.58 | 127240.7 | 39 | 3262.58 | 127240.7 | 72 | 41 | 230400 | 128759.3
2630 | CONSULTANT - EGL Levelling Consultancy | 10 | Started | Labour | (L)SITE EXISTING G.L & ROAD LEVEL AT VARIOUS POINT | LS | 1 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 1 | 6000 | 6000 | 1 | 6000 | 6000 | 1 | 0 | 6000 | 0
2631 | CONSULTANT - QC WORK | 10 | Started | Labour | (L)Professional Charges for QA/QC Audit | MAN/DAY | 96 | 5900 | 566400 | 0 | 0 | 0 | 10 | 5900 | 59000 | 96 | 5900 | 566400 | 8 | 5900 | 47200 | 86 | 88 | 507400 | 519200
2632 | CONSULTANT - QC WORK | 10 | Started | Material | (M)10 mm SIEVE | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 1014.06 | 1014.06 | 1 | 994.3 | 994.3 | 1 | 0 | 826 | -168.3
2633 | CONSULTANT - QC WORK | 10 | Started | Material | (M)150 MICRON SIEVE | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 1014.06 | 1014.06 | 1 | 994.3 | 994.3 | 1 | 0 | 826 | -168.3
2634 | CONSULTANT - QC WORK | 10 | Started | Material | (M)2.36 mm SIEVE | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 1014.06 | 1014.06 | 1 | 994.3 | 994.3 | 1 | 0 | 826 | -168.3
2635 | CONSULTANT - QC WORK | 10 | Started | Material | (M)300 MICRON SIEVE | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 1014.06 | 1014.06 | 1 | 994.3 | 994.3 | 1 | 0 | 826 | -168.3
2636 | CONSULTANT - QC WORK | 10 | Started | Material | (M)4.75 mm SIEVE | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 1014.06 | 1014.06 | 1 | 994.3 | 994.3 | 1 | 0 | 826 | -168.3
2637 | CONSULTANT - QC WORK | 10 | Started | Material | (M)600 MICRON SIEVE | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 1014.06 | 1014.06 | 1 | 994.3 | 994.3 | 1 | 0 | 826 | -168.3
2638 | CONSULTANT - QC WORK | 10 | Started | Material | (M)LID AND PAN FOR G.I FRAME 18" | NOS | 1 | 1003 | 1003 | 1 | 1003 | 1003 | 0 | 1003 | 0 | 1 | 944 | 944 | 1 | 923.35 | 923.35 | 1 | 0 | 1003 | 79.65
2639 | CONSULTANT - QC WORK | 10 | Started | Material | (M)Plastic graduated Measuring Cylinder | SET | 2 | 59 | 118 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 118 | 118
2640 | CONSULTANT - QC WORK | 10 | Started | Material | (M)Plastic graduated Measuring Cylinder 10 ML | SETS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 2 | 67.6 | 135.2 | 2 | 66.29 | 132.57 | 2 | 0 | 118 | -14.57
2641 | CONSULTANT - QC WORK | 10 | Started | Material | (M)Plastic graduated Measuring Cylinder 20 ML | SETS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 2 | 67.6 | 135.2 | 2 | 66.29 | 132.57 | 2 | 0 | 118 | -14.57
2642 | CONSULTANT - QC WORK | 10 | Started | Material | (M)Plastic graduated Measuring Cylinder 50 ML | SETS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 2 | 67.6 | 135.2 | 2 | 66.29 | 132.57 | 2 | 0 | 118 | -14.57
2643 | CONSULTANT - QC WORK | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 12.5 MM | NOS | 1 | 885 | 885 | 1 | 885 | 885 | 0 | 885 | 0 | 1 | 885 | 885 | 1 | 885 | 885 | 1 | 0 | 885 | 0
2644 | CONSULTANT - QC WORK | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 2.36 MM | NOS | 1 | 944 | 944 | 1 | 944 | 944 | 0 | 944 | 0 | 1 | 944 | 944 | 1 | 944 | 944 | 1 | 0 | 944 | 0
2645 | CONSULTANT - QC WORK | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 20 MM | NOS | 1 | 885 | 885 | 1 | 885 | 885 | 0 | 885 | 0 | 1 | 885 | 885 | 1 | 885 | 885 | 1 | 0 | 885 | 0
2646 | CONSULTANT - QC WORK | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 4.75 MM | NOS | 1 | 885 | 885 | 1 | 885 | 885 | 0 | 885 | 0 | 1 | 885 | 885 | 1 | 885 | 885 | 1 | 0 | 885 | 0
2647 | CONSULTANT - QC WORK | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 40MM | NOS | 1 | 885 | 885 | 1 | 885 | 885 | 0 | 885 | 0 | 1 | 885 | 885 | 1 | 885 | 885 | 1 | 0 | 885 | 0
2648 | CONSULTANT - QC WORK | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE-10 MM | NOS | 1 | 979.4 | 979.4 | 1 | 979.4 | 979.4 | 0 | 979.4 | 0 | 1 | 885 | 885 | 1 | 899 | 899 | 1 | 0 | 979.4 | 80.4
2649 | CONSULTANT - Fire Consultancy | 10 | Started | Labour | (L)FIRE CONSULTANCY CHARGE | NOS | 2 | 53100 | 106200 | 0 | 0 | 0 | 0 | 53100 | 0 | 2 | 619045 | 1238090 | 1.4 | 568025.71 | 795236 | 2 | 0.6 | 106200 | -689036
2650 | CONSULTANT - Geo Technical Consultancy | 10 | Started | Labour | (L)Geo-Tech. Design & Dwg. of Shoring of RWHT/STP/UGR | LS | 1 | 247800 | 247800 | 0 | 0 | 0 | 0 | 247800 | 0 | 1 | 247800 | 247800 | 0 | 0 | 0 | 1 | 1 | 247800 | 247800
2651 | CONSULTANT - Geo Technical Consultancy | 10 | Started | Labour | (L)Meeting with Geo-Tech Consultant & ORBL | NOS | 3 | 21240 | 63720 | 0 | 0 | 0 | 0 | 21240 | 0 | 3 | 21240 | 63720 | 0 | 0 | 0 | 3 | 3 | 63720 | 63720
2652 | CONSULTANT - Geo Technical Consultancy | 10 | Started | Labour | (L)Meeting with IIEST Shibpur | NOS | 1 | 21240 | 21240 | 0 | 0 | 0 | 0 | 21240 | 0 | 1 | 21240 | 21240 | 1 | 21240 | 21240 | 1 | 0 | 21240 | 0
2653 | CONSULTANT - Geo Technical Consultancy | 10 | Started | Labour | (L)Site Visit by Geo-Tech. Consultant | NOS | 4 | 23600 | 94400 | 0 | 0 | 0 | 0 | 23600 | 0 | 4 | 23600 | 94400 | 1 | 23600 | 23600 | 4 | 3 | 94400 | 70800
2654 | CONSULTANT - Geo Technical Consultancy | 10 | Started | Labour | (L)Study of Soil Report & Initial Load Test data for test pile | LS | 5 | 21240 | 106200 | 0 | 0 | 0 | 1 | 21240 | 21240 | 5 | 36108 | 180540 | 4 | 39825 | 159300 | 4 | 1 | 84960 | -53100
2655 | CONSULTANT - Design Mix Charges | 10 | Started | Labour | (L)Design Mix of M-25 Gr. Free Flow (SCC) for Typical Floor | NOS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 17700 | 17700
2656 | CONSULTANT - PF Consultancy | 10 | Started | Labour | (L)Charges- PF,ESIC ,Labour | LS | 12 | 7080 | 84960 | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 12 | 7080 | 84960 | 0 | 0 | 0 | 11 | 12 | 77880 | 84960
2657 | CONSULTANT - Design Mix Charges | 0 | Tentative | Labour | (L)Design Mix charges of Pile | NOS | 1 | 14160 | 14160 | 0 | 0 | 0 | 0 | 14160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 14160 | 14160
2658 | CONSULTANT - Design Mix Charges | 0 | Tentative | Labour | (L)Design Mix Charges of Sub & Super Structure | NOS | 1 | 14160 | 14160 | 0 | 0 | 0 | 0 | 14160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 14160 | 14160
2659 | CONSULTANT - HR Training and Consultancy Charges | 0 | Started | Labour | (L)HR Training & Consulting | Monthly | 12 | 53100 | 637200 | 0 | 0 | 0 | 0 | 53100 | 0 | 12 | 53100 | 637200 | 6 | 53100 | 318600 | 12 | 6 | 637200 | 318600
2660 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)ACP BOARD | NOS | 1 | 53100 | 53100 | 0 | 0 | 0 | 0 | 53100 | 0 | 1 | 53100 | 53100 | 1 | 53100 | 53100 | 1 | 0 | 53100 | 0
2661 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Acrylic Dispenser | PCS | 3 | 896.8 | 2690.4 | 0 | 0 | 0 | 0 | 896.8 | 0 | 3 | 896.8 | 2690.4 | 3 | 896.8 | 2690.4 | 3 | 0 | 2690.4 | 0
2662 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Acrylic Stand | NOS | 2 | 767 | 1534 | 0 | 0 | 0 | 0 | 767 | 0 | 2 | 619.5 | 1239 | 2 | 619.5 | 1239 | 2 | 0 | 1534 | 295
2663 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Airport 1 No gate fcg Ultadanga | LS | 6 | 32000 | 192000 | 0 | 0 | 0 | 1 | 32000 | 32000 | 3 | 37760 | 113280 | 3 | 37760 | 113280 | 5 | 3 | 160000 | 78720
2664 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Airport 1 No gate ftf vip road | LS | 2 | 59000 | 118000 | 0 | 0 | 0 | 0 | 59000 | 0 | 0.9667 | 59000 | 57035.3 | 0.9667 | 59000 | 57035.3 | 2 | 1.0333 | 118000 | 60964.7
2665 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Airport 1 No gate Xing | DAYS | 330 | 1 | 330 | 0 | 0 | 0 | 33 | 1 | 33 | 211 | 1252.7 | 264319.55 | 211 | 1252.7 | 264319.59 | 297 | 119 | 297 | -263989.59
2666 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Airport 1 No. Gate Fcg Ultadanga | DAYS | 210 | 1258.66 | 264318.6 | 0 | 0 | 0 | 21 | 1258.66 | 26431.86 | 55 | 1258.67 | 69226.63 | 55 | 1258.67 | 69226.63 | 189 | 155 | 237886.74 | 195091.97
2667 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)B T Road facing shyambazar | LS | 1 | 47200 | 47200 | 0 | 0 | 0 | 0 | 47200 | 0 | 0.9666 | 47200 | 45623.52 | 0.9666 | 47200 | 45623.52 | 1 | 0.0334 | 47200 | 1576.48
2668 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)B T Road facing shyambazar. | DAYS | 240 | 1 | 240 | 0 | 0 | 0 | 24 | 1 | 24 | 210 | 1573.33 | 330399.93 | 210 | 1573.33 | 330399.93 | 216 | 30 | 216 | -330159.93
2669 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)B.T.Road at Bon Hooghly Crossing | DAYS | 180 | 1180 | 212400 | 0 | 0 | 0 | 18 | 1180 | 21240 | 120 | 1475 | 176999.97 | 120 | 1475 | 176999.97 | 162 | 60 | 191160 | 35400.03
2670 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)B.T.Road/ Lockgate Road Flyover xing | DAYS | 90 | 1377.06 | 123935.4 | 0 | 0 | 0 | 9 | 1377.06 | 12393.54 | 30 | 1376.67 | 41299.98 | 30 | 1376.67 | 41299.98 | 81 | 60 | 111541.86 | 82635.42
2671 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Back Black Flex FT | FT | 54712 | 12.98 | 710161.76 | 0 | 0 | 0 | 5471 | 12.98 | 71013.58 | 42442 | 12.91 | 548059.26 | 42442 | 12.91 | 548059.26 | 49241 | 12270 | 639148.18 | 162102.5
2672 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)back black flex making & mounting | FT | 3760 | 24.78 | 93172.8 | 0 | 0 | 0 | 376 | 24.78 | 9317.28 | 3280 | 14.71 | 48238.4 | 3280 | 14.71 | 48238.4 | 3384 | 480 | 83855.52 | 44934.4
2673 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Back-lit Flex | FT | 10375 | 23.6 | 244850 | 0 | 0 | 0 | 1038 | 23.6 | 24496.8 | 4182 | 26.16 | 109409.6 | 4182 | 26.16 | 109409.6 | 9337 | 6193 | 220353.2 | 135440.4
2674 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Bamboo Structure with materials | LS | 1 | 7080 | 7080 | 0 | 0 | 0 | 0 | 7080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7080 | 7080
2675 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Belghoria Flyover | LS | 1 | 35400 | 35400 | 0 | 0 | 0 | 0 | 35400 | 0 | 0.966 | 35400 | 34196.4 | 0.966 | 35400 | 34196.4 | 1 | 0.034 | 35400 | 1203.6
2676 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Belghoria Flyover. | DAYS | 120 | 1 | 120 | 0 | 0 | 0 | 12 | 1 | 12 | 105 | 1180 | 123900 | 105 | 1180 | 123900 | 108 | 15 | 108 | -123780
2677 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Birati Flyover | LS | 1 | 25960 | 25960 | 0 | 0 | 0 | 0 | 25960 | 0 | 1 | 25960 | 25960 | 1 | 25960 | 25960 | 1 | 0 | 25960 | 0
2678 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Birati Flyover. | MONTH | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 25960 | 77880 | 3 | 25960 | 77880 | 4 | 1 | 4 | -77876
2679 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Board dismantling at site | PCS | 2 | 531 | 1062 | 0 | 0 | 0 | 0 | 531 | 0 | 2 | 531 | 1062 | 2 | 531 | 1062 | 2 | 0 | 1062 | 0
2680 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd Sinthee More towards Tobin Rd. Pole Kiosk(No.23) | DAYS | 120 | 1447.86 | 173743.2 | 0 | 0 | 0 | 12 | 1447.86 | 17374.32 | 37 | 1447.46 | 53555.98 | 37 | 1447.46 | 53555.98 | 108 | 83 | 156368.88 | 120187.22
2681 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd Tobin Rd. Fcg. Shyambazaar | DAYS | 310 | 313.88 | 97302.8 | 0 | 0 | 0 | 31 | 313.88 | 9730.28 | 251 | 681.36 | 171020.78 | 251 | 681.36 | 171020.76 | 279 | 59 | 87572.52 | -73717.96
2682 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Ananya CCD Fcg Dunlop | LS | 1 | 23000 | 23000 | 0 | 0 | 0 | 0 | 23000 | 0 | 1 | 27140 | 27140 | 1 | 27140 | 27140 | 1 | 0 | 23000 | -4140
2683 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Ananya CCD Fcg Dunlop. | DAYS | 810 | 1 | 810 | 0 | 0 | 0 | 81 | 1 | 81 | 579.391 | 878.66 | 509090.5444 | 579.391 | 878.67 | 509090.6 | 729 | 230.609 | 729 | -508280.6
2684 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Ananya Fcg Shyambazaar. | DAYS | 180 | 1 | 180 | 0 | 0 | 0 | 18 | 1 | 18 | 104 | 3505.96 | 364619.78 | 104 | 3505.96 | 364619.78 | 162 | 76 | 162 | -364439.78
2685 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Ananya Feg Shyambazaar | LS | 1 | 90000 | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 1 | 106200 | 106200 | 1 | 106200 | 106200 | 1 | 0 | 90000 | -16200
2686 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Bonhoogly facing Dunlop | MONTH | 5.4 | 47200 | 254880 | 0 | 0 | 0 | 1 | 47200 | 47200 | 4.8 | 47200 | 226560 | 4.8 | 47200 | 226560 | 4.4 | 0.6 | 207680 | 28320
2687 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Chiria More | DAYS | 180 | 1572.94 | 283129.2 | 0 | 0 | 0 | 18 | 1572.94 | 28312.92 | 154.5 | 1344.21 | 207679.9785 | 154.5 | 1344.21 | 207679.98 | 162 | 25.5 | 254816.28 | 75449.22
2688 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Dunlop ISI Gate facing Shyambazar | MONTH | 3 | 9440 | 28320 | 0 | 0 | 0 | 0 | 9440 | 0 | 3 | 9440 | 28320 | 3 | 9440 | 28320 | 3 | 0 | 28320 | 0
2689 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Dunlop xing Fcg Sodepur | DAYS | 360 | 865.33 | 311518.8 | 0 | 0 | 0 | 36 | 865.33 | 31151.88 | 300 | 1313.73 | 394119.975 | 300 | 1313.73 | 394119.98 | 324 | 60 | 280366.92 | -82601.18
2690 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Paikpara facing Dunlop | MONTH | 3 | 41300 | 123900 | 0 | 0 | 0 | 0 | 41300 | 0 | 0.4 | 41300 | 16520 | 0.4 | 41300 | 16520 | 3 | 2.6 | 123900 | 107380
2691 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Rathtala Xing Fcg Dunlop | LS | 1 | 24000 | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | 28320 | 28320 | 1 | 28320 | 28320 | 1 | 0 | 24000 | -4320
2692 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Rathtala Xing Fcg Dunlop. | DAYS | 240 | 1 | 240 | 0 | 0 | 0 | 24 | 1 | 24 | 151 | 937.75 | 141599.87 | 151 | 937.75 | 141599.87 | 216 | 89 | 216 | -141359.87
2693 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Rathtala Xing Fcg Sodepur | DAYS | 120 | 47200 | 5664000 | 0 | 0 | 0 | 12 | 47200 | 566400 | 77 | 1573.33 | 121146.6641 | 77 | 1573.33 | 121146.66 | 108 | 43 | 5097600 | 5542853.34
2694 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Sinthee More Crossing facing Shyambazar | MONTH | 7 | 25960 | 181720 | 0 | 0 | 0 | 1 | 25960 | 25960 | 4 | 25960 | 103840 | 4 | 25960 | 103840 | 6 | 3 | 155760 | 77880
2695 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Sinthee More Fcg Dunlop. | DAYS | 420 | 1 | 420 | 0 | 0 | 0 | 42 | 1 | 42 | 207 | 2387.74 | 494262.339 | 207 | 2387.74 | 494262.34 | 378 | 213 | 378 | -493842.34
2696 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Rd. Sinthee More towards Tobin Rd | DAYS | 90 | 62.93 | 5663.7 | 0 | 0 | 0 | 9 | 62.93 | 566.37 | 60 | 1447.47 | 86847.96 | 60 | 1447.47 | 86847.96 | 81 | 30 | 5097.33 | -81184.26
2697 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)BT Road Chiriyamore Fcing Shyambazar | DAYS | 90 | 1455.33 | 130979.7 | 0 | 0 | 0 | 9 | 1455.33 | 13097.97 | 90 | 1455.33 | 130979.997 | 90 | 1455.33 | 130980 | 81 | 0 | 117881.73 | -0.3
2698 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Chiriyamore facing shyambazar | MONTH | 6 | 47200 | 283200 | 0 | 0 | 0 | 1 | 47200 | 47200 | 6 | 47200 | 283200 | 6 | 47200 | 283200 | 5 | 0 | 236000 | 0
2699 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Conveyance | LS | 1 | 354 | 354 | 0 | 0 | 0 | 0 | 354 | 0 | 1 | 354 | 354 | 1 | 354 | 354 | 1 | 0 | 354 | 0
2700 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)CR Avenue Central Fcg Shyambazaar | LS | 1 | 165000 | 165000 | 0 | 0 | 0 | 0 | 165000 | 0 | 1 | 194700 | 194700 | 1 | 194700 | 194700 | 1 | 0 | 165000 | -29700
2701 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)CR Avenue Central Fcg Shyambazaar. | DAYS | 240 | 1 | 240 | 0 | 0 | 0 | 24 | 1 | 24 | 151 | 6447.02 | 973499.98 | 151 | 6447.02 | 973499.98 | 216 | 89 | 216 | -973259.98
2702 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)CR Avenue mission row crossing esplanade | LS | 8 | 76000 | 608000 | 0 | 0 | 0 | 1 | 76000 | 76000 | 6.4667 | 76760.89 | 496389.66 | 6.4667 | 76760.89 | 496389.66 | 7 | 1.5333 | 532000 | 111610.34
2703 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)DELIVER & INSTALLATION CHARGES | NOS | 1 | 10030 | 10030 | 0 | 0 | 0 | 0 | 10030 | 0 | 1 | 10030 | 10030 | 1 | 10030 | 10030 | 1 | 0 | 10030 | 0
2704 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Disclaimer Vinyl change | NOS | 1 | 295 | 295 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 295 | 295
2705 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dismantling Work of Marketing office | LS | 1 | 720 | 720 | 0 | 0 | 0 | 0 | 720 | 0 | 1 | 944 | 944 | 1 | 944 | 944 | 1 | 0 | 720 | -224
2706 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dum Dum 11 No. Bus Stand Fog Nagerbazaar | LS | 4 | 22000 | 88000 | 0 | 0 | 0 | 0 | 22000 | 0 | 3.6333 | 43919.75 | 159573.64 | 3.6333 | 43919.75 | 159573.64 | 4 | 0.3667 | 88000 | -71573.64
2707 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dum Dum Hanuman Mandir | DAYS | 180 | 1180 | 212400 | 0 | 0 | 0 | 18 | 1180 | 21240 | 161 | 1180 | 189980 | 161 | 1180 | 189980 | 162 | 19 | 191160 | 22420
2708 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dum Dum NagerBazar | DAYS | 450 | 1180 | 531000 | 0 | 0 | 0 | 45 | 1180 | 53100 | 312 | 1440.96 | 449579.92 | 312 | 1440.96 | 449579.94 | 405 | 138 | 477900 | 81420.06
2709 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dum Dum nr. station fac. chiriamore | LS | 1 | 9440 | 9440 | 0 | 0 | 0 | 0 | 9440 | 0 | 0.2 | 47200 | 9440 | 0.2 | 47200 | 9440 | 1 | 0.8 | 9440 | 0
2710 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dum Dum nr. station fc. chiriamore. | MONTH | 10 | 1 | 10 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 47200 | 236000 | 5 | 47200 | 236000 | 9 | 5 | 9 | -235990
2711 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Dunlop crossing facing Barrackpore | MONTH | 3 | 47200 | 141600 | 0 | 0 | 0 | 0 | 47200 | 0 | 1 | 47200 | 47200 | 1 | 47200 | 47200 | 3 | 2 | 141600 | 94400
2712 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Flex Printing | NOS | 28 | 3259.16 | 91256.48 | 0 | 0 | 0 | 3 | 3259.16 | 9777.48 | 28 | 1406.39 | 39378.96 | 26 | 1378.42 | 35838.96 | 25 | 2 | 81479 | 55417.52
2713 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Flex Printing (Front Lit) | SQFT | 3200 | 12.98 | 41536 | 0 | 0 | 0 | 320 | 12.98 | 4153.6 | 2800 | 12.98 | 36344 | 2800 | 12.98 | 36344 | 2880 | 400 | 37382.4 | 5192
2714 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Flex Printing and Mounting | NOS | 8205 | 15.34 | 125864.7 | 0 | 0 | 0 | 821 | 15.34 | 12594.14 | 7960 | 17.25 | 137309.52 | 7960 | 17.25 | 137309.52 | 7384 | 245 | 113270.56 | -11444.82
2715 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Flex Printing Standee | NOS | 90 | 16.52 | 1486.8 | 0 | 0 | 0 | 9 | 16.52 | 148.68 | 56 | 66.5 | 3724.08 | 56 | 66.5 | 3724.08 | 81 | 34 | 1338.12 | -2237.28
2716 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Frame boards making & mounting | FT | 918 | 29.5 | 27081 | 0 | 0 | 0 | 92 | 29.5 | 2714 | 108 | 29.5 | 3186 | 108 | 29.5 | 3186 | 826 | 810 | 24367 | 23895
2717 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Frontlit Flex | NOS | 800 | 1 | 800 | 0 | 0 | 0 | 80 | 1 | 80 | 800 | 12.98 | 10384 | 800 | 12.98 | 10384 | 720 | 0 | 720 | -9584
2718 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding | FT | 7286 | 15.34 | 111767.24 | 0 | 0 | 0 | 729 | 15.34 | 11182.86 | 6486 | 12.98 | 84188.28 | 6486 | 12.98 | 84188.28 | 6557 | 800 | 100584.38 | 27578.96
2719 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding - Sinthee More Facing Dunlop (60'X40') | Monthly | 9 | 106200 | 955800 | 0 | 0 | 0 | 1 | 106200 | 106200 | 9 | 106200 | 955800 | 2.6667 | 106200 | 283203.54 | 8 | 6.3333 | 849600 | 672596.46
2720 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding Charges - Shyambazar facing R G Kar | Monthly | 4 | 354000 | 1416000 | 0 | 0 | 0 | 0 | 354000 | 0 | 4 | 275825 | 1103300 | 1 | 354000 | 354000 | 4 | 3 | 1416000 | 1062000
2721 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding Chgs.- Flex printing | SQFT | 7125 | 12.98 | 92482.5 | 0 | 0 | 0 | 713 | 12.98 | 9254.74 | 7125 | 12.98 | 92482.5 | 7125 | 12.98 | 92482.5 | 6412 | 0 | 83227.76 | 0
2722 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding- B T Road Chiria More (40'X20') | Monthly | 6 | 43660 | 261960 | 0 | 0 | 0 | 1 | 43660 | 43660 | 6 | 43660 | 261960 | 4 | 43660 | 174640 | 5 | 2 | 218300 | 87320
2723 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding- B.T. Road Facing Tala Bridge (20'X20') | Monthly | 6 | 247800 | 1486800 | 0 | 0 | 0 | 1 | 247800 | 247800 | 6 | 41300 | 247800 | 0 | 0 | 0 | 5 | 6 | 1239000 | 1486800
2724 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding- Dumdum Hanuman Mandir (20'X25') | Monthly | 6 | 35400 | 212400 | 0 | 0 | 0 | 1 | 35400 | 35400 | 6 | 35400 | 212400 | 4 | 35400 | 141600 | 5 | 2 | 177000 | 70800
2725 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Hoarding-Dumdum Stn. Rd. 25X25 Frontlit | Monthly | 6 | 43660 | 261960 | 0 | 0 | 0 | 1 | 43660 | 43660 | 6 | 43660 | 261960 | 3 | 43660 | 130980 | 5 | 3 | 218300 | 130980
2726 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Inside Wall Branding | FT | 360 | 23.6 | 8496 | 0 | 0 | 0 | 36 | 23.6 | 849.6 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 360 | 7646.4 | 8496
2727 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Iron Halo pipe frame with sunboard & vinyl backdrop | NOS | 1 | 4720 | 4720 | 0 | 0 | 0 | 0 | 4720 | 0 | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 1 | 0 | 4720 | 0
2728 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Iron Halo-Pipe Frame with Flex Making & Mounting | NOS | 2420 | 849.6 | 2056032 | 0 | 0 | 0 | 242 | 849.6 | 205603.2 | 2420 | 86.01 | 208152 | 2320 | 53.1 | 123192 | 2178 | 100 | 1850428.8 | 1932840
2729 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Jessore Near Ordinance Factory Fcg Nager Bazaar | LS | 1 | 41300 | 41300 | 0 | 0 | 0 | 0 | 41300 | 0 | 1 | 41300 | 41300 | 1 | 41300 | 41300 | 1 | 0 | 41300 | 0
2730 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Jessore Rd Near Ordinance Factory Fcg Nager Bazaar | DAYS | 240 | 1.18 | 283.2 | 0 | 0 | 0 | 24 | 1.18 | 28.32 | 181 | 1369.05 | 247798.73 | 181 | 1369.05 | 247798.71 | 216 | 59 | 254.88 | -247515.51
2731 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Kamarhati municipality facing Barrackpore | MONTH | 3 | 41300 | 123900 | 0 | 0 | 0 | 0 | 41300 | 0 | 2.9667 | 41300 | 122524.72 | 2.9667 | 41300 | 122524.72 | 3 | 0.0333 | 123900 | 1375.28
2732 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Karunamoyee Lower | MONTH | 3 | 29500 | 88500 | 0 | 0 | 0 | 0 | 29500 | 0 | 2.9333 | 29500 | 86532.36 | 2.9333 | 29500 | 86532.36 | 3 | 0.0667 | 88500 | 1967.64
2733 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Laketown Water Tank Fcg. Jaya Cinema & VIP Road Middle | LS | 1 | 76700 | 76700 | 0 | 0 | 0 | 0 | 76700 | 0 | 1 | 327252.32 | 327252.32 | 1 | 327252.32 | 327252.32 | 1 | 0 | 76700 | -250552.32
2734 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)LED & POWER SUPPLY | NOS | 1 | 14160 | 14160 | 0 | 0 | 0 | 0 | 14160 | 0 | 1 | 14160 | 14160 | 1 | 14160 | 14160 | 1 | 0 | 14160 | 0
2735 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Madhamgram Choumatha. | DAYS | 240 | 1.18 | 283.2 | 0 | 0 | 0 | 24 | 1.18 | 28.32 | 151 | 1250.33 | 188799.75 | 151 | 1250.33 | 188799.75 | 216 | 89 | 254.88 | -188516.55
2736 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Madhyamgram Choumatha | LS | 1 | 37760 | 37760 | 0 | 0 | 0 | 0 | 37760 | 0 | 1 | 37760 | 37760 | 1 | 37760 | 37760 | 1 | 0 | 37760 | 0
2737 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Maniktala Xing ftf kakurgachi | LS | 2 | 59000 | 118000 | 0 | 0 | 0 | 0 | 59000 | 0 | 0.2667 | 59000 | 15735.3 | 0.2667 | 59000 | 15735.3 | 2 | 1.7333 | 118000 | 102264.7
2738 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Maniktala Xing ftf kakurgachi 40*40 | LS | 5 | 118000 | 590000 | 0 | 0 | 0 | 1 | 118000 | 118000 | 3.7 | 118000 | 436600 | 3.7 | 118000 | 436600 | 4 | 1.3 | 472000 | 153400
2739 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Matter- "ORCHARD" , "AMRITAYA" | NOS | 1 | 76700 | 76700 | 0 | 0 | 0 | 0 | 76700 | 0 | 1 | 76700 | 76700 | 1 | 76700 | 76700 | 1 | 0 | 76700 | 0
2740 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)MG Rd. xing Fcg Shyambazaar | LS | 1 | 70000 | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | 1 | 82600 | 82600 | 1 | 82600 | 82600 | 1 | 0 | 70000 | -12600
2741 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)MG Rd. xing Fcg Shyambazaar. | DAYS | 240 | 1.18 | 283.2 | 0 | 0 | 0 | 24 | 1.18 | 28.32 | 151 | 2735.1 | 412999.8 | 151 | 2735.1 | 412999.8 | 216 | 89 | 254.88 | -412716.6
2742 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Mobile Van Advertisement | DAYS | 30 | 3540 | 106200 | 0 | 0 | 0 | 3 | 3540 | 10620 | 30 | 3540 | 106200 | 30 | 3540 | 106200 | 27 | 0 | 95580 | 0
2743 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Mounting Charge | LS | 19 | 1.18 | 22.42 | 0 | 0 | 0 | 2 | 1.18 | 2.36 | 12 | 2382.13 | 28585.5 | 12 | 2382.13 | 28585.5 | 17 | 7 | 20.06 | -28563.08
2744 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Nagerbazaar Fly Over Fcg Airport | DAYS | 180 | 1.18 | 212.4 | 0 | 0 | 0 | 18 | 1.18 | 21.24 | 91 | 1556.04 | 141599.66 | 91 | 1556.04 | 141599.66 | 162 | 89 | 191.16 | -141387.26
2745 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Nagerbazaarr Fly Over Fcg Airpor | LS | 1 | 40000 | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 1 | 47200 | 47200 | 1 | 47200 | 47200 | 1 | 0 | 40000 | -7200
2746 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)New Flex & Fixing | FT | 350 | 17.7 | 6195 | 0 | 0 | 0 | 35 | 17.7 | 619.5 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 350 | 5575.5 | 6195
2747 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Printing Amritaya Flyer-Pocket | PCS | 1500 | 69.62 | 104430 | 0 | 0 | 0 | 150 | 69.62 | 10443 | 1500 | 69.62 | 104430 | 1500 | 69.62 | 104430 | 1350 | 0 | 93987 | 0
2748 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Printing Envelope For Amritaya Flyer | PCS | 1500 | 20.06 | 30090 | 0 | 0 | 0 | 150 | 20.06 | 3009 | 1500 | 20.06 | 30090 | 1500 | 20.06 | 30090 | 1350 | 0 | 27081 | 0
2749 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)QR Display stand with print | NOS | 10 | 206.5 | 2065 | 0 | 0 | 0 | 1 | 206.5 | 206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 1858.5 | 2065
2750 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Rental Charges for Hoarding | DAYS | 12 | 1573.34 | 18880.08 | 0 | 0 | 0 | 1 | 1573.34 | 1573.34 | 12 | 1573.34 | 18880.1 | 12 | 1573.34 | 18880.1 | 11 | 0 | 17306.74 | -0.02
2751 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Repairing & New Flex | LS | 2 | 1416 | 2832 | 0 | 0 | 0 | 0 | 1416 | 0 | 2 | 2183 | 4366 | 2 | 2183 | 4366 | 2 | 0 | 2832 | -1534
2752 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Road Marker | FT | 15000 | 23.6 | 354000 | 0 | 0 | 0 | 1500 | 23.6 | 35400 | 11100 | 23.6 | 261960 | 11100 | 23.6 | 261960 | 13500 | 3900 | 318600 | 92040
2753 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)SHYAMBAZAR CROSSING | LS | 24 | 94400 | 2265600 | 0 | 0 | 0 | 2 | 94400 | 188800 | 20.5 | 71099.32 | 1457536 | 20.5 | 71099.32 | 1457536 | 22 | 3.5 | 2076800 | 808064
2754 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Shyambazar Xing ftf sovabazar | LS | 2 | 118000 | 236000 | 0 | 0 | 0 | 0 | 118000 | 0 | 1.9667 | 118000 | 232070.6 | 1.9667 | 118000 | 232070.6 | 2 | 0.0333 | 236000 | 3929.4
2755 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Sinthee More Fcg Dunlop | LS | 4 | 22000 | 88000 | 0 | 0 | 0 | 0 | 22000 | 0 | 1 | 25960 | 25960 | 1 | 25960 | 25960 | 4 | 3 | 88000 | 62040
2756 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Sodepur Xing ftf station | LS | 5 | 30000 | 150000 | 0 | 0 | 0 | 1 | 30000 | 30000 | 4.4 | 35400 | 155760 | 4.4 | 35400 | 155760 | 4 | 0.6 | 120000 | -5760
2757 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Sovabazar Crossing | LS | 1 | 15340 | 15340 | 0 | 0 | 0 | 0 | 15340 | 0 | 0.935 | 15340 | 14342.9 | 0.935 | 15340 | 14342.9 | 1 | 0.065 | 15340 | 997.1
2758 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Sovabazar Crossing. | DAYS | 240 | 1.18 | 283.2 | 0 | 0 | 0 | 24 | 1.18 | 28.32 | 150 | 511.33 | 76699.95 | 150 | 511.33 | 76699.95 | 216 | 90 | 254.88 | -76416.75
2759 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Space for conference | LS | 2 | 8850 | 17700 | 0 | 0 | 0 | 0 | 8850 | 0 | 2 | 8850 | 17700 | 2 | 8850 | 17700 | 2 | 0 | 17700 | 0
2760 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Sunboard with eco solvent vinyl with cover box & stand | PCS | 1 | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 1 | 708 | 708 | 1 | 708 | 708 | 1 | 0 | 4000 | 3292
2761 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Supply of Back black flex at Sampark | FT | 2600 | 12.98 | 33748 | 0 | 0 | 0 | 260 | 12.98 | 3374.8 | 2600 | 12.98 | 33748 | 2600 | 12.98 | 33748 | 2340 | 0 | 30373.2 | 0
2762 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Tala Bridge traffic signal | NOS | 10 | 4956 | 49560 | 0 | 0 | 0 | 1 | 4956 | 4956 | 1 | 38350 | 38350 | 1 | 38350 | 38350 | 9 | 9 | 44604 | 11210
2763 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Temporary hoardings (including printing & mounting) | NOS | 2780 | 24.78 | 68888.4 | 0 | 0 | 0 | 278 | 24.78 | 6888.84 | 2760 | 23.86 | 65844 | 2760 | 23.86 | 65844 | 2502 | 20 | 61999.56 | 3044.4
2764 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Ultadanga facing hudco | LS | 1 | 76700 | 76700 | 0 | 0 | 0 | 0 | 76700 | 0 | 0.2 | 76700 | 15340 | 0.2 | 76700 | 15340 | 1 | 0.8 | 76700 | 61360
2765 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Ultadanga facing hudco. | DAYS | 120 | 1.18 | 141.6 | 0 | 0 | 0 | 12 | 1.18 | 14.16 | 105 | 2556.67 | 268449.91 | 105 | 2556.67 | 268449.93 | 108 | 15 | 127.44 | -268308.33
2766 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Unipole - sinthimore ftf shyambazar | LS | 6 | 60000 | 360000 | 0 | 0 | 0 | 1 | 60000 | 60000 | 5.4667 | 70800 | 387042.36 | 5.4667 | 70800 | 387042.36 | 5 | 0.5333 | 300000 | -27042.36
2767 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Unipole - sodepure panihati ftf dunlop | LS | 6 | 65000 | 390000 | 0 | 0 | 0 | 1 | 65000 | 65000 | 3.9667 | 76700 | 304245.9 | 3.9667 | 76700 | 304245.9 | 5 | 2.0333 | 325000 | 85754.1
2768 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)Vinyl printing Charge | NOS | 103 | 944 | 97232 | 0 | 0 | 0 | 10 | 944 | 9440 | 101 | 116.83 | 11800 | 101 | 116.83 | 11800 | 93 | 2 | 87792 | 85432
2769 | SELLING COST - Hoardings Charges | 10 | Started | Labour | (L)wooden frame, flex making & mounting | FT | 2843 | 23.6 | 67094.8 | 0 | 0 | 0 | 284 | 23.6 | 6702.4 | 2700 | 23.6 | 63720 | 2700 | 23.6 | 63720 | 2559 | 143 | 60392.4 | 3374.8
2770 | SELLING COST - Hoardings Expenses | 10 | Started | Labour | (L)Laketown Water Tank Fcg. Jaya Cinema & VIP Road Middle | LS | 1 | 76700 | 76700 | 0 | 0 | 0 | 0 | 76700 | 0 | 1 | 76700 | 76700 | 1 | 76700 | 76700 | 1 | 0 | 76700 | 0
2771 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Acrylic Stand | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Digital Marketing
2772 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Backlit flex FT | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Digital Marketing
2773 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Blog section in Amritaya website | LS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 9440 | 9440 | 1 | 9440 | 9440 | 2 | 1 | 2 | -9438 | Digital Marketing
2774 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Create 2 new pages in the Amritaya microsite. | NOS | 2 | 5900 | 11800 | 0 | 0 | 0 | 0 | 5900 | 0 | 2 | 5900 | 11800 | 2 | 5900 | 11800 | 2 | 0 | 11800 | 0 | Digital Marketing
2775 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Event Management on the date of 15-Jan-2023 | LS | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 275000 | 1100000 | 4 | 275000 | 1100000 | 4 | 0 | 4 | -1099996 | Digital Marketing
2776 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Home Loan Calculator | LS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0 | Digital Marketing
2777 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Iron Halo pipe frame with sunboard & vinyl backdrop | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Digital Marketing
2778 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Landing page for Amritaya Google Ads | LS | 1 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 0 | 1 | 41300 | 41300 | 1 | 41300 | 41300 | 1 | 0 | 30000 | -11300 | Digital Marketing
2779 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Landing page for teaser ads | LS | 1 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 0 | 1 | 35400 | 35400 | 1 | 35400 | 35400 | 1 | 0 | 30000 | -5400 | Digital Marketing
2780 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Lead Generation for Amritaya Project | LS | 2 | 354000 | 708000 | 0 | 0 | 0 | 0 | 354000 | 0 | 1 | 354000 | 354000 | 1 | 354000 | 354000 | 2 | 1 | 708000 | 354000 | Digital Marketing
2781 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Media Service Charges for Facebook & Google Ad | LS | 14 | 108332 | 1516648 | 0 | 0 | 0 | 1 | 108332 | 108332 | 2.204 | 127831.76 | 281741.208 | 2.204 | 127831.76 | 281741.21 | 13 | 11.796 | 1408316 | 1234906.79 | Digital Marketing
2782 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Software Development for Cx/Visitors Form | LS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 44840 | 44840 | 1 | 44840 | 44840 | 1 | 0 | 1.18 | -44838.82 | Digital Marketing
2783 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Testimonial & FAQ page | LUMSUM | 1 | 9440 | 9440 | 0 | 0 | 0 | 0 | 9440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9440 | 9440 | Digital Marketing
2784 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Website Design (Laravel - PHP) | NOS | 4 | 30000 | 120000 | 0 | 0 | 0 | 0 | 30000 | 0 | 4 | 12980 | 51920 | 4 | 12980 | 51920 | 4 | 0 | 120000 | 68080 | Digital Marketing
2785 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Website Design - Add Banking Logo in website | UNIT | 1 | 4130 | 4130 | 0 | 0 | 0 | 0 | 4130 | 0 | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 1 | 0 | 4130 | 0 | Digital Marketing
2786 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Website Maintenance fee | Quarterly | 8 | 29500 | 236000 | 0 | 0 | 0 | 1 | 29500 | 29500 | 8 | 14750 | 118000 | 0 | 0 | 0 | 7 | 8 | 206500 | 236000 | Digital Marketing
2787 | SELLING COST - Digital Marketing Website Charges | 10 | Started | Labour | (L)Website Page Creation-Refunf & Cancellation in Oswal Site | LS | 1 | 3540 | 3540 | 0 | 0 | 0 | 0 | 3540 | 0 | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 1 | 0 | 3540 | 0 | Digital Marketing
2788 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)3D Static Visual-Aerial | NOS | 1 | 21240 | 21240 | 0 | 0 | 0 | 0 | 21240 | 0 | 1 | 21240 | 21240 | 1 | 21240 | 21240 | 1 | 0 | 21240 | 0 | Digital Marketing
2789 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)3D Static Visual-Elevation | NOS | 2 | 17700 | 35400 | 0 | 0 | 0 | 0 | 17700 | 0 | 2 | 17700 | 35400 | 2 | 17700 | 35400 | 2 | 0 | 35400 | 0 | Digital Marketing
2790 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Amritaya walk- through video | NOS | 1 | 2500 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 0 | 2500 | 0 | Digital Marketing
2791 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Ananda Bazar Patrika (COC/PAGE-1 Colour Display) | LS | 2 | 1755600 | 3511200 | 0 | 0 | 0 | 0 | 1755600 | 0 | 2 | 1848000 | 3696000 | 2 | 1848000 | 3696000 | 2 | 0 | 3511200 | -184800 | Digital Marketing
2792 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Application Booking Form-WhatsApp Integration | LS | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5000 | -900 | Digital Marketing
2793 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Application Form with Payment Gateway Integration | NOS | 1 | 29000 | 29000 | 0 | 0 | 0 | 0 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 29000 | 29000 | Digital Marketing
2794 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Back Black Flex FT | FT | 1800 | 12.98 | 23364 | 0 | 0 | 0 | 180 | 12.98 | 2336.4 | 1800 | 18.88 | 33984 | 1800 | 18.88 | 33984 | 1620 | 0 | 21027.6 | -10620 | Digital Marketing
2795 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Back-lit Flex | FT | 200 | 23.6 | 4720 | 0 | 0 | 0 | 20 | 23.6 | 472 | 200 | 23.6 | 4720 | 200 | 23.6 | 4720 | 180 | 0 | 4248 | 0 | Digital Marketing
2796 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Bot:-Pay Per Journey | NOS | 10000 | 1 | 10000 | 0 | 0 | 0 | 1000 | 1 | 1000 | 10000 | 1.48 | 14750 | 10000 | 1.48 | 14750 | 9000 | 0 | 9000 | -4750 | Digital Marketing
2797 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Brand Audio Visual | NOS | 1 | 240000 | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 1 | 361080 | 361080 | 1 | 361080 | 361080 | 1 | 0 | 240000 | -121080 | Digital Marketing
2798 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Bulk WA Panel | NOS | 305000 | 0.15 | 45750 | 0 | 0 | 0 | 30500 | 0.15 | 4575 | 300001 | 0.2 | 59000 | 300001 | 0.2 | 59000 | 274500 | 4999 | 41175 | -13250 | Digital Marketing
2799 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Business Whatsapp MAU(Monthly Active Users) | MONTH | 12 | 3540 | 42480 | 0 | 0 | 0 | 1 | 3540 | 3540 | 12 | 3540 | 42480 | 12 | 3540 | 42480 | 11 | 0 | 38940 | 0 | Digital Marketing
2800 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Business Whatsapp OTC(One Time Charge) | LUMSUM | 1 | 3540 | 3540 | 0 | 0 | 0 | 0 | 3540 | 0 | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 1 | 0 | 3540 | 0 | Digital Marketing
2801 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Business Whatsapp Prepaid Recharge | LUMSUM | 10000 | 0.93 | 9300 | 0 | 0 | 0 | 1000 | 0.93 | 930 | 10000 | 0.93 | 9322 | 10000 | 0.93 | 9322 | 9000 | 0 | 8370 | -22 | Digital Marketing
2802 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)CELEBRITY PHOTOSHOOT | LS | 1 | 200000 | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 1 | 200000 | 200000 | 1 | 200000 | 200000 | 1 | 0 | 200000 | 0 | Digital Marketing
2803 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Charges for testimonial video shoot | LS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 37000 | 37000 | 1 | 37000 | 37000 | 1 | 0 | 1 | -36999 | Digital Marketing
2804 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Commission on Online Spent | LS | 13 | 70800 | 920400 | 0 | 0 | 0 | 1 | 70800 | 70800 | 13 | 81684.32 | 1061896.16 | 10.7058 | 84060.77 | 899937.83 | 12 | 2.2942 | 849600 | 20462.17 | Digital Marketing
2805 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Cost per BIC (Session-Based) | NOS | 10000 | 1 | 10000 | 0 | 0 | 0 | 1000 | 1 | 1000 | 10000 | 0.67 | 6726 | 10000 | 0.67 | 6726 | 9000 | 0 | 9000 | 3274 | Digital Marketing
2806 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Cost per UIC (Session-Based) | NOS | 10000 | 1 | 10000 | 0 | 0 | 0 | 1000 | 1 | 1000 | 10000 | 0.44 | 4366 | 10000 | 0.44 | 4366 | 9000 | 0 | 9000 | 5634 | Digital Marketing
2807 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Deshbandhu Park | MONTH | 12 | 629.34 | 7552.08 | 0 | 0 | 0 | 1 | 629.34 | 629.34 | 4.5766 | 15270.33 | 69886.2 | 4.5766 | 15270.33 | 69886.2 | 11 | 7.4234 | 6922.74 | -62334.12 | Digital Marketing
2808 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Development of an online Application Form 1 | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 1 | 0 | 1 | -3539 | Digital Marketing
2809 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Drone Shoot | NOS | 2 | 8000 | 16000 | 0 | 0 | 0 | 0 | 8000 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 2 | 1 | 16000 | 6000 | Digital Marketing
2810 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Drone Shoot Video Edit with Motion Graphics | NOS | 2 | 8260 | 16520 | 0 | 0 | 0 | 0 | 8260 | 0 | 1 | 7000 | 7000 | 1 | 7000 | 7000 | 2 | 1 | 16520 | 9520 | Digital Marketing
2811 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Dubbing artist charges | NOS | 2 | 2360 | 4720 | 0 | 0 | 0 | 0 | 2360 | 0 | 2 | 2500 | 5000 | 2 | 2500 | 5000 | 2 | 0 | 4720 | -280 | Digital Marketing
2812 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Dum Dum nr. station fc. chiriamore. | MONTH | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | Digital Marketing
2813 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Edit of 30 individual videos with graphics and text | LS | 2 | 60000 | 120000 | 0 | 0 | 0 | 0 | 60000 | 0 | 1 | 60000 | 60000 | 1 | 60000 | 60000 | 2 | 1 | 120000 | 60000 | Digital Marketing
2814 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Festives Creatives | LS | 7 | 1180 | 8260 | 0 | 0 | 0 | 1 | 1180 | 1180 | 7 | 4928.57 | 34500 | 7 | 4928.57 | 34500 | 6 | 0 | 7080 | -26240 | Digital Marketing
2815 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Flex Printing | NOS | 1 | 3259.16 | 3259.16 | 0 | 0 | 0 | 0 | 3259.16 | 0 | 1 | 2891 | 2891 | 1 | 2891 | 2891 | 1 | 0 | 3259.16 | 368.16 | Digital Marketing
2816 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Freelance Rendering Service 3D | PCS | 14 | 8000 | 112000 | 0 | 0 | 0 | 1 | 8000 | 8000 | 9 | 13388.89 | 120500 | 9 | 13388.89 | 120500 | 13 | 5 | 104000 | -8500 | Digital Marketing
2817 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Frontlit Flex | NOS | 3725 | 1 | 3725 | 0 | 0 | 0 | 373 | 1 | 373 | 3725 | 12.98 | 48350.5 | 3725 | 12.98 | 48350.5 | 3352 | 0 | 3352 | -44625.5 | Digital Marketing
2818 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Frontlit Flex (Back Black) | NOS | 15366 | 1 | 15366 | 0 | 0 | 0 | 1537 | 1 | 1537 | 15366 | 12.98 | 199450.68 | 15366 | 12.98 | 199450.68 | 13829 | 0 | 13829 | -184084.68 | Digital Marketing
2819 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Google Workspace Standard | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 11210 | 11210 | 1 | 11210 | 11210 | 4 | 3 | 4.72 | -11205.28 | Digital Marketing
2820 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Google Workspace Starter | NOS | 58 | 1.18 | 68.44 | 0 | 0 | 0 | 6 | 1.18 | 7.08 | 51 | 2073.34 | 105740.3 | 51 | 2073.34 | 105740.3 | 52 | 7 | 61.36 | -105671.86 | Digital Marketing
2821 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)ILLUSTRATION AMRITAYA MAP | LS | 1 | 1500 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 1 | 0 | 1500 | 0 | Digital Marketing
2822 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)ILLUSTRATION AMRITAYA MAP IN NEWSPAPER | LS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 1 | 17700 | 17700 | 1 | 17700 | 17700 | 1 | 0 | 17700 | 0 | Digital Marketing
2823 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Implementation of 3 Tire Payment Option | LS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0 | Digital Marketing
2824 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)IT Network Fixing-Technical Reconstruct of IV | LUMSUM | 1 | 180000 | 180000 | 0 | 0 | 0 | 0 | 180000 | 0 | 1 | 180000 | 180000 | 1 | 180000 | 180000 | 1 | 0 | 180000 | 0 | Digital Marketing
2825 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Jessore Near Ordinance Factory Fcg Nager Bazaar | LS | 1 | 41300 | 41300 | 0 | 0 | 0 | 0 | 41300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 41300 | 41300 | Digital Marketing
2826 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Launch Campaign | LS | 3 | 227150 | 681450 | 0 | 0 | 0 | 0 | 227150 | 0 | 3 | 587050 | 1761150 | 2.5682 | 467505.51 | 1200647.64 | 3 | 0.4318 | 681450 | -519197.64 | Digital Marketing
2827 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Misc. Work for Marketing | NOS | 330000 | 1.18 | 389400 | 0 | 0 | 0 | 33000 | 1.18 | 38940 | 330000 | 1.18 | 389400 | 63386 | 1.06 | 67328 | 297000 | 266614 | 350460 | 322072 | Digital Marketing
2828 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Monthly AMC for IVR Deflection Bot &amp; WhatsApp API Gups | Monthly | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 1 | 1.18 | 1.18 | 2 | 15340 | 30680 | 2 | 15340 | 30680 | 11 | 10 | 12.98 | -30665.84 | Digital Marketing
2829 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Mounting Charge | LS | 3 | 1.18 | 3.54 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54 | Digital Marketing
2830 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)One time setup cost for IVR Deflection Bot amp; WhatsApp AP | LUMSUM | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 17700 | 17700 | 1 | 17700 | 17700 | 1 | 0 | 1.18 | -17698.82 | Digital Marketing
2831 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Online application form for Anupa Addition Work | NOS | 3 | 2360 | 7080 | 0 | 0 | 0 | 0 | 2360 | 0 | 1 | 2360 | 2360 | 1 | 2360 | 2360 | 3 | 2 | 7080 | 4720 | Digital Marketing
2832 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Online Campaign & Promotion | LS | 2 | 731010 | 1462020 | 0 | 0 | 0 | 0 | 731010 | 0 | 1.9893 | 473752.76 | 942436.375 | 1.9893 | 473752.77 | 942436.38 | 2 | 0.0107 | 1462020 | 519583.62 | Digital Marketing
2833 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Online lead generation from property portal | LUMSUM | 2 | 767000 | 1534000 | 0 | 0 | 0 | 0 | 767000 | 0 | 2 | 767000 | 1534000 | 2 | 767000 | 1534000 | 2 | 0 | 1534000 | 0 | Digital Marketing
2834 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Osloyal Referral System | NOS | 1 | 230100 | 230100 | 0 | 0 | 0 | 0 | 230100 | 0 | 1 | 212400 | 212400 | 1 | 212400 | 212400 | 1 | 0 | 230100 | 17700 | Digital Marketing
2835 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Quiz web page | NOS | 1 | 2950 | 2950 | 0 | 0 | 0 | 0 | 2950 | 0 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 0 | 2950 | 450 | Digital Marketing
2836 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Retainership fees | Monthly | 32 | 68440 | 2190080 | 0 | 0 | 0 | 3 | 68440 | 205320 | 22 | 61681.82 | 1357000 | 22 | 61681.82 | 1357000 | 29 | 10 | 1984760 | 833080 | Digital Marketing
2837 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Roller Standees | PCS | 5 | 1.18 | 5.9 | 0 | 0 | 0 | 1 | 1.18 | 1.18 | 5 | 1180 | 5900 | 5 | 1180 | 5900 | 4 | 0 | 4.72 | -5894.1 | Digital Marketing
2838 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Scripting the Ganga laser graphics show | LS | 1 | 47200 | 47200 | 0 | 0 | 0 | 0 | 47200 | 0 | 1 | 47200 | 47200 | 1 | 47200 | 47200 | 1 | 0 | 47200 | 0 | Digital Marketing
2839 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)SEO for Amritaya & Oswal Group | LS | 2 | 7080 | 14160 | 0 | 0 | 0 | 0 | 7080 | 0 | 1 | 7080 | 7080 | 0 | 0 | 0 | 2 | 2 | 14160 | 14160 | Digital Marketing
2840 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)SEO Optimization & Blogging | Monthly | 48 | 22500 | 1080000 | 0 | 0 | 0 | 5 | 22500 | 112500 | 47.7604 | 42115.2 | 2011438.62 | 35.7686 | 40410.46 | 1445425.72 | 43 | 12.2314 | 967500 | -365425.72 | Digital Marketing
2841 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Service charge of Campaign | LS | 1 | 26000 | 26000 | 0 | 0 | 0 | 0 | 26000 | 0 | 1 | 30680 | 30680 | 1 | 30680 | 30680 | 1 | 0 | 26000 | -4680 | Digital Marketing
2842 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Social Media Management | Monthly | 30 | 29500 | 885000 | 0 | 0 | 0 | 3 | 29500 | 88500 | 25 | 29740 | 743500 | 19 | 29736.84 | 565000 | 27 | 11 | 796500 | 320000 | Digital Marketing
2843 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)STUDIO BOOKING | HOURS | 20.4443 | 450 | 9199.94 | 0 | 0 | 0 | 2 | 450 | 900 | 19.4443 | 519.43 | 10099.935 | 19.4443 | 519.43 | 10099.94 | 18.4443 | 1 | 8299.935 | -900.005 | Digital Marketing
2844 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Tala Bridge signal Advertising | DAYS | 450 | 1.18 | 531 | 0 | 0 | 0 | 45 | 1.18 | 53.1 | 342.13 | 981.85 | 335920.1513 | 342.13 | 981.85 | 335920.17 | 405 | 107.87 | 477.9 | -335389.17 | Digital Marketing
2845 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Technical Reconstruct of IV-Service | LUMSUM | 1 | 23600 | 23600 | 0 | 0 | 0 | 0 | 23600 | 0 | 1 | 20000 | 20000 | 1 | 20000 | 20000 | 1 | 0 | 23600 | 3600 | Digital Marketing
2846 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Times Of India (WB/COC/PAGE-1 Colour Display) | LS | 1 | 1016400 | 1016400 | 0 | 0 | 0 | 0 | 1016400 | 0 | 1 | 1016400 | 1016400 | 1 | 1016400 | 1016400 | 1 | 0 | 1016400 | 0 | Digital Marketing
2847 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Vivekananda Road Crossing | MONTH | 12 | 22420 | 269040 | 0 | 0 | 0 | 1 | 22420 | 22420 | 4.5569 | 18017.88 | 82105.7 | 4.5569 | 18017.88 | 82105.7 | 11 | 7.4431 | 246620 | 186934.3 | Digital Marketing
2848 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Voice plugin in oswal group website | NOS | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 1 | 0 | 1770 | 270 | Digital Marketing
2849 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)Website Maintenance fee | Quarterly | 20 | 29500 | 590000 | 0 | 0 | 0 | 2 | 29500 | 59000 | 8 | 7375 | 59000 | 8 | 7375 | 59000 | 18 | 12 | 531000 | 531000 | Digital Marketing
2850 | SELLING COST - Digital Marketing | 10 | Started | Labour | (L)WhatsApp Redressal System | NOS | 1 | 112100 | 112100 | 0 | 0 | 0 | 0 | 112100 | 0 | 1 | 94400 | 94400 | 1 | 94400 | 94400 | 1 | 0 | 112100 | 17700 | Digital Marketing
2851 | SELLING COST - Digital Marketing Google Ads | 10 | Started | Labour | (L)Campaigns-Advertising Service | Monthly | 24 | 35400 | 849600 | 0 | 0 | 0 | 2 | 35400 | 70800 | 17.1538 | 200547.31 | 3440148.4 | 13.3097 | 190307.88 | 2532940.8 | 22 | 10.6903 | 778800 | -1683340.8
2852 | SELLING COST - Digital Marketing Google Ads | 10 | Started | Labour | (L)Google Ads Service | NOS | 750000 | 1.18 | 885000 | 0 | 0 | 0 | 75000 | 1.18 | 88500 | 750000 | 1.18 | 885000 | 120880 | 1.18 | 142638.4 | 675000 | 629120 | 796500 | 742361.6
2853 | SELLING COST - Digital Marketing Facebook Ads | 10 | Started | Labour | (L)Campaigns-Advertising Service | Monthly | 24 | 35400 | 849600 | 0 | 0 | 0 | 2 | 35400 | 70800 | 18 | 354000 | 6372000 | 18 | 353999.67 | 6371994.06 | 22 | 6 | 778800 | -5522394.06
2854 | SELLING COST - Digital Marketing Facebook Ads | 10 | Started | Labour | (L)Meta Ads Service | NOS | 2040000 | 1.18 | 2407200 | 0 | 0 | 0 | 204000 | 1.18 | 240720 | 2040000 | 1.18 | 2407200 | 287885 | 1.18 | 339704.3 | 1836000 | 1752115 | 2166480 | 2067495.7
2855 | SELLING COST - Digital Marketing Whatsapp Bot | 10 | Started | Labour | (L)Maintenance Fees of Whatsapp | Quarterly | 2 | 15340 | 30680 | 0 | 0 | 0 | 0 | 15340 | 0 | 2 | 15340 | 30680 | 2 | 15340 | 30680 | 2 | 0 | 30680 | 0
2856 | SELLING COST - Digital Marketing Whatsapp Bot | 10 | Started | Labour | (L)ORAI Platform:060201 - OneTime Setup Cost - ORAI AI Platform | UNIT | 1 | 23600 | 23600 | 0 | 0 | 0 | 0 | 23600 | 0 | 1 | 23600 | 23600 | 1 | 23600 | 23600 | 1 | 0 | 23600 | 0
2857 | SELLING COST - Digital Marketing Whatsapp Bot | 10 | Started | Labour | (L)Whatapp Bot Maintenance Charge | Monthly | 12 | 10030 | 120360 | 0 | 0 | 0 | 1 | 10030 | 10030 | 12 | 10030 | 120360 | 12 | 10030 | 120360 | 11 | 0 | 110330 | 0
2858 | SELLING COST - Digital Marketing Whatsapp Bot | 10 | Started | Labour | (L)WhatsApp API:060203 - OneTime Setup Cost - WhatsApp Business | UNIT | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 1 | 17700 | 17700 | 1 | 17700 | 17700 | 1 | 0 | 17700 | 0
2859 | SELLING COST - Digital Marketing Ad Agencies | 10 | Started | Labour | (L)Durga Puja Pass MIRCHI TE DEBIPOKKHO | LUMSUM | 1 | 106200 | 106200 | 0 | 0 | 0 | 0 | 106200 | 0 | 1 | 106200 | 106200 | 1 | 106200 | 106200 | 1 | 0 | 106200 | 0
2860 | SELLING COST - Digital Marketing Ad Agencies | 10 | Started | Labour | (L)Retainership fees | Monthly | 24 | 68440 | 1642560 | 0 | 0 | 0 | 2 | 68440 | 136880 | 17 | 59000 | 1003000 | 10 | 59000 | 590000 | 22 | 14 | 1505680 | 1052560
2861 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Amritaya Gangotsav | LS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1031079.28 | 1031079.28 | 1 | 1031079.28 | 1031079.28 | 1 | 0 | 1 | -1031078.28 | Marketing
2862 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Artist's Payment | LS | 4 | 45000 | 180000 | 0 | 0 | 0 | 0 | 45000 | 0 | 4 | 40500 | 162000 | 4 | 40500 | 162000 | 4 | 0 | 180000 | 18000 | Marketing
2863 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Colour for Painting | LS | 3 | 20000 | 60000 | 0 | 0 | 0 | 0 | 20000 | 0 | 3 | 10000 | 30000 | 3 | 10000 | 30000 | 3 | 0 | 60000 | 30000 | Marketing
2864 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Compressor | LS | 4 | 8000 | 32000 | 0 | 0 | 0 | 0 | 8000 | 0 | 4 | 5500 | 22000 | 4 | 5500 | 22000 | 4 | 0 | 32000 | 10000 | Marketing
2865 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Feeding the Employees | LS | 4 | 20000 | 80000 | 0 | 0 | 0 | 0 | 20000 | 0 | 4 | 12000 | 48000 | 4 | 12000 | 48000 | 4 | 0 | 80000 | 32000 | Marketing
2866 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Footpath guard area Painting | NOS | 856 | 50.16 | 42936.96 | 0 | 0 | 0 | 86 | 50.16 | 4313.76 | 856 | 42.5 | 36380 | 856 | 42.5 | 36380 | 770 | 0 | 38623.2 | 6556.96 | Marketing
2867 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Full Wall Base Paint | LS | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 0 | 10000 | 0 | Marketing
2868 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Layout | LS | 3 | 10000 | 30000 | 0 | 0 | 0 | 0 | 10000 | 0 | 2 | 12500 | 25000 | 2 | 12500 | 25000 | 3 | 1 | 30000 | 5000 | Marketing
2869 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Outside wall area Painting | NOS | 3859 | 50.16 | 193567.44 | 0 | 0 | 0 | 386 | 50.16 | 19361.76 | 3859 | 42.5 | 164007.5 | 3859 | 42.5 | 164007.5 | 3473 | 0 | 174205.68 | 29559.94 | Marketing
2870 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Projector Charges | LS | 3 | 5900 | 17700 | 0 | 0 | 0 | 0 | 5900 | 0 | 2 | 4000 | 8000 | 2 | 4000 | 8000 | 3 | 1 | 17700 | 9700 | Marketing
2871 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Selfie Zone Design & Paint | NOS | 162 | 147.5 | 23895 | 0 | 0 | 0 | 16 | 147.5 | 2360 | 160 | 125 | 20000 | 160 | 125 | 20000 | 146 | 2 | 21535 | 3895 | Marketing
2872 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Labour | (L)Total Colour for base and painting | LS | 1 | 45000 | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 1 | 45000 | 45000 | 1 | 45000 | 45000 | 1 | 0 | 45000 | 0 | Marketing
2873 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Material | (M)BROCHURE PRINTING | NOS | 2800 | 504 | 1411200 | 0 | 0 | 0 | 280 | 504 | 141120 | 0 | 0 | 0 | 2800 | 148.16 | 414856.96 | 2520 | 0 | 1270080 | 996343.04 | Marketing
2874 | SELLING COST - Marketing Mural Project and Layout | 10 | Started | Material | (M)BROCHURE PRINTING (DIGITAL PRINTED SHEET) | NOS | 1440 | 11.2 | 16128 | 0 | 0 | 0 | 144 | 11.2 | 1612.8 | 0 | 0 | 0 | 1440 | 16.33 | 23514.62 | 1296 | 0 | 14515.2 | -7386.62 | Marketing
2875 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Cost of cleaning | NOS | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 1 | 1180 | 1180 | 1 | 0 | 1180 | 0
2876 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Cost of Model | LS | 3 | 967600 | 2902800 | 0 | 0 | 0 | 0 | 967600 | 0 | 3 | 329220 | 987660 | 3 | 329220 | 987660 | 3 | 0 | 2902800 | 1915140
2877 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)DELIVERY CHARGES | NOS | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | 2360 | 2360 | 1 | 2360 | 2360 | 1 | 0 | 1200 | -1160
2878 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Fixing Charge | NOS | 1 | 1770 | 1770 | 0 | 0 | 0 | 0 | 1770 | 0 | 1 | 1770 | 1770 | 1 | 1770 | 1770 | 1 | 0 | 1770 | 0
2879 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Glass for Miniature | LS | 2 | 6490 | 12980 | 0 | 0 | 0 | 0 | 6490 | 0 | 1.667 | 32221.72 | 53713.6 | 1.667 | 32221.72 | 53713.6 | 2 | 0.333 | 12980 | -40733.6
2880 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Lighting | LS | 1 | 45000 | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 0.667 | 53100 | 35417.7 | 0.6659 | 53100 | 35359.29 | 1 | 0.3341 | 45000 | 9640.71
2881 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Main road and landscape changing | LS | 1 | 45000 | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 0.667 | 53100 | 35417.7 | 0.667 | 53100 | 35417.7 | 1 | 0.333 | 45000 | 9582.3
2882 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Tower damage repairing cost | NOS | 1 | 14160 | 14160 | 0 | 0 | 0 | 0 | 14160 | 0 | 1 | 14160 | 14160 | 1 | 14160 | 14160 | 1 | 0 | 14160 | 0
2883 | SELLING COST - Marketing Scale Miniature Model | 10 | Started | Labour | (L)Tower re-installation | NOS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
2884 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)DELIVERY & INSTALLATION | NOS | 2 | 3500 | 7000 | 0 | 0 | 0 | 0 | 3500 | 0 | 2 | 5546 | 11092 | 2 | 5546 | 11092 | 2 | 0 | 7000 | -4092 | Marketing
2885 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)Matter - "AMRITAYA" | NOS | 2 | 22089.6 | 44179.2 | 0 | 0 | 0 | 0 | 22089.6 | 0 | 2 | 39718.8 | 79437.6 | 2 | 39718.8 | 79437.6 | 2 | 0 | 44179.2 | -35258.4 | Marketing
2886 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)Matter - "FOREVER BY THE GANGES" | NOS | 2 | 5400 | 10800 | 0 | 0 | 0 | 0 | 5400 | 0 | 2 | 6372 | 12744 | 2 | 6372 | 12744 | 2 | 0 | 10800 | -1944 | Marketing
2887 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)Matter - "ORCHARD" | NOS | 2 | 2100 | 4200 | 0 | 0 | 0 | 0 | 2100 | 0 | 2 | 2655 | 5310 | 2 | 2655 | 5310 | 2 | 0 | 4200 | -1110 | Marketing
2888 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)Matter - "OSWAL LOGO" | NOS | 1 | 17346 | 17346 | 0 | 0 | 0 | 0 | 17346 | 0 | 1 | 17346 | 17346 | 1 | 17346 | 17346 | 1 | 0 | 17346 | 0 | Marketing
2889 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)POWER SUPPLY | NOS | 1 | 10620 | 10620 | 0 | 0 | 0 | 0 | 10620 | 0 | 1 | 10620 | 10620 | 1 | 10620 | 10620 | 1 | 0 | 10620 | 0 | Marketing
2890 | SELLING COST - Marketing Outdoor and Indoor Signage | 10 | Started | Labour | (L)Repair,Fitting, Fixing & Wiring | NOS | 1 | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 1 | 0 | 4000 | -720 | Marketing
2891 | SELLING COST - Marketing Project Isometric View Fees | 10 | Started | Labour | (L)Creative Consultation Cost | NOS | 16 | 8260 | 132160 | 0 | 0 | 0 | 2 | 8260 | 16520 | 13 | 7000 | 91000 | 13 | 7000 | 91000 | 14 | 3 | 115640 | 41160 | Marketing
2892 | SELLING COST - Marketing Project Isometric View Fees | 10 | Started | Labour | (L)Entire Floor Plan View | NOS | 6 | 1770 | 10620 | 0 | 0 | 0 | 1 | 1770 | 1770 | 6 | 8500 | 51000 | 6 | 8500 | 51000 | 5 | 0 | 8850 | -40380 | Marketing
2893 | SELLING COST - Marketing SMS Campaign | 10 | Started | Labour | (L)DLT Registration | LS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
2894 | SELLING COST - Marketing SMS Campaign | 10 | Started | Labour | (L)SMS Blast | NOS | 69024 | 0.15 | 10353.6 | 0 | 0 | 0 | 6902 | 0.15 | 1035.3 | 34512 | 0.15 | 5294.14 | 34512 | 0.15 | 5294.14 | 62122 | 34512 | 9318.3 | 5059.46
2895 | SELLING COST - Marketing SMS Campaign | 10 | Started | Labour | (L)Transactional SMS | NOS | 10000 | 0.29 | 2900 | 0 | 0 | 0 | 1000 | 0.29 | 290 | 10000 | 0.3 | 2950 | 10000 | 0.3 | 2950 | 9000 | 0 | 2610 | -50
2896 | SELLING COST - Marketing SMS Campaign | 10 | Started | Labour | (L)WhatsApp Blast | NOS | 69024 | 0.89 | 61431.36 | 0 | 0 | 0 | 6902 | 0.89 | 6142.78 | 34512 | 0.89 | 30543.12 | 34512 | 0.89 | 30543.12 | 62122 | 34512 | 55288.58 | 30888.24
2897 | SELLING COST - Marketing News Paper Ads | 10 | Started | Labour | (L)ABP News Paper Advertisement | LS | 1 | 2647920 | 2647920 | 0 | 0 | 0 | 0 | 2647920 | 0 | 1 | 2356200 | 2356200 | 1 | 2356200 | 2356200 | 1 | 0 | 2647920 | 291720
2898 | SELLING COST - Marketing News Paper Ads | 10 | Started | Labour | (L)ABP(GNP/PAGE-L & 2 Colour) | LS | 1 | 2032800 | 2032800 | 0 | 0 | 0 | 0 | 2032800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2032800 | 2032800
2899 | SELLING COST - Marketing News Paper Ads | 10 | Started | Labour | (L)Notice publication | LS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 32340 | 32340 | 1 | 32340 | 32340 | 1 | 0 | 1.18 | -32338.82
2900 | SELLING COST - Marketing News Paper Ads | 10 | Started | Labour | (L)Sanmarg (COC page-1 & 2 Colour) | LS | 1 | 50820 | 50820 | 0 | 0 | 0 | 0 | 50820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50820 | 50820
2901 | SELLING COST - Marketing Radio Advertising | 10 | Started | Labour | (L)BIG FM | Secs | 4500 | 29.5 | 132750 | 0 | 0 | 0 | 450 | 29.5 | 13275 | 0 | 0 | 0 | 0 | 0 | 0 | 4050 | 4500 | 119475 | 132750
2902 | SELLING COST - Marketing Radio Advertising | 10 | Started | Labour | (L)RADIO MIRCHI | Secs | 6000 | 59 | 354000 | 0 | 0 | 0 | 600 | 59 | 35400 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 6000 | 318600 | 354000
2903 | SELLING COST - Marketing Radio Advertising | 10 | Started | Labour | (L)RED FM 93.5 | Secs | 4500 | 41.3 | 185850 | 0 | 0 | 0 | 450 | 41.3 | 18585 | 0 | 0 | 0 | 0 | 0 | 0 | 4050 | 4500 | 167265 | 185850
2904 | SELLING COST - Marketing Acrylic Stand and Poster Box | 10 | Started | Labour | (L)Sunboard with eco solvent vinyl with cover box & stand | PCS | 3 | 4000 | 12000 | 0 | 0 | 0 | 0 | 4000 | 0 | 3 | 5015 | 15045 | 1 | 5015 | 5015 | 3 | 2 | 12000 | 6985
2905 | SELLING COST - Marketing Acrylic Stand and Poster Box | 10 | Started | Labour | (L)Table display stand made by acrylic sheet | PCS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 649 | 2596 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
2906 | SELLING COST - Marketing Mailers | 10 | Started | Labour | (L)Email Templated for Mail Chimp | NOS | 3 | 1000 | 3000 | 0 | 0 | 0 | 0 | 1000 | 0 | 2 | 1500 | 3000 | 2 | 1500 | 3000 | 3 | 1 | 3000 | 0 | Digital Marketing
2907 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Actors for TVC Films | LUMSUM | 1 | 212400 | 212400 | 0 | 0 | 0 | 0 | 212400 | 0 | 1 | 23600 | 23600 | 1 | 23600 | 23600 | 1 | 0 | 212400 | 188800
2908 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Ad Film Shoot | LUMSUM | 2 | 566400 | 1132800 | 0 | 0 | 0 | 0 | 566400 | 0 | 2 | 377600 | 755200 | 2 | 377600 | 755200 | 2 | 0 | 1132800 | 377600
2909 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Ad Film Shoot incl. 4K Shoot, equipment & manpower | LS | 1 | 47200 | 47200 | 0 | 0 | 0 | 0 | 47200 | 0 | 1 | 51920 | 51920 | 1 | 51920 | 51920 | 1 | 0 | 47200 | -4720
2910 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Drone Shoot | NOS | 2 | 8000 | 16000 | 0 | 0 | 0 | 0 | 8000 | 0 | 1.75 | 21714.29 | 38000 | 1.625 | 20307.69 | 33000 | 2 | 0.375 | 16000 | -17000
2911 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Edit of 8 individual videos with graphics and text | NOS | 1 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 30000 | 30000
2912 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)GoPro Shoot | NOS | 1 | 8000 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 8000 | 0
2913 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Re-edit of location video | NOS | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 1 | 7000 | 7000 | 1 | 7000 | 7000 | 1 | 0 | 7000 | 0
2914 | SELLING COST - Marketing Film Shoot | 10 | Started | Labour | (L)Still photo and video shoot | LS | 2 | 20000 | 40000 | 0 | 0 | 0 | 0 | 20000 | 0 | 2 | 97969 | 195938 | 2 | 97969 | 195938 | 2 | 0 | 40000 | -155938
2915 | SELLING COST - Marketing Cab Services for Customer | 10 | Started | Labour | (L)Cab Service for Marketing | LS | 240000 | 1.18 | 283200 | 0 | 0 | 0 | 24000 | 1.18 | 28320 | 77287.48 | 1 | 77287.48 | 77287.48 | 1.07 | 82621.82 | 216000 | 162712.52 | 254880 | 200578.18
2916 | SELLING COST - Marketing Cab Services for Customer | 10 | Started | Labour | (L)Car Hire Charges | NOS | 100000 | 1.18 | 118000 | 0 | 0 | 0 | 10000 | 1.18 | 11800 | 100000 | 1.08 | 108250 | 21061.89 | 1.08 | 22676.55 | 90000 | 78938.11 | 106200 | 95323.45
2917 | SELLING COST - Marketing Cab Services for Customer | 10 | Started | Labour | (L)Car Rental Service | HOURS | 240 | 212.4 | 50976 | 0 | 0 | 0 | 24 | 212.4 | 5097.6 | 146.18 | 189 | 27628.02 | 146.18 | 189 | 27628.04 | 216 | 93.82 | 45878.4 | 23347.96
2918 | SELLING COST - Marketing Donation | 10 | Started | Material | (M)Big Size School Bags | NOS | 20 | 240 | 4800 | 20 | 240 | 4800 | 2 | 240 | 480 | 20 | 240 | 4800 | 20 | 240 | 4800 | 18 | 0 | 4320 | 0
2919 | SELLING COST - Marketing Donation | 10 | Started | Material | (M)JUTE BAG | NOS | 200 | 94.4 | 18880 | 200 | 94.4 | 18880 | 20 | 94.4 | 1888 | 200 | 102.07 | 20414 | 200 | 101.79 | 20358.88 | 180 | 0 | 16992 | -1478.88
2920 | SELLING COST - Marketing Donation | 10 | Started | Material | (M)Small Size School Bags | NOS | 60 | 175 | 10500 | 60 | 175 | 10500 | 6 | 175 | 1050 | 60 | 175 | 10500 | 60 | 175 | 10500 | 54 | 0 | 9450 | 0
2921 | SELLING COST - Marketing Painting | 0 | Started | Labour | (L)CANVAS PAINTING | LUMSUM | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 0 | 10000 | 0
2922 | SELLING COST - Marketing Project Events | 10 | Started | Labour | (L)Amritaya Launch Event | LS | 1 | 592920.5 | 592920.5 | 0 | 0 | 0 | 0 | 592920.5 | 0 | 1 | 592920.5 | 592920.5 | 1 | 592920.5 | 592920.5 | 1 | 0 | 592920.5 | 0
2923 | SELLING COST - Marketing Project Events | 10 | Started | Labour | (L)Catering Event for Lunch | LS | 1 | 270000 | 270000 | 0 | 0 | 0 | 0 | 270000 | 0 | 1 | 270000 | 270000 | 1 | 270000 | 270000 | 1 | 0 | 270000 | 0
2924 | SELLING COST - Marketing Project Events | 10 | Started | Labour | (L)Durga Puja Pass MIRCHI TE DEBIPOKKHO | LUMSUM | 1 | 106200 | 106200 | 0 | 0 | 0 | 0 | 106200 | 0 | 1 | 148680 | 148680 | 1 | 148680 | 148680 | 1 | 0 | 106200 | -42480
2925 | SELLING COST - Marketing Project Events | 10 | Started | Labour | (L)Event Management on the date of 6-Nov | LS | 3 | 200000 | 600000 | 0 | 0 | 0 | 0 | 200000 | 0 | 3 | 200000 | 600000 | 3 | 200000 | 600000 | 3 | 0 | 600000 | 0
2926 | SELLING COST - Marketing Project Events | 10 | Started | Labour | (L)R N R AWARD 2024 for 65 PAX | LS | 70 | 1050 | 73500 | 0 | 0 | 0 | 7 | 1050 | 7350 | 1 | 68250 | 68250 | 1 | 68250 | 68250 | 63 | 69 | 66150 | 5250
2927 | SELLING COST - Marketing Project Events | 10 | Started | Labour | (L)R N R AWARD 2024 Other Expenses | LS | 1 | 23600 | 23600 | 0 | 0 | 0 | 0 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 23600 | 23600
2928 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)4IN1 COMBO GIFT SET | SET | 10 | 861.4 | 8614 | 0 | 0 | 0 | 1 | 861.4 | 861.4 | 0 | 0 | 0 | 10 | 1063.31 | 10633.12 | 9 | 0 | 7752.6 | -2019.12
2929 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)ACRYLIC BADGE | NOS | 25 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 25 | 88.5 | 2212.5 | 22 | 0 | 0 | -2212.5
2930 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)AMRITAYA LAUNCHING EXPENSE | NOS | 83953 | 0 | 0 | 0 | 0 | 0 | 8395 | 0 | 0 | 0 | 0 | 0 | 83953 | 2 | 167906 | 75558 | 0 | 0 | -167906
2931 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)APPLE AIRPODS-3 | SET | 1 | 19505.4 | 19505.4 | 0 | 0 | 0 | 0 | 19505.4 | 0 | 0 | 0 | 0 | 1 | 19500 | 19500 | 1 | 0 | 19505.4 | 5.4
2932 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)APPLE I-PH-14 128GB | SET | 1 | 72499.2 | 72499.2 | 0 | 0 | 0 | 0 | 72499.2 | 0 | 0 | 0 | 0 | 1 | 72500 | 72500 | 1 | 0 | 72499.2 | -0.8
2933 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)ARETE 110" FIXED FRAME SCREEN | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 51920 | 51920 | 1 | 0 | 0 | -51920
2934 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)FRIDGE MAGNET | NOS | 1 | 70 | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 800 | 63.75 | 51000 | 1 | -799 | 70 | -50930
2935 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)JUTE BAG | NOS | 1 | 94.4 | 94.4 | 0 | 0 | 0 | 0 | 94.4 | 0 | 0 | 0 | 0 | 300 | 95.19 | 28557.9 | 1 | -299 | 94.4 | -28463.5
2936 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)JUTE FOLDER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 166.47 | 63092.89 | 1 | -378 | 0 | -63092.89
2937 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)JUTE POUCH | NOS | 1 | 23.6 | 23.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 800 | 21.28 | 17024.4 | 1 | -799 | 23.6 | -17000.8
2938 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)MAGNET | NOS | 1 | 106.2 | 106.2 | 0 | 0 | 0 | 0 | 106.2 | 0 | 0 | 0 | 0 | 1 | 39.33 | 39.33 | 1 | 0 | 106.2 | 66.87
2939 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)PHOTO FRAME | NOS | 10 | 5308.8 | 53088 | 10 | 5308.8 | 53088 | 1 | 5308.8 | 5308.8 | 10 | 275 | 2750 | 10 | 732.73 | 7327.27 | 9 | 0 | 47779.2 | 45760.73
2940 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)Pocket Badges Magnet | NOS | 9 | 177 | 1593 | 9 | 177 | 1593 | 1 | 177 | 177 | 9 | 150 | 1350 | 9 | 150 | 1350 | 8 | 0 | 1416 | 243
2941 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)PROJECT IMPLEMENTATION CHARGE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21968.02 | 21968.02 | 1 | 0 | 0 | -21968.02
2942 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)Rapz Active786 | NOS | 1 | 1734.6 | 1734.6 | 0 | 0 | 0 | 0 | 1734.6 | 0 | 0 | 0 | 0 | 40 | 1739.99 | 69599.72 | 1 | -39 | 1734.6 | -67865.12
2943 | SELLING COST - Marketing Project Events | 10 | Started | Material | (M)SHOWPIECE - FLAG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 165.2 | 33040 | 1 | -199 | 0 | -33040
2944 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)1 PC, ALAM OR HINDALCO 1.3 MM ALUMINIUM DOOR SHUTTER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2945 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)BALCONY SLIDING 5 MM PLAIN GLASS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2946 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)BOUNDARY WALL:- APPLYING Of 2 COAT FINE PUTTY | NOS | 1000 | 7.5 | 7500 | 0 | 0 | 0 | 0 | 7.5 | 0 | 214.08 | 9.44 | 2020.92 | 214.08 | 9.44 | 2020.92 | 1000 | 785.92 | 7500 | 5479.08
2947 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)COPPER COMMUNICATION CABLE | MTR | 17 | 1.18 | 20.06 | 0 | 0 | 0 | 0 | 1.18 | 0 | 17 | 229.05 | 3893.85 | 17 | 229.05 | 3893.85 | 17 | 0 | 20.06 | -3873.79
2948 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)COPPER PIPING | FT | 50 | 295 | 14750 | 0 | 0 | 0 | 0 | 295 | 0 | 50 | 318.6 | 15930 | 50 | 318.6 | 15930 | 50 | 0 | 14750 | -1180
2949 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)CUSTOMER SITTING AREA 5 MM PLAIN GLASS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2950 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)CUSTOMER SITTING AREA, A.V ROOM WINDOW & MARKETTING OFFICE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2951 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)DELIVERY CHARGES (INCLUDING LOADING & UN LOADING) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2952 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)Dismantling of 1.5 Ton AC | NOS | 4 | 590 | 2360 | 0 | 0 | 0 | 0 | 590 | 0 | 4 | 590 | 2360 | 4 | 590 | 2360 | 4 | 0 | 2360 | 0
2953 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)DOMAL 1.5 SECTION DOOR (7' 0" X 3' 0") POWDER COATED FRAME, | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2954 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)Gas Charging | NOS | 1 | 2006 | 2006 | 0 | 0 | 0 | 0 | 2006 | 0 | 1 | 2006 | 2006 | 1 | 2006 | 2006 | 1 | 0 | 2006 | 0
2955 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)GLASS DOOR & FIXED GLASS FIXING BETWEEN CUSTOMER SITTING | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2956 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)GLASS DOOR (12 MM TOUGHENED GLASS) AT MARKETTING OFFICE WITH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2957 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)GLASS FASSADE AT CUSTOMER SITTING AREA (12 MM TOUGHENENED | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2958 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)INVISIBLE ELEVATION GRILL FIXING (ONLY LABOR CHARGE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2959 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)KITCHEN WASH AREA 5 MM PLAIN GLASS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2960 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)L/C CHARGES FOR KERB STONE PAINTING | NOS | 800 | 11.8 | 9440 | 0 | 0 | 0 | 0 | 11.8 | 0 | 620.035 | 11.8 | 7316.41 | 620.035 | 11.8 | 7316.41 | 800 | 179.965 | 9440 | 2123.59
2961 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)L/C FOR M.S. STRUCTURAL PAINTING INCL. MAT.+LAB. | RFT | 300 | 11.8 | 3540 | 0 | 0 | 0 | 0 | 11.8 | 0 | 283.796 | 11.8 | 3348.8 | 283.796 | 11.8 | 3348.8 | 300 | 16.204 | 3540 | 191.2
2962 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)L/C FOR SHERA BOARD REPAIRING & FIXING | NOS | 150 | 41.3 | 6195 | 0 | 0 | 0 | 0 | 41.3 | 0 | 150 | 41.3 | 6195 | 150 | 41.3 | 6195 | 150 | 0 | 6195 | 0
2963 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)L/C FOR WHITE PAINT/PRIMER | NOS | 6010 | 11.8 | 70918 | 0 | 0 | 0 | 0 | 11.8 | 0 | 6005.071 | 11.8 | 70859.83 | 6005.071 | 11.8 | 70859.83 | 6010 | 4.929 | 70918 | 58.17
2964 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)L/C FOR WHITE PRIMIMG WORK | SQFT | 161 | 5.9 | 949.9 | 0 | 0 | 0 | 0 | 5.9 | 0 | 160.084 | 5.9 | 944.5 | 160.084 | 5.9 | 944.5 | 161 | 0.916 | 949.9 | 5.4
2965 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)Online Campaign & Promotion | LS | 1 | 731010 | 731010 | 0 | 0 | 0 | 0 | 731010 | 0 | 1 | 590000 | 590000 | 1 | 590000 | 590000 | 1 | 0 | 731010 | 141010
2966 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)SHERABOARD PAINT INCLUDING PAINT& LACQUER (BOTH SIDE) | NOS | 350 | 98 | 34300 | 0 | 0 | 0 | 0 | 98 | 0 | 159.907 | 115.64 | 18491.646 | 159.907 | 115.64 | 18491.65 | 350 | 190.093 | 34300 | 15808.35
2967 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)SHERABOARD PAINT INCLUDING PAINT& LACQUER (SINGLE SIDE) | NOS | 3318 | 50 | 165900 | 0 | 0 | 0 | 0 | 50 | 0 | 3317.63 | 59 | 195740.18 | 3317.63 | 59 | 195740.18 | 3318 | 0.37 | 165900 | -29840.18
2968 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Labour | (L)Std. Installation Charges for AC installation | NOS | 4 | 1770 | 7080 | 0 | 0 | 0 | 0 | 1770 | 0 | 4 | 1770 | 7080 | 4 | 1770 | 7080 | 4 | 0 | 7080 | 0
2969 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)1.5 TON AC | NOS | 2 | 33500.2 | 67000.4 | 2 | 33500.2 | 67000.4 | 0 | 33500.2 | 0 | 2 | 37000 | 74000 | 2 | 37000 | 74000 | 2 | 0 | 67000.4 | -6999.6
2970 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)7W COB DEEP RECESS | NOS | 3 | 696.2 | 2088.6 | 0 | 0 | 0 | 0 | 696.2 | 0 | 0 | 0 | 0 | 3 | 696.2 | 2088.6 | 3 | 0 | 2088.6 | 0
2971 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)AC DWF 1 | SQFT | 720.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720.9 | 11.95 | 8617.21 | 720.9 | 0 | 0 | -8617.21
2972 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)AC DWF 2 | SET | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 597.67 | 597.67 | 1 | 0 | 0 | -597.67
2973 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)AC DWF 3 | SQFT | 558.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558.9 | 5.98 | 3340.38 | 558.9 | 0 | 0 | -3340.38
2974 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)AC DWF. | FT | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 58.68 | 2347.07 | 40 | 0 | 0 | -2347.07
2975 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)BEDROOM1 CLOTH | MTR | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 886.2 | 2215.5 | 2.5 | 0 | 0 | -2215.5
2976 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)BEDROOM1 CLOTH (2) | MTR | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2320.5 | 4641 | 2 | 0 | 0 | -4641
2977 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)CLOTH D.CHAIR | MTR | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 837.9 | 2513.7 | 3 | 0 | 0 | -2513.7
2978 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)CR BC CARPET | SQFT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.31 | 64.52 | 5310.44 | 1 | -81.31 | 0 | -5310.44
2979 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)CR BC CARPET TILE | SQFT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 135.01 | 21872.06 | 1 | -161 | 0 | -21872.06
2980 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)CURTAIN | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 753.1 | 9413.75 | 1 | -11.5 | 0 | -9413.75
2981 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)DB 12A/88A | NOS | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 1 | 118 | 118 | 1 | 0 | 118 | 0
2982 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)DC JACK | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 2 | 35.4 | 70.8 | 1 | -1 | 35.4 | -35.4
2983 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)DENON SOUNDBAR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65962 | 65962 | 1 | 0 | 0 | -65962
2984 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)DIMOUT BEDROOM1 | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 413.7 | 827.4 | 1 | -1 | 0 | -827.4
2985 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)DINING ROOM CLOTH | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 942.9 | 6600.3 | 1 | -6 | 0 | -6600.3
2986 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Door Closure | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1330 | 2660 | 1 | -1 | 0 | -2660
2987 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)DORMA XL - C | SET | 1 | 9700 | 9700 | 0 | 0 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 1 | 9700 | 9700 | 1 | 0 | 9700 | 0
2988 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Dorset Cylinder Black | SETS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 569.8 | 1139.6 | 1 | -1 | 0 | -1139.6
2989 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Dorset Cylinder Black CI0501GM | SETS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 565.94 | 1131.88 | 1 | -1 | 0 | -1131.88
2990 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Dorset ML110 SS Mortise- | SETS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 708.4 | 2833.6 | 1 | -3 | 0 | -2833.6
2991 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Dorset Mortise Lock Farroto Altor-GM- | SETS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1971.19 | 7884.76 | 1 | -3 | 0 | -7884.76
2992 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)FL RDL FLIM | SQFT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 59.77 | 1673.48 | 1 | -27 | 0 | -1673.48
2993 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)FLOOR MAT | NOS | 1 | 3393.6 | 3393.6 | 0 | 0 | 0 | 0 | 3393.6 | 0 | 0 | 0 | 0 | 3 | 4087.33 | 12262 | 1 | -2 | 3393.6 | -8868.4
2994 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Frosted Film | SQFT | 112 | 153.4 | 17180.8 | 112 | 153.4 | 17180.8 | 0 | 153.4 | 0 | 112 | 182.9 | 20484.8 | 112 | 182.9 | 20484.8 | 112 | 0 | 17180.8 | -3304
2995 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)GANESH JI IDOL | NOS | 1 | 6500 | 6500 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6500 | 6500
2996 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)GARDEN TABLE & CHAIR WITH UMBRELLA | SET | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2997 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)GARDEN UMBRELLA | NOS | 1 | 190 | 190 | 0 | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 3 | 190 | 570 | 1 | -2 | 190 | -380
2998 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)GCL 119 | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 658.22 | 2632.86 | 1 | -3 | 0 | -2632.86
2999 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)GYPSUM SCREW | NOS | 1 | 23.6 | 23.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 30 | 21.64 | 649.24 | 1 | -29 | 23.6 | -625.64
3000 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)HALL Dining wall+Entrance | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3000 | 9000 | 1 | -2 | 0 | -9000
3001 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)HALL Divider | MTR | 1 | 2250 | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2 | 2250 | 4500 | 1 | -1 | 2250 | -2250
3002 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)HALL Pelmet | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2250 | 2250 | 1 | 0 | 0 | -2250
3003 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)HALL Sofa Wall | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3000 | 6000 | 1 | -1 | 0 | -6000
3004 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)HALL Tv wall | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3000 | 3000 | 1 | 0 | 0 | -3000
3005 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)HALOPIN 65940 40W G9 MIRCHI (OSRAM) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 118 | 236 | 1 | -1 | 0 | -236
3006 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)LED STRIP LIGHT | MTR | 40 | 1180 | 47200 | 40 | 1180 | 47200 | 0 | 1180 | 0 | 40 | 52.33 | 2093.2 | 0 | 0 | 0 | 40 | 40 | 47200 | 47200
3007 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)LED STRIP LIGHT ADAPTER | NOS | 10 | 118 | 1180 | 10 | 118 | 1180 | 0 | 118 | 0 | 10 | 124.6 | 1246 | 0 | 0 | 0 | 10 | 10 | 1180 | 1180
3008 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Living Room CLOTH | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 803.25 | 10040.62 | 1 | -11.5 | 0 | -10040.62
3009 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)LLF-133A-3K 12W CREE LED DEEP D/L (LEDLUM) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1214.04 | 33993.09 | 1 | -27 | 0 | -33993.09
3010 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)LM-SV 700 12V 9.6W/830 LED FLEX (OSRAM) | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.45 | 191.21 | 24943.83 | 1 | -129.45 | 0 | -24943.83
3011 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)LM-SV 700 12V 9.6W/830 LED FLEX(OSRAM) | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 190.4 | 1332.8 | 1 | -6 | 0 | -1332.8
3012 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Master Room Headboard | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3000 | 6000 | 1 | -1 | 0 | -6000
3013 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)Master Room Tv Wall | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3000 | 6000 | 1 | -1 | 0 | -6000
3014 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)MBR CLOTH | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 463.05 | 1852.2 | 1 | -3 | 0 | -1852.2
3015 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)MBR CLOTH (2) | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 836.85 | 3765.82 | 1 | -3.5 | 0 | -3765.82
3016 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)MILA- ANTIQUE GOLD WITH LED SINGLE PENDENT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6130.25 | 6130.25 | 1 | 0 | 0 | -6130.25
3017 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)ML-C137 5W LED JOOP SPOT PKW WW | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 663.08 | 5304.64 | 1 | -7 | 0 | -5304.64
3018 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)ML-C139 10W FLAVIA RD PKW-WW | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1012.64 | 15189.55 | 1 | -14 | 0 | -15189.55
3019 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)MOBILE PEDESTAL WITH LOCK 2D1F : 400W X 450D X 600HT | NOS | 1 | 8460.6 | 8460.6 | 0 | 0 | 0 | 0 | 8460.6 | 0 | 0 | 0 | 0 | 4 | 8260 | 33040 | 1 | -3 | 8460.6 | -24579.4
3020 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)MOUNT BOX | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 114.63 | 1604.8 | 1 | -13 | 0 | -1604.8
3021 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)NON CORRUGATED CARTONS | NOS | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 800 | 230.1 | 184080 | 1 | -799 | 236 | -183844
3022 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)OUTDOOR SWING DOLNA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33938.69 | 33938.69 | 1 | 0 | 0 | -33938.69
3023 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)PANNELING | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 794.33 | 21446.78 | 1 | -26 | 0 | -21446.78
3024 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)PHOTO FRAME | NOS | 1 | 5308.8 | 5308.8 | 0 | 0 | 0 | 0 | 5308.8 | 0 | 0 | 0 | 0 | 1 | 11151 | 11151 | 1 | 0 | 5308.8 | -5842.2
3025 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)PHOTO FRAME 12" X 18" | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1062 | 2124 | 1 | -1 | 0 | -2124
3026 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)PLASTIC SHOE COVER | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 1920 | 6.74 | 12948.86 | 1 | -1919 | 11.8 | -12937.06
3027 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)PVC CHAIR | NOS | 1 | 31860 | 31860 | 0 | 0 | 0 | 0 | 31860 | 0 | 0 | 0 | 0 | 4 | 26128.39 | 104513.54 | 1 | -3 | 31860 | -72653.54
3028 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)RL 3W G4 LED 3000K | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 224 | 448 | 1 | -1 | 0 | -448
3029 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)SANDWICH ACYRLIC BOARD | NOS | 1 | 767 | 767 | 0 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 1 | 767 | 767 | 1 | 0 | 767 | 0
3030 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)SG 2 SEATER SOFA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 28063.82 | 56127.64 | 1 | -1 | 0 | -56127.64
3031 | SELLING COST - Marketing Model Flat Finishing Of Sales Offic | 0 | Started | Material | (M)SG 3 SEATER SOFA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 46450.47 | 139351.4 | 1 | -2 | 0 | -139351.4
3032 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3'' X 2'' X 4'0"-5'0" HARDWOOD | CFT | 14.98 | 330 | 4943.4 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 14.98 | 354.75 | 5314.16 | 14.98 | 0 | 4943.4 | -370.76
3033 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3'' X 2'' X 7'0"-8' 0"HARDWOOD | CFT | 34.79 | 430 | 14959.7 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 34.79 | 462.25 | 16081.68 | 34.79 | 0 | 14959.7 | -1121.98
3034 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3/4" HOOK (CHINA) | NOS | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.61 | 66.09 | 10 | 0 | 0 | -66.09
3035 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3/4" UPVC BALL VALVE | NOS | 1 | 212.4 | 212.4 | 0 | 0 | 0 | 0 | 212.4 | 0 | 0 | 0 | 0 | 1 | 221.32 | 221.32 | 1 | 0 | 212.4 | -8.92
3036 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3/4" UPVC ELBOW | NOS | 4 | 23.6 | 94.4 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 4 | 17.74 | 70.95 | 4 | 0 | 94.4 | 23.45
3037 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3/4" UPVC END CAP | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11.11 | 33.34 | 3 | 0 | 0 | -33.34
3038 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)3/4" UPVC PIPE (10' LENGTH) | NOS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 278.32 | 1669.92 | 6 | 0 | 0 | -1669.92
3039 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)6" X 10'0"X 8 MM THICK SHERA BOARD | NOS | 450 | 70.8 | 31860 | 450 | 70.8 | 31860 | 0 | 70.8 | 0 | 450 | 71.52 | 32183.82 | 450 | 71.17 | 32028.44 | 450 | 0 | 31860 | -168.44
3040 | SELLING COST - Marketing Model Flat OUTSIDE WALL AND GATE CL | 0 | Started | Material | (M)GRANITE FLAME FOR OUTSIDE MODEL FLAT | NOS | 170 | 112.1 | 19057 | 170 | 112.1 | 19057 | 0 | 112.1 | 0 | 170 | 188.8 | 32096 | 170 | 186.98 | 31787.08 | 170 | 0 | 19057 | -12730.08
3041 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)ENAMAL PAINT AT GODOWN 3 NOS DOOR & BAJRANGBALI TEMPLE GATE | NOS | 700 | 4 | 2800 | 0 | 0 | 0 | 70 | 4 | 280 | 143.29 | 4 | 573.16 | 143.29 | 4 | 573.16 | 630 | 556.71 | 2520 | 2226.84
3042 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)EXTERIOR BOUNDARY WALL BACK SIDE OF MODEL FLAT | NOS | 900 | 3 | 2700 | 0 | 0 | 0 | 90 | 3 | 270 | 654.28 | 3 | 1962.84 | 654.28 | 3 | 1962.84 | 810 | 245.72 | 2430 | 737.16
3043 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)EXTERIOR BOUNDARY WALL OUT SIDE & BOTH SIDE OF ENTRANCE ROAD | NOS | 8000 | 4 | 32000 | 0 | 0 | 0 | 800 | 4 | 3200 | 4333.06 | 4 | 17332.24 | 4333.06 | 4 | 17332.24 | 7200 | 3666.94 | 28800 | 14667.76
3044 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)EXTERIOR PAINT OF KERB STONE | NOS | 1000 | 3 | 3000 | 0 | 0 | 0 | 100 | 3 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 1000 | 2700 | 3000
3045 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)EXTERIOR PAINT OF RED BRICKS OF CUSTOMER VIEW PATH BOTH SIDE | RFT | 1000 | 2 | 2000 | 0 | 0 | 0 | 100 | 2 | 200 | 827 | 2 | 1654 | 827 | 2 | 1654 | 900 | 173 | 1800 | 346
3046 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)EXTERIOR WALL PAINT OF RECEPTION AREA | NOS | 635 | 7 | 4445 | 0 | 0 | 0 | 64 | 7 | 448 | 601.64 | 7 | 4211.48 | 601.64 | 7 | 4211.48 | 571 | 33.36 | 3997 | 233.52
3047 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)EXTERIOR WALL PAINT OF SITE OFFICE, STORE ROOM & WATER TANK | NOS | 4500 | 4 | 18000 | 0 | 0 | 0 | 450 | 4 | 1800 | 2651.19 | 4 | 10604.76 | 2651.19 | 4 | 10604.76 | 4050 | 1848.81 | 16200 | 7395.24
3048 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)INSIDE WALL,CEILING PAINT AT SALES OFFICE | NOS | 385 | 4 | 1540 | 0 | 0 | 0 | 39 | 4 | 156 | 360.9 | 4 | 1443.6 | 360.9 | 4 | 1443.6 | 346 | 24.1 | 1384 | 96.4
3049 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)INSIDE WALL,CEILING PAINT G.M SIR ,SITE OFFICE , CONF.ROOM | NOS | 1700 | 7 | 11900 | 0 | 0 | 0 | 170 | 7 | 1190 | 1477.54 | 7 | 10342.78 | 1477.54 | 7 | 10342.78 | 1530 | 222.46 | 10710 | 1557.22
3050 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)INTERIOR WALL & CEILING PAINTING AT SECURITY ROOM | NOS | 700 | 6 | 4200 | 0 | 0 | 0 | 70 | 6 | 420 | 252.07 | 6 | 1512.42 | 252.07 | 6 | 1512.42 | 630 | 447.93 | 3780 | 2687.58
3051 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)MODEL FLAT TEXTURE AREA | NOS | 1600 | 2 | 3200 | 0 | 0 | 0 | 160 | 2 | 320 | 831.661 | 2 | 1663.322 | 831.661 | 2 | 1663.32 | 1440 | 768.339 | 2880 | 1536.68
3052 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Labour | (L)SOUTH SIDE BOUNDARY WALL | NOS | 4000 | 3 | 12000 | 0 | 0 | 0 | 400 | 3 | 1200 | 3542.75 | 3 | 10628.25 | 3542.75 | 3 | 10628.25 | 3600 | 457.25 | 10800 | 1371.75
3053 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)CEMENT BASE EXTERIOR PRIMER | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 205 | 820 | 4 | 0 | 0 | -820
3054 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)CEMENT PRIMER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 220 | 220 | 1 | 0 | 0 | -220
3055 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)EXTERIOR WATER BASE PRIMER | NOS | 1 | 224.2 | 224.2 | 0 | 0 | 0 | 0 | 224.2 | 0 | 0 | 0 | 0 | 60 | 160 | 9599.78 | 1 | -59 | 224.2 | -9375.58
3056 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)EXTERIOR WATER BASE PRIMER . | NOS | 1 | 3268.6 | 3268.6 | 0 | 0 | 0 | 0 | 3268.6 | 0 | 0 | 0 | 0 | 3 | 3314.16 | 9942.49 | 1 | -2 | 3268.6 | -6673.89
3057 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)FINE PUTTY | KG | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10249.99 | 10249.99 | 1 | 0 | 0 | -10249.99
3058 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)FINE PUTTY | NOS | 1 | 5015 | 5015 | 0 | 0 | 0 | 0 | 5015 | 0 | 0 | 0 | 0 | 120 | 20 | 2400.12 | 1 | -119 | 5015 | 2614.88
3059 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)FINE PUTTY. | BAG | 1 | 5015 | 5015 | 0 | 0 | 0 | 0 | 5015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5015 | 5015
3060 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)OIL BASE PAINT (SMOKE GREY | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 316.66 | 1899.98 | 1 | -5 | 0 | -1899.98
3061 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)OIL PAINT (DEEP ORANGE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17413.71 | 52241.13 | 1 | -2 | 0 | -52241.13
3062 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)OIL PAINT (DEEP ORANGE) | NOS | 1 | 472 | 472 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 60 | 477.62 | 28657.01 | 1 | -59 | 472 | -28185.01
3063 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)SAND PAPER | NOS | 1 | 23.6 | 23.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 30 | 20.49 | 614.67 | 1 | -29 | 23.6 | -591.07
3064 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)TARPIN OIL | NOS | 1 | 200.6 | 200.6 | 0 | 0 | 0 | 0 | 200.6 | 0 | 0 | 0 | 0 | 23 | 237.25 | 5456.8 | 1 | -22 | 200.6 | -5256.2
3065 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)TARPIN OIL . | LTR | 1 | 1829 | 1829 | 0 | 0 | 0 | 0 | 1829 | 0 | 0 | 0 | 0 | 4 | 1853.73 | 7414.9 | 1 | -3 | 1829 | -5585.9
3066 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)WATER PAPER | DOZ | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 180 | 180 | 1 | 0 | 0 | -180
3067 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)WEATHER GUARD EXTERIOR PAINT (NATURAL WHITE) | NOS | 1 | 389.4 | 389.4 | 0 | 0 | 0 | 0 | 389.4 | 0 | 0 | 0 | 0 | 40 | 290 | 11599.88 | 1 | -39 | 389.4 | -11210.48
3068 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)WEATHER GUARD EXTERIOR PAINT (NATURAL WHITE): | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 12512.5 | 25024.99 | 1 | -1 | 0 | -25024.99
3069 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)WEATHER GUARD EXTERIOR PAINT (SMOKE GREY | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7000 | 7000 | 1 | 0 | 0 | -7000
3070 | SELLING COST - Marketing Model Flat Interior and Exterior | 10 | Started | Material | (M)WEATHER GUARD EXTERIOR PAINT(SMOKE GREY | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 326.67 | 9800.14 | 1 | -29 | 0 | -9800.14
3071 | SELLING COST - Marketing Model Flat Plumbing Work | 10 | Started | Labour | (L)SUPPLY OF HELPER IN DAILY BASIC | NOS | 30 | 450 | 13500 | 0 | 0 | 0 | 3 | 450 | 1350 | 1 | 450 | 450 | 1 | 450 | 450 | 27 | 29 | 12150 | 13050
3072 | SELLING COST - Marketing Model Flat Plumbing Work | 10 | Started | Labour | (L)SUPPLY OF PLUMBER IN DAILY BASIC | NOS | 50 | 675 | 33750 | 0 | 0 | 0 | 5 | 675 | 3375 | 19.5 | 675 | 13162.5 | 19.5 | 675 | 13162.5 | 45 | 30.5 | 30375 | 20587.5
3073 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Labour | (L)Cost of Model | LS | 1 | 967600 | 967600 | 0 | 0 | 0 | 0 | 967600 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 967600 | 908600
3074 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)1.0 SQ.MM COPPER WIRE (GREEN, 180MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3075 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(BLACK, 180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3076 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)1.5 TON AC | NOS | 1 | 33500.2 | 33500.2 | 0 | 0 | 0 | 0 | 33500.2 | 0 | 0 | 0 | 0 | 1 | 36613.51 | 36613.51 | 1 | 0 | 33500.2 | -3113.31
3077 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)1/2" GYPSUM SCREW | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3078 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)12 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3079 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)16 AMP AC STARTER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3080 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)16 AMP SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3081 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)16 AMP SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3082 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)18 NO G.I WIRE | KG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3083 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)2 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3084 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)2.5 SQ.MM COPPER WIRE (RED,180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3085 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)25 MM 3 WAY CIRCULAR | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3086 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)25 MM FLEXIBLE PIPE | MTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3087 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)3 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3088 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)4 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3089 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)6 AMP 2 WAY SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3090 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)6 AMP SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3091 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)6 AMP SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3092 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)6 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3093 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)6/16 AMP SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3094 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)6/16 AMP SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3095 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)8 MOD COVER | NOS | 1 | 413 | 413 | 1 | 413 | 413 | 0 | 413 | 0 | 1 | 115.3 | 115.3 | 1 | 115.3 | 115.3 | 1 | 0 | 413 | 297.7
3096 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)8 MODULAR BOX (RECTANGULAR) COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3097 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)8 MODULAR BOX (SQUARE) COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3098 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)AC SOCKET | NOS | 1 | 448.4 | 448.4 | 1 | 448.4 | 448.4 | 0 | 448.4 | 0 | 1 | 126.22 | 126.22 | 1 | 126.22 | 126.22 | 1 | 0 | 448.4 | 322.18
3099 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)AC STARTER | NOS | 1 | 1510.4 | 1510.4 | 1 | 1510.4 | 1510.4 | 0 | 1510.4 | 0 | 1 | 421.6 | 421.6 | 1 | 421.6 | 421.6 | 1 | 0 | 1510.4 | 1088.8
3100 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)BLANK SWITCH | NOS | 6 | 61.36 | 368.16 | 0 | 0 | 0 | 1 | 61.36 | 61.36 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 306.8 | 368.16
3101 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)BLANK SWITCH (WHITE) | NOS | 6 | 70.8 | 424.8 | 6 | 70.8 | 424.8 | 1 | 70.8 | 70.8 | 6 | 18.83 | 112.9998 | 6 | 18.83 | 113 | 5 | 0 | 354 | 311.8
3102 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)BNC CONNECTOR | NOS | 53 | 47.2 | 2501.6 | 0 | 0 | 0 | 5 | 47.2 | 236 | 0 | 0 | 0 | 53 | 41.3 | 2188.9 | 48 | 0 | 2265.6 | 312.7
3103 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)CABLE TV SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3104 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)FAN REGULATOR | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3105 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)FOOT LAMP | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3106 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)PVC TAPE BLACK | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 21.56 | 107.82 | 0 | -5 | 0 | -107.82
3107 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)PVC TAPE BLUE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3108 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)PVC TAPE GREEN | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3109 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)PVC TAPE RED | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3110 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)PVC TAPE YELLOW | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3111 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)SINGLE POLE 10 AMP MCB | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3112 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)SINGLE POLE 20 AMP MCB | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3113 | SELLING COST - Marketing Model Flat Electrical | 10 | Started | Material | (M)TELEPHONE/ INTERCOME SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3114 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)BALDOCER LINUS GRAFITO. | BOX | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2046.16 | 18415.43 | 9 | 0 | 0 | -18415.43
3115 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)FL VNE FLORING | SQFT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558.9 | 101.6 | 56786.42 | 1 | -557.9 | 0 | -56786.42
3116 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)GRANITE FLAME FOR OUTSIDE MODEL FLAT | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3117 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)MEGHMA H/L | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3118 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)MEGHMA H/L. | BOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3119 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)MERLIN GRISS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3120 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)NICKSON BG | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3121 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)NOEMI WHITE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3122 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)PAULA DIMGRY | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3123 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)PAULA SANDLE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3124 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)TIJOLA H/L | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3125 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)TIJOLA H/L. | BOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3126 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)TILO FIX | BAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3127 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)WALL TIJOLA LT. | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3128 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)YORK DK | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3129 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)YORK DK. | BOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3130 | SELLING COST - Marketing Model Flat Flooring | 0 | Started | Material | (M)YORK LT | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3131 | SELLING COST - Marketing Model Flat Outside Wall Work | 10 | Started | Labour | (L)PERNILA STONE TEXTURE OUTSIDE OF MODEL FLAT | NOS | 2000 | 24 | 48000 | 0 | 0 | 0 | 200 | 24 | 4800 | 1941.44 | 28.32 | 54981.58 | 1941.44 | 28.32 | 54981.58 | 1800 | 58.56 | 43200 | -6981.58
3132 | SELLING COST - Road Development Plumbing Work | 10 | Started | Labour | (L)RUSTOMJEE PARSE RD. PLUMBING REPAIRING, LABOUR & MATERIALS | NOS | 35 | 8000 | 280000 | 0 | 0 | 0 | 4 | 8000 | 32000 | 35 | 8000 | 280000 | 35 | 8000 | 280000 | 31 | 0 | 248000 | 0
3133 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)40 MM JHAMA MAXIMUM | CFT | 8032 | 7 | 56224 | 0 | 0 | 0 | 803 | 7 | 5621 | 8032 | 8.26 | 66344.32 | 8032 | 8.26 | 66344.32 | 7229 | 0 | 50603 | -10120.32
3134 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)75 MM THICK WBM WITH JHAMA BATS (60:40) INCLUDING JCB, | SQM | 2265 | 165 | 373725 | 0 | 0 | 0 | 227 | 165 | 37455 | 2110.18 | 194.7 | 410852.04 | 2110.18 | 194.7 | 410852.06 | 2038 | 154.82 | 336270 | -37127.06
3135 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)8’’ BRICK WORK EXCLUDING CEMENT, SAND, BRICKS, LABOUR ETC. | CUM | 25 | 2035 | 50875 | 0 | 0 | 0 | 3 | 2035 | 6105 | 12.06 | 2401.3 | 28959.68 | 12.06 | 2401.3 | 28959.7 | 22 | 12.94 | 44770 | 21915.3
3136 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)BREAKING OR SCALING AND DISPOSAL OF BITUMEN AROUND 300 MM | CUM | 1250 | 309 | 386250 | 0 | 0 | 0 | 125 | 309 | 38625 | 1026.07 | 364.62 | 374125.65 | 1026.07 | 364.62 | 374125.65 | 1125 | 223.93 | 347625 | 12124.35
3137 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)JCB HIRE CHARGE | HOURS | 40 | 850 | 34000 | 0 | 0 | 0 | 4 | 850 | 3400 | 40 | 1003 | 40120 | 36 | 1003 | 36108 | 36 | 4 | 30600 | -2108
3138 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)KERB STONE (600 MM X 300 MM X 150 MM) FIXING EXCLUDING KERB | RMT | 350 | 165 | 57750 | 0 | 0 | 0 | 35 | 165 | 5775 | 350 | 194.7 | 68145 | 350 | 194.7 | 68145 | 315 | 0 | 51975 | -10395
3139 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)LEVELLING / DRESSING / FILLING OF 75 MM THICK GSB (STONE | SQM | 2665 | 138 | 367770 | 0 | 0 | 0 | 267 | 138 | 36846 | 2248.93 | 162.84 | 366215.78 | 2248.93 | 162.84 | 366215.78 | 2398 | 416.07 | 330924 | 1554.22
3140 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)MANHOLE PIT COVER LIFTING | NOS | 18 | 1000 | 18000 | 0 | 0 | 0 | 2 | 1000 | 2000 | 15 | 1180 | 17700 | 15 | 1180 | 17700 | 16 | 3 | 16000 | 300
3141 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)ONLY LABOUR CHARGE FOR 100 MM THICK PAVER BLOCK FIXING | SQM | 2665 | 121 | 322465 | 0 | 0 | 0 | 267 | 121 | 32307 | 2414.04 | 142.78 | 344676.64 | 2414.04 | 142.78 | 344676.64 | 2398 | 250.96 | 290158 | -22211.64
3142 | SELLING COST - Road Development Repairing Work | 10 | Started | Labour | (L)SAUCER DRAIN (450 MM X 200 MM X 100 MM THK) FIXING WITH LABO | RMT | 350 | 165 | 57750 | 0 | 0 | 0 | 35 | 165 | 5775 | 340 | 194.7 | 66198 | 340 | 194.7 | 66198 | 315 | 10 | 51975 | -8448
3143 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 17.85 | 1770 | 31594.5 | 0 | 0 | 0 | 2 | 1770 | 3540 | 0 | 0 | 0 | 4.21 | 1574.62 | 6629.17 | 15.85 | 13.64 | 28054.5 | 24965.33
3144 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 7420 | 10 | 74200 | 0 | 0 | 0 | 742 | 10 | 7420 | 0 | 0 | 0 | 1130 | 9.75 | 11012.75 | 6678 | 6290 | 66780 | 63187.25
3145 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)60 MM PAVER BLOCK | NOS | 20491 | 94.4 | 1934350.4 | 0 | 0 | 0 | 2049 | 94.4 | 193425.6 | 0 | 0 | 0 | 20491 | 89.68 | 1837632.88 | 18442 | 0 | 1740924.8 | 96717.52
3146 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)BRICKS BATS | CFT | 3480 | 40 | 139200 | 0 | 0 | 0 | 348 | 40 | 13920 | 0 | 0 | 0 | 0 | 0 | 0 | 3132 | 3480 | 125280 | 139200
3147 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)JHAMA BATS | CFT | 3446 | 50 | 172300 | 0 | 0 | 0 | 345 | 50 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 3101 | 3446 | 155050 | 172300
3148 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)KERB STONE | NOS | 781 | 200.6 | 156668.6 | 0 | 0 | 0 | 78 | 200.6 | 15646.8 | 0 | 0 | 0 | 697 | 200.6 | 139818.2 | 703 | 84 | 141021.8 | 16850.4
3149 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)PAVER BLOCK (200 MM X 200 MM X 60 MM) | NOS | 1142 | 59 | 67378 | 0 | 0 | 0 | 114 | 59 | 6726 | 0 | 0 | 0 | 1400 | 62.54 | 87556 | 1028 | -258 | 60652 | -20178
3150 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)PICKED JHAMA. | NOS | 5000 | 11 | 55000 | 0 | 0 | 0 | 500 | 11 | 5500 | 0 | 0 | 0 | 5000 | 8.5 | 42500 | 4500 | 0 | 49500 | 12500
3151 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)PSC CEMENT | BAG | 168 | 307.2 | 51609.6 | 0 | 0 | 0 | 17 | 307.2 | 5222.4 | 0 | 0 | 0 | 93 | 308 | 28643.55 | 151 | 75 | 46387.2 | 22966.05
3152 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)SAUCER DRAIN | NOS | 550 | 177 | 97350 | 0 | 0 | 0 | 55 | 177 | 9735 | 0 | 0 | 0 | 167 | 177 | 29559 | 495 | 383 | 87615 | 67791
3153 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)SILVER SAND | CFT | 427 | 25 | 10675 | 0 | 0 | 0 | 43 | 25 | 1075 | 0 | 0 | 0 | 427 | 29 | 12383 | 384 | 0 | 9600 | -1708
3154 | SELLING COST - Road Development Repairing Work | 10 | Started | Material | (M)STONE DUST | MT | 200.99 | 1400 | 281386 | 0 | 0 | 0 | 20 | 1400 | 28000 | 0 | 0 | 0 | 200.99 | 1400 | 281386 | 180.99 | 0 | 253386 | 0
3155 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 35.92 | 1770 | 63578.4 | 35.92 | 1770 | 63578.4 | 4 | 1770 | 7080 | 35.92 | 1800 | 64656 | 13.808 | 1690.49 | 23342.3 | 31.92 | 22.112 | 56498.4 | 40236.1
3156 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 12000 | 10 | 120000 | 12000 | 10 | 120000 | 1200 | 10 | 12000 | 12000 | 9.5 | 114000 | 6290 | 9.5 | 59755 | 10800 | 5710 | 108000 | 60245
3157 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)60 MM PAVER BLOCK | NOS | 25 | 94.4 | 2360 | 0 | 0 | 0 | 3 | 94.4 | 283.2 | 0 | 0 | 0 | 25 | 89.68 | 2242 | 22 | 0 | 2076.8 | 118
3158 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)BRICKS BATS | CFT | 3550 | 40 | 142000 | 3550 | 40 | 142000 | 355 | 40 | 14200 | 3480 | 40 | 139200 | 3480 | 40 | 139200 | 3195 | 70 | 127800 | 2800
3159 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)CONCRETE PAVER BLOCK (40 MM THICK) | NOS | 6.054 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6.054 | 50.74 | 307.18 | 5.054 | 0 | 0 | -307.18
3160 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)JHAMA BATS | CFT | 3470 | 50 | 173500 | 3467 | 50 | 173350 | 347 | 50 | 17350 | 3446 | 45 | 155070 | 3446 | 45 | 155070 | 3123 | 24 | 156150 | 18430
3161 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)KERB STONE | NOS | 1100 | 200.6 | 220660 | 1100 | 200.6 | 220660 | 110 | 200.6 | 22066 | 1100 | 200.6 | 220660 | 403 | 200.6 | 80841.8 | 990 | 697 | 198594 | 139818.2
3162 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)KOTA STONE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.37 | 45.39 | 3874.57 | 1 | -84.37 | 0 | -3874.57
3163 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)M.C. SAND | MT | 1.12 | 1711.5 | 1916.88 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 1.12 | 1689.09 | 1891.78 | 1.12 | 0 | 1916.88 | 25.1
3164 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)MS NAILS | KG | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11.8 | 11.8
3165 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)PPC CEMENT | BAG | 400 | 283.59 | 113436 | 0 | 0 | 0 | 40 | 283.59 | 11343.6 | 0 | 0 | 0 | 1 | 308.69 | 308.69 | 360 | 399 | 102092.4 | 113127.31
3166 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)PSC CEMENT | BAG | 400 | 307.2 | 122880 | 400 | 307.2 | 122880 | 40 | 307.2 | 12288 | 400 | 307.99 | 123197.44 | 134 | 308 | 41271.34 | 360 | 266 | 110592 | 81608.66
3167 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)SAUCER DRAIN | NOS | 750 | 177 | 132750 | 550 | 177 | 97350 | 75 | 177 | 13275 | 550 | 177 | 97350 | 383 | 177 | 67791 | 675 | 367 | 119475 | 64959
3168 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)SPEED BREAKER | MTR | 1 | 649 | 649 | 0 | 0 | 0 | 0 | 649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 649 | 649
3169 | SELLING COST - Road Development Renovation Work | 10 | Started | Material | (M)STONE DUST | MT | 206 | 1400 | 288400 | 201.26 | 1400 | 281764 | 21 | 1400 | 29400 | 200.99 | 1400 | 281386 | 0 | 0 | 0 | 185 | 206 | 259000 | 288400
3170 | SELLING COST - Road Development Beautification Work | 10 | Started | Labour | (L)BOUNDARY WALL:- APPLYING Of 2 COAT FINE PUTTY | NOS | 25000 | 7.5 | 187500 | 0 | 0 | 0 | 2500 | 7.5 | 18750 | 3145.34 | 7.5 | 23590.05 | 3145.34 | 7.5 | 23590.05 | 22500 | 21854.66 | 168750 | 163909.95
3171 | SELLING COST - Road Development Beautification Work | 10 | Started | Labour | (L)ENAMEL PAINT AT LIGHT POST , ELECTRICAL FEEDER BOX : | NOS | 2000 | 8.5 | 17000 | 0 | 0 | 0 | 200 | 8.5 | 1700 | 383.29 | 8.5 | 3257.965 | 383.29 | 8.5 | 3257.97 | 1800 | 1616.71 | 15300 | 13742.03
3172 | SELLING COST - Road Development Beautification Work | 10 | Started | Labour | (L)ENAMEL PAINT AT WOODEN DOOR, WINDOW, GRILL, SHUTTER, G.I | NOS | 12000 | 8.5 | 102000 | 0 | 0 | 0 | 1200 | 8.5 | 10200 | 4604.87 | 8.5 | 39141.395 | 4604.87 | 8.5 | 39141.4 | 10800 | 7395.13 | 91800 | 62858.6
3173 | SELLING COST - Road Development Beautification Work | 10 | Started | Labour | (L)EXTERIOR BUILDING WALL PAINT :- SCARUBBING BY SAND PAPER | NOS | 50000 | 8.5 | 425000 | 0 | 0 | 0 | 5000 | 8.5 | 42500 | 16584.76 | 8.5 | 140970.46 | 16584.76 | 8.5 | 140970.46 | 45000 | 33415.24 | 382500 | 284029.54
3174 | SELLING COST - Road Development Beautification Work | 10 | Started | Labour | (L)EXTERIOR PAINT OF KERB STONE:- APPLYING OF 1 COAT PRIMER | NOS | 3000 | 8.5 | 25500 | 0 | 0 | 0 | 300 | 8.5 | 2550 | 1754.58 | 8.5 | 14913.93 | 1754.58 | 8.5 | 14913.93 | 2700 | 1245.42 | 22950 | 10586.07
3175 | SELLING COST - Road Development Beautification Work | 10 | Started | Labour | (L)EXTERIOR ROOF TILES PAINT:- APPLYING OF 1 COAT EXTERIOR | NOS | 30000 | 8.5 | 255000 | 0 | 0 | 0 | 3000 | 8.5 | 25500 | 6501.92 | 8.5 | 55266.32 | 6501.92 | 8.5 | 55266.32 | 27000 | 23498.08 | 229500 | 199733.68
3176 | SELLING COST - Road Development Speed Breaker Fixing | 10 | Started | Labour | (L)10 MM X 150 MM HST 3R HILTI MAKE ANCHOR | NOS | 24 | 100 | 2400 | 0 | 0 | 0 | 2 | 100 | 200 | 24 | 118 | 2832 | 24 | 118 | 2832 | 22 | 0 | 2200 | -432
3177 | SELLING COST - Road Development Speed Breaker Fixing | 10 | Started | Labour | (L)ANCHOR FIXING (WITHOUT CHEMICAL) FOR SPEED BREAKER | NOS | 800 | 41.3 | 33040 | 0 | 0 | 0 | 80 | 41.3 | 3304 | 700 | 41.3 | 28910 | 700 | 41.3 | 28910 | 720 | 100 | 29736 | 4130
3178 | SELLING COST - Road Development Speed Breaker Fixing | 10 | Started | Material | (M)EPOXY | SET | 2 | 1239 | 2478 | 0 | 0 | 0 | 0 | 1239 | 0 | 0 | 0 | 0 | 8 | 1282.43 | 10259.4 | 2 | -6 | 2478 | -7781.4
3179 | SELLING COST - Road Development Speed Breaker Fixing | 10 | Started | Material | (M)MS NAILS | KG | 330 | 11.8 | 3894 | 0 | 0 | 0 | 33 | 11.8 | 389.4 | 0 | 0 | 0 | 768 | 7.31 | 5611.93 | 297 | -438 | 3504.6 | -1717.93
3180 | SELLING COST - Road Development Speed Breaker Fixing | 10 | Started | Material | (M)PSC CEMENT | BAG | 6 | 307.2 | 1843.2 | 0 | 0 | 0 | 1 | 307.2 | 307.2 | 0 | 0 | 0 | 6 | 308 | 1847.97 | 5 | 0 | 1536 | -4.77
3181 | SELLING COST - Road Development Speed Breaker Fixing | 10 | Started | Material | (M)SPEED BREAKER | MTR | 43.5 | 649 | 28231.5 | 0 | 0 | 0 | 4 | 649 | 2596 | 0 | 0 | 0 | 48 | 673.49 | 32327.36 | 39.5 | -4.5 | 25635.5 | -4095.86
3182 | SELLING COST - Road Development CBR and Field Density Test | 10 | Started | Labour | (L)Conducting field density of soil in place by the Core Cutter | NOS | 10 | 1350 | 13500 | 0 | 0 | 0 | 1 | 1350 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 12150 | 13500
3183 | SELLING COST - Road Development CBR and Field Density Test | 10 | Started | Labour | (L)Conducting laboratory CBR test of compacted soil | NOS | 10 | 1800 | 18000 | 0 | 0 | 0 | 1 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 16200 | 18000
3184 | SELLING COST - Road Development CBR and Field Density Test | 10 | Started | Labour | (L)To & fro Sample Collection Charges | LS | 1 | 900 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 900 | 900
3185 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)10" BRICK WORK | CUM | 30 | 700 | 21000 | 0 | 0 | 0 | 3 | 700 | 2100 | 29.12 | 700 | 20384 | 29.12 | 700 | 20384 | 27 | 0.88 | 18900 | 616
3186 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)5" BRICK WORK | SQM | 210 | 200 | 42000 | 0 | 0 | 0 | 21 | 200 | 4200 | 160.49 | 200 | 32098 | 160.49 | 200 | 32098 | 189 | 49.51 | 37800 | 9902
3187 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)DAILY HELPER (8 HOURS) | NOS | 30 | 450 | 13500 | 0 | 0 | 0 | 3 | 450 | 1350 | 30 | 450 | 13500 | 30 | 450 | 13500 | 27 | 0 | 12150 | 0
3188 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)DAILY MASON (8 HOURS) | NOS | 30 | 700 | 21000 | 0 | 0 | 0 | 3 | 700 | 2100 | 28.5 | 700 | 19950 | 28.5 | 700 | 19950 | 27 | 1.5 | 18900 | 1050
3189 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)NET CEMENT | SQM | 120 | 55 | 6600 | 0 | 0 | 0 | 12 | 55 | 660 | 52.07 | 55 | 2863.85 | 52.07 | 55 | 2863.85 | 108 | 67.93 | 5940 | 3736.15
3190 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)WALL CHIPPING | SQM | 420 | 170 | 71400 | 0 | 0 | 0 | 42 | 170 | 7140 | 396.37 | 170 | 67382.9 | 396.37 | 170 | 67382.9 | 378 | 23.63 | 64260 | 4017.1
3191 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Labour | (L)WALL PLASTER | SQM | 693 | 150 | 103950 | 0 | 0 | 0 | 69 | 150 | 10350 | 690.63 | 150 | 103594.5 | 690.63 | 150 | 103594.5 | 624 | 2.37 | 93600 | 355.5
3192 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 9.758 | 1770 | 17271.66 | 0 | 0 | 0 | 1 | 1770 | 1770 | 0 | 0 | 0 | 9.758 | 1574.62 | 15365.19 | 8.758 | 0 | 15501.66 | 1906.47
3193 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 0.18 | 1750 | 315 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0.18 | 2000 | 360 | 0.18 | 0 | 315 | -45
3194 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Material | (M)2ND CLASS BRICKS | NOS | 1430 | 10 | 14300 | 0 | 0 | 0 | 143 | 10 | 1430 | 0 | 0 | 0 | 1430 | 9.75 | 13936.49 | 1287 | 0 | 12870 | 363.51
3195 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Material | (M)M.C. SAND | MT | 4.12 | 1711.5 | 7051.38 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 4.12 | 1652.58 | 6808.61 | 4.12 | 0 | 7051.38 | 242.77
3196 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Material | (M)PPC CEMENT | BAG | 5 | 283.59 | 1417.95 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 5 | 307.76 | 1538.79 | 4 | 0 | 1134.36 | -120.84
3197 | SELLING COST - Road Development Boundary Wall Repairing | 10 | Started | Material | (M)PSC CEMENT | BAG | 89 | 307.2 | 27340.8 | 0 | 0 | 0 | 9 | 307.2 | 2764.8 | 0 | 0 | 0 | 89 | 308 | 27411.57 | 80 | 0 | 24576 | -70.77
3198 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)BAJRANGBALI TEMPLE FLOOR TILES FIXING | NOS | 250 | 20 | 5000 | 0 | 0 | 0 | 25 | 20 | 500 | 211.56 | 20 | 4231.2 | 211.56 | 20 | 4231.2 | 225 | 38.44 | 4500 | 768.8
3199 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)FRONT SIDE NEAR R.C.P.C COVER 6" WIDE GRANITE STRIP FIXING | RFT | 10 | 60 | 600 | 0 | 0 | 0 | 1 | 60 | 60 | 10 | 60 | 600 | 10 | 60 | 600 | 9 | 0 | 540 | 0
3200 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)GANESH JI IDOL CLEANING TEMPLE IN SIDE MARBLE TEMPLE OUT | LS | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | 15000 | 15000 | 1 | 15000 | 15000 | 1 | 0 | 15000 | 0
3201 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)GANESH JI IDOL PAINT(INCLUDING ALL MATERIALS & LABOUR) | NOS | 1 | 9500 | 9500 | 0 | 0 | 0 | 0 | 9500 | 0 | 1 | 9500 | 9500 | 1 | 9500 | 9500 | 1 | 0 | 9500 | 0
3202 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)LOUNGE AREA OUTSIDE 6" WIDE GRANITE STRIP HALF, MOULDING SIN | RFT | 7 | 40 | 280 | 0 | 0 | 0 | 1 | 40 | 40 | 7 | 40 | 280 | 7 | 40 | 280 | 6 | 0 | 240 | 0
3203 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)LOUNGE AREA OUTSIDE 6" WIDE STRIP FIXING | RFT | 20 | 60 | 1200 | 0 | 0 | 0 | 2 | 60 | 120 | 20 | 60 | 1200 | 20 | 60 | 1200 | 18 | 0 | 1080 | 0
3204 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)LOUNGE AREA OUTSIDE LANDSCAPE AREA 4" X 6" GRANITE STRIP CUT | NOS | 500 | 60 | 30000 | 0 | 0 | 0 | 50 | 60 | 3000 | 139 | 60 | 8340 | 139 | 60 | 8340 | 450 | 361 | 27000 | 21660
3205 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)MAIN GATE ALL BROKEN GRANITE REMOVING , CHEAPING AND PAVERS | NOS | 36.75 | 65.3 | 2399.78 | 0 | 0 | 0 | 4 | 65.3 | 261.2 | 36.75 | 65.3 | 2399.775 | 36.75 | 65.3 | 2399.78 | 32.75 | 0 | 2138.575 | -0.005
3206 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)NEW KOTA STEPPING STONE FIXING BY SOIL CUTTING & LEVELLING | NOS | 50 | 50 | 2500 | 0 | 0 | 0 | 5 | 50 | 250 | 50 | 50 | 2500 | 50 | 50 | 2500 | 45 | 0 | 2250 | 0
3207 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)NEW MARWAR WHITE MARBLE | NOS | 60 | 80 | 4800 | 0 | 0 | 0 | 6 | 80 | 480 | 56.25 | 80 | 4500 | 56.25 | 80 | 4500 | 54 | 3.75 | 4320 | 300
3208 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)NEW MARWAR WHITE MARBLE TRANSPORTING CHARGE | NOS | 60 | 10 | 600 | 0 | 0 | 0 | 6 | 10 | 60 | 60 | 10 | 600 | 60 | 10 | 600 | 54 | 0 | 540 | 0
3209 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)OUT SIDE GANESH JI TEMPLE STEP & SLAB BROKEN MARBLE | NOS | 60 | 183.33 | 10999.8 | 0 | 0 | 0 | 6 | 183.33 | 1099.98 | 60 | 183.3 | 10998 | 60 | 183.3 | 10998 | 54 | 0 | 9899.82 | 1.8
3210 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Labour | (L)OUTSIDE NEAR GANESH JI TEMPLE LANDSCAPE AREA 4" X 6" GRANITE | NOS | 100 | 60 | 6000 | 0 | 0 | 0 | 10 | 60 | 600 | 74 | 60 | 4440 | 74 | 60 | 4440 | 90 | 26 | 5400 | 1560
3211 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Material | (M)(CAMOR DK ) (SIZE - 300 X 450) | NOS | 610.32 | 35.4 | 21605.33 | 0 | 0 | 0 | 61 | 35.4 | 2159.4 | 0 | 0 | 0 | 610.32 | 36.88 | 22510.68 | 549.32 | 0 | 19445.928 | -905.352
3212 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Material | (M)(COLORADO BR LT ) (SIZE - 300 X 450) | NOS | 950.48 | 35.4 | 33646.99 | 0 | 0 | 0 | 95 | 35.4 | 3363 | 0 | 0 | 0 | 950.48 | 36.98 | 35152.84 | 855.48 | 0 | 30283.992 | -1505.848
3213 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Material | (M)FIJI (SIZE - 600 X 600) | NOS | 387.5 | 47.2 | 18290 | 0 | 0 | 0 | 39 | 47.2 | 1840.8 | 0 | 0 | 0 | 387.5 | 53.01 | 20543.12 | 348.5 | 0 | 16449.2 | -2253.12
3214 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Material | (M)KOTA STONE | NOS | 166.63 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 166.63 | 45.39 | 7562.6 | 149.63 | 0 | 0 | -7562.6
3215 | SELLING COST - CSR Activity Tiles Work At Bajrangbali Temple | 10 | Started | Material | (M)PSC CEMENT | BAG | 56 | 307.2 | 17203.2 | 0 | 0 | 0 | 6 | 307.2 | 1843.2 | 0 | 0 | 0 | 56 | 308 | 17247.74 | 50 | 0 | 15360 | -44.54
3216 | SELLING COST - CSR Activity Outside Temple Grill Work | 10 | Started | Labour | (L)TEMPLE GRILL WORK SQ | NOS | 63 | 159.2 | 10029.6 | 0 | 0 | 0 | 6 | 159.2 | 955.2 | 63 | 134.92 | 8499.96 | 0 | 0 | 0 | 57 | 63 | 9074.4 | 10029.6
3217 | SELLING COST - CSR Activity Outside Temple Grill Work | 10 | Started | Material | (M)WHITE PEBBLES | NOS | 1 | 63 | 63 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 50 | 73 | 3649.91 | 1 | -49 | 63 | -3586.91
3218 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)CARRYING COST OF CEMENT BAGS | NOS | 60 | 7.5 | 450 | 0 | 0 | 0 | 6 | 7.5 | 45 | 60 | 7.5 | 450 | 60 | 7.5 | 450 | 54 | 0 | 405 | 0
3219 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)CARRYING COST OF SAND BAGS | NOS | 334 | 7.5 | 2505 | 0 | 0 | 0 | 33 | 7.5 | 247.5 | 334 | 7.5 | 2505 | 334 | 7.5 | 2505 | 301 | 0 | 2257.5 | 0
3220 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)CARRYING COST OF TILES | NOS | 1200 | 5 | 6000 | 0 | 0 | 0 | 120 | 5 | 600 | 1200 | 5 | 6000 | 1200 | 5 | 6000 | 1080 | 0 | 5400 | 0
3221 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)DAILY HELPER FOR TILES MISC .WORK INCLUDING TILES REMOVING | NOS | 83 | 450 | 37350 | 0 | 0 | 0 | 8 | 450 | 3600 | 83 | 450 | 37350 | 83 | 450 | 37350 | 75 | 0 | 33750 | 0
3222 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)DAILY TILES MISTRI FOR TILES MISC WORK ,KOTA POLISHING | NOS | 43 | 700 | 30100 | 0 | 0 | 0 | 4 | 700 | 2800 | 43 | 700 | 30100 | 43 | 700 | 30100 | 39 | 0 | 27300 | 0
3223 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)KOTA STONE FIXING AT TAP FLOOR AREA AT COSSIPORE ROAD | NOS | 166.63 | 72 | 11997.36 | 0 | 0 | 0 | 17 | 72 | 1224 | 166.63 | 72 | 11997.36 | 166.63 | 72 | 11997.36 | 149.63 | 0 | 10773.36 | 0
3224 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)MACHINE CHARGES OF OLF TILES ,REMOVAL OF DEBRIS ETC. | NOS | 64 | 200 | 12800 | 0 | 0 | 0 | 6 | 200 | 1200 | 64 | 200 | 12800 | 64 | 200 | 12800 | 58 | 0 | 11600 | 0
3225 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Labour | (L)TILES WORK FIXING AT MANDIR & WATER TAP WALL COSSIPORE ROAD | NOS | 1948.1764 | 25 | 48704.41 | 0 | 0 | 0 | 195 | 25 | 4875 | 1948.1764 | 25 | 48704.41 | 1948.1764 | 25 | 48704.41 | 1753.1764 | 0 | 43829.41 | 0
3226 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Material | (M)(CAMOR DK ) (SIZE - 300 X 450) | NOS | 87.28 | 35.4 | 3089.71 | 0 | 0 | 0 | 9 | 35.4 | 318.6 | 0 | 0 | 0 | 87.28 | 36.88 | 3219.18 | 78.28 | 0 | 2771.112 | -129.468
3227 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Material | (M)Cicogres Patchwork Combi | BOX | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2783.9 | 8351.71 | 1 | -2 | 0 | -8351.71
3228 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Material | (M)CONCRETE PAVER BLOCK (40 MM THICK) | NOS | 2454 | 0 | 0 | 0 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 2454 | 50.74 | 124515.96 | 2209 | 0 | 0 | -124515.96
3229 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Material | (M)GRANITE FLAME FOR OUTSIDE MODEL FLAT | NOS | 1 | 112.1 | 112.1 | 0 | 0 | 0 | 0 | 112.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 112.1 | 112.1
3230 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Material | (M)Granite Slabs | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.75 | 180.36 | 2480 | 1 | -12.75 | 0 | -2480
3231 | SELLING COST - CSR Activity Tiles Work At Temple | 10 | Started | Material | (M)SILVER SAND | CFT | 555.9 | 25 | 13897.5 | 0 | 0 | 0 | 56 | 25 | 1400 | 0 | 0 | 0 | 555.9 | 29 | 16121.1 | 499.9 | 0 | 12497.5 | -2223.6
3232 | SELLING COST - CSR Activity Temple Marble Work | 10 | Started | Labour | (L)MARBLE WORK(INCLUDING LABOUR & MATERIAL) | LS | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 1 | 15000 | 15000 | 1 | 15000 | 15000 | 1 | 0 | 15000 | 0
3233 | SELLING COST - CSR Activity Fabric Canopy at Temple | 10 | Started | Labour | (L)Fabrication & Erection of MS structure | NOS | 250 | 310 | 77500 | 0 | 0 | 0 | 25 | 310 | 7750 | 250 | 365.8 | 91450 | 250 | 365.8 | 91450 | 225 | 0 | 69750 | -13950
3234 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Labour | (L)FIXING OF GRANITE | NOS | 156.47 | 55 | 8605.85 | 0 | 0 | 0 | 16 | 55 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 140.47 | 156.47 | 7725.85 | 8605.85
3235 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Labour | (L)FIXING OF KERB STONE | RFT | 33.67 | 95 | 3198.65 | 0 | 0 | 0 | 3 | 95 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 30.67 | 33.67 | 2913.65 | 3198.65
3236 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Labour | (L)PAVERS BLOCK LAYING INCLUDING GUARD WALL | NOS | 2130 | 20 | 42600 | 0 | 0 | 0 | 213 | 20 | 4260 | 0 | 0 | 0 | 0 | 0 | 0 | 1917 | 2130 | 38340 | 42600
3237 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Labour | (L)SKILLED TILE LABOUR | NOS | 8 | 600 | 4800 | 0 | 0 | 0 | 1 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 4200 | 4800
3238 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Labour | (L)TOOLS | NOS | 7 | 150 | 1050 | 0 | 0 | 0 | 1 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 900 | 1050
3239 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Labour | (L)UNSKILLED TILE LABOUR | NOS | 8 | 472 | 3776 | 0 | 0 | 0 | 1 | 472 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 3304 | 3776
3240 | SELLING COST - CSR Activity Tiles And Granite Work at Temple | 10 | Started | Material | (M)CONCRETE PAVER BLOCK (40 MM THICK) | NOS | 86 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 79.946 | 50.74 | 4056.46 | 77 | 6.054 | 0 | -4056.46
3241 | Selling Cost - CSR Activity MISC. CSR Works | 0 | Started | Material | (M)Buddha Belly Bamboo | NOS | 330 | 354 | 116820 | 330 | 354 | 116820 | 0 | 354 | 0 | 330 | 300 | 99000 | 330 | 300 | 99000 | 330 | 0 | 116820 | 17820
3242 | Selling Cost - CSR Activity MISC. CSR Works | 0 | Started | Material | (M)Compost Fertiliser | BAG | 20 | 1180 | 23600 | 20 | 1180 | 23600 | 0 | 1180 | 0 | 20 | 1000 | 20000 | 20 | 1000 | 20000 | 20 | 0 | 23600 | 3600
3243 | Selling Cost - CSR Activity MISC. CSR Works | 0 | Started | Material | (M)Golden Bamboo | NOS | 350 | 354 | 123900 | 350 | 354 | 123900 | 0 | 354 | 0 | 350 | 300 | 105000 | 350 | 300 | 105000 | 350 | 0 | 123900 | 18900
3244 | Selling Cost - CSR Activity MISC. CSR Works | 0 | Started | Material | (M)Pandanus Pygmaeus | NOS | 1000 | 40 | 40000 | 1000 | 40 | 40000 | 0 | 40 | 0 | 1000 | 40 | 40000 | 1000 | 40 | 40000 | 1000 | 0 | 40000 | 0
3245 | Selling Cost - CSR Activity MISC. CSR Works | 0 | Started | Material | (M)Spider Lilly | NOS | 1000 | 30 | 30000 | 1000 | 30 | 30000 | 0 | 30 | 0 | 1000 | 26 | 26000 | 1000 | 26 | 26000 | 1000 | 0 | 30000 | 4000
3246 | SELLING COST - Site Beautification Structural Work | 0 | Started | Labour | (L)Fabrication, Erection and commissioning of Mezzanine Floor | NOS | 800 | 90 | 72000 | 0 | 0 | 0 | 0 | 90 | 0 | 800 | 106.2 | 84960 | 800 | 106.2 | 84960 | 800 | 0 | 72000 | -12960
3247 | SELLING COST - Site Beautification Structural Work | 0 | Started | Labour | (L)Fabrication, Erection and commissioning of Stair Case Struct | NOS | 400 | 90 | 36000 | 0 | 0 | 0 | 0 | 90 | 0 | 400 | 106.2 | 42480 | 400 | 106.2 | 42480 | 400 | 0 | 36000 | -6480
3248 | SELLING COST - Site Beautification Structural Work | 0 | Started | Labour | (L)Fabrication, Erection and commissioning of Tensile Canopy | NOS | 150 | 310 | 46500 | 0 | 0 | 0 | 0 | 310 | 0 | 150 | 365.8 | 54870 | 150 | 365.8 | 54870 | 150 | 0 | 46500 | -8370
3249 | SELLING COST - Site Beautification Structural Work | 0 | Started | Material | (M)50 MM CHINA SADDLE | NOS | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 10.81 | 540.72 | 50 | 0 | 0 | -540.72
3250 | SELLING COST - Site Beautification Signage Lollipop Signage | 10 | Started | Labour | (L)DELIVERY INCLUDING INSTALLATION | NOS | 21 | 250 | 5250 | 0 | 0 | 0 | 2 | 250 | 500 | 21 | 295 | 6195 | 21 | 295 | 6195 | 19 | 0 | 4750 | -945
3251 | SELLING COST - Site Beautification Signage Lollipop Signage | 10 | Started | Labour | (L)Matter will be made in acrylic (round shape), Size - 2ftx2ft | NOS | 25 | 3250 | 81250 | 0 | 0 | 0 | 3 | 3250 | 9750 | 21 | 4130 | 86730 | 21 | 4130 | 86730 | 22 | 4 | 71500 | -5480
3252 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)10MM ROUND GLASS TOP | NOS | 1 | 9440 | 9440 | 0 | 0 | 0 | 0 | 9440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9440 | 9440
3253 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)32*8 Screw (S.S) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3254 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)4" Hinges | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3255 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)CLAMP FOR FIXING DOOR FRAME | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3256 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)DOOR CLOSER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3257 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)DOOR FRAME (900 X 2100) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3258 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)DOOR HANDLE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3259 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)DOOR LOCK | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3260 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)DOOR SHUTTER (2075 X 810) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3261 | SELLING COST - Site Office Door Work | 0 | Started | Material | (M)FLOOR TILES NEW PROJECT OFFICE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3262 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)1" BALL VALVE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346.8 | 346.8 | 1 | 0 | 0 | -346.8
3263 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(GREEN,180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3264 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(RED, 90 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3265 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(RED,180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3266 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(YELLOW, 180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3267 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(YELLOW, 90 MTR) | COIL | 1 | 2572.4 | 2572.4 | 0 | 0 | 0 | 0 | 2572.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2572.4 | 2572.4
3268 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)10 AMP SINGLE POLE MCB | NOS | 6 | 236 | 1416 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 6 | 156.99 | 941.93 | 6 | 0 | 1416 | 474.07
3269 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)10 WATT CEILING AHUJA | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1729.43 | 6917.73 | 4 | 0 | 0 | -6917.73
3270 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)12 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3271 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)12 WATT CEILING LIGHT | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3272 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)16 AMP AC STARTER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3273 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)16 AMP SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3274 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)16 WATT WALL AHUJA | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3325.83 | 6651.66 | 2 | 0 | 0 | -6651.66
3275 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)2 MODULAR BOX | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3276 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)2 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3277 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)3 MODULAR BOX | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3278 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)4 POLE 63 AMP MCB | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3279 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)4 WAY TPN HORIZONTAL DB | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3280 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)4.0 SQ.MM COPPER WIRE(RED, 180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3281 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)6 AMP SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3282 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)6 AMP SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 53.86 | 2800.46 | 0 | -52 | 0 | -2800.46
3283 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)6 MODULAR BOX | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3284 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)6 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3285 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)8 MODULAR BOX (SQUARE) COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3286 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)BLANK SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3287 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)COPPER WIRE | KG | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 354 | 354 | 1 | 0 | 0 | -354
3288 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)MCB 4 POLE 32 AMP WITH EXTERNAL COVER | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1416 | 1416
3289 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)PVC BOX 12X10 | NOS | 1 | 153.4 | 153.4 | 0 | 0 | 0 | 0 | 153.4 | 0 | 0 | 0 | 0 | 3 | 150.48 | 451.44 | 1 | -2 | 153.4 | -298.04
3290 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)PVC BOX 4 X 4 | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 3 | 47.2 | 141.6 | 1 | -2 | 47.2 | -94.4
3291 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)PVC BOX 6X4 | NOS | 1 | 106.2 | 106.2 | 0 | 0 | 0 | 0 | 106.2 | 0 | 0 | 0 | 0 | 3 | 108.35 | 325.04 | 1 | -2 | 106.2 | -218.84
3292 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)PVC TAPE GREEN | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3293 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)PVC TAPE RED | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 48.87 | 48.87 | 0 | -1 | 0 | -48.87
3294 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)PVC TAPE YELLOW | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3295 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)SINGLE POLE 10 AMP MCB | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3296 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)SINGLE POLE 20 AMP MCB | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3297 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)TESTER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 69.08 | 69.08 | 1 | 0 | 0 | -69.08
3298 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)UP - DOWN LIGHTER | NOS | 1 | 1994.2 | 1994.2 | 0 | 0 | 0 | 0 | 1994.2 | 0 | 0 | 0 | 0 | 6 | 2021.12 | 12126.73 | 1 | -5 | 1994.2 | -10132.53
3299 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)WALL HI-SPEED FAN | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3300 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)WATERPROOF TAPE | NOS | 1 | 342.2 | 342.2 | 0 | 0 | 0 | 0 | 342.2 | 0 | 0 | 0 | 0 | 5 | 298.98 | 1494.91 | 1 | -4 | 342.2 | -1152.71
3301 | SELLING COST - Site Office Electrical Work | 0 | Started | Material | (M)WATERPROOF TAPE. | MTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3302 | SELLING COST - Site Office Civil Construction | 0 | Started | Labour | (L)AC REPAIRING | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 55000 | 55000 | 0 | 0 | 0 | 1 | 1 | 1 | 1
3303 | SELLING COST - Site Office Civil Construction | 0 | Started | Labour | (L)Decorating | LS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 250000 | 250000 | 1 | 250000 | 250000 | 1 | 0 | 1 | -249999
3304 | SELLING COST - Site Office Civil Construction | 0 | Started | Material | (M)10 MM DIA TMT | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3305 | SELLING COST - Site Office Civil Construction | 0 | Started | Material | (M)2ND CLASS BRICKS | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3306 | SELLING COST - Site Office Civil Construction | 0 | Started | Material | (M)8 MM DIA TMT | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3307 | SELLING COST - Site Office Civil Construction | 0 | Started | Material | (M)ORGANIC GRASS | LS | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 0 | 8000 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 8000 | 0
3308 | SELLING COST - Site Office Civil Construction | 0 | Started | Material | (M)PPC CEMENT | BAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3309 | SELLING COST - Site Office Civil Construction | 0 | Started | Material | (M)SILVER SAND | CFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3310 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)1-1/4" CP BASIN WASTE | NOS | 1 | 460.2 | 460.2 | 0 | 0 | 0 | 0 | 460.2 | 0 | 0 | 0 | 0 | 1 | 459 | 459 | 1 | 0 | 460.2 | 1.2
3311 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)1-1/4" TANK NIPLE UPVC | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 133.47 | 266.93 | 2 | 0 | 0 | -266.93
3312 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)1-1/4" X 1" REDUCER (UPVC) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 44.35 | 44.35 | 1 | 0 | 0 | -44.35
3313 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)1-1/4" x 1-1/4" M.T. A | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 606.68 | 606.68 | 1 | 0 | 0 | -606.68
3314 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)2" ELBOW (UPVC) | NOS | 8 | 82.6 | 660.8 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 8 | 82.12 | 656.97 | 8 | 0 | 660.8 | 3.83
3315 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)2" GRATING WITH OUT HOLE | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 56.69 | 113.38 | 2 | 0 | 0 | -113.38
3316 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)2" HALF ELBOW | NOS | 6 | 118 | 708 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 6 | 73.25 | 439.47 | 6 | 0 | 708 | 268.53
3317 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)2" M.T.A (METAL) | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 866.35 | 1732.69 | 2 | 0 | 0 | -1732.69
3318 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)2" SOCKET | NOS | 8 | 59 | 472 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 8 | 49.94 | 399.52 | 8 | 0 | 472 | 72.48
3319 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)2" UPVC PIPE 20' - 0" | NOS | 1 | 2808.4 | 2808.4 | 0 | 0 | 0 | 0 | 2808.4 | 0 | 0 | 0 | 0 | 1 | 1579.99 | 1579.99 | 1 | 0 | 2808.4 | 1228.41
3320 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)32 MM PPR END CAP | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3321 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)32 MM PPR PIPE | MTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 155.05 | 6977.34 | 0 | -45 | 0 | -6977.34
3322 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)32 MM PPR PLAIN ELBOW | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3323 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)32 MM PPR SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3324 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)32 MM PPR TEE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3325 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)BROWN TAPE | NOS | 36 | 47.2 | 1699.2 | 36 | 47.2 | 1699.2 | 0 | 47.2 | 0 | 36 | 42.48 | 1529.28 | 0 | 0 | 0 | 36 | 36 | 1699.2 | 1699.2
3326 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)SOLVENT CEMENT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 253.43 | 760.28 | 1 | -2 | 0 | -760.28
3327 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)UPVC SOLVENT | GRAM | 1 | 306.8 | 306.8 | 0 | 0 | 0 | 0 | 306.8 | 0 | 0 | 0 | 0 | 250 | 0.82 | 204.7 | 1 | -249 | 306.8 | 102.1
3328 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)UPVC SOLVENT CEMENT | ML | 1 | 0.78 | 0.78 | 0 | 0 | 0 | 0 | 0.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.78 | 0.78
3329 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)Urinal Auto closing push cock | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1919.86 | 1919.86 | 1 | 0 | 0 | -1919.86
3330 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)URINAL PUSH BRASS VALVE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 584.79 | 584.79 | 1 | 0 | 0 | -584.79
3331 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)URINAL WASTE PIPE | NOS | 1 | 39 | 39 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 39 | 39
3332 | SELLING COST - Site Office Plumbing Work | 0 | Started | Material | (M)URINAL. | NOS | 1 | 7700.01 | 7700.01 | 0 | 0 | 0 | 0 | 7700.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7700.01 | 7700.01
3333 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)1/2" test plug | NOS | 8 | 11.8 | 94.4 | 8 | 11.8 | 94.4 | 0 | 11.8 | 0 | 8 | 6.4 | 51.2 | 8 | 6.34 | 50.69 | 8 | 0 | 94.4 | 43.71
3334 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)110 mm SWR Plain Bend | NOS | 4 | 167.56 | 670.24 | 4 | 167.56 | 670.24 | 0 | 167.56 | 0 | 4 | 178.81 | 715.24 | 4 | 177.11 | 708.43 | 4 | 0 | 670.24 | -38.19
3335 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)110 mm x 2'0" D/S Pipe | NOS | 2 | 259.6 | 519.2 | 2 | 259.6 | 519.2 | 0 | 259.6 | 0 | 2 | 277.05 | 554.1 | 2 | 274.42 | 548.83 | 2 | 0 | 519.2 | -29.63
3336 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)110 mm x 4'0" D/S Pipe | NOS | 2 | 440.14 | 880.28 | 2 | 440.14 | 880.28 | 0 | 440.14 | 0 | 2 | 469.55 | 939.1 | 2 | 465.09 | 930.17 | 2 | 0 | 880.28 | -49.89
3337 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)110 mm x 45° Swr half Bend | NOS | 4 | 133.34 | 533.36 | 4 | 133.34 | 533.36 | 0 | 133.34 | 0 | 4 | 142.88 | 571.52 | 4 | 141.52 | 566.07 | 4 | 0 | 533.36 | -32.71
3338 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)20 MM CLAMP (GI) | NOS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6.61 | 39.66 | 6 | 0 | 0 | -39.66
3339 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)3/4" UPVC PIPE (10'0" ) LONG | MTR | 2 | 256.06 | 512.12 | 2 | 256.06 | 512.12 | 0 | 256.06 | 0 | 2 | 274.02 | 548.04 | 2 | 271.42 | 542.84 | 2 | 0 | 512.12 | -30.72
3340 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)3/4" UPVC PLAIN ELBOW | NOS | 6 | 23.6 | 141.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 6 | 20.29 | 121.72 | 6 | 0 | 141.6 | 19.88
3341 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)3/4" UPVC SOCKET | NOS | 6 | 12.98 | 77.88 | 4 | 12.98 | 51.92 | 0 | 12.98 | 0 | 4 | 14.54 | 58.16 | 6 | 13.83 | 82.97 | 6 | 0 | 77.88 | -5.09
3342 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)3/4" UPVC TEE | NOS | 6 | 22.42 | 134.52 | 6 | 22.42 | 134.52 | 0 | 22.42 | 0 | 6 | 24.81 | 148.86 | 6 | 24.58 | 147.45 | 6 | 0 | 134.52 | -12.93
3343 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)3/4" X 1/2" F.T. ELBOW | NOS | 8 | 155.76 | 1246.08 | 8 | 155.76 | 1246.08 | 0 | 155.76 | 0 | 8 | 166.83 | 1334.62 | 8 | 165.25 | 1321.96 | 8 | 0 | 1246.08 | -75.88
3344 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)50 mm agriculture elbow | NOS | 4 | 59 | 236 | 4 | 59 | 236 | 0 | 59 | 0 | 4 | 44.07 | 176.26 | 4 | 43.64 | 174.57 | 4 | 0 | 236 | 61.43
3345 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)50 mm agriculture Tee | NOS | 4 | 28.32 | 113.28 | 4 | 28.32 | 113.28 | 0 | 28.32 | 0 | 4 | 55.61 | 222.42 | 4 | 55.08 | 220.32 | 4 | 0 | 113.28 | -107.04
3346 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)50 MM CLAMP (GI) | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13.22 | 52.86 | 4 | 0 | 0 | -52.86
3347 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)MTA (UPVC) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 258.48 | 516.95 | 1 | -1 | 0 | -516.95
3348 | SELLING COST - Site Office Customer Toilet External Plumbing | 0 | Started | Material | (M)UPVC SOLVENT CEMENT | ML | 237 | 0.78 | 184.86 | 237 | 0.78 | 184.86 | 0 | 0.78 | 0 | 237 | 0.83 | 197.6817 | 237 | 0.83 | 196.26 | 237 | 0 | 184.86 | -11.4
3349 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)1/2" ANGULAR STOP COCK | NOS | 5 | 953.99 | 4769.95 | 3 | 953.99 | 2861.97 | 0 | 953.99 | 0 | 3 | 954 | 2861.9901 | 5 | 648 | 3239.99 | 5 | 0 | 4769.95 | 1529.96
3350 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)1/2"X2' HEAVY DUTY CONNECTOR PIPE | NOS | 2 | 141.6 | 283.2 | 2 | 141.6 | 283.2 | 0 | 141.6 | 0 | 2 | 90.59 | 181.1872 | 2 | 89.12 | 178.23 | 2 | 0 | 283.2 | 104.97
3351 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)25 MM UPVC SOCKET | NOS | 1 | 23.6 | 23.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 0 | 0 | 0 | 2 | 20.28 | 40.55 | 1 | -1 | 23.6 | -16.95
3352 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)5" CIRCULAR CP GRATINGS WITHOUT HOLE | NOS | 1 | 60 | 60 | 1 | 60 | 60 | 0 | 60 | 0 | 1 | 60 | 60 | 1 | 60 | 60 | 1 | 0 | 60 | 0
3353 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)BASIN PILLAR COCK | NOS | 1 | 1403.99 | 1403.99 | 1 | 1403.99 | 1403.99 | 0 | 1403.99 | 0 | 1 | 1403.99 | 1403.99 | 1 | 1403.99 | 1403.99 | 1 | 0 | 1403.99 | 0
3354 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)BOTTLE TRAP | NOS | 1 | 1341 | 1341 | 1 | 1341 | 1341 | 0 | 1341 | 0 | 1 | 1341 | 1341 | 1 | 1341 | 1341 | 1 | 0 | 1341 | 0
3355 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)C.P BASIN WASTE 1-1/4" DIA | NOS | 1 | 405 | 405 | 1 | 405 | 405 | 0 | 405 | 0 | 1 | 405 | 405 | 1 | 405 | 405 | 1 | 0 | 405 | 0
3356 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)Health Faucet | NOS | 1 | 1269 | 1269 | 1 | 1269 | 1269 | 0 | 1269 | 0 | 1 | 1269 | 1269 | 1 | 1089 | 1089 | 1 | 0 | 1269 | 180
3357 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)KERAKOLL SUPERFLEX | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 526.84 | 16858.72 | 1 | -31 | 0 | -16858.72
3358 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)SINGLE PIECE "S" TRAP WC (4/2LPF) WITH SIT COVER | NOS | 1 | 13570 | 13570 | 1 | 13570 | 13570 | 0 | 13570 | 0 | 1 | 10986.43 | 10986.43 | 1 | 14001.44 | 14001.44 | 1 | 0 | 13570 | -431.44
3359 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)URINAL | SET | 1 | 5833.92 | 5833.92 | 1 | 5833.92 | 5833.92 | 0 | 5833.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5833.92 | 5833.92
3360 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)URINAL WASTE PIPE | NOS | 1 | 39 | 39 | 1 | 39 | 39 | 0 | 39 | 0 | 1 | 39 | 39 | 1 | 39 | 39 | 1 | 0 | 39 | 0
3361 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)URINAL. | NOS | 1 | 7700.01 | 7700.01 | 1 | 7700.01 | 7700.01 | 0 | 7700.01 | 0 | 1 | 7919.28 | 7919.28 | 1 | 7885.58 | 7885.58 | 1 | 0 | 7700.01 | -185.57
3362 | SELLING COST - Site Office Customer Toilet Internal Plumbing | 0 | Started | Material | (M)WASH BASIN | NOS | 1 | 3245 | 3245 | 1 | 3245 | 3245 | 0 | 3245 | 0 | 1 | 2336.92 | 2336.92 | 1 | 3639.83 | 3639.83 | 1 | 0 | 3245 | -394.83
3363 | SELLING COST - Site Office Customer Toilet Work | 10 | Started | Material | (M)4 MOD COVER | NOS | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 0 | 283.2 | 0 | 1 | 107.38 | 107.38 | 6 | 78.19 | 469.16 | 1 | -5 | 283.2 | -185.96
3364 | SELLING COST - Site Office Customer Toilet Work | 10 | Started | Material | (M)6 AMP SWITCH | NOS | 4 | 142.78 | 571.12 | 4 | 142.78 | 571.12 | 0 | 142.78 | 0 | 4 | 75.58 | 302.3152 | 0 | 0 | 0 | 4 | 4 | 571.12 | 571.12
3365 | SELLING COST - Site Office Customer Toilet Work | 10 | Started | Material | (M)BLANK SWITCH | NOS | 1 | 61.36 | 61.36 | 1 | 61.36 | 61.36 | 0 | 61.36 | 0 | 1 | 30.56 | 30.56 | 0 | 0 | 0 | 1 | 1 | 61.36 | 61.36
3366 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)0.5" BIB COCK | NOS | 2 | 3009 | 6018 | 0 | 0 | 0 | 0 | 3009 | 0 | 0 | 0 | 0 | 2 | 3007 | 6013.99 | 2 | 0 | 6018 | 4.01
3367 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)1-1/4" COUPLING WITH PVC WASTE PIPE | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3368 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)1/2" ANGULAR STOP COCK | NOS | 2 | 953.99 | 1907.98 | 0 | 0 | 0 | 0 | 953.99 | 0 | 0 | 0 | 0 | 2 | 648 | 1296 | 2 | 0 | 1907.98 | 611.98
3369 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)1/2"X 1" CP EXTENSION SHORT PIECE | NOS | 2 | 106.2 | 212.4 | 2 | 106.2 | 212.4 | 0 | 106.2 | 0 | 2 | 106.2 | 212.4 | 2 | 106.2 | 212.4 | 2 | 0 | 212.4 | 0
3370 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)1/2"X 2" CP EXTENSION SHORT PIECE | NOS | 4 | 153.4 | 613.6 | 4 | 153.4 | 613.6 | 0 | 153.4 | 0 | 4 | 153.4 | 613.6 | 4 | 153.4 | 613.6 | 4 | 0 | 613.6 | 0
3371 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)1/2"X2' HEAVY DUTY CONNECTOR PIPE | NOS | 2 | 141.6 | 283.2 | 2 | 141.6 | 283.2 | 0 | 141.6 | 0 | 2 | 88.5 | 177.0016 | 2 | 89.12 | 178.23 | 2 | 0 | 283.2 | 104.97
3372 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)BASIN PILLAR COCK | NOS | 1 | 1403.99 | 1403.99 | 0 | 0 | 0 | 0 | 1403.99 | 0 | 0 | 0 | 0 | 1 | 1403.99 | 1403.99 | 1 | 0 | 1403.99 | 0
3373 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)BASIN SUMO BOLT | PAIR | 1 | 224.2 | 224.2 | 1 | 224.2 | 224.2 | 0 | 224.2 | 0 | 1 | 230.37 | 230.37 | 1 | 229.39 | 229.39 | 1 | 0 | 224.2 | -5.19
3374 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)Basin waste pipe | NOS | 1 | 35.4 | 35.4 | 1 | 35.4 | 35.4 | 0 | 35.4 | 0 | 1 | 29.5 | 29.5 | 1 | 29.5 | 29.5 | 1 | 0 | 35.4 | 5.9
3375 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)Cementum Gris 2 x 2. | BOX | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1385.19 | 4155.56 | 3 | 0 | 0 | -4155.56
3376 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)Cementum Nero Rt 600 x 600. | BOX | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1385.19 | 2770.38 | 2 | 0 | 0 | -2770.38
3377 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)GLASS PUDDING | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3378 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)Health Faucet | NOS | 1 | 1269 | 1269 | 0 | 0 | 0 | 0 | 1269 | 0 | 0 | 0 | 0 | 1 | 1089 | 1089 | 1 | 0 | 1269 | 180
3379 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)SINGLE PIECE "S" TRAP WC (4/2LPF) WITH SIT COVER | NOS | 1 | 13570 | 13570 | 1 | 13570 | 13570 | 0 | 13570 | 0 | 1 | 17420.86 | 17420.86 | 1 | 14001.44 | 14001.44 | 1 | 0 | 13570 | -431.44
3380 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)TEFLON TAPE | NOS | 10 | 23.6 | 236 | 10 | 23.6 | 236 | 0 | 23.6 | 0 | 10 | 18.88 | 188.8 | 4 | 18.88 | 75.52 | 10 | 6 | 236 | 160.48
3381 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)TWO IN ONE BIB COCK | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3382 | SELLING COST - Site Office Ladies Toilet Work | 0 | Started | Material | (M)WASH BASIN | NOS | 1 | 3245 | 3245 | 1 | 3245 | 3245 | 0 | 3245 | 0 | 1 | 5139 | 5139 | 1 | 3639.83 | 3639.83 | 1 | 0 | 3245 | -394.83
3383 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)1 MODULAR COVER | NOS | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 1 | 80.53 | 80.53 | 1 | 0 | 236 | 155.47
3384 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)1.0 SQ.MM COPPER WIRE (GREEN, 180MTR) | COIL | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 0 | 3540 | 0 | 1 | 1847.15 | 1847.15 | 1 | 1841.84 | 1841.84 | 1 | 0 | 3540 | 1698.16
3385 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(BLUE,180 MTR) | COIL | 2 | 5144.8 | 10289.6 | 2 | 5144.8 | 10289.6 | 0 | 5144.8 | 0 | 2 | 2678.36 | 5356.72 | 2 | 2670.68 | 5341.35 | 2 | 0 | 10289.6 | 4948.25
3386 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(RED,180 MTR) | COIL | 2 | 5144.8 | 10289.6 | 2 | 5144.8 | 10289.6 | 0 | 5144.8 | 0 | 2 | 2678.36 | 5356.72 | 0 | 0 | 0 | 2 | 2 | 10289.6 | 10289.6
3387 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)12 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3388 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)2.5 SQ.MM COPPER WIRE (BLUE, 180 MTR) | COIL | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 0 | 5900 | 0 | 1 | 4433.16 | 4433.16 | 1 | 4420.43 | 4420.43 | 1 | 0 | 5900 | 1479.57
3389 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)20MM PVC CONDUIT PIPE (MEDIUM DUTY) | BUNDLE | 1 | 3681.6 | 3681.6 | 1 | 3681.6 | 3681.6 | 0 | 3681.6 | 0 | 1 | 3752.01 | 3752.01 | 1 | 3741.24 | 3741.24 | 1 | 0 | 3681.6 | -59.64
3390 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)25 MM PVC CONDUIT PIPE (MEDIUM DUTY) | BUNDLE | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 0 | 3068 | 0 | 1 | 3126.68 | 3126.68 | 1 | 3117.7 | 3117.7 | 1 | 0 | 3068 | -49.7
3391 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)3 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3392 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)4 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3393 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)4.0 SQ.MM COPPER WIRE (BLUE, 180 MTR) | COIL | 1 | 13216 | 13216 | 1 | 13216 | 13216 | 0 | 13216 | 0 | 1 | 6926.79 | 6926.79 | 1 | 6906.91 | 6906.91 | 1 | 0 | 13216 | 6309.09
3394 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)4.0 SQ.MM COPPER WIRE(RED, 180 MTR) | COIL | 1 | 13216 | 13216 | 1 | 13216 | 13216 | 0 | 13216 | 0 | 1 | 6926.79 | 6926.79 | 1 | 6906.91 | 6906.91 | 1 | 0 | 13216 | 6309.09
3395 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)6 AMP SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3396 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)6/16 AMP SOCKET | NOS | 9 | 274.94 | 2474.46 | 0 | 0 | 0 | 0 | 274.94 | 0 | 0 | 0 | 0 | 7 | 188.2 | 1317.4 | 9 | 2 | 2474.46 | 1157.06
3397 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)6/16 AMP SWITCH | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3398 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)8 MODULAR BOX (SQUARE) COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3399 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)BLANK SWITCH | NOS | 5 | 61.36 | 306.8 | 0 | 0 | 0 | 0 | 61.36 | 0 | 0 | 0 | 0 | 5 | 30.69 | 153.45 | 5 | 0 | 306.8 | 153.35
3400 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)Copenhegen grey - | NOS | 540.36 | 135.7 | 73326.85 | 0 | 0 | 0 | 0 | 135.7 | 0 | 0 | 0 | 0 | 540.36 | 120.53 | 65132.18 | 540.36 | 0 | 73326.852 | 8194.672
3401 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)HDMI CABLE | MTR | 20 | 236 | 4720 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 20 | 237.48 | 4749.5 | 20 | 0 | 4720 | -29.5
3402 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 0 | Started | Material | (M)TELEPHONE/ INTERCOME SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3403 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)1 MODULAR COVER | NOS | 1 | 236 | 236 | 1 | 236 | 236 | 0 | 236 | 0 | 1 | 80.53 | 80.53 | 0 | 0 | 0 | 1 | 1 | 236 | 236
3404 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)1.0 SQ.MM COPPER WIRE (GREEN, 180MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3405 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(BLUE,180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3406 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(RED,180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3407 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)12 MOD COVER | NOS | 1 | 731.6 | 731.6 | 1 | 731.6 | 731.6 | 0 | 731.6 | 0 | 1 | 256.06 | 256.06 | 1 | 256.06 | 256.06 | 1 | 0 | 731.6 | 475.54
3408 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)12 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3409 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)2 MOD COVER | NOS | 1 | 62.65 | 62.65 | 1 | 62.65 | 62.65 | 0 | 62.65 | 0 | 1 | 73.93 | 73.93 | 1 | 73.93 | 73.93 | 1 | 0 | 62.65 | -11.28
3410 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)2.5 SQ.MM COPPER WIRE (BLUE, 180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3411 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)20MM PVC CONDUIT PIPE (MEDIUM DUTY) | BUNDLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3412 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)25 MM PVC CONDUIT PIPE (MEDIUM DUTY) | BUNDLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3413 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)3 MOD COVER | NOS | 5 | 247.8 | 1239 | 4 | 247.8 | 991.2 | 1 | 247.8 | 247.8 | 4 | 87.15 | 348.58 | 5 | 87.33 | 436.65 | 4 | 0 | 991.2 | 802.35
3414 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)3 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3415 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)4 MODULAR BOX COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3416 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)4.0 SQ.MM COPPER WIRE (BLUE, 180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3417 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)4.0 SQ.MM COPPER WIRE(RED, 180 MTR) | COIL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3418 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)6 AMP SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3419 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)6 AMP SWITCH | NOS | 12 | 142.78 | 1713.36 | 12 | 142.78 | 1713.36 | 1 | 142.78 | 142.78 | 12 | 75.58 | 906.9456 | 0 | 0 | 0 | 11 | 12 | 1570.58 | 1713.36
3420 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)6 MOD COVER | NOS | 2 | 401.2 | 802.4 | 1 | 401.2 | 401.2 | 0 | 401.2 | 0 | 1 | 141.65 | 141.65 | 2 | 142.4 | 284.8 | 2 | 0 | 802.4 | 517.6
3421 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)6/16 AMP SOCKET | NOS | 6 | 274.94 | 1649.64 | 6 | 274.94 | 1649.64 | 1 | 274.94 | 274.94 | 6 | 187.92 | 1127.5002 | 0 | 0 | 0 | 5 | 6 | 1374.7 | 1649.64
3422 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)6/16 AMP SWITCH | NOS | 6 | 142.78 | 856.68 | 6 | 142.78 | 856.68 | 1 | 142.78 | 142.78 | 6 | 115.64 | 693.84 | 6 | 115.64 | 693.84 | 5 | 0 | 713.9 | 162.84
3423 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)8 MODULAR BOX (SQUARE) COVER | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3424 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)BLANK SWITCH | NOS | 2 | 61.36 | 122.72 | 2 | 61.36 | 122.72 | 0 | 61.36 | 0 | 2 | 30.56 | 61.12 | 0 | 0 | 0 | 2 | 2 | 122.72 | 122.72
3425 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)HDMI CABLE | MTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3426 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)TELEPHONE SOCKET | NOS | 1 | 354 | 354 | 1 | 354 | 354 | 0 | 354 | 0 | 1 | 123.49 | 123.49 | 1 | 123.49 | 123.49 | 1 | 0 | 354 | 230.51
3427 | SELLING COST - Site Office Meeting Area AVR Customer Toilet | 10 | Started | Material | (M)TELEPHONE/ INTERCOME SOCKET | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3428 | SELLING COST - Site Office Outside Reparing Work | 10 | Started | Labour | (L)OUTSIDE BOARD AND PLY REPAIR (ONLY LABOUR) | SQM | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 20000 | 20000
3429 | SELLING COST - Site Office Outside Reparing Work | 10 | Started | Labour | (L)OUTSIDE CRACK REPAIR (ONLY LABOURI) | SQM | 2 | 25000 | 50000 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 50000 | 50000
3430 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Labour | (L)GLASS DOOR LOCK | NOS | 2 | 3300 | 6600 | 0 | 0 | 0 | 0 | 3300 | 0 | 2 | 3300 | 6600 | 2 | 3300 | 6600 | 2 | 0 | 6600 | 0
3431 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Labour | (L)LABOUR CHARGES | NOS | 2 | 600 | 1200 | 0 | 0 | 0 | 0 | 600 | 0 | 2 | 600 | 1200 | 2 | 600 | 1200 | 2 | 0 | 1200 | 0
3432 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Material | (M)Balcony Bedroom Buddha Wall | MTR | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3000 | 6000 | 2 | 0 | 0 | -6000
3433 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Material | (M)Balcony Bedroom Headboard | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6300 | 6300 | 1 | 0 | 0 | -6300
3434 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Material | (M)Balcony Bedroom Headboard opp.wall | MTR | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2250 | 4500 | 2 | 0 | 0 | -4500
3435 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Material | (M)Balcony Bedroom Labour | MTR | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 500 | 11500 | 23 | 0 | 0 | -11500
3436 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Material | (M)Balcony Bedroom Lounge | MTR | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3000 | 15000 | 5 | 0 | 0 | -15000
3437 | SELLING COST - Site Office Reception Lounge Area Work | 0 | Started | Material | (M)BALCONY CLOTH | MTR | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1447.95 | 8687.7 | 6 | 0 | 0 | -8687.7
3438 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Labour | (L)4NOS GLASS, 4MM MS 1"X 1" (4' 0" X 4' 0") WITH POWDER COATIN | UNIT | 1 | 10400 | 10400 | 0 | 0 | 0 | 0 | 10400 | 0 | 1 | 10400 | 10400 | 1 | 10400 | 10400 | 1 | 0 | 10400 | 0
3439 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Labour | (L)ADJUSTMENT OF VERTICAL MEMBERS OF BALCONY SLIDING DUE TO IN | NOS | 1 | 1100 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 1 | 1100 | 1100 | 1 | 1100 | 1100 | 1 | 0 | 1100 | 0
3440 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Labour | (L)LOCK | NOS | 1 | 2600 | 2600 | 0 | 0 | 0 | 0 | 2600 | 0 | 1 | 2600 | 2600 | 1 | 2600 | 2600 | 1 | 0 | 2600 | 0
3441 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Labour | (L)LOUVER GLASS ALUMINIUM SECTION WITH POWDER COATING | NOS | 1 | 1000 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 1 | 0 | 1000 | 0
3442 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Labour | (L)SILICON PASTING OUTSIDE OF LOUNGE ,RECEPTION ,MODEL FLAT | NOS | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 1 | 0 | 5000 | 0
3443 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Labour | (L)SPECIAL ARRANGEMENT FOR FIXING THE PROJECTOR FROM CEILING IN | NOS | 1 | 3800 | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 1 | 3800 | 3800 | 1 | 3800 | 3800 | 1 | 0 | 3800 | 0
3444 | SELLING COST - Site Office Ladies Toilet Model Flat Lounge | 0 | Started | Material | (M)RAPIDEX 1200 X 600. VITRIFIED TILES. | BOX | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1819.98 | 20019.8 | 1 | -10 | 0 | -20019.8
3445 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)CONFERENCE ROOM | NOS | 1 | 500 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 500 | 500
3446 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)FILE CABINET AT CONFERENCE ROOM 37.125 SQ.FT | NOS | 37.125 | 1500 | 55687.5 | 0 | 0 | 0 | 4 | 1500 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 33.125 | 37.125 | 49687.5 | 55687.5
3447 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)GODOWN GATE | NOS | 1 | 2000 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 1 | 2000 | 2000 | 1 | 2000 | 2000 | 1 | 0 | 2000 | 0
3448 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)LAPTOP TABLE AT A.V ROOM 6.25 SQ.FT ( 2'6" X 2'6" X 1'6") | NOS | 6.25 | 1855 | 11593.75 | 0 | 0 | 0 | 1 | 1855 | 1855 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 6.25 | 9738.75 | 11593.75
3449 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)LAPTOP TABLE AT A.V ROOM 6.25 SQ.FT ( 2'6" X 2'6" X 1'6"):- | NOS | 6.25 | 2500 | 15625 | 0 | 0 | 0 | 1 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 6.25 | 13125 | 15625
3450 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)OUTSIDE OF MARKETTING OFFICE | NOS | 1 | 4500 | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 1 | 4500 | 4500 | 1 | 4500 | 4500 | 1 | 0 | 4500 | 0
3451 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)OVER HEAD CABINET AT SALES OFFICE 24.50 SQ.FT | AREA | 49 | 1500 | 73500 | 0 | 0 | 0 | 5 | 1500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 49 | 66000 | 73500
3452 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)PORTA CABIN | NOS | 1 | 17750 | 17750 | 0 | 0 | 0 | 0 | 17750 | 0 | 1 | 17750 | 17750 | 1 | 17750 | 17750 | 1 | 0 | 17750 | 0
3453 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)SALES OFFICE | NOS | 1 | 2500 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 0 | 2500 | 0
3454 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Labour | (L)SQUARE TABLE 3.75 SQ.FT ( 1'6" X 1'6" BOTTOM ; 1'2" X 1'2 | NOS | 3.75 | 2500 | 9375 | 0 | 0 | 0 | 0 | 2500 | 0 | 0.001 | 2500 | 2.5 | 0.0004 | 2200 | 0.88 | 3.75 | 3.7496 | 9375 | 9374.12
3455 | SELLING COST - Site Office Repairing And New Furniture | 10 | Started | Material | (M)EPWC Seat Cover | NOS | 2 | 2360 | 4720 | 2 | 2360 | 4720 | 0 | 2360 | 0 | 2 | 2360 | 4720 | 2 | 2360 | 4720 | 2 | 0 | 4720 | 0
3456 | SELLING COST - Site Office New Pantry Work with Shera Board | 10 | Started | Labour | (L)OVER HEAD CABINET AT PANTRY 9 SQ.FT ( 4'6" X 2'0" X 1'4") | NOS | 9 | 1300 | 11700 | 0 | 0 | 0 | 1 | 1300 | 1300 | 9 | 1300 | 11700 | 9 | 1300 | 11700 | 8 | 0 | 10400 | 0
3457 | SELLING COST - Site Office New Pantry Work with Shera Board | 10 | Started | Labour | (L)PARTITION DISMANTLING , RE - MAKING :- INCLUDING SCREW; | LS | 1 | 4500 | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 1 | 4500 | 4500 | 1 | 4500 | 4500 | 1 | 0 | 4500 | 0
3458 | SELLING COST - Site Office New Pantry Work with Shera Board | 10 | Started | Labour | (L)SHERA BORAD REPAIRING & FIXING | LS | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 1 | 0 | 5000 | 0
3459 | SELLING COST - Site Office New Pantry Work with Shera Board | 10 | Started | Labour | (L)SHERABOARD PAINT INCLUDING PAINT& LACQUER (BOTH SIDE) | NOS | 325 | 98 | 31850 | 0 | 0 | 0 | 33 | 98 | 3234 | 323.65 | 98 | 31717.7 | 323.65 | 98 | 31717.7 | 292 | 1.35 | 28616 | 132.3
3460 | SELLING COST - Site Office New Pantry Work with Shera Board | 10 | Started | Labour | (L)SHERABOARD PAINT INCLUDING PAINT& LACQUER (SINGLE SIDE) | NOS | 352 | 50 | 17600 | 0 | 0 | 0 | 35 | 50 | 1750 | 351.21 | 50 | 17560.5 | 351.21 | 50 | 17560.5 | 317 | 0.79 | 15850 | 39.5
3461 | SELLING COST - Site Office New Pantry Work with Shera Board | 10 | Started | Labour | (L)UNDER SLAB PANTRY CABINET 16.25 SQ.FT | NOS | 16.25 | 1600 | 26000 | 0 | 0 | 0 | 2 | 1600 | 3200 | 16.25 | 1600 | 26000 | 16.25 | 1600 | 26000 | 14.25 | 0 | 22800 | 0
3462 | SELLING COST - Site Office Reception Side New Drawer | 10 | Started | Labour | (L)NEW DRAWER | LS | 1 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 1 | 6000 | 6000 | 1 | 6000 | 6000 | 1 | 0 | 6000 | 0
3463 | SELLING COST - Site Office Electrical AVR | 10 | Started | Material | (M)12 MOD COVER | NOS | 1 | 731.6 | 731.6 | 0 | 0 | 0 | 0 | 731.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 731.6 | 731.6
3464 | SELLING COST - Site Office Electrical AVR | 10 | Started | Material | (M)12 MODULAR PVC BOARD | NOS | 2 | 507.4 | 1014.8 | 0 | 0 | 0 | 0 | 507.4 | 0 | 0 | 0 | 0 | 2 | 300.9 | 601.8 | 2 | 0 | 1014.8 | 413
3465 | SELLING COST - Site Office Electrical AVR | 10 | Started | Material | (M)12 MODULER PLATE | NOS | 2 | 625.4 | 1250.8 | 0 | 0 | 0 | 0 | 625.4 | 0 | 0 | 0 | 0 | 2 | 175.11 | 350.22 | 2 | 0 | 1250.8 | 900.58
3466 | SELLING COST - Site Office Electrical AVR | 10 | Started | Material | (M)12MM CLIP | PKT | 2 | 401.2 | 802.4 | 0 | 0 | 0 | 0 | 401.2 | 0 | 0 | 0 | 0 | 2 | 401.86 | 803.71 | 2 | 0 | 802.4 | -1.31
3467 | SELLING COST - Site Office Electrical AVR | 10 | Started | Material | (M)AHUJA AMPLIFIER | NOS | 1 | 11210 | 11210 | 0 | 0 | 0 | 0 | 11210 | 0 | 0 | 0 | 0 | 1 | 12638.15 | 12638.15 | 1 | 0 | 11210 | -1428.15
3468 | SELLING COST - Site Office Electrical AVR | 10 | Started | Material | (M)HDMI CABLE | MTR | 20 | 236 | 4720 | 20 | 236 | 4720 | 2 | 236 | 472 | 20 | 171.1 | 3422 | 20 | 237.48 | 4749.5 | 18 | 0 | 4248 | -29.5
3469 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)1.5 SQ MM 2 CORE CABLE (COPPER) | MTR | 400 | 47.2 | 18880 | 400 | 47.2 | 18880 | 40 | 47.2 | 1888 | 400 | 35.82 | 14329.92 | 400 | 36.82 | 14727.6 | 360 | 0 | 16992 | 4152.4
3470 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)1.5 SQ MM WIRE | MTR | 180 | 23.6 | 4248 | 0 | 0 | 0 | 18 | 23.6 | 424.8 | 0 | 0 | 0 | 180 | 14.24 | 2562.79 | 162 | 0 | 3823.2 | 1685.21
3471 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(BLUE,180 MTR) | COIL | 2 | 5144.8 | 10289.6 | 0 | 0 | 0 | 0 | 5144.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 10289.6 | 10289.6
3472 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)1.5 SQ.MM COPPER WIRE(RED,180 MTR) | COIL | 2 | 5144.8 | 10289.6 | 0 | 0 | 0 | 0 | 5144.8 | 0 | 0 | 0 | 0 | 2 | 2670.68 | 5341.35 | 2 | 0 | 10289.6 | 4948.25
3473 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)200 WATT LED LIGHT | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3474 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)CL 9W LED MODULE | NOS | 21 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 21 | 596.33 | 12522.94 | 19 | 0 | 0 | -12522.94
3475 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)COLUMN LIGHT | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4125.96 | 8251.92 | 2 | 0 | 0 | -8251.92
3476 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)DOUBLE POLE MCB 20 AMP | NOS | 1 | 1345.2 | 1345.2 | 0 | 0 | 0 | 0 | 1345.2 | 0 | 0 | 0 | 0 | 1 | 602.63 | 602.63 | 1 | 0 | 1345.2 | 742.57
3477 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)FAWN-8 CHANDELIER FITTING | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29303.18 | 29303.18 | 1 | 0 | 0 | -29303.18
3478 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)GEF-5020 CFLOOR LIGHT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15306.53 | 15306.53 | 1 | 0 | 0 | -15306.53
3479 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)GEH0151-1 HANGING LAMP | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9472.08 | 9472.08 | 1 | 0 | 0 | -9472.08
3480 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED 10AMP SMPS DRIVER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 952 | 952 | 1 | 0 | 0 | -952
3481 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED 2AMP SMPS DRIVER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 292.54 | 292.54 | 1 | 0 | 0 | -292.54
3482 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED 5AMP SMPS DRIVER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 506.17 | 16197.55 | 1 | -31 | 0 | -16197.55
3483 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED BULB 4.9W/827 FR E27 LVCLP40 LEDVANCE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 250.37 | 500.73 | 1 | -1 | 0 | -500.73
3484 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED CANDLE 4.9W/827 E14 LVCLB40 (OSRAM) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 215.69 | 1725.55 | 1 | -7 | 0 | -1725.55
3485 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED LIGHT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 265.5 | 265.5 | 1 | 0 | 0 | -265.5
3486 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LED TUBE LIGHT | NOS | 1 | 263.39 | 263.39 | 0 | 0 | 0 | 0 | 263.39 | 0 | 0 | 0 | 0 | 15 | 247.8 | 3717 | 1 | -14 | 263.39 | -3453.61
3487 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)LEGRAND I/O | NOS | 1 | 708 | 708 | 0 | 0 | 0 | 0 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 708 | 708
3488 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)STREET LIGHT | NOS | 21 | 3056.2 | 64180.2 | 0 | 0 | 0 | 2 | 3056.2 | 6112.4 | 0 | 0 | 0 | 16 | 4214.55 | 67432.77 | 19 | 5 | 58067.8 | -3252.57
3489 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)UP LIGHTER 5 WATT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1375.32 | 20629.79 | 1 | -14 | 0 | -20629.79
3490 | SELLING COST - Site Office Electrical Light | 10 | Started | Material | (M)XQ-AE059 | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6145.37 | 6145.37 | 1 | 0 | 0 | -6145.37
3491 | SELLING COST - Site Office Electrical Panel Earthing Labour | 10 | Started | Labour | (L)Laying the 25mm X 6mm GI Strip | RMT | 13 | 75 | 975 | 0 | 0 | 0 | 1 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13 | 900 | 975
3492 | SELLING COST - Site Office Electrical Panel Earthing Labour | 10 | Started | Labour | (L)Laying the running Earth by 50mm. X 6mm. GI Strip | RMT | 15 | 1250 | 18750 | 0 | 0 | 0 | 2 | 1250 | 2500 | 12 | 147.5 | 1770 | 12 | 147.5 | 1770 | 13 | 3 | 16250 | 16980
3493 | SELLING COST - Site Office Electrical Panel Earthing Labour | 10 | Started | Labour | (L)Making of GI Perforated Earthing Pipe 50mm. x 3.15mm dia. | NOS | 2 | 2650 | 5300 | 0 | 0 | 0 | 0 | 2650 | 0 | 2 | 3127 | 6254 | 2 | 3127 | 6254 | 2 | 0 | 5300 | -954
3494 | SELLING COST - Site Office Electrical Panel Earthing Labour | 10 | Started | Material | (M)EARTHING SALT | BAG | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 324.5 | 324.5 | 1 | 0 | 0 | -324.5
3495 | SELLING COST - Site Office Electrical Panel Earthing Labour | 10 | Started | Material | (M)EARTHING CHARCOAL | BAG | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 182.9 | 182.9 | 1 | 0 | 0 | -182.9
3496 | SELLING COST - Site Office Electrical Panel Earthing Labour | 10 | Started | Material | (M)G. I EARTHING PIPE | PICS | 1 | 2277.4 | 2277.4 | 0 | 0 | 0 | 0 | 2277.4 | 0 | 0 | 0 | 0 | 2 | 2271.5 | 4543 | 1 | -1 | 2277.4 | -2265.6
3497 | SELLING COST - Site Office Supply Of Electrician Daily Basic | 10 | Started | Labour | (L)SUPPLY OF ELECTRICIAN | NOS | 60 | 550 | 33000 | 0 | 0 | 0 | 6 | 550 | 3300 | 26 | 649 | 16874 | 26 | 649 | 16874 | 54 | 34 | 29700 | 16126
3498 | BROKERAGE ON SALES - Brokerage on Sales | 10 | Started | Labour | (L)Brokerage on Sale | NOS | 27800000 | 1.18 | 32804000 | 0 | 0 | 0 | 2780000 | 1.18 | 3280400 | 18072153.0071 | 1.81 | 32701953.0941 | 10921060.0071 | 2.22 | 24263663.35 | 25020000 | 16878939.9929 | 29523600 | 8540336.65
3499 | FIXED ASSETS - Assets | 10 | Started | Labour | (L)Autocad Including Specialised With AMC | NOS | 2 | 94400 | 188800 | 0 | 0 | 0 | 0 | 94400 | 0 | 2 | 94400 | 188800 | 2 | 94400 | 188800 | 2 | 0 | 188800 | 0
3500 | FIXED ASSETS - Assets | 10 | Started | Labour | (L)HO SERVER CABINET | LS | 1 | 17841.6 | 17841.6 | 0 | 0 | 0 | 0 | 17841.6 | 0 | 1 | 15100 | 15100 | 1 | 15100 | 15100 | 1 | 0 | 17841.6 | 2741.6
3501 | FIXED ASSETS - Assets | 10 | Started | Labour | (L)L/C for driving Z Section Sheet Piles by Power Winch | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3502 | FIXED ASSETS - Assets | 10 | Started | Labour | (L)L/C for extracting Z section Sheet Piles by Power Winch | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3503 | FIXED ASSETS - Assets | 10 | Started | Labour | (L)L/C for Fabrication & Erection of supporting Str. Members | MT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3504 | FIXED ASSETS - Assets | 10 | Started | Material | (M)12U Loaded Networking Rack | NOS | 1 | 6755.5 | 6755.5 | 1 | 6755.5 | 6755.5 | 0 | 6755.5 | 0 | 1 | 6755.5 | 6755.5 | 1 | 6755.5 | 6755.5 | 1 | 0 | 6755.5 | 0
3505 | FIXED ASSETS - Assets | 10 | Started | Material | (M)16 MM TIE - ROD 1.50 MTR EACH | MTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3506 | FIXED ASSETS - Assets | 10 | Started | Material | (M)18mm Concrete Breaker w/Chisel Hammer Bit set,Wt.5Kg(220V) | NOS | 2 | 94400 | 188800 | 2 | 94400 | 188800 | 0 | 94400 | 0 | 2 | 14910.88 | 29821.76 | 2 | 14887.56 | 29775.12 | 2 | 0 | 188800 | 159024.88
3507 | FIXED ASSETS - Assets | 10 | Started | Material | (M)200 WATT LED LIGHT | NOS | 5 | 1.18 | 5.9 | 0 | 0 | 0 | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 1 | 3545.31 | 3545.31 | 4 | 4 | 4.72 | -3539.41
3508 | FIXED ASSETS - Assets | 10 | Started | Material | (M)250MM CABLE TIE | PKT | 2 | 413 | 826 | 2 | 413 | 826 | 0 | 413 | 0 | 2 | 413 | 826 | 2 | 413 | 826 | 2 | 0 | 826 | 0
3509 | FIXED ASSETS - Assets | 10 | Started | Material | (M)3'' DELIVERY PIPE | MTR | 180 | 129.8 | 23364 | 90 | 129.8 | 11682 | 18 | 129.8 | 2336.4 | 90 | 129.8 | 11682 | 180 | 105.02 | 18903.6 | 162 | 0 | 21027.6 | 4460.4
3510 | FIXED ASSETS - Assets | 10 | Started | Material | (M)5 MTR LONG LEVEL STAFF | NOS | 1 | 2124 | 2124 | 1 | 2124 | 2124 | 0 | 2124 | 0 | 1 | 2124 | 2124 | 1 | 2124 | 2124 | 1 | 0 | 2124 | 0
3511 | FIXED ASSETS - Assets | 10 | Started | Material | (M)ADJUSTABLE TELESCOPIC SPAN (2360MM.X 2360MM.) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3512 | FIXED ASSETS - Assets | 10 | Started | Material | (M)ADJUSTABLE TELESCOPIC SPAN (3000MM X 3000MM) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3513 | FIXED ASSETS - Assets | 10 | Started | Material | (M)BAR CUTTING MACHINE | NOS | 1 | 200600 | 200600 | 1 | 200600 | 200600 | 0 | 200600 | 0 | 1 | 182900 | 182900 | 0 | 0 | 0 | 1 | 1 | 200600 | 200600
3514 | FIXED ASSETS - Assets | 10 | Started | Material | (M)BASE PLATE (150 MM X150 MM) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3515 | FIXED ASSETS - Assets | 10 | Started | Material | (M)Cable Manager | NOS | 2 | 377.6 | 755.2 | 2 | 377.6 | 755.2 | 0 | 377.6 | 0 | 2 | 377.6 | 755.2 | 2 | 377.6 | 755.2 | 2 | 0 | 755.2 | 0
3516 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CABLE WIRE 1.5 MM | SQM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3517 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CADMATE Professional standalone 2024 | NOS | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 59000 | 0
3518 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CANVAS HOSE PIPE (80 MM DIA) (30 MTR) | COIL | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
3519 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CAST IRON CEMENT CUBE MOULD WITH BAES PLATE (SIZE - 50 MM) | NOS | 6 | 649 | 3894 | 6 | 649 | 3894 | 1 | 649 | 649 | 6 | 649 | 3894 | 6 | 649 | 3894 | 5 | 0 | 3245 | 0
3520 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CCTV CAMERA | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3521 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CENTRAL INTERCEPT X ADVANCED FOR ENDPOINT WITH XDR | NOS | 45 | 1876.2 | 84429 | 45 | 1876.2 | 84429 | 5 | 1876.2 | 9381 | 45 | 2007.31 | 90328.95 | 45 | 1987.27 | 89427.2 | 40 | 0 | 75048 | -4998.2
3522 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CENTRIFUGAL MONO BLOCK PUMP SINGLE PHASE | NOS | 1 | 17605.6 | 17605.6 | 1 | 17605.6 | 17605.6 | 0 | 17605.6 | 0 | 1 | 13055.91 | 13055.91 | 1 | 12943.81 | 12943.81 | 1 | 0 | 17605.6 | 4661.79
3523 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CHAIN PULLEY | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3524 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CPU | SET | 1 | 29736 | 29736 | 1 | 29736 | 29736 | 0 | 29736 | 0 | 1 | 29736 | 29736 | 1 | 29736 | 29736 | 1 | 0 | 29736 | 0
3525 | FIXED ASSETS - Assets | 10 | Started | Material | (M)CYBERPOWER 650VA UPS | NOS | 1 | 2879.2 | 2879.2 | 1 | 2879.2 | 2879.2 | 0 | 2879.2 | 0 | 1 | 2832 | 2832 | 1 | 2832 | 2832 | 1 | 0 | 2879.2 | 47.2
3526 | FIXED ASSETS - Assets | 10 | Started | Material | (M)DESKTOP | NOS | 1 | 32697.8 | 32697.8 | 1 | 32697.8 | 32697.8 | 0 | 32697.8 | 0 | 1 | 16520 | 16520 | 6 | 27247.27 | 163483.64 | 1 | -5 | 32697.8 | -130785.84
3527 | FIXED ASSETS - Assets | 10 | Started | Material | (M)DRILL MACHINE | NOS | 6 | 9699.6 | 58197.6 | 4 | 9699.6 | 38798.4 | 1 | 9699.6 | 9699.6 | 4 | 7270.08 | 29080.3 | 6 | 8692.31 | 52153.87 | 5 | 0 | 48498 | 6043.73
3528 | FIXED ASSETS - Assets | 10 | Started | Material | (M)FIXED TYPE ELECTROPLATED COUPLER(40X40) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3529 | FIXED ASSETS - Assets | 10 | Started | Material | (M)FOOT VALVE (NP) 2"(METAL) | NOS | 1 | 814.2 | 814.2 | 1 | 814.2 | 814.2 | 0 | 814.2 | 0 | 1 | 808.3 | 808.3 | 1 | 808.3 | 808.3 | 1 | 0 | 814.2 | 5.9
3530 | FIXED ASSETS - Assets | 10 | Started | Material | (M)FOOT VALVE (NP) 3"(METAL) | NOS | 1 | 1121 | 1121 | 1 | 1121 | 1121 | 0 | 1121 | 0 | 1 | 1121 | 1121 | 1 | 1121 | 1121 | 1 | 0 | 1121 | 0
3531 | FIXED ASSETS - Assets | 10 | Started | Material | (M)Furniture & Fixture | NOS | 43661 | 1.18 | 51519.98 | 1 | 1.18 | 1.18 | 4366 | 1.18 | 5151.88 | 1 | 43665 | 43665 | 1 | 43665 | 43665 | 39295 | 43660 | 46368.1 | 7854.98
3532 | FIXED ASSETS - Assets | 10 | Started | Material | (M)GARDEN TABLE & CHAIR | SET | 1 | 23600 | 23600 | 1 | 23600 | 23600 | 0 | 23600 | 0 | 1 | 24780 | 24780 | 0 | 0 | 0 | 1 | 1 | 23600 | 23600
3533 | FIXED ASSETS - Assets | 10 | Started | Material | (M)HARDWARE NUT | PKT | 2 | 283.2 | 566.4 | 1 | 283.2 | 283.2 | 0 | 283.2 | 0 | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 2 | 1 | 566.4 | 283.2
3534 | FIXED ASSETS - Assets | 10 | Started | Material | (M)Headphones with microphone | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3535 | FIXED ASSETS - Assets | 10 | Started | Material | (M)HORIZENTAL PUMP (3 HP) | NOS | 1 | 26007.2 | 26007.2 | 1 | 26007.2 | 26007.2 | 0 | 26007.2 | 0 | 1 | 27190.74 | 27190.74 | 1 | 27009.55 | 27009.55 | 1 | 0 | 26007.2 | -1002.35
3536 | FIXED ASSETS - Assets | 10 | Started | Material | (M)ISMB 300 | KG | 2209 | 76.7 | 169430.3 | 2209 | 76.7 | 169430.3 | 221 | 76.7 | 16950.7 | 0 | 0 | 0 | 0 | 0 | 0 | 1988 | 2209 | 152479.6 | 169430.3
3537 | FIXED ASSETS - Assets | 10 | Started | Material | (M)LAPTOP | NOS | 4 | 34869 | 139476 | 4 | 34869 | 139476 | 0 | 34869 | 0 | 4 | 30296.5 | 121186 | 3 | 34023.33 | 102070 | 4 | 1 | 139476 | 37406
3538 | FIXED ASSETS - Assets | 10 | Started | Material | (M)LED LIGHT | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3539 | FIXED ASSETS - Assets | 10 | Started | Material | (M)LENGTH GUAGE | NOS | 1 | 590 | 590 | 1 | 590 | 590 | 0 | 590 | 0 | 1 | 590 | 590 | 1 | 590 | 590 | 1 | 0 | 590 | 0
3540 | FIXED ASSETS - Assets | 10 | Started | Material | (M)MOBILE PEDESTAL WITH LOCK 2D1F : 400W X 450D X 600HT | NOS | 4 | 8460.6 | 33842.4 | 4 | 8460.6 | 33842.4 | 0 | 8460.6 | 0 | 4 | 8260 | 33040 | 4 | 8650.67 | 34602.66 | 4 | 0 | 33842.4 | -760.26
3541 | FIXED ASSETS - Assets | 10 | Started | Material | (M)Mobile Phone | NOS | 3 | 11823.6 | 35470.8 | 3 | 11823.6 | 35470.8 | 0 | 11823.6 | 0 | 3 | 27999.67 | 83999.015 | 2 | 36749.51 | 73499.01 | 3 | 1 | 35470.8 | -38028.21
3542 | FIXED ASSETS - Assets | 10 | Started | Material | (M)MS O365 | NOS | 1 | 5935.4 | 5935.4 | 1 | 5935.4 | 5935.4 | 0 | 5935.4 | 0 | 1 | 6018 | 6018 | 1 | 6018 | 6018 | 1 | 0 | 5935.4 | -82.6
3543 | FIXED ASSETS - Assets | 10 | Started | Material | (M)NOZZLE VIBRATOR MACHINE 2HP 220V | NOS | 2 | 12980 | 25960 | 2 | 12980 | 25960 | 0 | 12980 | 0 | 2 | 13332.82 | 26665.64 | 2 | 13278.63 | 26557.26 | 2 | 0 | 25960 | -597.26
3544 | FIXED ASSETS - Assets | 10 | Started | Material | (M)RACK TRAY | NOS | 2 | 560.5 | 1121 | 2 | 560.5 | 1121 | 0 | 560.5 | 0 | 2 | 560.5 | 1121 | 2 | 560.5 | 1121 | 2 | 0 | 1121 | 0
3545 | FIXED ASSETS - Assets | 10 | Started | Material | (M)REBAR TYING MACHINE | NOS | 5 | 21240 | 106200 | 5 | 21240 | 106200 | 1 | 21240 | 21240 | 5 | 21240 | 106200 | 5 | 21240 | 106200 | 4 | 0 | 84960 | 0
3546 | FIXED ASSETS - Assets | 10 | Started | Material | (M)REVOLVING CHAIR | NOS | 6 | 5900 | 35400 | 6 | 5900 | 35400 | 1 | 5900 | 5900 | 6 | 5900 | 35400 | 6 | 5900 | 35400 | 5 | 0 | 29500 | 0
3547 | FIXED ASSETS - Assets | 10 | Started | Material | (M)Seagate 1TB USB 3.0 Ext Hdd | NOS | 1 | 5251 | 5251 | 1 | 5251 | 5251 | 0 | 5251 | 0 | 1 | 5251 | 5251 | 1 | 5251 | 5251 | 1 | 0 | 5251 | 0
3548 | FIXED ASSETS - Assets | 10 | Started | Material | (M)SERVICE CHARGES FOR RACK INSTALLATION, | NOS | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 0 | 4720 | 0 | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 1 | 0 | 4720 | 1180
3549 | FIXED ASSETS - Assets | 10 | Started | Material | (M)STARTER 3 PHASE 7.5 HP | NOS | 2 | 3658 | 7316 | 2 | 3658 | 7316 | 0 | 3658 | 0 | 2 | 2235.33 | 4470.66 | 2 | 2235.33 | 4470.66 | 2 | 0 | 7316 | 2845.34
3550 | FIXED ASSETS - Assets | 10 | Started | Material | (M)SWIVEL TYPE ELECTROPLATED COUPLER(40X40) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 76.28 | 30510.08 | 0 | -400 | 0 | -30510.08
3551 | FIXED ASSETS - Assets | 10 | Started | Material | (M)T TIE | PKT | 2 | 306.8 | 613.6 | 2 | 306.8 | 613.6 | 0 | 306.8 | 0 | 2 | 306.8 | 613.6 | 2 | 306.8 | 613.6 | 2 | 0 | 613.6 | 0
3552 | FIXED ASSETS - Assets | 10 | Started | Material | (M)THICKNESS GUAGE | NOS | 1 | 590 | 590 | 1 | 590 | 590 | 0 | 590 | 0 | 1 | 590 | 590 | 1 | 590 | 590 | 1 | 0 | 590 | 0
3553 | FIXED ASSETS - Assets | 10 | Started | Material | (M)U-HEAD (18" /455 MM | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3554 | FIXED ASSETS - Assets | 10 | Started | Material | (M)VICAT APPARATUS | NOS | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 0 | 3068 | 0 | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 1 | 0 | 3068 | 0
3555 | FIXED ASSETS - Assets | 10 | Started | Material | (M)WINDOWS 10 HOME | NOS | 2 | 8496 | 16992 | 2 | 8496 | 16992 | 0 | 8496 | 0 | 2 | 8496 | 16992 | 2 | 8496 | 16992 | 2 | 0 | 16992 | 0
3556 | FIXED ASSETS - Assets | 10 | Started | Material | (M)WING NUT (16 MM) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 33.37 | 18687.42 | 0 | -560 | 0 | -18687.42
3557 | FIXED ASSETS - Assets | 10 | Started | Material | (M)Z SHEET PILE (E-250 GRADE 12M LONG) | MT | 53.295 | 80240 | 4276390.8 | 53.295 | 80240 | 4276390.8 | 5 | 80240 | 401200 | 53.06 | 80240 | 4257534.4 | 53.06 | 80240 | 4257534.4 | 48.295 | 0.235 | 3875190.8 | 18856.4
3558 | FIXED ASSETS - Site Assets | 0 | Started | Labour | (L)FREIGHT CHARGES | TRIP | 3 | 7080 | 21240 | 0 | 0 | 0 | 0 | 7080 | 0 | 3 | 1888 | 5664 | 3 | 1888 | 5664 | 3 | 0 | 21240 | 15576
3559 | FIXED ASSETS - Site Assets | 0 | Started | Labour | (L)Safety Ext. Bracket for Chajja | KG | 1350 | 118 | 159300 | 0 | 0 | 0 | 0 | 118 | 0 | 980 | 118 | 115640 | 980 | 118 | 115640 | 1350 | 370 | 159300 | 43660
3560 | FIXED ASSETS - Site Assets | 0 | Started | Labour | (L)Supply & making of MS table (hollow sq. bar) incl. priming | KG | 1350 | 106.2 | 143370 | 0 | 0 | 0 | 0 | 106.2 | 0 | 1350 | 106.2 | 143370 | 1350 | 106.2 | 143370 | 1350 | 0 | 143370 | 0
3561 | FIXED ASSETS - Site Assets | 0 | Started | Labour | (L)Supply & making of Safety Ext. Bracket as per spec.. | KG | 1550 | 103.84 | 160952 | 0 | 0 | 0 | 0 | 103.84 | 0 | 1450 | 103.84 | 150568 | 1450 | 103.84 | 150568 | 1550 | 100 | 160952 | 10384
3562 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)16 MM X 50MM PIN | NOS | 40800 | 11.8 | 481440 | 40800 | 11.8 | 481440 | 0 | 11.8 | 0 | 40800 | 9.95 | 406144 | 34860 | 9.88 | 344302.95 | 40800 | 5940 | 481440 | 137137.05
3563 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)20 MM PVC PIPE | NOS | 830 | 76.7 | 63661 | 0 | 0 | 0 | 0 | 76.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 830 | 63661 | 63661
3564 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)3'' DELIVERY PIPE | MTR | 120 | 129.8 | 15576 | 120 | 129.8 | 15576 | 0 | 129.8 | 0 | 120 | 76.7 | 9204 | 120 | 76.7 | 9204 | 120 | 0 | 15576 | 6372
3565 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)40mm X 40mmX2.8mm hollow MS square bar 6m Length | KG | 3600 | 71.98 | 259128 | 3115 | 71.98 | 224217.7 | 0 | 71.98 | 0 | 3115 | 79.77 | 248492.64 | 3115 | 79.48 | 247582.69 | 3600 | 485 | 259128 | 11545.31
3566 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)8 MM DIA STEEL ROPE | RMT | 350 | 70.8 | 24780 | 350 | 70.8 | 24780 | 0 | 70.8 | 0 | 350 | 70.8 | 24780 | 350 | 70.8 | 24780 | 350 | 0 | 24780 | 0
3567 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)ADJ. BASE JACK 450MM | NOS | 50 | 306.8 | 15340 | 50 | 306.8 | 15340 | 0 | 306.8 | 0 | 50 | 312.31 | 15615.5 | 50 | 311.46 | 15573.17 | 50 | 0 | 15340 | -233.17
3568 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)ADJ. U-HEAD JACK 450MM | NOS | 50 | 306.8 | 15340 | 50 | 306.8 | 15340 | 0 | 306.8 | 0 | 50 | 312.31 | 15615.5 | 50 | 311.46 | 15573.17 | 50 | 0 | 15340 | -233.17
3569 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)ADJUSTABLE TELESCOPIC SPAN (2360MM.X 2360MM.) | NOS | 2500 | 82.6 | 206500 | 2425 | 82.6 | 200305 | 0 | 82.6 | 0 | 2425 | 86.53 | 209835.25 | 0 | 0 | 0 | 2500 | 2500 | 206500 | 206500
3570 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)ANUTRON-1616 PP SHEET - 1 MTR X 2 MTR X 10MM | SQM | 80 | 2183 | 174640 | 80 | 2183 | 174640 | 0 | 2183 | 0 | 80 | 2205.13 | 176410.4 | 36 | 2201.56 | 79256 | 80 | 44 | 174640 | 95384
3571 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)ANUTRON-1616 PP SHEET - 1 MTR X 2 MTR X 15 MM | SQM | 14 | 2578.3 | 36096.2 | 14 | 2578.3 | 36096.2 | 0 | 2578.3 | 0 | 14 | 3375.64 | 47258.96 | 14 | 3359.96 | 47039.5 | 14 | 0 | 36096.2 | -10943.3
3572 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)BRACKET TIE ROD 500MM | NOS | 635 | 115.64 | 73431.4 | 635 | 115.64 | 73431.4 | 0 | 115.64 | 0 | 635 | 117.08 | 74345.8 | 305 | 116.76 | 35612.32 | 635 | 330 | 73431.4 | 37819.08
3573 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)D CLAMP | PCS | 250 | 11.8 | 2950 | 250 | 11.8 | 2950 | 0 | 11.8 | 0 | 250 | 14.16 | 3540 | 250 | 14.16 | 3540 | 250 | 0 | 2950 | -590
3574 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)DESKTOP | NOS | 2 | 32697.8 | 65395.6 | 2 | 32697.8 | 65395.6 | 0 | 32697.8 | 0 | 2 | 40120 | 80240 | 2 | 40120 | 80240 | 2 | 0 | 65395.6 | -14844.4
3575 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)DRIP MOULD (PVC) | NOS | 510 | 147.5 | 75225 | 510 | 147.5 | 75225 | 0 | 147.5 | 0 | 510 | 194.7 | 99297 | 150 | 194.7 | 29205 | 510 | 360 | 75225 | 46020
3576 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)HOLE BARI | NOS | 15 | 141.6 | 2124 | 15 | 141.6 | 2124 | 0 | 141.6 | 0 | 15 | 145.75 | 2186.25 | 15 | 145.36 | 2180.35 | 15 | 0 | 2124 | -56.35
3577 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)KEYBOARD & MOUSE | NOS | 1 | 802.4 | 802.4 | 1 | 802.4 | 802.4 | 0 | 802.4 | 0 | 1 | 802.4 | 802.4 | 1 | 802.4 | 802.4 | 1 | 0 | 802.4 | 0
3578 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)KICKER BOLT (16MM DIA x 80MM Long /HALF THREAD ) | NOS | 1050 | 18.88 | 19824 | 1050 | 18.88 | 19824 | 0 | 18.88 | 0 | 1050 | 18.88 | 19824 | 1050 | 18.88 | 19824 | 1050 | 0 | 19824 | 0
3579 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)KICKER NUT 16 MM DIA | NOS | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 4.18 | 41800 | 2020 | 4.17 | 8423.6 | 10000 | 7980 | 0 | -8423.6
3580 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)LINE ADJUSTER JACK | NOS | 830 | 342.2 | 284026 | 0 | 0 | 0 | 0 | 342.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 830 | 284026 | 284026
3581 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)LONG PIN (16MM DIA X 195MM LONG) | NOS | 286 | 68.44 | 19573.84 | 175 | 68.44 | 11977 | 0 | 68.44 | 0 | 175 | 68.1 | 11917.5 | 175 | 67.91 | 11884.68 | 286 | 111 | 19573.84 | 7689.16
3582 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)LVP Wall Mount Speaker | PAIR | 1 | 12944.6 | 12944.6 | 1 | 12944.6 | 12944.6 | 0 | 12944.6 | 0 | 1 | 12944.6 | 12944.6 | 1 | 12944.6 | 12944.6 | 1 | 0 | 12944.6 | 0
3583 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MECHANICAL SHUTT OFF VALVE DN125 & SEAL | NOS | 1 | 30912.9 | 30912.9 | 1 | 30912.9 | 30912.9 | 0 | 30912.9 | 0 | 1 | 30912.9 | 30912.9 | 1 | 30774.85 | 30774.85 | 1 | 0 | 30912.9 | 138.05
3584 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MONITOR | NOS | 3 | 22951 | 68853 | 3 | 22951 | 68853 | 0 | 22951 | 0 | 3 | 5782 | 17346 | 3 | 5782 | 17346 | 3 | 0 | 68853 | 51507
3585 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS BOLT 16x30 MM (ROCKER) | NOS | 4050 | 11.8 | 47790 | 4050 | 11.8 | 47790 | 0 | 11.8 | 0 | 4050 | 12.27 | 49697.5 | 4050 | 12.11 | 49031.65 | 4050 | 0 | 47790 | -1241.65
3586 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS FLAT WASHER 16 MM DIA | NOS | 5550 | 0 | 0 | 5550 | 0 | 0 | 0 | 0 | 0 | 5550 | 2.99 | 16594.5 | 665 | 2.98 | 1980.77 | 5550 | 4885 | 0 | -1980.77
3587 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS NUT 16 MM (ROCKER) | NOS | 5550 | 0 | 0 | 5550 | 0 | 0 | 0 | 0 | 0 | 5550 | 2.99 | 16594.5 | 5450 | 3.03 | 16530.57 | 5550 | 100 | 0 | -16530.57
3588 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS PROP ADJ. 1.0M X 1.5M | NOS | 100 | 914.5 | 91450 | 100 | 914.5 | 91450 | 0 | 914.5 | 0 | 100 | 930.91 | 93091 | 100 | 928.4 | 92840.04 | 100 | 0 | 91450 | -1390.04
3589 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS PROP ADJ. 1.5M X 1.5M | NOS | 100 | 1044.3 | 104430 | 100 | 1044.3 | 104430 | 0 | 1044.3 | 0 | 100 | 1063.04 | 106304 | 100 | 1060.17 | 106017.34 | 100 | 0 | 104430 | -1587.34
3590 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS PROP ADJ. 1.5M X 2M | NOS | 200 | 1168.2 | 233640 | 200 | 1168.2 | 233640 | 0 | 1168.2 | 0 | 200 | 1189.17 | 237834 | 200 | 1185.96 | 237191.34 | 200 | 0 | 233640 | -3551.34
3591 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)MS WINDOWS | NOS | 1 | 10773.4 | 10773.4 | 1 | 10773.4 | 10773.4 | 0 | 10773.4 | 0 | 1 | 11682 | 11682 | 1 | 11682 | 11682 | 1 | 0 | 10773.4 | -908.6
3592 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)NUT BOLT WASHER 6X50 MM | KG | 27000 | 0 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 27000 | 4.66 | 125874 | 15800 | 4.65 | 73496.52 | 27000 | 11200 | 0 | -73496.52
3593 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)NUT BOLT WASHER 6X75 MM | KG | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 5.73 | 14335 | 2500 | 5.73 | 14312.93 | 2500 | 0 | 0 | -14312.93
3594 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PANEL PULLAR | NOS | 13 | 590 | 7670 | 13 | 590 | 7670 | 0 | 590 | 0 | 13 | 643.89 | 8370.56 | 9 | 642.06 | 5778.54 | 13 | 4 | 7670 | 1891.46
3595 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 100 X 65 X 30 (1 MTR) | NOS | 208 | 654.9 | 136219.2 | 208 | 654.9 | 136219.2 | 0 | 654.9 | 0 | 208 | 1300.04 | 270408.32 | 208 | 1297.9 | 269964.11 | 208 | 0 | 136219.2 | -133744.91
3596 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 100 X 65 X 30 (1450 MM) | NOS | 2 | 654.9 | 1309.8 | 0 | 0 | 0 | 0 | 654.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1309.8 | 1309.8
3597 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 100 X 65 X 30 (1650 MM) | NOS | 5 | 654.9 | 3274.5 | 0 | 0 | 0 | 0 | 654.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3274.5 | 3274.5
3598 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 100 X 65 X 30 (2200 MM) | NOS | 74 | 654.9 | 48462.6 | 0 | 0 | 0 | 0 | 654.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 74 | 48462.6 | 48462.6
3599 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 100 X 65 X 30 (850 MM) | NOS | 42 | 654.9 | 27505.8 | 0 | 0 | 0 | 0 | 654.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 27505.8 | 27505.8
3600 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 200 X 165 X 30 (1 MTR) | NOS | 6 | 654.9 | 3929.4 | 6 | 654.9 | 3929.4 | 0 | 654.9 | 0 | 6 | 2278.05 | 13668.3 | 6 | 2274.31 | 13645.86 | 6 | 0 | 3929.4 | -9716.46
3601 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 200 X 165 X 30 (1450MM) | NOS | 1 | 654.9 | 654.9 | 0 | 0 | 0 | 0 | 654.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 654.9 | 654.9
3602 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PHE GROOVE 300 X 265 X 30 (1 MTR) | NOS | 16 | 654.9 | 10478.4 | 16 | 654.9 | 10478.4 | 0 | 654.9 | 0 | 16 | 3029.45 | 48471.2 | 16 | 3024.47 | 48391.59 | 16 | 0 | 10478.4 | -37913.19
3603 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PRINTER | NOS | 1 | 21830 | 21830 | 1 | 21830 | 21830 | 0 | 21830 | 0 | 1 | 15340 | 15340 | 1 | 15340 | 15340 | 1 | 0 | 21830 | 6490
3604 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC CONE 20MM DIA | NOS | 17500 | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 17500 | 2.63 | 45955 | 0 | 0 | 0 | 17500 | 17500 | 0 | 0
3605 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC PIPE 20MM DIA*3MTR. LONG | NOS | 830 | 59 | 48970 | 830 | 59 | 48970 | 0 | 59 | 0 | 830 | 53.1 | 44073 | 10 | 53.1 | 531 | 830 | 820 | 48970 | 48439
3606 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC SLEEVE COVER ROLL | RMT | 400 | 649 | 259600 | 400 | 649 | 259600 | 0 | 649 | 0 | 400 | 6.57 | 2628 | 0 | 0 | 0 | 400 | 400 | 259600 | 259600
3607 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC SLEEVE SHEET (1200 x 1800) | NOS | 15 | 17.7 | 265.5 | 15 | 17.7 | 265.5 | 0 | 17.7 | 0 | 15 | 209.07 | 3136.05 | 0 | 0 | 0 | 15 | 15 | 265.5 | 265.5
3608 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC WALL TIE SLEEVE (100MM TH. WALL) | NOS | 1400 | 14.76 | 20664 | 1400 | 14.76 | 20664 | 0 | 14.76 | 0 | 1400 | 14.64 | 20489 | 1000 | 14.6 | 14595.2 | 1400 | 400 | 20664 | 6068.8
3609 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC WALL TIE SLEEVE (125MM TH. WALL) | NOS | 165 | 14.76 | 2435.4 | 165 | 14.76 | 2435.4 | 0 | 14.76 | 0 | 165 | 18.4 | 3036.33 | 165 | 18.35 | 3027.45 | 165 | 0 | 2435.4 | -592.05
3610 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC WALL TIE SLEEVE (150MM TH. WALL) | NOS | 560 | 22.13 | 12392.8 | 560 | 22.13 | 12392.8 | 0 | 22.13 | 0 | 560 | 22.1 | 12376 | 560 | 22.04 | 12343.41 | 560 | 0 | 12392.8 | 49.39
3611 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC WALL TIE SLEEVE (160MM TH. WALL) | NOS | 540 | 23.6 | 12744 | 540 | 23.6 | 12744 | 0 | 23.6 | 0 | 540 | 23.6 | 12741.3 | 540 | 23.53 | 12706.77 | 540 | 0 | 12744 | 37.23
3612 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)PVC WALL TIE SLEEVE (200MM TH. WALL) | NOS | 2720 | 29.5 | 80240 | 2720 | 29.5 | 80240 | 0 | 29.5 | 0 | 2720 | 29.27 | 79614.4 | 1275 | 29.19 | 37217.7 | 2720 | 1445 | 80240 | 43022.3
3613 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 100 MM | NOS | 2670 | 35.4 | 94518 | 1500 | 35.4 | 53100 | 0 | 35.4 | 0 | 1500 | 28.07 | 42105 | 700 | 28 | 19599.3 | 2670 | 1970 | 94518 | 74918.7
3614 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 125 MM | NOS | 200 | 35.4 | 7080 | 200 | 35.4 | 7080 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 7080 | 7080
3615 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 150 MM | NOS | 560 | 35.4 | 19824 | 560 | 35.4 | 19824 | 0 | 35.4 | 0 | 560 | 31.66 | 17729.6 | 560 | 31.57 | 17681.05 | 560 | 0 | 19824 | 2142.95
3616 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 160 MM | NOS | 1910 | 35.4 | 67614 | 1500 | 35.4 | 53100 | 0 | 35.4 | 0 | 1500 | 32.26 | 48390 | 1300 | 32.17 | 41819.78 | 1910 | 610 | 67614 | 25794.22
3617 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 200 MM | NOS | 5000 | 35.4 | 177000 | 3000 | 35.4 | 106200 | 0 | 35.4 | 0 | 3000 | 35.24 | 105720 | 1400 | 35.15 | 49206.71 | 5000 | 3600 | 177000 | 127793.29
3618 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 225 MM | NOS | 40 | 47.2 | 1888 | 40 | 47.2 | 1888 | 0 | 47.2 | 0 | 40 | 37.34 | 1493.4 | 0 | 0 | 0 | 40 | 40 | 1888 | 1888
3619 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REUSABLE WALL TIE 250 MM | NOS | 90 | 47.2 | 4248 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 4248 | 4248
3620 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)REVOLVING CHAIR | NOS | 9 | 5900 | 53100 | 9 | 5900 | 53100 | 0 | 5900 | 0 | 9 | 5900 | 53100 | 9 | 5900 | 53100 | 9 | 0 | 53100 | 0
3621 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)RUBBER HAMMER | NOS | 5 | 590 | 2950 | 5 | 590 | 2950 | 0 | 590 | 0 | 5 | 590 | 2950 | 0 | 0 | 0 | 5 | 5 | 2950 | 2950
3622 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)SACRIFICED WALL TIE (500 MM TH. WALL) | NOS | 130 | 74.05 | 9626.5 | 130 | 74.05 | 9626.5 | 0 | 74.05 | 0 | 130 | 59.73 | 7764.9 | 0 | 0 | 0 | 130 | 130 | 9626.5 | 9626.5
3623 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)SACRIFICED WALL TIE (525 MM TH. WALL) | NOS | 130 | 77.88 | 10124.4 | 130 | 77.88 | 10124.4 | 0 | 77.88 | 0 | 130 | 62.12 | 8075.6 | 0 | 0 | 0 | 130 | 130 | 10124.4 | 10124.4
3624 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)SACRIFICED WALL TIE (550 MM TH. WALL) | NOS | 130 | 81.42 | 10584.6 | 130 | 81.42 | 10584.6 | 0 | 81.42 | 0 | 130 | 64.51 | 8386.3 | 40 | 64.34 | 2573.6 | 130 | 90 | 10584.6 | 8011
3625 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)SACRIFICED WALL TIE (575 MM TH. WALL) | NOS | 130 | 84.96 | 11044.8 | 130 | 84.96 | 11044.8 | 0 | 84.96 | 0 | 130 | 68.1 | 8853 | 0 | 0 | 0 | 130 | 130 | 11044.8 | 11044.8
3626 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)T-TIE ROD 16MM DIA X 500MM LONG | NOS | 365 | 105.02 | 38332.3 | 365 | 105.02 | 38332.3 | 0 | 105.02 | 0 | 365 | 90.79 | 33138.35 | 300 | 90.55 | 27164.97 | 365 | 65 | 38332.3 | 11167.33
3627 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)TURN BUCKLE | NOS | 40 | 389.4 | 15576 | 40 | 389.4 | 15576 | 0 | 389.4 | 0 | 40 | 359.9 | 14396 | 40 | 357.19 | 14287.53 | 40 | 0 | 15576 | 1288.47
3628 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)WALL TIE PULLAR | NOS | 9 | 743.4 | 6690.6 | 9 | 743.4 | 6690.6 | 0 | 743.4 | 0 | 9 | 848.21 | 7633.89 | 0 | 0 | 0 | 9 | 9 | 6690.6 | 6690.6
3629 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)WALLER 1500 | NOS | 18 | 1534 | 27612 | 18 | 1534 | 27612 | 0 | 1534 | 0 | 18 | 1541.12 | 27740.16 | 1 | 1536.97 | 1536.97 | 18 | 17 | 27612 | 26075.03
3630 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)WALLER HOLDER | NOS | 70 | 141.6 | 9912 | 70 | 141.6 | 9912 | 0 | 141.6 | 0 | 70 | 151.72 | 10620.4 | 70 | 151.31 | 10591.98 | 70 | 0 | 9912 | -679.98
3631 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)WEDGE | NOS | 61300 | 0 | 0 | 61300 | 0 | 0 | 0 | 0 | 0 | 61300 | 4.04 | 247430.5 | 53260 | 3.96 | 210677.92 | 61300 | 8040 | 0 | -210677.92
3632 | FIXED ASSETS - Site Assets | 0 | Started | Material | (M)Wireless Hand-held Microphone | NOS | 1 | 3835 | 3835 | 1 | 3835 | 3835 | 0 | 3835 | 0 | 1 | 5605 | 5605 | 1 | 5334.87 | 5334.87 | 1 | 0 | 3835 | -1499.87
3633 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)16 MM X 50MM PIN | NOS | 9000 | 11.8 | 106200 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 9000 | 10.07 | 90627.3 | 9000 | 0 | 106200 | 15572.7
3634 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)16MM x 50MM PIN | NOS | 19500 | 10.04 | 195780 | 0 | 0 | 0 | 0 | 10.04 | 0 | 0 | 0 | 0 | 19500 | 10.13 | 197439.45 | 19500 | 0 | 195780 | -1659.45
3635 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)4 X 50 MM BOLT, NUT & WASHER | NOS | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 4.05 | 850.02 | 210 | 0 | 0 | -850.02
3636 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)4x50 MM BOLT, NUT & WASHER | NOS | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 3.55 | 1420.08 | 400 | 0 | 0 | -1420.08
3637 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)6 X 50 MM BOLT, NUT & WASHER | NOS | 7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 4.38 | 33789.14 | 7716 | 0 | 0 | -33789.14
3638 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)6 X 75 MM BOLT, NUT& WASHER | SET | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 870 | 10.15 | 8827.28 | 870 | 0 | 0 | -8827.28
3639 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)6 X 75MM BOLT, NUT & WASHER . | NOS | 1350 | 11.8 | 15930 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 1350 | 10.39 | 14028.12 | 1350 | 0 | 15930 | 1901.88
3640 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)6x50 MM BOLT, NUT & WASHER | NOS | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 3.12 | 1871.52 | 600 | 0 | 0 | -1871.52
3641 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ADJUSTABLE TELESCOPIC SPAN (2360MM.X 2360MM.) | NOS | 2425 | 82.6 | 200305 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 2425 | 86.52 | 209819 | 2425 | 0 | 200305 | -9514
3642 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ADJUSTABLE TELESCOPIC SPAN (3000MM X 3000MM) | NOS | 459 | 82.6 | 37913.4 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 459 | 85.81 | 39386.61 | 459 | 0 | 37913.4 | -1473.21
3643 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ADJUSTABLE WINDOW PROP 1800 MM | NOS | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1573.53 | 94411.8 | 60 | 0 | 0 | -94411.8
3644 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)admixture/solvent for Lacquer | NOS | 150 | 129.8 | 19470 | 0 | 0 | 0 | 0 | 129.8 | 0 | 0 | 0 | 0 | 150 | 132.14 | 19820.46 | 150 | 0 | 19470 | -350.46
3645 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)Aluminium Formwork Material (Balance Components) | SQM | 1833.31 | 9676 | 17739107.56 | 1833.309 | 9676 | 17739097.88 | 0 | 9676 | 0 | 1833.309 | 9887.72 | 18127239.4686 | 1747.339 | 9849.95 | 17211205.44 | 1833.31 | 85.971 | 17739107.56 | 527902.12
3646 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ANCHOR NUT 16 MMID X 90MM OD | NOS | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 56.1 | 28051.65 | 500 | 0 | 0 | -28051.65
3647 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ANCHOR NUT 90 MM | NOS | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 56.29 | 33771.84 | 600 | 0 | 0 | -33771.84
3648 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)BASE PLATE (150 MM X150 MM) | NOS | 120 | 106.2 | 12744 | 0 | 0 | 0 | 0 | 106.2 | 0 | 0 | 0 | 0 | 120 | 109.65 | 13157.47 | 120 | 0 | 12744 | -413.47
3649 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)BEAM BAR (LB) | NOS | 100 | 236 | 23600 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 100 | 235.09 | 23509.32 | 100 | 0 | 23600 | 90.68
3650 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)CHAJA BRACKET/ SLAB BRACKET | NOS | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1139.72 | 85479.05 | 75 | 0 | 0 | -85479.05
3651 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)DRIP MOULD (PVC) | NOS | 1 | 147.5 | 147.5 | 0 | 0 | 0 | 0 | 147.5 | 0 | 0 | 0 | 0 | 155 | 156.82 | 24307.41 | 1 | -154 | 147.5 | -24159.91
3652 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ELEVATION GROOVE (25 X 15 X 10 X 1 MTR) | RMT | 1500 | 182.9 | 274350 | 1500 | 182.9 | 274350 | 0 | 182.9 | 0 | 1500 | 184.08 | 276120 | 1050 | 180.8 | 189836.83 | 1500 | 450 | 274350 | 84513.17
3653 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ELEVATION GROVE(25 X 15 X 10) | RMT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705 | 167.12 | 117816.99 | 1 | -704 | 0 | -117816.99
3654 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ERX 61 mm | RMT | 80 | 354 | 28320 | 80 | 354 | 28320 | 0 | 354 | 0 | 80 | 354 | 28320 | 80 | 354 | 28320 | 80 | 0 | 28320 | 0
3655 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)FIXED TYPE ELECTROPLATED COUPLER(40X40) | NOS | 1 | 70.8 | 70.8 | 0 | 0 | 0 | 0 | 70.8 | 0 | 0 | 0 | 0 | 600 | 76.28 | 45765.12 | 1 | -599 | 70.8 | -45694.32
3656 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)HOLE BARI | NOS | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 20 | 150.55 | 3010.98 | 1 | -19 | 141.6 | -2869.38
3657 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)HORIZONTAL LEDGER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 399.86 | 25590.95 | 1 | -63 | 0 | -25590.95
3658 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)KICKER BOLT (16MM DIA x 80MM Long /HALF THREAD ) | NOS | 1 | 18.88 | 18.88 | 0 | 0 | 0 | 0 | 18.88 | 0 | 0 | 0 | 0 | 414 | 14.56 | 6027.47 | 1 | -413 | 18.88 | -6008.59
3659 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)KICKER NUT16 MM DIA (650 NOS EACH FLOOR ) @6 NOS FLOOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 4.23 | 16482.57 | 1 | -3899 | 0 | -16482.57
3660 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)L BRACKET | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 590 | 590 | 1 | 0 | 0 | -590
3661 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)L-PIN 16MM x 225MM LONG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 50.18 | 4516.47 | 1 | -89 | 0 | -4516.47
3662 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)lacquer for Aluform panel | NOS | 1 | 424.8 | 424.8 | 0 | 0 | 0 | 0 | 424.8 | 0 | 0 | 0 | 0 | 150 | 432.45 | 64866.96 | 1 | -149 | 424.8 | -64442.16
3663 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)LINE ADJUSTER JACK | NOS | 1 | 342.2 | 342.2 | 0 | 0 | 0 | 0 | 342.2 | 0 | 0 | 0 | 0 | 1300 | 369.06 | 479772.28 | 1 | -1299 | 342.2 | -479430.08
3664 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)LONG PIN (16MM DIA X 190MM LONG) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 66.22 | 6688.6 | 1 | -100 | 0 | -6688.6
3665 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)MS BOLT 16x30 MM (ROCKER) | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 350 | 8.24 | 2884.7 | 1 | -349 | 11.8 | -2872.9
3666 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)MS materials Supply & Fabrication and painting | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 | 97.94 | 2337827.8 | 1 | -23869 | 0 | -2337827.8
3667 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)MS NUT 16 MM (ROCKER) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 2.77 | 969.96 | 1 | -349 | 0 | -969.96
3668 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)NEW ALUMINIUM FROM WORK COMPONENT | SQM | 194 | 9794 | 1900036 | 0 | 0 | 0 | 0 | 9794 | 0 | 0 | 0 | 0 | 98.545 | 10502 | 1034919.62 | 194 | 95.455 | 1900036 | 865116.38
3669 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)OLD ALUMINIUM FROM WORK COMPONENT | SQM | 1675.133 | 5310 | 8894956.23 | 1328.24 | 5310 | 7052954.4 | 0 | 5310 | 0 | 1328.23 | 5310 | 7052901.3 | 1527.411 | 5310 | 8110552.41 | 1675.133 | 147.722 | 8894956.23 | 784403.82
3670 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)PANEL PULLAR | NOS | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 16 | 550.89 | 8814.2 | 1 | -15 | 590 | -8224.2
3671 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)PVC CONE 20MM DIA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1.88 | 940.95 | 1 | -499 | 0 | -940.95
3672 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)PVC PLASTIC ROLL | NOS | 1 | 448.4 | 448.4 | 0 | 0 | 0 | 0 | 448.4 | 0 | 0 | 0 | 0 | 8.4 | 448.4 | 3766.56 | 1 | -7.4 | 448.4 | -3318.16
3673 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)PVC SHEET | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 217.12 | 2171.2 | 1 | -9 | 0 | -2171.2
3674 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)RED OXIDE PRIMER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 314.13 | 9109.79 | 1 | -28 | 0 | -9109.79
3675 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 100 MM | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 805 | 31.78 | 25579.6 | 1 | -804 | 35.4 | -25544.2
3676 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 125 MM | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 668 | 34.02 | 22724.36 | 1 | -667 | 35.4 | -22688.96
3677 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 150 MM | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 249 | 45.32 | 11284.11 | 1 | -248 | 35.4 | -11248.71
3678 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 160 MM | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 850 | 37.13 | 31556.25 | 1 | -849 | 35.4 | -31520.85
3679 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 185 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 39.52 | 395.2 | 1 | -9 | 0 | -395.2
3680 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 200 MM | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 1000 | 48.29 | 48288.2 | 1 | -999 | 35.4 | -48252.8
3681 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 225 MM | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 124 | 51.44 | 6378.26 | 1 | -123 | 47.2 | -6331.06
3682 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 250 MM | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 200 | 53.95 | 10789.36 | 1 | -199 | 47.2 | -10742.16
3683 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 250 MM. | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 211 | 54.13 | 11421.3 | 1 | -210 | 47.2 | -11374.1
3684 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 310 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 62.73 | 5645.59 | 1 | -89 | 0 | -5645.59
3685 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 350 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 53.47 | 5347.2 | 1 | -99 | 0 | -5347.2
3686 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 400 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 59.28 | 1778.41 | 1 | -29 | 0 | -1778.41
3687 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE 75 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 32.62 | 130.48 | 1 | -3 | 0 | -130.48
3688 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 185 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26.95 | 269.46 | 1 | -9 | 0 | -269.46
3689 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 200 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630 | 26.22 | 42738.27 | 1 | -1629 | 0 | -42738.27
3690 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 225 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 31.98 | 3966.05 | 1 | -123 | 0 | -3966.05
3691 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 250 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426 | 33.58 | 14304.19 | 1 | -425 | 0 | -14304.19
3692 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 310 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 42.65 | 3838.47 | 1 | -89 | 0 | -3838.47
3693 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 350 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 46.52 | 4745.51 | 1 | -101 | 0 | -4745.51
3694 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)REUSABLE WALL TIE SLEEVE 400 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 51.71 | 1551.22 | 1 | -29 | 0 | -1551.22
3695 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)ROCKER 50MM | RMT | 150.4 | 619.5 | 93172.8 | 150.4 | 619.5 | 93172.8 | 0 | 619.5 | 0 | 150.4 | 635.32 | 95551.68 | 150.4 | 635.32 | 95551.68 | 150.4 | 0 | 93172.8 | -2378.88
3696 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)SACRIFIES WALL TIE 660 MM LONG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 85.56 | 9582.59 | 1 | -111 | 0 | -9582.59
3697 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)SACRIFIES WALL TIE 700 MM LONG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 91.89 | 22054.61 | 1 | -239 | 0 | -22054.61
3698 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)SACRIFiIES WALL TIE 700 MM LONG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 91.58 | 3663.36 | 1 | -39 | 0 | -3663.36
3699 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)SCAFFOLDING PIPE (40MM OD,2.25MM THK,6 M LONG | NOS | 1 | 70.8 | 70.8 | 0 | 0 | 0 | 0 | 70.8 | 0 | 0 | 0 | 0 | 2160 | 73.89 | 159605.86 | 1 | -2159 | 70.8 | -159535.06
3700 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)SWIVEL TYPE ELECTROPLATED COUPLER(40X40) | NOS | 1 | 70.8 | 70.8 | 0 | 0 | 0 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70.8 | 70.8
3701 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)TIE ROD 16MM DIA x 0.60M LONG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 90.33 | 36131.8 | 1 | -399 | 0 | -36131.8
3702 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)TIE ROD 16MM DIA x 1.150M LONG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 173.13 | 2596.97 | 1 | -14 | 0 | -2596.97
3703 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)TURN BUCKLE | NOS | 1 | 389.4 | 389.4 | 0 | 0 | 0 | 0 | 389.4 | 0 | 0 | 0 | 0 | 14 | 445.6 | 6238.37 | 1 | -13 | 389.4 | -5848.97
3704 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)TURN BUCKLE MS WIRE ROPE | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 326.77 | 65354.3 | 1 | -199 | 0 | -65354.3
3705 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WALKWAY BRACKET | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228 | 1518.35 | 346183.71 | 1 | -227 | 0 | -346183.71
3706 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WALL TIE PULLAR | NOS | 1 | 743.4 | 743.4 | 0 | 0 | 0 | 0 | 743.4 | 0 | 0 | 0 | 0 | 16 | 690.02 | 11040.27 | 1 | -15 | 743.4 | -10296.87
3707 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WALLER 1500 | NOS | 1 | 1534 | 1534 | 0 | 0 | 0 | 0 | 1534 | 0 | 0 | 0 | 0 | 28 | 1551.79 | 43450.24 | 1 | -27 | 1534 | -41916.24
3708 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WALLER HOLDER | NOS | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 760 | 144.51 | 109825.78 | 1 | -759 | 141.6 | -109684.18
3709 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WALLTIE SLEEVE EJECTOR-300 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 536.43 | 7509.99 | 1 | -13 | 0 | -7509.99
3710 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WALLTIE SLEEVE EJECTOR-450 MM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 576.66 | 1153.32 | 1 | -1 | 0 | -1153.32
3711 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WEDGE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 4.86 | 93377.28 | 1 | -19199 | 0 | -93377.28
3712 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WEDGE 3MM | NOS | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 4.53 | 54324 | 20000 | 4.45 | 89008 | 12000 | -8000 | 0 | -89008
3713 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WING NUT (16 MM) | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 35.4 | 35.4
3714 | FIXED ASSETS - Aluminium From Work with Component | 0 | Started | Material | (M)WIRE MOUSE | NOS | 1 | 342.2 | 342.2 | 0 | 0 | 0 | 0 | 342.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 342.2 | 342.2
3715 | FIXED ASSETS - Porta Cabin Shifting Work | 0 | Started | Labour | (L)TAILER (8"X 20") | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFRA
3716 | FIXED ASSETS - Porta Cabin Shifting Work | 0 | Started | Labour | (L)TAILER (8"X 40") | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFRA
3717 | FIXED ASSETS - Porta Cabin Shifting Work | 0 | Started | Material | (M)20' 0" x 10' 0" porta cabin bare container | NOS | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 212990 | 1064950 | 5 | 0 | 0 | -1064950 | INFRA
3718 | FIXED ASSETS - Porta Cabin Shifting Work | 0 | Started | Material | (M)20' 0" x 10' 0" porta cabin container with insulation | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 243257 | 486514 | 2 | 0 | 0 | -486514 | INFRA
3719 | FIXED ASSETS - Porta Cabin Shifting Work | 0 | Started | Material | (M)8 MM MDF BOARD | NOS | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 56.13 | 23350.45 | 416 | 0 | 0 | -23350.45 | INFRA
3720 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Labour | (L)Repairing of Dual Feeding System & Fixing of Spare Parts | JOB | 1 | 70800 | 70800 | 0 | 0 | 0 | 0 | 70800 | 0 | 1 | 70800 | 70800 | 1 | 70800 | 70800 | 1 | 0 | 70800 | 0
3721 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)18mm Concrete Breaker w/Chisel Hammer Bit set,Wt.5Kg(220V) | NOS | 3 | 94400 | 283200 | 1 | 94400 | 94400 | 0 | 94400 | 0 | 1 | 22066 | 22066 | 1 | 22028.65 | 22028.65 | 3 | 2 | 283200 | 261171.35
3722 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)25 MM DRILL BIT | NOS | 24 | 377.6 | 9062.4 | 24 | 377.6 | 9062.4 | 2 | 377.6 | 755.2 | 24 | 377.6 | 9062.4 | 14 | 377.78 | 5288.96 | 22 | 10 | 8307.2 | 3773.44
3723 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)30 MTR MEASUREMENT TAPE | NOS | 2 | 531 | 1062 | 2 | 531 | 1062 | 0 | 531 | 0 | 2 | 531 | 1062 | 2 | 531 | 1062 | 2 | 0 | 1062 | 0
3724 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)5 MTR MEASUREMENT TAPE | NOS | 6 | 141.6 | 849.6 | 6 | 141.6 | 849.6 | 1 | 141.6 | 141.6 | 6 | 94.4 | 566.4 | 6 | 94.4 | 566.4 | 5 | 0 | 708 | 283.2
3725 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)6 MM DRILL BIT | NOS | 35 | 82.6 | 2891 | 35 | 82.6 | 2891 | 4 | 82.6 | 330.4 | 35 | 94.99 | 3324.6605 | 35 | 94.99 | 3324.66 | 31 | 0 | 2560.6 | -433.66
3726 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)Aluminium Telescopic Tripod | NOS | 1 | 7965 | 7965 | 1 | 7965 | 7965 | 0 | 7965 | 0 | 1 | 7965 | 7965 | 1 | 7965 | 7965 | 1 | 0 | 7965 | 0
3727 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)ASSEMBLED DESKTOP | NOS | 1 | 83933.4 | 83933.4 | 1 | 83933.4 | 83933.4 | 0 | 83933.4 | 0 | 1 | 32155 | 32155 | 0 | 0 | 0 | 1 | 1 | 83933.4 | 83933.4
3728 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)AutoCAD including Specialized Toolset AD Commercial | NOS | 1 | 101480 | 101480 | 1 | 101480 | 101480 | 0 | 101480 | 0 | 1 | 98530 | 98530 | 1 | 98530 | 98530 | 1 | 0 | 101480 | 2950
3729 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)BAR CUTTING MACHINE | NOS | 1 | 200600 | 200600 | 1 | 200600 | 200600 | 0 | 200600 | 0 | 1 | 204730 | 204730 | 1 | 204090.44 | 204090.44 | 1 | 0 | 200600 | -3490.44
3730 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)Mini Prism | SET | 1 | 18909.5 | 18909.5 | 1 | 18909.5 | 18909.5 | 0 | 18909.5 | 0 | 1 | 18909.5 | 18909.5 | 1 | 18909.5 | 18909.5 | 1 | 0 | 18909.5 | 0
3731 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)MULTILINE LASER PM 40 | NOS | 2 | 95100.29 | 190200.58 | 2 | 95100.29 | 190200.58 | 0 | 95100.29 | 0 | 2 | 95100.3 | 190200.6 | 2 | 94675.58 | 189351.16 | 2 | 0 | 190200.58 | 849.42
3732 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)Range Pole Tripod | NOS | 1 | 6472.3 | 6472.3 | 1 | 6472.3 | 6472.3 | 0 | 6472.3 | 0 | 1 | 6472.3 | 6472.3 | 1 | 6472.3 | 6472.3 | 1 | 0 | 6472.3 | 0
3733 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)Single Range Pole Assembly | SET | 1 | 23034.78 | 23034.78 | 1 | 23034.78 | 23034.78 | 0 | 23034.78 | 0 | 1 | 23034.78 | 23034.78 | 1 | 23034.78 | 23034.78 | 1 | 0 | 23034.78 | 0
3734 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)SOKKIA Reflectorless Elec. Total Station (Model iM-55) | NOS | 1 | 342200 | 342200 | 1 | 342200 | 342200 | 0 | 342200 | 0 | 1 | 312700 | 312700 | 1 | 312700 | 312700 | 1 | 0 | 342200 | 29500
3735 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)Tubular Compass | NOS | 1 | 5310 | 5310 | 1 | 5310 | 5310 | 0 | 5310 | 0 | 1 | 5310 | 5310 | 1 | 5310 | 5310 | 1 | 0 | 5310 | 0
3736 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)Windows-11 Home. | NOS | 1 | 9322 | 9322 | 1 | 9322 | 9322 | 0 | 9322 | 0 | 1 | 9322 | 9322 | 1 | 11682 | 11682 | 1 | 0 | 9322 | -2360
3737 | FIXED ASSETS - Co.'S Tools And Equipment | 10 | Started | Material | (M)WOOD CUTTING BLADE 4" | NOS | 5 | 212.4 | 1062 | 5 | 212.4 | 1062 | 1 | 212.4 | 212.4 | 5 | 212.4 | 1062 | 5 | 212.4 | 1062 | 4 | 0 | 849.6 | 0
3738 | FIXED ASSETS - Mivan Supervision During Mivan Shutering | 0 | Started | Labour | (L)Prefabrication of existing components formwork modulation | NOS | 30094 | 70 | 2106580 | 0 | 0 | 0 | 0 | 70 | 0 | 30094 | 82.6 | 2485764.4 | 21282.771 | 82.6 | 1757956.89 | 30094 | 8811.229 | 2106580 | 348623.11
3739 | FIXED ASSETS - Mivan Supervision During Mivan Shutering | 0 | Started | Labour | (L)Redesigning & Supervision at site of Aluminium formwork | SQM | 5308 | 180 | 955440 | 0 | 0 | 0 | 0 | 180 | 0 | 5308 | 212.4 | 1127419.2 | 4697 | 212.4 | 997642.8 | 5308 | 611 | 955440 | -42202.8
3740 | FIXED ASSETS - Mivan Supervision During Mivan Shutering | 0 | Started | Material | (M)GREASE (WHITE) | NOS | 10 | 188.8 | 1888 | 10 | 188.8 | 1888 | 0 | 188.8 | 0 | 10 | 193 | 1929.993 | 10 | 193 | 1929.99 | 10 | 0 | 1888 | -41.99
3741 | FIXED ASSETS - Mivan Supervision During Mivan Shutering | 0 | Started | Material | (M)WIRE BRUSH | NOS | 12 | 59 | 708 | 12 | 59 | 708 | 0 | 59 | 0 | 12 | 59 | 708 | 0 | 0 | 0 | 12 | 12 | 708 | 708
3742 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)10 MM STONE CHIPS. | MT | 0.74 | 1770 | 1309.8 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0.298 | 1451.58 | 432.57 | 0.74 | 0.442 | 1309.8 | 877.23
3743 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)20 MM STONE CHIPS. | MT | 0.74 | 1750 | 1295 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0.298 | 2074.87 | 618.31 | 0.74 | 0.442 | 1295 | 676.69
3744 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)CAST IRON CEMENT CUBE MOULD WITH BAES PLATE (SIZE - 50 MM) | NOS | 12 | 649 | 7788 | 12 | 649 | 7788 | 1 | 649 | 649 | 12 | 1534 | 18408 | 12 | 1534 | 18408 | 11 | 0 | 7139 | -10620
3745 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)Graduated Measuring Cylinder 1000ml (plastic) | NOS | 1 | 342.2 | 342.2 | 1 | 342.2 | 342.2 | 0 | 342.2 | 0 | 1 | 236 | 236 | 1 | 236 | 236 | 1 | 0 | 342.2 | 106.2
3746 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)Graduated Measuring Cylinder 100ml (plastic) | NOS | 1 | 212.4 | 212.4 | 1 | 212.4 | 212.4 | 0 | 212.4 | 0 | 1 | 53.1 | 53.1 | 1 | 53.1 | 53.1 | 1 | 0 | 212.4 | 159.3
3747 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)Graduated Measuring Cylinder 250ml (plastic) | NOS | 1 | 271.4 | 271.4 | 1 | 271.4 | 271.4 | 0 | 271.4 | 0 | 1 | 94.4 | 94.4 | 1 | 94.4 | 94.4 | 1 | 0 | 271.4 | 177
3748 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)Graduated Measuring Cylinder 500ml (plastic) | NOS | 1 | 295 | 295 | 1 | 295 | 295 | 0 | 295 | 0 | 1 | 177 | 177 | 1 | 177 | 177 | 1 | 0 | 295 | 118
3749 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)HIND PLAST SUPER 160 | KG | 3.25 | 36.58 | 118.89 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 2.65 | 52.71 | 139.68 | 3.25 | 0.6 | 118.885 | -20.795
3750 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)LID AND PAN FOR BRASS FRAME 8" | NOS | 1 | 1534 | 1534 | 0 | 0 | 0 | 0 | 1534 | 0 | 0 | 0 | 0 | 1 | 1303.9 | 1303.9 | 1 | 0 | 1534 | 230.1
3751 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)LID AND PAN FOR G.I FRAME 18" | NOS | 1 | 1003 | 1003 | 0 | 0 | 0 | 0 | 1003 | 0 | 0 | 0 | 0 | 1 | 923.35 | 923.35 | 1 | 0 | 1003 | 79.65
3752 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)M.C. SAND | MT | 1.01 | 1711.5 | 1728.62 | 0 | 0 | 0 | 0 | 1711.5 | 0 | 0 | 0 | 0 | 0.372 | 1690 | 628.68 | 1.01 | 0.638 | 1728.615 | 1099.935
3753 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)POLYTHENE SHEET | KG | 10.3 | 110 | 1133 | 0 | 0 | 0 | 1 | 110 | 110 | 0 | 0 | 0 | 10.3 | 141.6 | 1458.48 | 9.3 | 0 | 1023 | -325.48
3754 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)PPC CEMENT | BAG | 10 | 283.59 | 2835.9 | 0 | 0 | 0 | 1 | 283.59 | 283.59 | 0 | 0 | 0 | 4 | 313.43 | 1253.7 | 9 | 6 | 2552.31 | 1582.2
3755 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)SLUMP TEST WITH TAMPING ROD | NOS | 1 | 3068 | 3068 | 0 | 0 | 0 | 0 | 3068 | 0 | 0 | 0 | 0 | 1 | 3102.98 | 3102.98 | 1 | 0 | 3068 | -34.98
3756 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 1.18 MM | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 0 | 0 | 0 | 1 | 1217.32 | 1217.32 | 1 | 0 | 1416 | 198.68
3757 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 150 MICRON | NOS | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 1 | 1014.43 | 1014.43 | 1 | 0 | 1180 | 165.57
3758 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 2.36 MM | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 0 | 0 | 0 | 1 | 1217.32 | 1217.32 | 1 | 0 | 1416 | 198.68
3759 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 300 MICRON | NOS | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 1 | 1014.43 | 1014.43 | 1 | 0 | 1180 | 165.57
3760 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 4.75 MM | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 0 | 0 | 0 | 1 | 1217.32 | 1217.32 | 1 | 0 | 1416 | 198.68
3761 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 45 MICRON | NOS | 1 | 1534 | 1534 | 1 | 1534 | 1534 | 0 | 1534 | 0 | 1 | 1404.2 | 1404.2 | 2 | 1412.21 | 2824.41 | 1 | -1 | 1534 | -1290.41
3762 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES BRASS FRAME 8" SIZE- 600 MICRON | NOS | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 1 | 1014.43 | 1014.43 | 1 | 0 | 1180 | 165.57
3763 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 12.5 MM | NOS | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
3764 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 2.36 MM | NOS | 1 | 944 | 944 | 0 | 0 | 0 | 0 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 944 | 944
3765 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 20 MM | NOS | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
3766 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 4.75 MM | NOS | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
3767 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE 40MM | NOS | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
3768 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE- 16 MM | NOS | 1 | 1062 | 1062 | 0 | 0 | 0 | 0 | 1062 | 0 | 0 | 0 | 0 | 1 | 912.99 | 912.99 | 1 | 0 | 1062 | 149.01
3769 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE-10 MM | NOS | 1 | 979.4 | 979.4 | 0 | 0 | 0 | 0 | 979.4 | 0 | 0 | 0 | 0 | 1 | 899 | 899 | 1 | 0 | 979.4 | 80.4
3770 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE-12.5 MM | NOS | 1 | 1062 | 1062 | 0 | 0 | 0 | 0 | 1062 | 0 | 0 | 0 | 0 | 1 | 912.99 | 912.99 | 1 | 0 | 1062 | 149.01
3771 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TEST SIEVES G.I. FRAME 18" SIZE-20 MM | NOS | 1 | 1062 | 1062 | 0 | 0 | 0 | 0 | 1062 | 0 | 0 | 0 | 0 | 1 | 912.99 | 912.99 | 1 | 0 | 1062 | 149.01
3772 | FIXED ASSETS - Qc And Lab Test | 10 | Started | Material | (M)TIMC TEST SIEVES BRASS FRAME – 8” (20 CM) DIA. 2” | NOS | 1 | 1652 | 1652 | 0 | 0 | 0 | 0 | 1652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1652 | 1652
3773 | ADMIN EXPENSES - Naukri.com | 0 | Started | Labour | (L)ALL INDIA USAGE BASED DATABASE | Yearly | 2 | 76700 | 153400 | 0 | 0 | 0 | 0 | 76700 | 0 | 2 | 82600 | 165200 | 2 | 82600 | 165200 | 2 | 0 | 153400 | -11800
3774 | ADMIN EXPENSES - Naukri.com | 0 | Started | Labour | (L)Annual Maintenance for naukri.com | Yearly | 1 | 100300 | 100300 | 0 | 0 | 0 | 0 | 100300 | 0 | 1 | 100300 | 100300 | 1 | 100300 | 100300 | 1 | 0 | 100300 | 0
3775 | ADMIN EXPENSES - Naukri.com | 0 | Started | Labour | (L)Usage Based Resdex- PAN INDIA with 1 Login | Monthly | 3 | 7906 | 23718 | 0 | 0 | 0 | 0 | 7906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 23718 | 23718
3776 | ADMIN EXPENSES - Water Purifier Maintenance | 10 | Started | Labour | (L)AMC OF WATER PURIFIER | NOS | 3 | 2700.01 | 8100.03 | 0 | 0 | 0 | 0 | 2700.01 | 0 | 3 | 4533 | 13598.99 | 3 | 4532.99 | 13598.97 | 3 | 0 | 8100.03 | -5498.94
3777 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)Entire Carpet Area Deep Clean With Dry Clean and Wet Clean | NOS | 5000 | 9.44 | 47200 | 0 | 0 | 0 | 500 | 9.44 | 4720 | 5000 | 5.6 | 27980.76 | 5000 | 5.6 | 27980.76 | 4500 | 0 | 42480 | 19219.24
3778 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)L/C for Plastic Wrapping & Furniture Shifting | LS | 1 | 14986 | 14986 | 0 | 0 | 0 | 0 | 14986 | 0 | 1 | 14986 | 14986 | 1 | 14986 | 14986 | 1 | 0 | 14986 | 0
3779 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)Office Carpet Area Deep Clean (Dry & Wet Cleaning) | NOS | 1 | 18691.2 | 18691.2 | 0 | 0 | 0 | 0 | 18691.2 | 0 | 1 | 18691.2 | 18691.2 | 1 | 18691.2 | 18691.2 | 1 | 0 | 18691.2 | 0
3780 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)PEST CONTROL | LS | 6 | 1.18 | 7.08 | 0 | 0 | 0 | 1 | 1.18 | 1.18 | 5 | 1180 | 5900 | 5 | 1180 | 5900 | 5 | 1 | 5.9 | -5892.92
3781 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)PROVIDING AND LAYING PAINT | SQFT | 3994.681 | 22.42 | 89560.75 | 0 | 0 | 0 | 399 | 22.42 | 8945.58 | 3994.681 | 22.42 | 89560.739 | 3994.681 | 22.42 | 89560.74 | 3595.681 | 0 | 80615.168 | 0.008
3782 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)PROVIDING AND MAKING DUCO PAINT ON MS PIPES | RFT | 1521.822 | 112.1 | 170596.25 | 0 | 0 | 0 | 152 | 112.1 | 17039.2 | 1521.822 | 112.1 | 170596.25 | 1521.822 | 112.1 | 170596.25 | 1369.822 | 0 | 153557.046 | -0.0038
3783 | ADMIN EXPENSES - Office Deep Clean | 10 | Started | Labour | (L)PROVIDING AND MAKING DUCO PAINT ON MS PLATES | SQFT | 163.195 | 135.7 | 22145.56 | 0 | 0 | 0 | 16 | 135.7 | 2171.2 | 163.195 | 135.7 | 22145.565 | 163.195 | 135.7 | 22145.57 | 147.195 | 0 | 19974.362 | -0.0085
3784 | ADMIN EXPENSES - Training Course Fees | 10 | Started | Labour | (L)Professional Charges | LS | 1 | 107510.98 | 107510.98 | 0 | 0 | 0 | 0 | 107510.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 107510.98 | 107510.98
3785 | ADMIN EXPENSES - Training Course Fees | 10 | Started | Labour | (L)Voice Modulation Training | Session | 6 | 6000 | 36000 | 0 | 0 | 0 | 1 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 30000 | 36000
3786 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Call Centre Integration Smart Ping | NOS | 1 | 132750 | 132750 | 0 | 0 | 0 | 0 | 132750 | 0 | 1 | 132750 | 132750 | 1 | 132750 | 132750 | 1 | 0 | 132750 | 0
3787 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Commercial for Call Centre Solution -Supervisor | NOS | 1 | 1711 | 1711 | 0 | 0 | 0 | 0 | 1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1711 | 1711
3788 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Commercial for Call Centre Solution Monthly Rental | NOS | 120 | 1711 | 205320 | 0 | 0 | 0 | 12 | 1711 | 20532 | 120 | 1711 | 205320 | 20.0001 | 1711 | 34220.17 | 108 | 99.9999 | 184788 | 171099.83
3789 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Employee Background Verification Charges | LS | 1 | 1593 | 1593 | 0 | 0 | 0 | 0 | 1593 | 0 | 1 | 1593 | 1593 | 0 | 0 | 0 | 1 | 1 | 1593 | 1593
3790 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Glass Door Repairing | LS | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 9440 | 28320 | 3 | 9440 | 28320 | 3 | 0 | 3 | -28317
3791 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)HO MAINTENANCE CHARGES | LS | 1000000 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 853870 | 1.18 | 1007566.6 | 853870 | 1.18 | 1007566.6 | 900000 | 146130 | 0 | -1007566.6
3792 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Maintenance/Service Charges | Monthly | 24 | 94400 | 2265600 | 0 | 0 | 0 | 2 | 94400 | 188800 | 5.2405 | 94400 | 494703.2 | 5.2405 | 94399.9 | 494702.68 | 22 | 18.7595 | 2076800 | 1770897.32
3793 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Office Admin Expense | LS | 3200000 | 1.18 | 3776000 | 0 | 0 | 0 | 320000 | 1.18 | 377600 | 3198357.6 | 1.18 | 3774061.98 | 3198357.6 | 1.12 | 3583941.28 | 2880000 | 1642.4 | 3398400 | 192058.72
3794 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)One time setup cost CCS Commercial | NOS | 10 | 1180 | 11800 | 0 | 0 | 0 | 1 | 1180 | 1180 | 10 | 1180 | 11800 | 0 | 0 | 0 | 9 | 10 | 10620 | 11800
3795 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Professional Charges | LS | 1 | 107510.98 | 107510.98 | 0 | 0 | 0 | 0 | 107510.98 | 0 | 1 | 236000 | 236000 | 1 | 236000 | 236000 | 1 | 0 | 107510.98 | -128489.02
3796 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Recruitment charges for HR Intern | NOS | 1 | 9440 | 9440 | 0 | 0 | 0 | 0 | 9440 | 0 | 1 | 9440 | 9440 | 1 | 9440 | 9440 | 1 | 0 | 9440 | 0
3797 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Rent Office IT Lagoon | Monthly | 24 | 55102.5 | 1322460 | 0 | 0 | 0 | 2 | 55102.5 | 110205 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24 | 1212255 | 1322460
3798 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)RENT OFFICE IT LAGOON (2024-25) | NOS | 10 | 63369 | 633690 | 0 | 0 | 0 | 1 | 63369 | 63369 | 10 | 63369 | 633690 | 3 | 63369 | 190107 | 9 | 7 | 570321 | 443583
3799 | ADMIN EXPENSES - Admin Expense | 10 | Started | Labour | (L)Training Module for Sales Executives | NOS | 2 | 123900 | 247800 | 0 | 0 | 0 | 0 | 123900 | 0 | 1.9997 | 203538.05 | 407015.04 | 1.9997 | 203538.05 | 407015.04 | 2 | 0.0003 | 247800 | -159215.04
3800 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)30MM SCREEN ANODISED | NOS | 2 | 5557.8 | 11115.6 | 2 | 5557.8 | 11115.6 | 0 | 5557.8 | 0 | 2 | 5735.08 | 11470.16 | 4 | 5555.87 | 22223.46 | 2 | -2 | 11115.6 | -11107.86
3801 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)A3 PAPER | PKT | 1 | 683.2 | 683.2 | 0 | 0 | 0 | 0 | 683.2 | 0 | 0 | 0 | 0 | 1 | 632.8 | 632.8 | 1 | 0 | 683.2 | 50.4
3802 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)A4 - 70gsm | NOS | 20 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 20 | 291.2 | 5824 | 18 | 0 | 0 | -5824
3803 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)A4 size Paper | PKT | 140 | 291.2 | 40768 | 0 | 0 | 0 | 14 | 291.2 | 4076.8 | 0 | 0 | 0 | 140 | 297.2 | 41608 | 126 | 0 | 36691.2 | -840
3804 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)A5 NOTE BOOK | NOS | 10 | 247.8 | 2478 | 0 | 0 | 0 | 1 | 247.8 | 247.8 | 0 | 0 | 0 | 10 | 305.88 | 3058.84 | 9 | 0 | 2230.2 | -580.84
3805 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)APPLICATION FORM | NOS | 1500 | 23.6 | 35400 | 1500 | 23.6 | 35400 | 150 | 23.6 | 3540 | 1500 | 23.6 | 35400 | 1500 | 23.6 | 35400 | 1350 | 0 | 31860 | 0
3806 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)AQSA AUTOMATIC HAND DRYER-7835 | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3926.28 | 3926.28 | 1 | 0 | 0 | -3926.28
3807 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Arch file (Big) | PCS | 24 | 106.2 | 2548.8 | 0 | 0 | 0 | 2 | 106.2 | 212.4 | 0 | 0 | 0 | 24 | 100.3 | 2407.2 | 22 | 0 | 2336.4 | 141.6
3808 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)AutoCAD including Specialized Toolset AD Commercial | NOS | 10 | 101480 | 1014800 | 4 | 101480 | 405920 | 1 | 101480 | 101480 | 3 | 101480 | 304440 | 1 | 101480 | 101480 | 9 | 9 | 913320 | 913320
3809 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BALL PEN (BLACK) | PKT | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11.8 | 11.8
3810 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BALL PEN(BLUE) | PKT | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11.8 | 11.8
3811 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BIG PUNCHING MACHINE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1239 | 1239 | 1 | 0 | 0 | -1239
3812 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BINDER CLIP 25 MM | BOX | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 37.04 | 37.04 | 1 | 0 | 0 | -37.04
3813 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BINDER CLIP 32 MM . | BOX | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 51.59 | 51.59 | 1 | 0 | 0 | -51.59
3814 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Biometrc Time & Attendance Device with Battery | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7670 | 7670 | 1 | 0 | 0 | -7670
3815 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Biometric | NOS | 2 | 1.18 | 2.36 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 0 | 0 | 1 | 11521.64 | 11521.64 | 2 | 1 | 2.36 | -11519.28
3816 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BLACK BOARD MARKER PEN | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 23.17 | 278.08 | 11 | 0 | 0 | -278.08
3817 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BLACK MARKER PEN | NOS | 20 | 23.6 | 472 | 20 | 23.6 | 472 | 2 | 23.6 | 47.2 | 20 | 23.6 | 472 | 20 | 23.6 | 472 | 18 | 0 | 424.8 | 0
3818 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BLACK PEN | NOS | 40 | 1.18 | 47.2 | 20 | 1.18 | 23.6 | 4 | 1.18 | 4.72 | 20 | 11.8 | 236 | 40 | 5.31 | 212.4 | 36 | 0 | 42.48 | -165.2
3819 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BLAK.OUT KING | MTR | 29.5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 29.5 | 212.1 | 6256.96 | 26.5 | 0 | 0 | -6256.96
3820 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BLUE BOARD MARKER PEN | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 18.3 | 219.54 | 11 | 0 | 0 | -219.54
3821 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)BLUE PEN | NOS | 80 | 1.18 | 94.4 | 20 | 1.18 | 23.6 | 8 | 1.18 | 9.44 | 20 | 11.8 | 236 | 80 | 5.31 | 424.8 | 72 | 0 | 84.96 | -330.4
3822 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)CALANDER | NOS | 1000 | 177 | 177000 | 1000 | 177 | 177000 | 100 | 177 | 17700 | 1000 | 177 | 177000 | 1000 | 177 | 177000 | 900 | 0 | 159300 | 0
3823 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)CAT 6 CABLE | MTR | 14 | 35.4 | 495.6 | 14 | 35.4 | 495.6 | 1 | 35.4 | 35.4 | 14 | 29.5 | 413 | 14 | 29.5 | 413 | 13 | 0 | 460.2 | 82.6
3824 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)CHANNEL FILE | PICS | 30 | 11.8 | 354 | 0 | 0 | 0 | 3 | 11.8 | 35.4 | 0 | 0 | 0 | 30 | 15.87 | 476.2 | 27 | 0 | 318.6 | -122.2
3825 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)CHINA CLIP 6MM | PKT | 2 | 271.4 | 542.8 | 0 | 0 | 0 | 0 | 271.4 | 0 | 0 | 0 | 0 | 2 | 265.5 | 531 | 2 | 0 | 542.8 | 11.8
3826 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)CHINA CLIP 8MM | PKT | 2 | 271.4 | 542.8 | 0 | 0 | 0 | 0 | 271.4 | 0 | 0 | 0 | 0 | 2 | 265.5 | 531 | 2 | 0 | 542.8 | 11.8
3827 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)COBRA BOARD FILE | NOS | 480 | 35.4 | 16992 | 0 | 0 | 0 | 48 | 35.4 | 1699.2 | 0 | 0 | 0 | 480 | 35.06 | 16826.54 | 432 | 0 | 15292.8 | 165.46
3828 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)COMPUTER PAPER | PKT | 2 | 1770 | 3540 | 2 | 1770 | 3540 | 0 | 1770 | 0 | 2 | 1770 | 3540 | 0 | 0 | 0 | 2 | 2 | 3540 | 3540
3829 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)COVER FILE | PICS | 24 | 47.2 | 1132.8 | 24 | 47.2 | 1132.8 | 2 | 47.2 | 94.4 | 24 | 41.3 | 991.2 | 24 | 41.3 | 991.2 | 22 | 0 | 1038.4 | 141.6
3830 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)DIARY | NOS | 50 | 354 | 17700 | 50 | 354 | 17700 | 5 | 354 | 1770 | 50 | 354 | 17700 | 50 | 354 | 17700 | 45 | 0 | 15930 | 0
3831 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)DOOR LOCK | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3832 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)DUSTER | PICS | 6 | 21 | 126 | 6 | 21 | 126 | 1 | 21 | 21 | 6 | 15.75 | 94.5 | 6 | 15.75 | 94.5 | 5 | 0 | 105 | 31.5
3833 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)ELECTRO MAGNETIC LOCK | NOS | 1 | 2236.1 | 2236.1 | 1 | 2236.1 | 2236.1 | 0 | 2236.1 | 0 | 1 | 2236.1 | 2236.1 | 1 | 2236.1 | 2236.1 | 1 | 0 | 2236.1 | 0
3834 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)ENVELOPE PRINTING (JACKET PRINTING) | NOS | 400 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 400 | 83.78 | 33512 | 360 | 0 | 0 | -33512
3835 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Exercise Book (21/17 cm - 192 pgs- ruling) | NOS | 12 | 56 | 672 | 12 | 56 | 672 | 1 | 56 | 56 | 12 | 58.24 | 698.88 | 12 | 58.24 | 698.88 | 11 | 0 | 616 | -26.88
3836 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Exercise Book (33/21 cm - 160 pgs- ruling) | NOS | 12 | 89.6 | 1075.2 | 12 | 89.6 | 1075.2 | 1 | 89.6 | 89.6 | 12 | 84 | 1008 | 12 | 84 | 1008 | 11 | 0 | 985.6 | 67.2
3837 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)FILE | NOS | 200 | 1.18 | 236 | 200 | 1.18 | 236 | 20 | 1.18 | 23.6 | 200 | 47.2 | 9440 | 200 | 47.2 | 9440 | 180 | 0 | 212.4 | -9204
3838 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Flat file | NOS | 1 | 35.4 | 35.4 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 24 | 32.4 | 777.55 | 1 | -23 | 35.4 | -742.15
3839 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)FLYER | NOS | 500 | 82.6 | 41300 | 500 | 82.6 | 41300 | 50 | 82.6 | 4130 | 500 | 82.6 | 41300 | 500 | 82.6 | 41300 | 450 | 0 | 37170 | 0
3840 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)FLYER PRINTING | NOS | 1 | 44.8 | 44.8 | 0 | 0 | 0 | 0 | 44.8 | 0 | 0 | 0 | 0 | 2000 | 49.28 | 98560 | 1 | -1999 | 44.8 | -98515.2
3841 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Gate Pass | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59 | 590 | 1 | -9 | 0 | -590
3842 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)HIGHLIGHTER(PKT) | PKT | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 118 | 118 | 1 | 118 | 118 | 1 | 0 | 1.18 | -116.82
3843 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)HP 2600 DESK JET COLOUR INK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 991.2 | 1982.4 | 1 | -1 | 0 | -1982.4
3844 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)HP 88A TONNER | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 1 | 9440 | 9440 | 1 | 0 | 1.18 | -9438.82
3845 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)HP PRINTER CARTRIDGE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2419 | 7257 | 1 | -2 | 0 | -7257
3846 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)I- PAD 64GB | SET | 1 | 43494.8 | 43494.8 | 0 | 0 | 0 | 0 | 43494.8 | 0 | 0 | 0 | 0 | 1 | 43500.01 | 43500.01 | 1 | 0 | 43494.8 | -5.21
3847 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Indent Book | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 118 | 1180 | 1 | -9 | 0 | -1180
3848 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)INSPECTION AND TESTING CHARGES | NOS | 1 | 590 | 590 | 1 | 590 | 590 | 0 | 590 | 0 | 1 | 590 | 590 | 1 | 590 | 590 | 1 | 0 | 590 | 0
3849 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)INSTALLATION | PICS | 1 | 590 | 590 | 1 | 590 | 590 | 0 | 590 | 0 | 1 | 590 | 590 | 2 | 1770 | 3540 | 1 | -1 | 590 | -2950
3850 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)INSTALLATION CHARGES | NOS | 1 | 625.4 | 625.4 | 1 | 625.4 | 625.4 | 0 | 625.4 | 0 | 1 | 354 | 354 | 0 | 0 | 0 | 1 | 1 | 625.4 | 625.4
3851 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)LETTER HEAD | NOS | 100 | 11.8 | 1180 | 100 | 11.8 | 1180 | 10 | 11.8 | 118 | 100 | 11.8 | 1180 | 100 | 11.8 | 1180 | 90 | 0 | 1062 | 0
3852 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)LUXOR PEN | PKT | 11 | 129.8 | 1427.8 | 1 | 129.8 | 129.8 | 1 | 129.8 | 129.8 | 1 | 118 | 118 | 3 | 133.73 | 401.2 | 10 | 8 | 1298 | 1026.6
3853 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)PAMPHLET | NOS | 300 | 47.2 | 14160 | 300 | 47.2 | 14160 | 30 | 47.2 | 1416 | 300 | 47.2 | 14160 | 300 | 47.2 | 14160 | 270 | 0 | 12744 | 0
3854 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)PENCIL | BOX | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
3855 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Printer reparing and servicing | NOS | 1 | 495.6 | 495.6 | 0 | 0 | 0 | 0 | 495.6 | 0 | 0 | 0 | 0 | 1 | 413 | 413 | 1 | 0 | 495.6 | 82.6
3856 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)PUNCH FILE | PICS | 12 | 70.8 | 849.6 | 12 | 70.8 | 849.6 | 1 | 70.8 | 70.8 | 12 | 100.3 | 1203.6 | 12 | 100.3 | 1203.6 | 11 | 0 | 778.8 | -354
3857 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)Refilling of toner 337A | NOS | 9 | 271.4 | 2442.6 | 3 | 271.4 | 814.2 | 1 | 271.4 | 271.4 | 3 | 265.5 | 796.5 | 5 | 265.5 | 1327.5 | 8 | 4 | 2171.2 | 1115.1
3858 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)RJ 45 CONNECTOR | NOS | 6 | 11.8 | 70.8 | 6 | 11.8 | 70.8 | 1 | 11.8 | 11.8 | 6 | 11.8 | 70.8 | 6 | 11.8 | 70.8 | 5 | 0 | 59 | 0
3859 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)SERVICE CHARGES | NOS | 1 | 1817.2 | 1817.2 | 1 | 1817.2 | 1817.2 | 0 | 1817.2 | 0 | 0 | 0 | 0 | 1 | 1416 | 1416 | 1 | 0 | 1817.2 | 401.2
3860 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)STAPLER PIN | PKT | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 165.2 | 330.4 | 2 | 165.2 | 330.4 | 2 | 0 | 2.36 | -328.04
3861 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)STAPLER PIN (BIG) | PKT | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3862 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)STEPLER PIN (BIG) | BOX | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 472 | 944 | 2 | 472 | 944 | 2 | 0 | 2.36 | -941.64
3863 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)TALLY AMC | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2950 | 2950 | 1 | 0 | 0 | -2950
3864 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)TALLY SOFTWARE SERVICE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4248 | 4248 | 1 | 0 | 0 | -4248
3865 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)TCENV | NOS | 500 | 1.18 | 590 | 500 | 1.18 | 590 | 50 | 1.18 | 59 | 500 | 17.7 | 8850 | 500 | 17.7 | 8850 | 450 | 0 | 531 | -8260
3866 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)TCENVV | NOS | 100 | 1.18 | 118 | 100 | 1.18 | 118 | 10 | 1.18 | 11.8 | 100 | 11.8 | 1180 | 100 | 11.8 | 1180 | 90 | 0 | 106.2 | -1062
3867 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)TV Wall Mount | NOS | 1 | 1652 | 1652 | 1 | 1652 | 1652 | 0 | 1652 | 0 | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 1 | 0 | 1652 | -2478
3868 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)VISTING CARD | NOS | 1000 | 11.8 | 11800 | 1000 | 11.8 | 11800 | 100 | 11.8 | 1180 | 1000 | 5.9 | 5900 | 1000 | 5.9 | 5900 | 900 | 0 | 10620 | 5900
3869 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)WHITENER PEN | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 33.04 | 198.24 | 6 | 33.04 | 198.24 | 5 | 0 | 5.9 | -191.16
3870 | ADMIN EXPENSES - Admin Expense | 10 | Started | Material | (M)WRITING PAD | NOS | 12 | 70.8 | 849.6 | 12 | 70.8 | 849.6 | 1 | 70.8 | 70.8 | 12 | 112.1 | 1345.2 | 12 | 112.1 | 1345.2 | 11 | 0 | 778.8 | -495.6
3871 | ADMIN EXPENSES - Staff Picnic Expenses | 10 | Started | Labour | (L)Bus Rent | NOS | 2 | 13000 | 26000 | 0 | 0 | 0 | 0 | 13000 | 0 | 1 | 19000 | 19000 | 1 | 19000 | 19000 | 2 | 1 | 26000 | 7000
3872 | ADMIN EXPENSES - Staff Picnic Expenses | 10 | Started | Labour | (L)Food charges (Non Veg) | Head | 129 | 787.5 | 101587.5 | 0 | 0 | 0 | 13 | 787.5 | 10237.5 | 129 | 1064 | 137256 | 128.25 | 1065.62 | 136665.38 | 116 | 0.75 | 91350 | -35077.88
3873 | ADMIN EXPENSES - Staff Picnic Expenses | 10 | Started | Labour | (L)Food charges (Veg) | Head | 6 | 651 | 3906 | 0 | 0 | 0 | 1 | 651 | 651 | 5.0041 | 768.5 | 3845.662 | 5.004 | 768.51 | 3845.64 | 5 | 0.996 | 3255 | 60.36
3874 | ADMIN EXPENSES - Office Meeting | 10 | Started | Labour | (L)Space for conference | LS | 7 | 8850 | 61950 | 0 | 0 | 0 | 1 | 8850 | 8850 | 6.8476 | 9538.38 | 65314.98 | 6.8476 | 9538.38 | 65314.98 | 6 | 0.1524 | 53100 | -3364.98
3875 | ADMIN EXPENSES - Internal Audit | 10 | Started | Labour | (L)Internal Audit | LS | 9 | 300000 | 2700000 | 0 | 0 | 0 | 1 | 300000 | 300000 | 9 | 147500 | 1327500 | 8 | 147500 | 1180000 | 8 | 1 | 2400000 | 1520000
3876 | ADMIN EXPENSES - Staff Verification Charges | 10 | Started | Labour | (L)Address Verification (Digital) | NOS | 10 | 236 | 2360 | 0 | 0 | 0 | 1 | 236 | 236 | 10 | 236 | 2360 | 10 | 236 | 2360 | 9 | 0 | 2124 | 0
3877 | ADMIN EXPENSES - Staff Verification Charges | 10 | Started | Labour | (L)Address Verification( Physical) | NOS | 10 | 472 | 4720 | 0 | 0 | 0 | 1 | 472 | 472 | 10 | 472 | 4720 | 9 | 472 | 4248 | 9 | 1 | 4248 | 472
3878 | ADMIN EXPENSES - Staff Verification Charges | 10 | Started | Labour | (L)Criminal Record Verification | NOS | 10 | 531 | 5310 | 0 | 0 | 0 | 1 | 531 | 531 | 10 | 531 | 5310 | 5 | 531 | 2655 | 9 | 5 | 4779 | 2655
3879 | ADMIN EXPENSES - Staff Verification Charges | 10 | Started | Labour | (L)Education Verificaiton | NOS | 10 | 590 | 5900 | 0 | 0 | 0 | 1 | 590 | 590 | 10 | 590 | 5900 | 5 | 590 | 2950 | 9 | 5 | 5310 | 2950
3880 | ADMIN EXPENSES - Staff Verification Charges | 10 | Started | Labour | (L)Employment Verification | NOS | 10 | 442.5 | 4425 | 0 | 0 | 0 | 1 | 442.5 | 442.5 | 10 | 442.5 | 4425 | 5 | 442.5 | 2212.5 | 9 | 5 | 3982.5 | 2212.5
3881 | ADMIN EXPENSES - IT Expenses | 0 | Started | Labour | (L)Amazon Web Services (AWS) | LS | 16 | 35400 | 566400 | 5 | 35400 | 177000 | 0 | 35400 | 0 | 16 | 51435.33 | 822965.28 | 9.049 | 60127.21 | 544091.16 | 16 | 6.951 | 566400 | 22308.84
3882 | ADMIN EXPENSES - IT Expenses | 0 | Started | Labour | (L)ESSL ETIMETRACKLITE WEB LICENSE | NOS | 3 | 7080 | 21240 | 0 | 0 | 0 | 0 | 7080 | 0 | 2 | 7080 | 14160 | 2 | 7080 | 14160 | 3 | 1 | 21240 | 7080
3883 | ADMIN EXPENSES - IT Expenses | 0 | Started | Labour | (L)M S Office Renewal | UNIT | 17 | 6018 | 102306 | 0 | 0 | 0 | 0 | 6018 | 0 | 7 | 6018 | 42126 | 7 | 6018 | 42126 | 17 | 10 | 102306 | 60180
3884 | ADMIN EXPENSES - IT Expenses | 0 | Started | Labour | (L)Sophos XGS116 Xstream Protection Renewal | Yearly | 1 | 35400 | 35400 | 0 | 0 | 0 | 0 | 35400 | 0 | 1 | 35400 | 35400 | 1 | 35400 | 35400 | 1 | 0 | 35400 | 0
3885 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)CRYSTAL 16 LINES EPAX SYSTEM | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17000 | 17000 | 1 | 0 | 0 | -17000
3886 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)CYBERPOWER 1 KVA UPS | NOS | 1 | 4873.4 | 4873.4 | 0 | 0 | 0 | 0 | 4873.4 | 0 | 0 | 0 | 0 | 1 | 4720 | 4720 | 1 | 0 | 4873.4 | 153.4
3887 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)CYBERPOWER 650VA UPS | NOS | 1 | 2879.2 | 2879.2 | 0 | 0 | 0 | 0 | 2879.2 | 0 | 0 | 0 | 0 | 1 | 2920.5 | 2920.5 | 1 | 0 | 2879.2 | -41.3
3888 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)D LINK 8 PORT SWITCH | NOS | 1 | 1156.4 | 1156.4 | 0 | 0 | 0 | 0 | 1156.4 | 0 | 0 | 0 | 0 | 1 | 1156.4 | 1156.4 | 1 | 0 | 1156.4 | 0
3889 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)D-LINK POE SWITCH 4 PORT | NOS | 1 | 2950 | 2950 | 0 | 0 | 0 | 0 | 2950 | 0 | 0 | 0 | 0 | 1 | 2950 | 2950 | 1 | 0 | 2950 | 0
3890 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)DESKTOP | NOS | 1 | 32697.8 | 32697.8 | 0 | 0 | 0 | 0 | 32697.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 32697.8 | 32697.8
3891 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Device Installation + Configuration + Device Training | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2183 | 2183 | 1 | 0 | 0 | -2183
3892 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)EPSON 4K PROJECTOR 3000 LUMENS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 169999.36 | 169999.36 | 1 | 0 | 0 | -169999.36
3893 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)EXTENTION CABLE 5 MTR | NOS | 1 | 2407.2 | 2407.2 | 0 | 0 | 0 | 0 | 2407.2 | 0 | 0 | 0 | 0 | 1 | 2407.2 | 2407.2 | 1 | 0 | 2407.2 | 0
3894 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)EZVIZ 360 WIRELESS CAMERA | NOS | 1 | 3009 | 3009 | 0 | 0 | 0 | 0 | 3009 | 0 | 0 | 0 | 0 | 1 | 3009 | 3009 | 1 | 0 | 3009 | 0
3895 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)FUJITSU DOCUMENT SCANNER | NOS | 1 | 29500 | 29500 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 1 | 29500 | 29500 | 1 | 0 | 29500 | 0
3896 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)GIGABYTE ROUTER BASIC | NOS | 1 | 2550 | 2550 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 1 | 3009 | 3009 | 1 | 0 | 2550 | -459
3897 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)GREYTIP ONLINE USAGE CHARGES | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33396.61 | 33396.61 | 1 | 0 | 0 | -33396.61
3898 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)HANDSET BEETEL B25 | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 1 | 790.6 | 790.6 | 1 | 0 | 1.18 | -789.42
3899 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Hang Tag (CCTV) | PCS | 56 | 33.6 | 1881.6 | 56 | 33.6 | 1881.6 | 0 | 33.6 | 0 | 56 | 35.4 | 1982.4 | 56 | 35.4 | 1982.4 | 56 | 0 | 1881.6 | -100.8
3900 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)HARD DISK 1 TB | NOS | 1 | 4484 | 4484 | 0 | 0 | 0 | 0 | 4484 | 0 | 0 | 0 | 0 | 3 | 4484 | 13452 | 1 | -2 | 4484 | -8968
3901 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)HARD DISK 2 TB | NOS | 1 | 5369 | 5369 | 0 | 0 | 0 | 0 | 5369 | 0 | 0 | 0 | 0 | 1 | 6195 | 6195 | 1 | 0 | 5369 | -826
3902 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)HEADPHONES | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2950 | 2950 | 1 | 0 | 0 | -2950
3903 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)HEADSET | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 41300 | 41300 | 1 | 0 | 0 | -41300
3904 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)INSTALLATION CHARGES | NOS | 1 | 625.4 | 625.4 | 1 | 625.4 | 625.4 | 0 | 625.4 | 0 | 1 | 590 | 590 | 0 | 0 | 0 | 1 | 1 | 625.4 | 625.4
3905 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Intercom | NOS | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 6 | 767 | 4602 | 1 | -5 | 118 | -4484
3906 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Intercom Beetel B- 25 Bet | NOS | 1 | 826 | 826 | 0 | 0 | 0 | 0 | 826 | 0 | 0 | 0 | 0 | 1 | 826 | 826 | 1 | 0 | 826 | 0
3907 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)INTERNET SECURITY 10 USERS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8201 | 16402 | 1 | -1 | 0 | -16402
3908 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)INTERNET SECURITY 3 USERS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4366 | 8732 | 1 | -1 | 0 | -8732
3909 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)KEYBOARD LAPTOP | NOS | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 0 | 2065 | 0 | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 1 | 0 | 2065 | 0
3910 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)LAPTOP ADAPTER | NOS | 1 | 2018.98 | 2018.98 | 1 | 2018.98 | 2018.98 | 0 | 2018.98 | 0 | 1 | 1994.2 | 1994.2 | 1 | 1994.2 | 1994.2 | 1 | 0 | 2018.98 | 24.78
3911 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Laptop For rent | MONTH | 1 | 3186 | 3186 | 0 | 0 | 0 | 0 | 3186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3186 | 3186
3912 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Lenovo Laptop | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 35341 | 70682 | 1 | -1 | 0 | -70682
3913 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)LOGITECH WEB CAMERA C920 | NOS | 1 | 9322 | 9322 | 0 | 0 | 0 | 0 | 9322 | 0 | 0 | 0 | 0 | 1 | 9322 | 9322 | 1 | 0 | 9322 | 0
3914 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Memory/ RAM | NOS | 1 | 1298 | 1298 | 1 | 1298 | 1298 | 0 | 1298 | 0 | 1 | 1298 | 1298 | 1 | 1298 | 1298 | 1 | 0 | 1298 | 0
3915 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)MICROSOFT POWER BI PRO | NOS | 1 | 8936.14 | 8936.14 | 1 | 8936.14 | 8936.14 | 0 | 8936.14 | 0 | 1 | 8936.14 | 8936.14 | 1 | 8936.14 | 8936.14 | 1 | 0 | 8936.14 | 0
3916 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Mobile Phone | NOS | 1 | 11823.6 | 11823.6 | 0 | 0 | 0 | 0 | 11823.6 | 0 | 0 | 0 | 0 | 7 | 12278.57 | 85949.98 | 1 | -6 | 11823.6 | -74126.38
3917 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)MONITOR | NOS | 2 | 22951 | 45902 | 1 | 22951 | 22951 | 0 | 22951 | 0 | 1 | 5782 | 5782 | 2 | 22951 | 45902 | 2 | 0 | 45902 | 0
3918 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Mouse Pad | NOS | 1 | 177 | 177 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 177 | 177
3919 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)MS O365 | NOS | 1 | 5935.4 | 5935.4 | 0 | 0 | 0 | 0 | 5935.4 | 0 | 0 | 0 | 0 | 4 | 5900 | 23600 | 1 | -3 | 5935.4 | -17664.6
3920 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)MS OFFICE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6077 | 6077 | 1 | 0 | 0 | -6077
3921 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)MS WINDOWS | NOS | 1 | 10773.4 | 10773.4 | 0 | 0 | 0 | 0 | 10773.4 | 0 | 0 | 0 | 0 | 2 | 10325 | 20650 | 1 | -1 | 10773.4 | -9876.6
3922 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)MSI PRO H410M-B MOTHERBOARD | NOS | 1 | 6077 | 6077 | 0 | 0 | 0 | 0 | 6077 | 0 | 0 | 0 | 0 | 1 | 6077 | 6077 | 1 | 0 | 6077 | 0
3923 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)One time Remote Installation | NOS | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
3924 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Power Supply | LS | 1 | 885 | 885 | 1 | 885 | 885 | 0 | 885 | 0 | 1 | 885 | 885 | 0 | 0 | 0 | 1 | 1 | 885 | 885
3925 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)PRINTER | NOS | 1 | 21830 | 21830 | 0 | 0 | 0 | 0 | 21830 | 0 | 0 | 0 | 0 | 3 | 29047.67 | 87143 | 1 | -2 | 21830 | -65313
3926 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Printer parts pick up roller change | NOS | 1 | 472 | 472 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 472 | 472
3927 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)RAM - DN150 (PART NO - 10006214) | PCS | 1 | 5345.4 | 5345.4 | 0 | 0 | 0 | 0 | 5345.4 | 0 | 0 | 0 | 0 | 2 | 5481.18 | 10962.35 | 1 | -1 | 5345.4 | -5616.95
3928 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)RAM 8GB | NOS | 1 | 2171.2 | 2171.2 | 1 | 2171.2 | 2171.2 | 0 | 2171.2 | 0 | 1 | 2065 | 2065 | 6 | 2153.5 | 12921 | 1 | -5 | 2171.2 | -10749.8
3929 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Rapoo Wired Mouse | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 342.2 | 684.4 | 1 | -1 | 0 | -684.4
3930 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)RJ 45 CONNECTOR | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 20 | 11.8 | 236 | 1 | -19 | 11.8 | -224.2
3931 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)RJ 6 CABLE | MTR | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 180 | 43.47 | 7824.69 | 1 | -179 | 47.2 | -7777.49
3932 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)ROUTER(TP-Link-Archer 5 DSL ) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3127 | 3127 | 1 | 0 | 0 | -3127
3933 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)S/C for Computer Networking & 2 nos. camera blinking repair | JOB | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 708 | 708 | 1 | 708 | 708 | 1 | 0 | 1.18 | -706.82
3934 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)SD CARD 128 GB | NOS | 1 | 1274.4 | 1274.4 | 0 | 0 | 0 | 0 | 1274.4 | 0 | 0 | 0 | 0 | 1 | 1268.5 | 1268.5 | 1 | 0 | 1274.4 | 5.9
3935 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)SERVICE CHARGES | NOS | 2 | 1817.2 | 3634.4 | 2 | 1817.2 | 3634.4 | 0 | 1817.2 | 0 | 2 | 590 | 1180 | 2 | 3331.85 | 6663.7 | 2 | 0 | 3634.4 | -3029.3
3936 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)SMPS 12 VOLT 10 AMP | NOS | 1 | 944 | 944 | 0 | 0 | 0 | 0 | 944 | 0 | 0 | 0 | 0 | 3 | 944 | 2832 | 1 | -2 | 944 | -1888
3937 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Sophos XGS 116 HW Appliance | NOS | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 59000 | 0
3938 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)SSD Drive | NOS | 2 | 1770 | 3540 | 2 | 1770 | 3540 | 0 | 1770 | 0 | 2 | 1770 | 3540 | 3 | 3245 | 9735 | 2 | -1 | 3540 | -6195
3939 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)TELEPHONE CABLE - 2 PAIR 0.5 GAUGE-180 MTR (90 MTRX 2 COIL | COIL | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1399.1 | 2798.2 | 1 | -1 | 0 | -2798.2
3940 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Telephone cord | NOS | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
3941 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)TELEPHONE SOCKET | NOS | 1 | 354 | 354 | 0 | 0 | 0 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 354 | 354
3942 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Telephone splliter | NOS | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
3943 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)TP-LINK EAP-225 INDOOR | NOS | 1 | 6490 | 6490 | 0 | 0 | 0 | 0 | 6490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6490 | 6490
3944 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)TP-LINK OMADA AC 1750 DUAL BAND | NOS | 1 | 7316 | 7316 | 0 | 0 | 0 | 0 | 7316 | 0 | 0 | 0 | 0 | 2 | 7316 | 14632 | 1 | -1 | 7316 | -7316
3945 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)UPS | NOS | 1 | 2761.2 | 2761.2 | 0 | 0 | 0 | 0 | 2761.2 | 0 | 0 | 0 | 0 | 9 | 2573.06 | 23157.5 | 1 | -8 | 2761.2 | -20396.3
3946 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)USB 3.0 ETHERNET ADAPTER | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 0 | 0 | 0 | 4 | 1416 | 5664 | 1 | -3 | 1416 | -4248
3947 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)USB 3.0 EXTERNAL HDD/SSD CASING 2.5” | NOS | 1 | 885 | 885 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 885 | 885
3948 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)USB CABLE | NOS | 1 | 649 | 649 | 0 | 0 | 0 | 0 | 649 | 0 | 0 | 0 | 0 | 1 | 649 | 649 | 1 | 0 | 649 | 0
3949 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)USB Gigabit to Lan | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1563.5 | 14071.5 | 1 | -8 | 0 | -14071.5
3950 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)USB to Ethernet Lan Wired Adapter TPLINK | NOS | 1 | 1510.4 | 1510.4 | 0 | 0 | 0 | 0 | 1510.4 | 0 | 0 | 0 | 0 | 1 | 1504.5 | 1504.5 | 1 | 0 | 1510.4 | 5.9
3951 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)USB TO LAN ADAPTOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1770 | 3540 | 1 | -1 | 0 | -3540
3952 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)VGA Cable | NOS | 1 | 354 | 354 | 0 | 0 | 0 | 0 | 354 | 0 | 0 | 0 | 0 | 2 | 354 | 708 | 1 | -1 | 354 | -354
3953 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)WB 12A/88A | NOS | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 118
3954 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)WINDOWS 10 HOME | NOS | 1 | 8496 | 8496 | 1 | 8496 | 8496 | 0 | 8496 | 0 | 1 | 8496 | 8496 | 1 | 8496 | 8496 | 1 | 0 | 8496 | 0
3955 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Windows 10 Pro 64 bit | NOS | 1 | 11446 | 11446 | 0 | 0 | 0 | 0 | 11446 | 0 | 0 | 0 | 0 | 1 | 11446 | 11446 | 1 | 0 | 11446 | 0
3956 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Wired Mouse | NOS | 1 | 354 | 354 | 0 | 0 | 0 | 0 | 354 | 0 | 0 | 0 | 0 | 5 | 356.36 | 1781.8 | 1 | -4 | 354 | -1427.8
3957 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)WIRELESS DONGLE | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1097.4 | 4389.6 | 1 | -3 | 0 | -4389.6
3958 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)WIRELESS KEYBOARD & MOUSE | NOS | 1 | 3280.4 | 3280.4 | 0 | 0 | 0 | 0 | 3280.4 | 0 | 0 | 0 | 0 | 1 | 2792.67 | 2792.67 | 1 | 0 | 3280.4 | 487.73
3959 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)WIRELESS LAN CARD | NOS | 1 | 1475 | 1475 | 1 | 1475 | 1475 | 0 | 1475 | 0 | 1 | 1475 | 1475 | 1 | 1475 | 1475 | 1 | 0 | 1475 | 0
3960 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)WIRELESS MOUSE | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 3 | 796.5 | 2389.5 | 1 | -2 | 1.18 | -2388.32
3961 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)Xstream Protection | NOS | 1 | 29500 | 29500 | 1 | 29500 | 29500 | 0 | 29500 | 0 | 1 | 29500 | 29500 | 1 | 29500 | 29500 | 1 | 0 | 29500 | 0
3962 | ADMIN EXPENSES - IT Expenses | 0 | Started | Material | (M)YEASTAR S2 MODULE | NOS | 1 | 7552 | 7552 | 0 | 0 | 0 | 0 | 7552 | 0 | 0 | 0 | 0 | 2 | 7552 | 15104 | 1 | -1 | 7552 | -7552
3963 | ADMIN EXPENSES - IP Phone Support | 10 | Started | Labour | (L)Yeastar IPPBX Annual Remote Support | Monthly | 12 | 6490 | 77880 | 0 | 0 | 0 | 1 | 6490 | 6490 | 12 | 6490 | 77880 | 12 | 6490 | 77880 | 11 | 0 | 71390 | 0
3964 | ADMIN EXPENSES - Printing Work | 10 | Started | Material | (M)DRUM | NOS | 4 | 236 | 944 | 4 | 236 | 944 | 0 | 236 | 0 | 4 | 236 | 944 | 0 | 0 | 0 | 4 | 4 | 944 | 944
3965 | ADMIN EXPENSES - Printing Work | 10 | Started | Material | (M)Printer parts pick up roller change | NOS | 1 | 472 | 472 | 1 | 472 | 472 | 0 | 472 | 0 | 1 | 472 | 472 | 1 | 472 | 472 | 1 | 0 | 472 | 0
3966 | ADMIN EXPENSES - Printing Work | 10 | Started | Material | (M)Printer reparing and servicing | NOS | 2 | 495.6 | 991.2 | 2 | 495.6 | 991.2 | 0 | 495.6 | 0 | 2 | 531 | 1062 | 2 | 531 | 1062 | 2 | 0 | 991.2 | -70.8
3967 | ADMIN EXPENSES - Printing Work | 10 | Started | Material | (M)Refilling of toner 337A | NOS | 7 | 271.4 | 1899.8 | 7 | 271.4 | 1899.8 | 1 | 271.4 | 271.4 | 7 | 265.5 | 1858.5 | 7 | 265.5 | 1858.5 | 6 | 0 | 1628.4 | 41.3
3968 | ADMIN EXPENSES - Printing Work | 10 | Started | Material | (M)Refilling of toner 925 | NOS | 2 | 271.4 | 542.8 | 2 | 271.4 | 542.8 | 0 | 271.4 | 0 | 2 | 265.5 | 531 | 2 | 265.5 | 531 | 2 | 0 | 542.8 | 11.8
3969 | ADMIN EXPENSES - Printing Work | 10 | Started | Material | (M)WB 12A/88A | NOS | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 1 | 118 | 118 | 1 | 118 | 118 | 1 | 0 | 118 | 0
3970 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Labour | (L)Annual Maintenance, Support & Upgrades Costing Highrise | NOS | 2 | 209509 | 419018 | 0 | 0 | 0 | 0 | 209509 | 0 | 2 | 209509 | 419018 | 1 | 209509 | 209509 | 2 | 1 | 419018 | 209509
3971 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Labour | (L)ESSL LICENSE ONE TIME | NOS | 3 | 1416 | 4248 | 0 | 0 | 0 | 0 | 1416 | 0 | 3 | 1416 | 4248 | 0 | 0 | 0 | 3 | 3 | 4248 | 4248
3972 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Labour | (L)Greyt HR GROWTH Plan Software | Yearly | 1 | 88721.84 | 88721.84 | 0 | 0 | 0 | 0 | 88721.84 | 0 | 1 | 88721.84 | 88721.84 | 1 | 88721.84 | 88721.84 | 1 | 0 | 88721.84 | 0
3973 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Labour | (L)Hire Charges of Decorating Items | LS | 1 | 15812 | 15812 | 0 | 0 | 0 | 0 | 15812 | 0 | 1 | 15812 | 15812 | 1 | 15812 | 15812 | 1 | 0 | 15812 | 0
3974 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Labour | (L)Service CHARGES for Software Configuration One Time | NOS | 1 | 2950 | 2950 | 0 | 0 | 0 | 0 | 2950 | 0 | 1 | 2950 | 2950 | 0 | 0 | 0 | 1 | 1 | 2950 | 2950
3975 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)12V 2AMP CCTV ADAPTER | NOS | 3 | 531 | 1593 | 2 | 531 | 1062 | 0 | 531 | 0 | 2 | 649 | 1298 | 3 | 570.33 | 1711 | 3 | 0 | 1593 | -118
3976 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)8/6 PVC BOX | NOS | 2 | 129.8 | 259.6 | 2 | 129.8 | 259.6 | 0 | 129.8 | 0 | 2 | 129.8 | 259.6 | 2 | 129.8 | 259.6 | 2 | 0 | 259.6 | 0
3977 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)A4 size Paper | PKT | 100 | 291.2 | 29120 | 100 | 291.2 | 29120 | 10 | 291.2 | 2912 | 100 | 291.2 | 29120 | 50 | 291.2 | 14560 | 90 | 50 | 26208 | 14560
3978 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ADAPTOR 12V2AMP | NOS | 1 | 767 | 767 | 1 | 767 | 767 | 0 | 767 | 0 | 1 | 1593 | 1593 | 1 | 1593 | 1593 | 1 | 0 | 767 | -826
3979 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ALDO 24" DUFFLE BAG WITH WHEEL | PCS | 67 | 1416 | 94872 | 67 | 1416 | 94872 | 7 | 1416 | 9912 | 67 | 1416 | 94872 | 67 | 1416 | 94872 | 60 | 0 | 84960 | 0
3980 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Arch file (Big) | PCS | 37 | 106.2 | 3929.4 | 36 | 106.2 | 3823.2 | 4 | 106.2 | 424.8 | 36 | 100.3 | 3610.8 | 36 | 100.3 | 3610.8 | 33 | 1 | 3504.6 | 318.6
3981 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ARCH FILE (SMALL) | NOS | 24 | 94.4 | 2265.6 | 24 | 94.4 | 2265.6 | 2 | 94.4 | 188.8 | 24 | 94.4 | 2265.6 | 24 | 94.4 | 2265.6 | 22 | 0 | 2076.8 | 0
3982 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ARIEL SLIM WALLET-BLACK | PCS | 46 | 649 | 29854 | 46 | 649 | 29854 | 5 | 649 | 3245 | 46 | 649 | 29854 | 46 | 649 | 29854 | 41 | 0 | 26609 | 0
3983 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ARTIFICIAL GRASS CARPET | SQFT | 269 | 1.18 | 317.42 | 269 | 1.18 | 317.42 | 27 | 1.18 | 31.86 | 269 | 64.9 | 17458.1 | 269 | 62.2 | 16730.56 | 242 | 0 | 285.56 | -16413.14
3984 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BLACK PEN | NOS | 21 | 1.18 | 24.78 | 20 | 1.18 | 23.6 | 2 | 1.18 | 2.36 | 20 | 5.31 | 106.2 | 20 | 11.8 | 236 | 19 | 1 | 22.42 | -211.22
3985 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BLUE PEN | NOS | 40 | 1.18 | 47.2 | 40 | 1.18 | 47.2 | 4 | 1.18 | 4.72 | 40 | 5.31 | 212.4 | 20 | 11.8 | 236 | 36 | 20 | 42.48 | -188.8
3986 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BNC CONNECTOR | NOS | 2 | 47.2 | 94.4 | 2 | 47.2 | 94.4 | 0 | 47.2 | 0 | 2 | 41.3 | 82.6 | 0 | 0 | 0 | 2 | 2 | 94.4 | 94.4
3987 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BOTH SIDE TAPE | NOS | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 1 | 584.1 | 584.1 | 1 | 0 | 590 | 5.9
3988 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BOTTLE INK BLACK COLOUR | NOS | 2 | 802.4 | 1604.8 | 2 | 802.4 | 1604.8 | 0 | 802.4 | 0 | 2 | 796.5 | 1593 | 3 | 796.5 | 2389.5 | 2 | -1 | 1604.8 | -784.7
3989 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BOTTLE INK CYAN COLOUR | NOS | 1 | 660.8 | 660.8 | 1 | 660.8 | 660.8 | 0 | 660.8 | 0 | 1 | 678.5 | 678.5 | 2 | 663.75 | 1327.5 | 1 | -1 | 660.8 | -666.7
3990 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BOTTLE INK MAGENTA COLOUR | NOS | 1 | 660.8 | 660.8 | 1 | 660.8 | 660.8 | 0 | 660.8 | 0 | 1 | 678.5 | 678.5 | 2 | 663.75 | 1327.5 | 1 | -1 | 660.8 | -666.7
3991 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BOTTLE INK YELLOW COLOUR | NOS | 1 | 660.8 | 660.8 | 1 | 660.8 | 660.8 | 0 | 660.8 | 0 | 1 | 678.5 | 678.5 | 2 | 663.75 | 1327.5 | 1 | -1 | 660.8 | -666.7
3992 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)BUTTON FOLDER | NOS | 24 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 24 | 31.86 | 764.64 | 22 | 0 | 0 | -764.64
3993 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CALCULATOR | NOS | 22 | 224.2 | 4932.4 | 0 | 0 | 0 | 2 | 224.2 | 448.4 | 0 | 0 | 0 | 22 | 238.93 | 5256.35 | 20 | 0 | 4484 | -323.95
3994 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Carbon Paper | PCS | 100 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 100 | 1.71 | 171.1 | 90 | 0 | 0 | -171.1
3995 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CARD HOLDER BOOK | NOS | 6 | 177 | 1062 | 0 | 0 | 0 | 1 | 177 | 177 | 0 | 0 | 0 | 6 | 177 | 1062 | 5 | 0 | 885 | 0
3996 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CARTRIDGE | PICS | 5 | 944 | 4720 | 1 | 944 | 944 | 1 | 944 | 944 | 1 | 1003 | 1003 | 5 | 908.6 | 4543 | 4 | 0 | 3776 | 177
3997 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CAT 6 CABLE FINOLEX | MTR | 42 | 23.6 | 991.2 | 42 | 23.6 | 991.2 | 4 | 23.6 | 94.4 | 42 | 24.78 | 1040.76 | 42 | 24.78 | 1040.76 | 38 | 0 | 896.8 | -49.56
3998 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CD MARKER PEN | NOS | 10 | 11.8 | 118 | 10 | 11.8 | 118 | 1 | 11.8 | 11.8 | 10 | 16.52 | 165.2 | 10 | 16.52 | 165.2 | 9 | 0 | 106.2 | -47.2
3999 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CELLO GRIPPER PEN BLACK | PKT | 5 | 82.6 | 413 | 0 | 0 | 0 | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 5 | 70.8 | 354 | 4 | 0 | 330.4 | 59
4000 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CELLO GRIPPER PEN BLUE | PKT | 20 | 1.18 | 23.6 | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 2 | 106.2 | 212.4 | 9 | 73.42 | 660.8 | 18 | 11 | 21.24 | -637.2
4001 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CELLO TAPE 1'' | NOS | 12 | 29.5 | 354 | 0 | 0 | 0 | 1 | 29.5 | 29.5 | 0 | 0 | 0 | 12 | 23.6 | 283.2 | 11 | 0 | 324.5 | 70.8
4002 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CELLO TAPE 1.5" | PCS | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 1 | 1.18 | 1.18 | 12 | 23.6 | 283.2 | 12 | 23.6 | 283.2 | 11 | 0 | 12.98 | -269.04
4003 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CELLO TAPE 1/2' | MTR | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 16.52 | 49.56 | 3 | 0 | 0 | -49.56
4004 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CELLO TAPE 2 " | PCS | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 1 | 1.18 | 1.18 | 12 | 41.3 | 495.6 | 12 | 41.3 | 495.6 | 11 | 0 | 12.98 | -481.44
4005 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)COBRA BOARD FILE | NOS | 60 | 35.4 | 2124 | 60 | 35.4 | 2124 | 6 | 35.4 | 212.4 | 60 | 29.5 | 1770 | 60 | 29.5 | 1770.01 | 54 | 0 | 1911.6 | 353.99
4006 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CONFERENCE TABLE SOCKET | SET | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 0 | 7080 | 0 | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 1 | 0 | 7080 | 0
4007 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)CORRECTION PEN | NOS | 15 | 1.18 | 17.7 | 15 | 1.18 | 17.7 | 2 | 1.18 | 2.36 | 15 | 33.04 | 495.6 | 21 | 32.03 | 672.6 | 13 | -6 | 15.34 | -654.9
4008 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)COVER FILE | PICS | 84 | 47.2 | 3964.8 | 24 | 47.2 | 1132.8 | 8 | 47.2 | 377.6 | 24 | 41.3 | 991.2 | 84 | 41.3 | 3469.2 | 76 | 0 | 3587.2 | 495.6
4009 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)COVER FILE 14*10 F/C | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 41.3 | 1486.8 | 1 | -35 | 0 | -1486.8
4010 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)COVER FILE 16*12 A/3 | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 76.7 | 1840.8 | 1 | -23 | 0 | -1840.8
4011 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)D LINK 8 PORT SWITCH | NOS | 1 | 1156.4 | 1156.4 | 1 | 1156.4 | 1156.4 | 0 | 1156.4 | 0 | 1 | 1156.4 | 1156.4 | 0 | 0 | 0 | 1 | 1 | 1156.4 | 1156.4
4012 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)DB 36A/88A/328A | NOS | 4 | 118 | 472 | 4 | 118 | 472 | 0 | 118 | 0 | 4 | 118 | 472 | 4 | 118 | 472 | 4 | 0 | 472 | 0
4013 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)DESKTOP | NOS | 1 | 32697.8 | 32697.8 | 1 | 32697.8 | 32697.8 | 0 | 32697.8 | 0 | 1 | 48970 | 48970 | 1 | 48970 | 48970 | 1 | 0 | 32697.8 | -16272.2
4014 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)DOOR HANDLE | NOS | 1 | 171.1 | 171.1 | 1 | 171.1 | 171.1 | 0 | 171.1 | 0 | 1 | 15930 | 15930 | 1 | 15930 | 15930 | 1 | 0 | 171.1 | -15758.9
4015 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Door Lock Istallation for One time | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1416 | 1416
4016 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)DRUM | NOS | 8 | 236 | 1888 | 8 | 236 | 1888 | 1 | 236 | 236 | 8 | 236 | 1888 | 4 | 236 | 944 | 7 | 4 | 1652 | 944
4017 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)DRUM 36A/88A/78A/328A | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 236 | 472 | 2 | 236 | 472 | 2 | 0 | 2.36 | -469.64
4018 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)DUSTER | PICS | 26 | 21 | 546 | 24 | 21 | 504 | 3 | 21 | 63 | 24 | 15.75 | 378 | 46 | 15.75 | 724.5 | 23 | -20 | 483 | -178.5
4019 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)EM LOCK | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2891 | 2891 | 1 | 0 | 0 | -2891
4020 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ENVELOP | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 500 | 7.08 | 3540 | 1 | -499 | 11.8 | -3528.2
4021 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ENVELOP PRINTING | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 2000 | 17.68 | 35352.8 | 1 | -1999 | 11.8 | -35341
4022 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ERASER | NOS | 27 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 26 | 2.89 | 75.14 | 24 | 1 | 0 | -75.14
4023 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Exercise Book (21/17 cm - 192 pgs- ruling) | NOS | 6 | 56 | 336 | 6 | 56 | 336 | 1 | 56 | 56 | 6 | 58.24 | 349.44 | 6 | 58.24 | 349.44 | 5 | 0 | 280 | -13.44
4024 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Exercise Book (21/17cm - 192 pgs- no ruling) | NOS | 6 | 56 | 336 | 6 | 56 | 336 | 1 | 56 | 56 | 6 | 58.24 | 349.44 | 6 | 58.24 | 349.44 | 5 | 0 | 280 | -13.44
4025 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Exercise Book (33/21 cm - 160 pgs- ruling) | NOS | 6 | 89.6 | 537.6 | 6 | 89.6 | 537.6 | 1 | 89.6 | 89.6 | 6 | 84 | 504 | 6 | 84 | 504 | 5 | 0 | 448 | 33.6
4026 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)FABTRO-43" I-SHAPE DIGITAL SIGNAGE | NOS | 1 | 61006 | 61006 | 1 | 61006 | 61006 | 0 | 61006 | 0 | 1 | 69926.8 | 69926.8 | 1 | 68558.54 | 68558.54 | 1 | 0 | 61006 | -7552.54
4027 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Frosted Film | SQFT | 35 | 153.4 | 5369 | 35 | 153.4 | 5369 | 4 | 153.4 | 613.6 | 35 | 141.6 | 4956 | 167 | 141.6 | 23647.2 | 31 | -132 | 4755.4 | -18278.2
4028 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Gel Pen (Black) | NOS | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 1 | 1.18 | 1.18 | 10 | 10.62 | 106.2 | 10 | 10.62 | 106.2 | 9 | 0 | 10.62 | -94.4
4029 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Gel Pen (Blue) | NOS | 10 | 11.8 | 118 | 10 | 11.8 | 118 | 1 | 11.8 | 11.8 | 10 | 10.62 | 106.2 | 10 | 10.62 | 106.2 | 9 | 0 | 106.2 | 11.8
4030 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Gel Pen (Red) | NOS | 10 | 11.8 | 118 | 10 | 11.8 | 118 | 1 | 11.8 | 11.8 | 10 | 10.62 | 106.2 | 10 | 10.62 | 106.2 | 9 | 0 | 106.2 | 11.8
4031 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)GEMS CLIP | BOX | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 10 | 22 | 220.04 | 1 | -9 | 1.18 | -218.86
4032 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)GLUE STICK | NOS | 15 | 35.4 | 531 | 6 | 35.4 | 212.4 | 2 | 35.4 | 70.8 | 6 | 29.5 | 177 | 18 | 29.5 | 531 | 13 | -3 | 460.2 | 0
4033 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)HAND SANITIZER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 137.99 | 1379.89 | 1 | -9 | 0 | -1379.89
4034 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)HANDSET BEETEL B25 | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 826 | 1652 | 2 | 826 | 1652 | 2 | 0 | 2.36 | -1649.64
4035 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)HDD BRACKET | NOS | 1 | 590 | 590 | 1 | 590 | 590 | 0 | 590 | 0 | 1 | 590 | 590 | 1 | 590 | 590 | 1 | 0 | 590 | 0
4036 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)HDMI CABLE . | NOS | 1 | 472 | 472 | 1 | 472 | 472 | 0 | 472 | 0 | 1 | 560.5 | 560.5 | 1 | 560.5 | 560.5 | 1 | 0 | 472 | -88.5
4037 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Highlighter | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 20 | 21.97 | 439.31 | 1 | -19 | 1.18 | -438.13
4038 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)HIGHLIGHTER(PKT) | PKT | 5 | 1.18 | 5.9 | 5 | 1.18 | 5.9 | 1 | 1.18 | 1.18 | 5 | 118 | 590 | 5 | 118 | 590 | 4 | 0 | 4.72 | -584.1
4039 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)HIKVISION 30MTRS BULLET CAMERA 2MP | NOS | 1 | 2891 | 2891 | 1 | 2891 | 2891 | 0 | 2891 | 0 | 1 | 2891 | 2891 | 1 | 2891 | 2891 | 1 | 0 | 2891 | 0
4040 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)INSTALLATION CHARGES | NOS | 2 | 625.4 | 1250.8 | 2 | 625.4 | 1250.8 | 0 | 625.4 | 0 | 2 | 944 | 1888 | 2 | 708 | 1416 | 2 | 0 | 1250.8 | -165.2
4041 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Intercom | NOS | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 1 | 15340 | 15340 | 1 | 15340 | 15340 | 1 | 0 | 118 | -15222
4042 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Intercom Beetel B- 25 Bet | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 826 | 826 | 0 | 0 | 0 | 1 | 1 | 826 | 826
4043 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Issue Voucher | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 118 | 1180 | 1 | -9 | 0 | -1180
4044 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)KEY BOARD | NOS | 2 | 1191.8 | 2383.6 | 2 | 1191.8 | 2383.6 | 0 | 1191.8 | 0 | 2 | 767 | 1534 | 6 | 977.43 | 5864.6 | 2 | -4 | 2383.6 | -3481
4045 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)KEYBOARD LAPTOP | NOS | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 0 | 2065 | 0 | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 1 | 0 | 2065 | 0
4046 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)LAN CABLE 1 MTR | NOS | 2 | 177 | 354 | 2 | 177 | 354 | 0 | 177 | 0 | 2 | 177 | 354 | 2 | 177 | 354 | 2 | 0 | 354 | 0
4047 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)LAN CABLE 3 MTR | NOS | 1 | 236 | 236 | 1 | 236 | 236 | 0 | 236 | 0 | 1 | 236 | 236 | 1 | 236 | 236 | 1 | 0 | 236 | 0
4048 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)LAPTOP | NOS | 1 | 34869 | 34869 | 1 | 34869 | 34869 | 0 | 34869 | 0 | 1 | 57230 | 57230 | 11 | 35464.36 | 390108 | 1 | -10 | 34869 | -355239
4049 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Laptop Bag | NOS | 25 | 1298 | 32450 | 25 | 1298 | 32450 | 3 | 1298 | 3894 | 25 | 1298 | 32450 | 25 | 1298 | 32450 | 22 | 0 | 28556 | 0
4050 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Laptop Battery | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 3422 | 3422 | 1 | 3422 | 3422 | 1 | 0 | 1.18 | -3420.82
4051 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)LEGRAND I/O | NOS | 3 | 708 | 2124 | 3 | 708 | 2124 | 0 | 708 | 0 | 3 | 711.54 | 2134.62 | 3 | 711.54 | 2134.62 | 3 | 0 | 2124 | -10.62
4052 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)LETTER HEAD | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11.8 | 11.8
4053 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)MAGNET | NOS | 24 | 106.2 | 2548.8 | 24 | 106.2 | 2548.8 | 2 | 106.2 | 212.4 | 24 | 49.17 | 1180 | 24 | 52.44 | 1258.67 | 22 | 0 | 2336.4 | 1290.13
4054 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)MATERIAL ISSUE / RECEIVED VOUCHER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 82.6 | 826 | 1 | -9 | 0 | -826
4055 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Mobile Charger | NOS | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 0 | 1416 | 0 | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 1 | 0 | 1416 | 0
4056 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Mouse Pad | NOS | 3 | 177 | 531 | 3 | 177 | 531 | 0 | 177 | 0 | 3 | 177 | 531 | 23 | 177 | 4071 | 3 | -20 | 531 | -3540
4057 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)NOTE BOOK 24X18 PLAIN | NOS | 1 | 59 | 59 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 6 | 53.1 | 318.6 | 1 | -5 | 59 | -259.6
4058 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)NOTE BOOK 24X18 RULE | NOS | 1 | 59 | 59 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 6 | 53.1 | 318.6 | 1 | -5 | 59 | -259.6
4059 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)NOTE BOOK PLAIN 33X21 | NOS | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 0 | 82.6 | 0 | 0 | 0 | 0 | 6 | 76.7 | 460.2 | 1 | -5 | 82.6 | -377.6
4060 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)NOTE BOOK RULE 33x21 | NOS | 1 | 78.4 | 78.4 | 0 | 0 | 0 | 0 | 78.4 | 0 | 0 | 0 | 0 | 6 | 72.8 | 436.8 | 1 | -5 | 78.4 | -358.4
4061 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)NOTE PAD | NOS | 60 | 23.6 | 1416 | 12 | 23.6 | 283.2 | 6 | 23.6 | 141.6 | 12 | 29.5 | 354 | 66 | 26.76 | 1765.89 | 54 | -6 | 1274.4 | -349.89
4062 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)OFFICE STATIONERY MATERIALS | LOT | 7 | 8260 | 57820 | 7 | 8260 | 57820 | 1 | 8260 | 8260 | 7 | 4036.97 | 28258.78 | 7 | 4036.97 | 28258.78 | 6 | 0 | 49560 | 29561.22
4063 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)ORIGAMI ECONOMY HRT | MTR | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 315.11 | 7562.74 | 1 | -23 | 0 | -7562.74
4064 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PAMPHLET | NOS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 47.2 | 47.2
4065 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PAPER CUTTER BIG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29.5 | 29.5 | 1 | 0 | 0 | -29.5
4066 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PAPER CUTTER SMALL | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17.7 | 17.7 | 1 | 0 | 0 | -17.7
4067 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PAPER WEIGHT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 52.91 | 105.82 | 1 | -1 | 0 | -105.82
4068 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PCR | NOS | 6 | 118 | 708 | 4 | 118 | 472 | 1 | 118 | 118 | 4 | 118 | 472 | 7 | 118 | 826 | 5 | -1 | 590 | -118
4069 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PEN STAND | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 140.09 | 1260.81 | 1 | -8 | 0 | -1260.81
4070 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PEN STAND BIG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 145.51 | 291.01 | 1 | -1 | 0 | -291.01
4071 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PEN STAND SMALL | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 138.89 | 416.68 | 1 | -2 | 0 | -416.68
4072 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PENCIL | BOX | 2 | 47.2 | 94.4 | 2 | 47.2 | 94.4 | 0 | 47.2 | 0 | 2 | 41.3 | 82.6 | 6 | 45.94 | 275.65 | 2 | -4 | 94.4 | -181.25
4073 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PENCIL. | PKT | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 2 | 47.2 | 94.4 | 1 | -1 | 47.2 | -47.2
4074 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PENDRIVE 32 GB SANDISK | NOS | 2 | 295 | 590 | 2 | 295 | 590 | 0 | 295 | 0 | 2 | 295 | 590 | 2 | 295 | 590 | 2 | 0 | 590 | 0
4075 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Permanent Marker | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 21.24 | 254.88 | 1 | -11 | 0 | -254.88
4076 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PLASTIC BUTTON FOLDER | PCS | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 24 | 41.3 | 991.2 | 1 | -23 | 47.2 | -944
4077 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PLASTIC SCALE | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 12 | 14.16 | 169.92 | 1 | -11 | 11.8 | -158.12
4078 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PLASTIC SHOE COVER | NOS | 960 | 11.8 | 11328 | 960 | 11.8 | 11328 | 96 | 11.8 | 1132.8 | 960 | 8.05 | 7723.488 | 960 | 7.9 | 7582.37 | 864 | 0 | 10195.2 | 3745.63
4079 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)POST IT PAD | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 29.5 | 59 | 1 | -1 | 0 | -59
4080 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)POWER SPIKE BUSTER | NOS | 2 | 560.5 | 1121 | 2 | 560.5 | 1121 | 0 | 560.5 | 0 | 2 | 1003 | 2006 | 2 | 1003 | 2006 | 2 | 0 | 1121 | -885
4081 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PRINTER | NOS | 1 | 21830 | 21830 | 1 | 21830 | 21830 | 0 | 21830 | 0 | 1 | 13629 | 13629 | 1 | 13629 | 13629 | 1 | 0 | 21830 | 8201
4082 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PRINTER ADF LOCK CHANGE | NOS | 1 | 767 | 767 | 1 | 767 | 767 | 0 | 767 | 0 | 1 | 767 | 767 | 1 | 767 | 767 | 1 | 0 | 767 | 0
4083 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Printer reparing and servicing | NOS | 2 | 495.6 | 991.2 | 2 | 495.6 | 991.2 | 0 | 495.6 | 0 | 2 | 472 | 944 | 1 | 531 | 531 | 2 | 1 | 991.2 | 460.2
4084 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PROX CARD WITH BOTH SIDE PRINT | NOS | 1 | 224.2 | 224.2 | 0 | 0 | 0 | 0 | 224.2 | 0 | 0 | 0 | 0 | 24 | 221.84 | 5324.16 | 1 | -23 | 224.2 | -5099.96
4085 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Prox card with both side print with Card holder and Card | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 289.1 | 9829.4 | 1 | -33 | 0 | -9829.4
4086 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PUNCH FILE | PICS | 30 | 70.8 | 2124 | 0 | 0 | 0 | 3 | 70.8 | 212.4 | 0 | 0 | 0 | 30 | 41.99 | 1259.75 | 27 | 0 | 1911.6 | 864.25
4087 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)PUNCHING MACHINE DP-800 | NOS | 7 | 590 | 4130 | 1 | 590 | 590 | 1 | 590 | 590 | 1 | 1593 | 1593 | 7 | 312.3 | 2186.11 | 6 | 0 | 3540 | 1943.89
4088 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)RECYCLING OF TONER | NOS | 7 | 531 | 3717 | 7 | 531 | 3717 | 1 | 531 | 531 | 7 | 531 | 3717 | 7 | 531 | 3717 | 6 | 0 | 3186 | 0
4089 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)RED PEN | NOS | 20 | 4.49 | 89.8 | 20 | 4.49 | 89.8 | 2 | 4.49 | 8.98 | 20 | 5.31 | 106.2 | 20 | 5.31 | 106.2 | 18 | 0 | 80.82 | -16.4
4090 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)REFILLING OF TONER | NOS | 25 | 271.4 | 6785 | 20 | 271.4 | 5428 | 3 | 271.4 | 814.2 | 20 | 265.5 | 5310 | 33 | 265.5 | 8761.5 | 22 | -8 | 5970.8 | -1976.5
4091 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)REFILLING OF TONER 1666 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 265.5 | 265.5 | 1 | 265.5 | 265.5 | 1 | 0 | 1.18 | -264.32
4092 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Refilling of toner 337A | NOS | 20 | 271.4 | 5428 | 19 | 271.4 | 5156.6 | 2 | 271.4 | 542.8 | 19 | 265.5 | 5044.5 | 17 | 265.5 | 4513.5 | 18 | 3 | 4885.2 | 914.5
4093 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Refilling of toner 925 | NOS | 1 | 271.4 | 271.4 | 0 | 0 | 0 | 0 | 271.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 271.4 | 271.4
4094 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)REFILLING OF TONNER | NOS | 50 | 271.4 | 13570 | 36 | 271.4 | 9770.4 | 5 | 271.4 | 1357 | 36 | 267.96 | 9646.5 | 74 | 266.7 | 19735.5 | 45 | -24 | 12213 | -6165.5
4095 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)REFILLING OFTONER | NOS | 23 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 23 | 0 | 0
4096 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Return Voucher | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 118 | 1180 | 1 | -9 | 0 | -1180
4097 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)REVOLVING CHAIR | NOS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5900 | 5900
4098 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)RIBBON WITH COLOR PRINT | NOS | 1 | 129.8 | 129.8 | 0 | 0 | 0 | 0 | 129.8 | 0 | 0 | 0 | 0 | 70 | 119.01 | 8330.8 | 1 | -69 | 129.8 | -8201
4099 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)RULER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 36.59 | 219.54 | 1 | -5 | 0 | -219.54
4100 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SAMSUNG 55BU8570U LED | NOS | 1 | 74240 | 74240 | 0 | 0 | 0 | 0 | 74240 | 0 | 0 | 0 | 0 | 1 | 76036.61 | 76036.61 | 1 | 0 | 74240 | -1796.61
4101 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SAMSUNG GALAXY TAB A7 LITE | NOS | 1 | 13994.8 | 13994.8 | 0 | 0 | 0 | 0 | 13994.8 | 0 | 0 | 0 | 0 | 1 | 14000 | 14000 | 1 | 0 | 13994.8 | -5.2
4102 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Samsung M13 | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10749.5 | 21499 | 1 | -1 | 0 | -21499
4103 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Samsung Mobile(A03) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11400 | 11400 | 1 | 0 | 0 | -11400
4104 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Samsung Mobile(A12) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12350 | 12350 | 1 | 0 | 0 | -12350
4105 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SCISSORS | NOS | 10 | 94.4 | 944 | 6 | 94.4 | 566.4 | 1 | 94.4 | 94.4 | 6 | 53.1 | 318.6 | 16 | 89.15 | 1426.43 | 9 | -6 | 849.6 | -482.43
4106 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SERVICE CHARGES | NOS | 5 | 1817.2 | 9086 | 5 | 1817.2 | 9086 | 1 | 1817.2 | 1817.2 | 5 | 678.2 | 3391 | 5 | 970.8 | 4854 | 4 | 0 | 7268.8 | 4232
4107 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SHARPENER | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3.13 | 37.52 | 1 | -11 | 0 | -37.52
4108 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SMALL BINDER CLIP 19 MM | BOX | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 2 | 37.38 | 74.76 | 1 | -1 | 1.18 | -73.58
4109 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)SPIN MOP REFILL | PCS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 578.2 | 1156.4 | 2 | 578.2 | 1156.4 | 2 | 0 | 2.36 | -1154.04
4110 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STAMP PAD | NOS | 9 | 1.18 | 10.62 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 29.5 | 177 | 9 | 33.43 | 300.9 | 8 | 0 | 9.44 | -290.28
4111 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STAMP PAD INK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 29.5 | 59 | 1 | -1 | 0 | -59
4112 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STAPLER HP-45 | NOS | 13 | 1.18 | 15.34 | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 1 | 271.4 | 271.4 | 13 | 265.82 | 3455.65 | 12 | 0 | 14.16 | -3440.31
4113 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STAPLER NO 10 | PCS | 6 | 59 | 354 | 6 | 59 | 354 | 1 | 59 | 59 | 6 | 53.1 | 318.6 | 6 | 53.1 | 318.6 | 5 | 0 | 295 | 35.4
4114 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STAPLER PIN | PKT | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 50 | 22.89 | 1144.6 | 1 | -49 | 1.18 | -1143.42
4115 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STICKY NOTE (BIG) | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 35.4 | 35.4 | 1 | 35.4 | 35.4 | 1 | 0 | 1.18 | -34.22
4116 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)STICKY NOTE (SMALL) | NOS | 2 | 35.4 | 70.8 | 2 | 35.4 | 70.8 | 0 | 35.4 | 0 | 2 | 35.4 | 70.8 | 2 | 35.4 | 70.8 | 2 | 0 | 70.8 | 0
4117 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TCENV | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
4118 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TCENVV | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
4119 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Telephone cord | NOS | 2 | 100 | 200 | 2 | 100 | 200 | 0 | 100 | 0 | 2 | 100 | 200 | 2 | 100 | 200 | 2 | 0 | 200 | 0
4120 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Telephone splliter | NOS | 1 | 100 | 100 | 1 | 100 | 100 | 0 | 100 | 0 | 1 | 100 | 100 | 1 | 100 | 100 | 1 | 0 | 100 | 0
4121 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TISSUE ROLE | NOS | 28 | 1.18 | 33.04 | 28 | 1.18 | 33.04 | 3 | 1.18 | 3.54 | 28 | 124.74 | 3492.8 | 28 | 124.74 | 3492.8 | 25 | 0 | 29.5 | -3459.76
4122 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TOILET PAPER ROLL | NOS | 10 | 306.8 | 3068 | 10 | 306.8 | 3068 | 1 | 306.8 | 306.8 | 10 | 306.8 | 3068 | 10 | 306.8 | 3068 | 9 | 0 | 2761.2 | 0
4123 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TORK SOAP LIQ MINI WHITE DISPENSER. 561000 | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1288.31 | 1288.31 | 1 | 0 | 0 | -1288.31
4124 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TP-LINK EAP-225 INDOOR | NOS | 2 | 6490 | 12980 | 2 | 6490 | 12980 | 0 | 6490 | 0 | 2 | 6490 | 12980 | 2 | 6490 | 12980 | 2 | 0 | 12980 | 0
4125 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TRAPWELL | NOS | 1 | 955.8 | 955.8 | 0 | 0 | 0 | 0 | 955.8 | 0 | 0 | 0 | 0 | 1 | 956.01 | 956.01 | 1 | 0 | 955.8 | -0.21
4126 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)TRONE LAPTOP SLEEVE | PCS | 20 | 1062 | 21240 | 20 | 1062 | 21240 | 2 | 1062 | 2124 | 20 | 1062 | 21240 | 20 | 1062 | 21240 | 18 | 0 | 19116 | 0
4127 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)U BRACKET | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 708 | 708 | 1 | 0 | 0 | -708
4128 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)U-HEAD (18" /455 MM | NOS | 1 | 295 | 295 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 175 | 291.99 | 51098.43 | 1 | -174 | 295 | -50803.43
4129 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)UPS | NOS | 1 | 2761.2 | 2761.2 | 1 | 2761.2 | 2761.2 | 0 | 2761.2 | 0 | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 1 | 0 | 2761.2 | -306.8
4130 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)USB 3.0 EXTERNAL HDD/SSD CASING 2.5” | NOS | 1 | 885 | 885 | 1 | 885 | 885 | 0 | 885 | 0 | 1 | 885 | 885 | 1 | 885 | 885 | 1 | 0 | 885 | 0
4131 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)UVC 35B MICROPHONE | NOS | 1 | 24780 | 24780 | 1 | 24780 | 24780 | 0 | 24780 | 0 | 1 | 24780 | 24780 | 1 | 24780 | 24780 | 1 | 0 | 24780 | 0
4132 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)VISIT CHARGE | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1180 | 2360 | 1 | -1 | 0 | -2360
4133 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)VISTING CARD | NOS | 1 | 11.8 | 11.8 | 0 | 0 | 0 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11.8 | 11.8
4134 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)VOUCHER | SET | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 41.3 | 1239 | 1 | -29 | 0 | -1239
4135 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WB 12A/88A | NOS | 2 | 118 | 236 | 2 | 118 | 236 | 0 | 118 | 0 | 2 | 118 | 236 | 2 | 118 | 236 | 2 | 0 | 236 | 0
4136 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WHITE INK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25.61 | 102.45 | 1 | -3 | 0 | -102.45
4137 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)Wifi Dongle | NOS | 1 | 1475 | 1475 | 1 | 1475 | 1475 | 0 | 1475 | 0 | 1 | 1475 | 1475 | 1 | 1475 | 1475 | 1 | 0 | 1475 | 0
4138 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WIRE MOUSE | NOS | 2 | 342.2 | 684.4 | 2 | 342.2 | 684.4 | 0 | 342.2 | 0 | 2 | 342.2 | 684.4 | 2 | 342.2 | 684.4 | 2 | 0 | 684.4 | 0
4139 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WIRELESS KEYBOARD & MOUSE | NOS | 2 | 3280.4 | 6560.8 | 2 | 3280.4 | 6560.8 | 0 | 3280.4 | 0 | 2 | 1829 | 3658 | 2 | 2792.67 | 5585.33 | 2 | 0 | 6560.8 | 975.47
4140 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WIRELESS MOUSE | NOS | 17 | 1.18 | 20.06 | 12 | 1.18 | 14.16 | 2 | 1.18 | 2.36 | 12 | 782.73 | 9392.8 | 16 | 772.9 | 12366.4 | 15 | 1 | 17.7 | -12346.34
4141 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WRITING PAD | NOS | 12 | 70.8 | 849.6 | 12 | 70.8 | 849.6 | 1 | 70.8 | 70.8 | 12 | 29.5 | 354 | 12 | 29.5 | 354 | 11 | 0 | 778.8 | 495.6
4142 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)WRITING PAD (BIG) | NOS | 12 | 118 | 1416 | 12 | 118 | 1416 | 1 | 118 | 118 | 12 | 112.1 | 1345.2 | 12 | 112.1 | 1345.2 | 11 | 0 | 1298 | 70.8
4143 | ADMIN EXPENSES - Head Office Expenses | 10 | Started | Material | (M)XEROX PAPER | PKT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 260.46 | 15627.5 | 1 | -59 | 0 | -15627.5
4144 | ADMIN EXPENSES - HO Expenses | 10 | Started | Labour | (L)Autocad Including Specialised With AMC | NOS | 2 | 94400 | 188800 | 0 | 0 | 0 | 0 | 94400 | 0 | 2 | 92040 | 184080 | 1 | 86140 | 86140 | 2 | 1 | 188800 | 102660
4145 | ADMIN EXPENSES - HO Expenses | 10 | Started | Labour | (L)HEAD OFFICE MAINTENACE CHARGES - INFINITY | NOS | 375000 | 1.18 | 442500 | 0 | 0 | 0 | 37500 | 1.18 | 44250 | 375000 | 1.18 | 442500 | 236889.75 | 1.18 | 279529.91 | 337500 | 138110.25 | 398250 | 162970.09
4146 | ADMIN EXPENSES - HO Expenses | 10 | Started | Labour | (L)HO and Admin Expenses | NOS | 900000 | 1.18 | 1062000 | 0 | 0 | 0 | 90000 | 1.18 | 106200 | 900000 | 1.18 | 1062000 | 50433.5 | 1.15 | 58118.34 | 810000 | 849566.5 | 955800 | 1003881.66
4147 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)1. XEROX PAPER A/4 75 GSM (COPY POWER) | PKT | 30 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 212.13 | 6363.84 | 27 | 0 | 0 | -6363.84
4148 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)10 MM CHINA CLIP | PKT | 1 | 245.01 | 245.01 | 0 | 0 | 0 | 0 | 245.01 | 0 | 0 | 0 | 0 | 1 | 289.1 | 289.1 | 1 | 0 | 245.01 | -44.09
4149 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)10 mm SIEVE | NOS | 1 | 826 | 826 | 0 | 0 | 0 | 0 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 826 | 826
4150 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)15 MM BINDER CLIPS | BOX | 10 | 33.04 | 330.4 | 10 | 33.04 | 330.4 | 1 | 33.04 | 33.04 | 10 | 18.88 | 188.8 | 10 | 18.88 | 188.8 | 9 | 0 | 297.36 | 141.6
4151 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)32mm BINDER CLIP | PKT | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 1 | 1.18 | 1.18 | 6 | 57.82 | 346.92 | 6 | 57.82 | 346.92 | 5 | 0 | 5.9 | -339.84
4152 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)41 MM BINDER CLIP | BOX | 6 | 181.72 | 1090.32 | 6 | 181.72 | 1090.32 | 1 | 181.72 | 181.72 | 6 | 88.5 | 531 | 6 | 88.5 | 531 | 5 | 0 | 908.6 | 559.32
4153 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)A3 PAPER | PKT | 2 | 683.2 | 1366.4 | 2 | 683.2 | 1366.4 | 0 | 683.2 | 0 | 2 | 728 | 1456 | 2 | 728 | 1456 | 2 | 0 | 1366.4 | -89.6
4154 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)A4 BOND PAPER | PKT | 3 | 660.8 | 1982.4 | 3 | 660.8 | 1982.4 | 0 | 660.8 | 0 | 3 | 386.4 | 1159.2 | 3 | 386.4 | 1159.2 | 3 | 0 | 1982.4 | 823.2
4155 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)A4 size Paper | PKT | 80 | 291.2 | 23296 | 80 | 291.2 | 23296 | 8 | 291.2 | 2329.6 | 80 | 264.88 | 21190.4 | 80 | 264.88 | 21190.4 | 72 | 0 | 20966.4 | 2105.6
4156 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Alpin (T Pin) | BOX | 5 | 47.2 | 236 | 5 | 47.2 | 236 | 1 | 47.2 | 47.2 | 5 | 41.3 | 206.5 | 5 | 41.3 | 206.5 | 4 | 0 | 188.8 | 29.5
4157 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Arch file (Big) | PCS | 30 | 106.2 | 3186 | 30 | 106.2 | 3186 | 3 | 106.2 | 318.6 | 30 | 98.88 | 2966.52 | 30 | 98.88 | 2966.52 | 27 | 0 | 2867.4 | 219.48
4158 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)ARCH FILE (SMALL) | NOS | 12 | 94.4 | 1132.8 | 12 | 94.4 | 1132.8 | 1 | 94.4 | 94.4 | 12 | 96.76 | 1161.12 | 12 | 96.76 | 1161.12 | 11 | 0 | 1038.4 | -28.32
4159 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BATTERY(UPS) | NOS | 2 | 1156.4 | 2312.8 | 2 | 1156.4 | 2312.8 | 0 | 1156.4 | 0 | 2 | 1248 | 2496 | 2 | 1248 | 2496 | 2 | 0 | 2312.8 | -183.2
4160 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BLACK PEN | NOS | 20 | 1.18 | 23.6 | 20 | 1.18 | 23.6 | 2 | 1.18 | 2.36 | 20 | 4.72 | 94.4 | 20 | 4.72 | 94.4 | 18 | 0 | 21.24 | -70.8
4161 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BLUE PEN | NOS | 40 | 1.18 | 47.2 | 40 | 1.18 | 47.2 | 4 | 1.18 | 4.72 | 40 | 4.01 | 160.48 | 40 | 4.01 | 160.48 | 36 | 0 | 42.48 | -113.28
4162 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BOTTLE INK BLACK COLOUR | NOS | 1 | 802.4 | 802.4 | 1 | 802.4 | 802.4 | 0 | 802.4 | 0 | 1 | 796.5 | 796.5 | 1 | 796.5 | 796.5 | 1 | 0 | 802.4 | 5.9
4163 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BOTTLE INK CYAN COLOUR | NOS | 1 | 660.8 | 660.8 | 1 | 660.8 | 660.8 | 0 | 660.8 | 0 | 1 | 678.5 | 678.5 | 1 | 678.5 | 678.5 | 1 | 0 | 660.8 | -17.7
4164 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BOTTLE INK MAGENTA COLOUR | NOS | 1 | 660.8 | 660.8 | 1 | 660.8 | 660.8 | 0 | 660.8 | 0 | 1 | 678.5 | 678.5 | 1 | 678.5 | 678.5 | 1 | 0 | 660.8 | -17.7
4165 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)BOTTLE INK YELLOW COLOUR | NOS | 1 | 660.8 | 660.8 | 1 | 660.8 | 660.8 | 0 | 660.8 | 0 | 1 | 678.5 | 678.5 | 1 | 678.5 | 678.5 | 1 | 0 | 660.8 | -17.7
4166 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)CALCULATOR | NOS | 2 | 224.2 | 448.4 | 2 | 224.2 | 448.4 | 0 | 224.2 | 0 | 2 | 295 | 590 | 2 | 295 | 590 | 2 | 0 | 448.4 | -141.6
4167 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Card | NOS | 500 | 8.86 | 4430 | 500 | 8.86 | 4430 | 50 | 8.86 | 443 | 500 | 8.85 | 4425 | 500 | 8.85 | 4425 | 450 | 0 | 3987 | 5
4168 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)CASING 2.5" HDD | NOS | 1 | 2950 | 2950 | 1 | 2950 | 2950 | 0 | 2950 | 0 | 1 | 767 | 767 | 1 | 767 | 767 | 1 | 0 | 2950 | 2183
4169 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)CELLO TAPE 1'' | NOS | 12 | 29.5 | 354 | 12 | 29.5 | 354 | 1 | 29.5 | 29.5 | 12 | 12.39 | 148.68 | 12 | 12.39 | 148.68 | 11 | 0 | 324.5 | 205.32
4170 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)COBRA BOARD FILE | NOS | 24 | 35.4 | 849.6 | 24 | 35.4 | 849.6 | 2 | 35.4 | 70.8 | 24 | 29.5 | 708 | 24 | 29.5 | 708 | 22 | 0 | 778.8 | 141.6
4171 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)CONFERENCE FOLDER | NOS | 200 | 167.56 | 33512 | 200 | 167.56 | 33512 | 20 | 167.56 | 3351.2 | 200 | 167.56 | 33512 | 200 | 167.56 | 33512 | 180 | 0 | 30160.8 | 0
4172 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)DB 36A/88A/328A | NOS | 3 | 118 | 354 | 3 | 118 | 354 | 0 | 118 | 0 | 3 | 118 | 354 | 3 | 118 | 354 | 3 | 0 | 354 | 0
4173 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)DESKTOP | NOS | 1 | 32697.8 | 32697.8 | 1 | 32697.8 | 32697.8 | 0 | 32697.8 | 0 | 1 | 16520 | 16520 | 6 | 29392.73 | 176356.36 | 1 | -5 | 32697.8 | -143658.56
4174 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)DRUM | NOS | 7 | 236 | 1652 | 7 | 236 | 1652 | 1 | 236 | 236 | 7 | 252.86 | 1770 | 7 | 252.86 | 1770 | 6 | 0 | 1416 | -118
4175 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)DUSTER | PICS | 26 | 21 | 546 | 26 | 21 | 546 | 3 | 21 | 63 | 26 | 21.65 | 562.8 | 26 | 21.65 | 562.8 | 23 | 0 | 483 | -16.8
4176 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)GLUE STICK | NOS | 6 | 35.4 | 212.4 | 6 | 35.4 | 212.4 | 1 | 35.4 | 35.4 | 6 | 28.32 | 169.92 | 6 | 28.32 | 169.92 | 5 | 0 | 177 | 42.48
4177 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)HDD 8TB INTERNAL | NOS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 20178 | 20178 | 1 | 20178 | 20178 | 1 | 0 | 1 | -20177
4178 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)HDMI CABLE . | NOS | 2 | 472 | 944 | 2 | 472 | 944 | 0 | 472 | 0 | 2 | 295 | 590 | 2 | 295 | 590 | 2 | 0 | 944 | 354
4179 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)HP 88A TONNER | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 265.5 | 1062 | 4 | 265.5 | 1062 | 4 | 0 | 4.72 | -1057.28
4180 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Inserter | NOS | 96000 | 1.41 | 135360 | 96000 | 1.41 | 135360 | 9600 | 1.41 | 13536 | 96000 | 1.4 | 134803.2 | 96000 | 1.4 | 134803.2 | 86400 | 0 | 121824 | 556.8
4181 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)LAPTOP | NOS | 1 | 34869 | 34869 | 1 | 34869 | 34869 | 0 | 34869 | 0 | 1 | 41300 | 41300 | 1 | 41300 | 41300 | 1 | 0 | 34869 | -6431
4182 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)LAPTOP ADAPTER | NOS | 2 | 2018.98 | 4037.96 | 2 | 2018.98 | 4037.96 | 0 | 2018.98 | 0 | 2 | 1666.75 | 3333.5 | 2 | 1666.75 | 3333.5 | 2 | 0 | 4037.96 | 704.46
4183 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Laptop Adaptor (AC 45W) | NOS | 1 | 2183 | 2183 | 0 | 0 | 0 | 0 | 2183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2183 | 2183
4184 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)LAPTOP SCREEN CHANGE | NOS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 6667 | 6667 | 1 | 6667 | 6667 | 1 | 0 | 1 | -6666
4185 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)MAGNET | NOS | 5 | 106.2 | 531 | 5 | 106.2 | 531 | 1 | 106.2 | 106.2 | 5 | 118 | 590 | 5 | 118 | 590 | 4 | 0 | 424.8 | -59
4186 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)METAL POCKET BADGES | NOS | 4 | 150 | 600 | 4 | 150 | 600 | 0 | 150 | 0 | 4 | 150 | 600 | 4 | 150 | 600 | 4 | 0 | 600 | 0
4187 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Mobile Charger | NOS | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 0 | 1416 | 0 | 1 | 1299.99 | 1299.99 | 1 | 1299.99 | 1299.99 | 1 | 0 | 1416 | 116.01
4188 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Mobile Phone | NOS | 5 | 11823.6 | 59118 | 5 | 11823.6 | 59118 | 1 | 11823.6 | 11823.6 | 5 | 31400 | 157000.02 | 5 | 31400.01 | 157000.04 | 4 | 0 | 47294.4 | -97882.04
4189 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)MONITOR | NOS | 1 | 22951 | 22951 | 1 | 22951 | 22951 | 0 | 22951 | 0 | 1 | 5782 | 5782 | 1 | 5782 | 5782 | 1 | 0 | 22951 | 17169
4190 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)MS O365 | NOS | 1 | 5935.4 | 5935.4 | 1 | 5935.4 | 5935.4 | 0 | 5935.4 | 0 | 1 | 6136 | 6136 | 1 | 6136 | 6136 | 1 | 0 | 5935.4 | -200.6
4191 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)NOTE PAD | NOS | 12 | 23.6 | 283.2 | 12 | 23.6 | 283.2 | 1 | 23.6 | 23.6 | 12 | 18.88 | 226.56 | 12 | 18.88 | 226.56 | 11 | 0 | 259.6 | 56.64
4192 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Notepad (6 No.) | NOS | 6 | 29.5 | 177 | 6 | 29.5 | 177 | 1 | 29.5 | 29.5 | 6 | 53.1 | 318.6 | 6 | 53.1 | 318.6 | 5 | 0 | 147.5 | -141.6
4193 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)PCR | NOS | 3 | 118 | 354 | 3 | 118 | 354 | 0 | 118 | 0 | 3 | 118 | 354 | 3 | 118 | 354 | 3 | 0 | 354 | 0
4194 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)PENCIL. | PKT | 1 | 47.2 | 47.2 | 1 | 47.2 | 47.2 | 0 | 47.2 | 0 | 1 | 41.3 | 41.3 | 1 | 41.3 | 41.3 | 1 | 0 | 47.2 | 5.9
4195 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)PENDRIVE | NOS | 2 | 1062 | 2124 | 2 | 1062 | 2124 | 0 | 1062 | 0 | 2 | 1162.3 | 2324.6 | 2 | 1162.3 | 2324.6 | 2 | 0 | 2124 | -200.6
4196 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Plain Envolopes | NOS | 50 | 35.4 | 1770 | 50 | 35.4 | 1770 | 5 | 35.4 | 177 | 50 | 35.4 | 1770 | 50 | 35.4 | 1770 | 45 | 0 | 1593 | 0
4197 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)PLASTIC BUTTON FOLDER | PCS | 72 | 47.2 | 3398.4 | 72 | 47.2 | 3398.4 | 7 | 47.2 | 330.4 | 72 | 31.07 | 2237.28 | 72 | 31.07 | 2237.28 | 65 | 0 | 3068 | 1161.12
4198 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Power Supply Board | NOS | 1 | 2124 | 2124 | 1 | 2124 | 2124 | 0 | 2124 | 0 | 1 | 2124 | 2124 | 1 | 2124 | 2124 | 1 | 0 | 2124 | 0
4199 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Printer parts pick up roller change | NOS | 1 | 472 | 472 | 1 | 472 | 472 | 0 | 472 | 0 | 1 | 413 | 413 | 1 | 413 | 413 | 1 | 0 | 472 | 59
4200 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Printer reparing and servicing | NOS | 1 | 495.6 | 495.6 | 1 | 495.6 | 495.6 | 0 | 495.6 | 0 | 1 | 472 | 472 | 1 | 472 | 472 | 1 | 0 | 495.6 | 23.6
4201 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)REFILLING OF TONER | NOS | 20 | 271.4 | 5428 | 5 | 271.4 | 1357 | 2 | 271.4 | 542.8 | 5 | 265.5 | 1327.5 | 5 | 265.5 | 1327.5 | 18 | 15 | 4885.2 | 4100.5
4202 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Refilling of toner 337A | NOS | 26 | 271.4 | 7056.4 | 26 | 271.4 | 7056.4 | 3 | 271.4 | 814.2 | 26 | 265.5 | 6903 | 26 | 265.5 | 6903 | 23 | 0 | 6242.2 | 153.4
4203 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)Scroll Card | NOS | 125 | 66.08 | 8260 | 125 | 66.08 | 8260 | 13 | 66.08 | 859.04 | 125 | 66.08 | 8260 | 125 | 66.08 | 8260 | 112 | 0 | 7400.96 | 0
4204 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)SERVICE CHARGES | NOS | 3 | 1817.2 | 5451.6 | 3 | 1817.2 | 5451.6 | 0 | 1817.2 | 0 | 3 | 550.67 | 1652 | 0 | 0 | 0 | 3 | 3 | 5451.6 | 5451.6
4205 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)SMALL BINDER CLIP 19 MM | BOX | 10 | 1.18 | 11.8 | 10 | 1.18 | 11.8 | 1 | 1.18 | 1.18 | 10 | 25.96 | 259.6 | 10 | 25.96 | 259.6 | 9 | 0 | 10.62 | -247.8
4206 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)SSD Drive | NOS | 2 | 1770 | 3540 | 2 | 1770 | 3540 | 0 | 1770 | 0 | 2 | 4454.5 | 8909 | 1 | 3127 | 3127 | 2 | 1 | 3540 | 413
4207 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)STAPLER NO 10 | PCS | 12 | 59 | 708 | 12 | 59 | 708 | 1 | 59 | 59 | 12 | 53.69 | 644.28 | 12 | 53.69 | 644.28 | 11 | 0 | 649 | 63.72
4208 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)TISSUE ROLE | NOS | 24 | 1.18 | 28.32 | 24 | 1.18 | 28.32 | 2 | 1.18 | 2.36 | 24 | 23.6 | 566.4 | 24 | 23.6 | 566.4 | 22 | 0 | 25.96 | -538.08
4209 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)TOILET PAPER ROLL | NOS | 10 | 306.8 | 3068 | 10 | 306.8 | 3068 | 1 | 306.8 | 306.8 | 10 | 377.6 | 3776 | 10 | 377.6 | 3776 | 9 | 0 | 2761.2 | -708
4210 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)WB 36A/88A | NOS | 2 | 118 | 236 | 2 | 118 | 236 | 0 | 118 | 0 | 2 | 118 | 236 | 2 | 118 | 236 | 2 | 0 | 236 | 0
4211 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)WHITENER PEN | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 33.04 | 132.16 | 4 | 33.04 | 132.16 | 4 | 0 | 4.72 | -127.44
4212 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)WINDOWS 10 HOME | NOS | 1 | 8496 | 8496 | 1 | 8496 | 8496 | 0 | 8496 | 0 | 1 | 8496 | 8496 | 1 | 8496 | 8496 | 1 | 0 | 8496 | 0
4213 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)WIRELESS ADAPTER | NOS | 3 | 1416 | 4248 | 3 | 1416 | 4248 | 0 | 1416 | 0 | 3 | 1200 | 3600.0099 | 3 | 1200 | 3600.01 | 3 | 0 | 4248 | 647.99
4214 | ADMIN EXPENSES - HO Expenses | 10 | Started | Material | (M)WIRELESS MOUSE | NOS | 5 | 1.18 | 5.9 | 5 | 1.18 | 5.9 | 1 | 1.18 | 1.18 | 5 | 743.4 | 3717 | 5 | 743.4 | 3717 | 4 | 0 | 4.72 | -3711.1
4215 | ADMIN EXPENSES - Legal Expenses | 0 | Started | Labour | (L)Advocate Fees and Legal Expenses | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 358200 | 358200 | 1 | 358200 | 358200 | 1 | 0 | 1 | -358199
4216 | COMPANY EXPENSES - Gift Purpose | 0 | Started | Labour | (L)Gift Distribution on Special Occasions | NOS | 46500 | 1 | 46500 | 0 | 0 | 0 | 0 | 1 | 0 | 46500 | 1 | 46500 | 46500 | 1 | 46500 | 46500 | 0 | 46500 | 0
4217 | COMPANY EXPENSES - Gift Purpose | 0 | Started | Material | (M)APPLE AIRPODS-3 | SET | 1 | 19505.4 | 19505.4 | 1 | 19505.4 | 19505.4 | 0 | 19505.4 | 0 | 1 | 19500 | 19500 | 0 | 0 | 0 | 1 | 1 | 19505.4 | 19505.4
4218 | COMPANY EXPENSES - Gift Purpose | 0 | Started | Material | (M)APPLE I-PH-14 128GB | SET | 1 | 72499.2 | 72499.2 | 1 | 72499.2 | 72499.2 | 0 | 72499.2 | 0 | 1 | 72500 | 72500 | 0 | 0 | 0 | 1 | 1 | 72499.2 | 72499.2
4219 | COMPANY EXPENSES - Gift Purpose | 0 | Started | Material | (M)I- PAD 64GB | SET | 1 | 43494.8 | 43494.8 | 1 | 43494.8 | 43494.8 | 0 | 43494.8 | 0 | 1 | 43500.01 | 43500.01 | 0 | 0 | 0 | 1 | 1 | 43494.8 | 43494.8
4220 | COMPANY EXPENSES - Professional Fees | 0 | Started | Labour | (L)Professional Charges | LS | 4 | 107510.98 | 430043.92 | 0 | 0 | 0 | 0 | 107510.98 | 0 | 4 | 45555.5 | 182222 | 4 | 45555.5 | 182222 | 4 | 0 | 430043.92 | 247821.92
4221 | COMPANY EXPENSES - Professional Fees | 0 | Started | Labour | (L)Professional Charges for Issue of Form-6 RERA | LS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
4222 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage - Akansha Advisory | NOS | 1 | 38794.86 | 38794.86 | 0 | 0 | 0 | 0 | 38794.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 38794.86 | 38794.86 | Admin
4223 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage - Ambika Sarees | NOS | 1 | 38794.86 | 38794.86 | 0 | 0 | 0 | 0 | 38794.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 38794.86 | 38794.86 | Admin
4224 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage - Manoj Anand | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18 | Admin
4225 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage - Poonam Pharma | NOS | 1 | 104745.06 | 104745.06 | 0 | 0 | 0 | 0 | 104745.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 104745.06 | 104745.06 | Admin
4226 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage- Amit Kr. Sethi | LS | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 1 | 1 | 1000000 | 1000000 | Admin
4227 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage- Const. Fin. from Bajaj Housing | LS | 1 | 1180000 | 1180000 | 0 | 0 | 0 | 0 | 1180000 | 0 | 1 | 1180000 | 1180000 | 0 | 0 | 0 | 1 | 1 | 1180000 | 1180000 | Admin
4228 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage- Vinsar Advisory | LS | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 1 | 1 | 1000000 | 1000000 | Admin
4229 | FINANCE CHARGES - Financial Brokerage | 0 | Started | Labour | (L)Financial Brokerage-Manoj Kr. Meharia | LS | 1 | 25000 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 1 | 0 | 25000 | 0 | Admin
4230 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)250/230/200 MM BRICK WORK | CUM | 7 | 700 | 4900 | 0 | 0 | 0 | 0 | 700 | 0 | 6.79 | 700 | 4753 | 6.79 | 700 | 4753 | 7 | 0.21 | 4900 | 147
4231 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Calibration Charges for 01 no. FIP & 06 nos. Injector | NOS | 2 | 23600 | 47200 | 0 | 0 | 0 | 0 | 23600 | 0 | 2 | 23600 | 47200 | 2 | 23600 | 47200 | 2 | 0 | 47200 | 0
4232 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Erection S/C of passenger Rack & Pinion for Mat. Hoist | DAYS | 7 | 3540 | 24780 | 0 | 0 | 0 | 0 | 3540 | 0 | 7 | 3540 | 24780 | 0 | 0 | 0 | 7 | 7 | 24780 | 24780
4233 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)L/C for Repairing Baby Mixer Machine | LS | 1 | 10856 | 10856 | 0 | 0 | 0 | 0 | 10856 | 0 | 1 | 9200 | 9200 | 1 | 9200 | 9200 | 1 | 0 | 10856 | 1656
4234 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)LABOUR CHARGES FOR RMC CONCRETING | CUM | 4 | 200.6 | 802.4 | 0 | 0 | 0 | 0 | 200.6 | 0 | 4 | 150 | 600 | 4 | 150 | 600 | 4 | 0 | 802.4 | 202.4
4235 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Main Alternator Heat Varnishing | JOB | 1 | 21240 | 21240 | 0 | 0 | 0 | 0 | 21240 | 0 | 1 | 21240 | 21240 | 1 | 21240 | 21240 | 1 | 0 | 21240 | 0
4236 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)PLY SHUTTERING, BOARD MAKING, DE- SHUTTERING SUB-STR.& FDN. | SQM | 3.15 | 295 | 929.25 | 0 | 0 | 0 | 0 | 295 | 0 | 3.06 | 257.5 | 787.95 | 3.06 | 257.5 | 787.95 | 3.15 | 0.09 | 929.25 | 141.3
4237 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)REINFORCEMENT WORK | MT | 0.11 | 4248 | 467.28 | 0 | 0 | 0 | 0 | 4248 | 0 | 0.102 | 5250 | 535.5 | 0.102 | 5250 | 535.5 | 0.11 | 0.008 | 467.28 | -68.22
4238 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Repair of 100 KG Digital Balance | LS | 1 | 4838 | 4838 | 0 | 0 | 0 | 0 | 4838 | 0 | 1 | 4100 | 4100 | 1 | 4100 | 4100 | 1 | 0 | 4838 | 738
4239 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Repair work of IT Related | NOS | 1 | 2065 | 2065 | 0 | 0 | 0 | 0 | 2065 | 0 | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 1 | 0 | 2065 | 0
4240 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)S/C for erection of Rack & Pinion for Mat. Hoist | MTR | 45 | 1416 | 63720 | 0 | 0 | 0 | 0 | 1416 | 0 | 45 | 1416 | 63720 | 0 | 0 | 0 | 45 | 45 | 63720 | 63720
4241 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)S/C for rectification in Safety Ext. Bracket | LS | 1 | 59000 | 59000 | 0 | 0 | 0 | 0 | 59000 | 0 | 1 | 59000 | 59000 | 0 | 0 | 0 | 1 | 1 | 59000 | 59000
4242 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Service Charges (Fuel Tank Removal/Fitting/Cleaning) | NOS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
4243 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Service Charges for Bar Bending Mach. (Pin) repair | NOS | 4 | 2183 | 8732 | 0 | 0 | 0 | 0 | 2183 | 0 | 4 | 2183 | 8732 | 0 | 0 | 0 | 4 | 4 | 8732 | 8732
4244 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Labour | (L)Service Charges-6R1080TA DG Set Oil Service & Primary Check | NOS | 1 | 3540 | 3540 | 0 | 0 | 0 | 0 | 3540 | 0 | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 1 | 0 | 3540 | 0
4245 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" BALL VALVE | NOS | 1 | 701.52 | 701.52 | 1 | 701.52 | 701.52 | 0 | 701.52 | 0 | 1 | 701.05 | 701.05 | 1 | 693.95 | 693.95 | 1 | 0 | 701.52 | 7.57
4246 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" CHINA CLAMP | NOS | 60 | 11.8 | 708 | 60 | 11.8 | 708 | 0 | 11.8 | 0 | 60 | 12.01 | 720.6 | 60 | 11.88 | 713.02 | 60 | 0 | 708 | -5.02
4247 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" ELBOW (UPVC) | NOS | 4 | 82.6 | 330.4 | 4 | 82.6 | 330.4 | 0 | 82.6 | 0 | 4 | 70.86 | 283.42 | 4 | 70.14 | 280.57 | 4 | 0 | 330.4 | 49.83
4248 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" PIPE | NOS | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 0
4249 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" SOCKET (UPVC) | NOS | 18 | 35.4 | 637.2 | 18 | 35.4 | 637.2 | 0 | 35.4 | 0 | 18 | 42.97 | 773.46 | 18 | 42.53 | 765.56 | 18 | 0 | 637.2 | -128.36
4250 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" SUCTION PIPE | FT | 30 | 59 | 1770 | 30 | 59 | 1770 | 0 | 59 | 0 | 30 | 59 | 1770 | 30 | 59 | 1770 | 30 | 0 | 1770 | 0
4251 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" TEE | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 323.51 | 323.51 | 1 | 320.24 | 320.24 | 1 | 0 | 1.18 | -319.06
4252 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)2" X 3" SHORT PIC | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 73.11 | 73.11 | 1 | 72.37 | 72.37 | 1 | 0 | 1.18 | -71.19
4253 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)3" FOOT VALVE JOINING SOCKET | NOS | 1 | 826 | 826 | 1 | 826 | 826 | 0 | 826 | 0 | 1 | 826 | 826 | 1 | 826 | 826 | 1 | 0 | 826 | 0
4254 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)3" NIPPLE | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 424.8 | 424.8 | 1 | 424.8 | 424.8 | 1 | 0 | 1.18 | -423.62
4255 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)3" SUCTION PIPE | FT | 60 | 283.2 | 16992 | 60 | 283.2 | 16992 | 0 | 283.2 | 0 | 60 | 283.2 | 16992 | 60 | 283.2 | 16992 | 60 | 0 | 16992 | 0
4256 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 AMP 4 POLE RCCB | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 2223.64 | 4447.28 | 2 | 2214.5 | 4429 | 2 | 0 | 2.36 | -4426.64
4257 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 AMP 4 POLE RCCB COVER BOX | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 529.11 | 1058.22 | 2 | 526.93 | 1053.86 | 2 | 0 | 2.36 | -1051.5
4258 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM BARREL PIPE | NOS | 3 | 318.6 | 955.8 | 2 | 318.6 | 637.2 | 0 | 318.6 | 0 | 2 | 346.71 | 693.42 | 2 | 344.21 | 688.42 | 3 | 1 | 955.8 | 267.38
4259 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM JOIN SOCKET | NOS | 7 | 153.4 | 1073.8 | 6 | 153.4 | 920.4 | 0 | 153.4 | 0 | 6 | 210.5 | 1263 | 6 | 128.73 | 772.4 | 7 | 1 | 1073.8 | 301.4
4260 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM NOZZEL BEARING | NOS | 5 | 141.6 | 708 | 4 | 141.6 | 566.4 | 0 | 141.6 | 0 | 4 | 185.74 | 742.96 | 4 | 184.4 | 737.59 | 5 | 1 | 708 | -29.59
4261 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM NOZZEL END (CHERA) NTIVE | NOS | 6 | 1.18 | 7.08 | 5 | 1.18 | 5.9 | 0 | 1.18 | 0 | 5 | 43.34 | 216.7 | 5 | 43.03 | 215.13 | 6 | 1 | 7.08 | -208.05
4262 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM NOZZEL HEAD | NOS | 3 | 141.6 | 424.8 | 2 | 141.6 | 283.2 | 0 | 141.6 | 0 | 2 | 148.59 | 297.18 | 2 | 147.52 | 295.04 | 3 | 1 | 424.8 | 129.76
4263 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM NOZZEL OIL SEAL | NOS | 7 | 23.6 | 165.2 | 6 | 23.6 | 141.6 | 0 | 23.6 | 0 | 6 | 7.43 | 44.58 | 6 | 7.38 | 44.26 | 7 | 1 | 165.2 | 120.94
4264 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM NOZZEL ROTER | NOS | 3 | 318.6 | 955.8 | 2 | 318.6 | 637.2 | 0 | 318.6 | 0 | 2 | 346.71 | 693.42 | 2 | 344.21 | 688.42 | 3 | 1 | 955.8 | 267.38
4265 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM NOZZEL ROTER END TIP | NOS | 6 | 23.6 | 141.6 | 5 | 23.6 | 118 | 0 | 23.6 | 0 | 5 | 18.57 | 92.85 | 5 | 18.44 | 92.2 | 6 | 1 | 141.6 | 49.4
4266 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)40 MM VIBRATOR NOZZLE | NOS | 2 | 2867.4 | 5734.8 | 2 | 2867.4 | 5734.8 | 0 | 2867.4 | 0 | 2 | 3095.59 | 6191.18 | 2 | 3073.31 | 6146.62 | 2 | 0 | 5734.8 | -411.82
4267 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)50 MM UPVC PIPE SCH-80 (3 mtr length) | NOS | 17 | 696.2 | 11835.4 | 17 | 696.2 | 11835.4 | 0 | 696.2 | 0 | 17 | 735.94 | 12511.0599 | 17 | 728.48 | 12384.24 | 17 | 0 | 11835.4 | -548.84
4268 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)6" X 10'0"X 8 MM THICK SHERA BOARD | NOS | 175 | 70.8 | 12390 | 175 | 70.8 | 12390 | 0 | 70.8 | 0 | 175 | 73.16 | 12803 | 120 | 72.44 | 8692.42 | 175 | 55 | 12390 | 3697.58
4269 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM BARREL PIPE | NOS | 2 | 472 | 944 | 2 | 472 | 944 | 0 | 472 | 0 | 2 | 433.38 | 866.76 | 2 | 430.27 | 860.53 | 2 | 0 | 944 | 83.47
4270 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM JOIN SOCKET | NOS | 6 | 153.4 | 920.4 | 6 | 153.4 | 920.4 | 0 | 153.4 | 0 | 6 | 210.5 | 1263 | 12 | 128.73 | 1544.8 | 6 | -6 | 920.4 | -624.4
4271 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM NOZZEL BEARING | NOS | 4 | 177 | 708 | 4 | 177 | 708 | 0 | 177 | 0 | 4 | 198.12 | 792.48 | 4 | 196.69 | 786.77 | 4 | 0 | 708 | -78.77
4272 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM NOZZEL END (CHERA) NTIVE | NOS | 5 | 1.18 | 5.9 | 5 | 1.18 | 5.9 | 0 | 1.18 | 0 | 5 | 43.34 | 216.7 | 5 | 43.03 | 215.13 | 5 | 0 | 5.9 | -209.23
4273 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM NOZZEL HEAD | NOS | 2 | 295 | 590 | 2 | 295 | 590 | 0 | 295 | 0 | 2 | 309.56 | 619.12 | 2 | 307.33 | 614.66 | 2 | 0 | 590 | -24.66
4274 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM NOZZEL OIL SEAL | NOS | 6 | 23.6 | 141.6 | 6 | 23.6 | 141.6 | 0 | 23.6 | 0 | 6 | 12.38 | 74.28 | 6 | 12.29 | 73.76 | 6 | 0 | 141.6 | 67.84
4275 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM NOZZEL ROTER | NOS | 2 | 483.8 | 967.6 | 2 | 483.8 | 967.6 | 0 | 483.8 | 0 | 2 | 458.15 | 916.3 | 2 | 454.85 | 909.7 | 2 | 0 | 967.6 | 57.9
4276 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM NOZZEL ROTER END TIP | NOS | 5 | 23.6 | 118 | 5 | 23.6 | 118 | 0 | 23.6 | 0 | 5 | 18.57 | 92.85 | 5 | 18.44 | 92.2 | 5 | 0 | 118 | 25.8
4277 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)60 MM VIBRATOR NOZZLE | NOS | 2 | 3304 | 6608 | 2 | 3304 | 6608 | 0 | 3304 | 0 | 2 | 3714.71 | 7429.42 | 2 | 3687.97 | 7375.94 | 2 | 0 | 6608 | -767.94
4278 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)ADAPTOR 12V2AMP | NOS | 1 | 767 | 767 | 1 | 767 | 767 | 0 | 767 | 0 | 1 | 1593 | 1593 | 1 | 1593 | 1593 | 1 | 0 | 767 | -826
4279 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)AIR FILTER OUTER | LOT | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
4280 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Air Filter Outer. | NOS | 1 | 3417.28 | 3417.28 | 1 | 3417.28 | 3417.28 | 0 | 3417.28 | 0 | 1 | 2896 | 2896 | 1 | 2896 | 2896 | 1 | 0 | 3417.28 | 521.28
4281 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)BOLT ASSEMBLY FOR WALL MTG. BRACKET | NOS | 24 | 601.8 | 14443.2 | 0 | 0 | 0 | 0 | 601.8 | 0 | 0 | 0 | 0 | 24 | 501.81 | 12043.32 | 24 | 0 | 14443.2 | 2399.88
4282 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)BOLT ASSEMBLY FOR WALL TIE MTG | NOS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 551.75 | 3310.48 | 6 | 0 | 0 | -3310.48
4283 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)BOLT ASSEMBLY FOR WALL TIE MTG NUT | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 91.96 | 1103.49 | 12 | 0 | 0 | -1103.49
4284 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)BOLT ASSEMBLY FOR WALL TIE MTG PLAIN WASHER | NOS | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 43.56 | 1045.42 | 24 | 0 | 0 | -1045.42
4285 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)BOLT ASSEMBLY FOR WALL TIE MTG RING WASHER | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 44.53 | 534.33 | 12 | 0 | 0 | -534.33
4286 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CABLE ARM ASSEMBLY | NOS | 1 | 16944.8 | 16944.8 | 0 | 0 | 0 | 0 | 16944.8 | 0 | 0 | 0 | 0 | 1 | 14129.25 | 14129.25 | 1 | 0 | 16944.8 | 2815.55
4287 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CENTER PUNCH | NOS | 1 | 70.8 | 70.8 | 1 | 70.8 | 70.8 | 0 | 70.8 | 0 | 1 | 74.29 | 74.29 | 1 | 73.76 | 73.76 | 1 | 0 | 70.8 | -2.96
4288 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CHAIN PULLEY | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9613.22 | 9613.22 | 1 | 0 | 0 | -9613.22
4289 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CHAJA BRACKET /SLAB BRACKET MS 40 X40 X 3 MM | NOS | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1184.55 | 119639.5 | 101 | 0 | 0 | -119639.5
4290 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CLAMP JOINING | NOS | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 522.71 | 28226.23 | 54 | 0 | 0 | -28226.23
4291 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CUP TENSION CLAMP DN150 | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2889.77 | 5779.54 | 1 | -1 | 0 | -5779.54
4292 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)CUP TENSION COUPLING DN125 | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 2445.74 | 205441.74 | 1 | -83 | 0 | -205441.74
4293 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)DRIVING PINIONS | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 19186.66 | 38373.32 | 1 | -1 | 0 | -38373.32
4294 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)ELBOW | NOS | 5 | 1.18 | 5.9 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 713.9 | 713.9 | 1 | 713.9 | 713.9 | 5 | 4 | 5.9 | -708
4295 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)FERROSEAL- MILD STEEL ELECTRODE 3.15 MM | PKT | 7 | 460.2 | 3221.4 | 7 | 460.2 | 3221.4 | 0 | 460.2 | 0 | 7 | 466.1 | 3262.7 | 1 | 468.42 | 468.42 | 7 | 6 | 3221.4 | 2752.98
4296 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)FILTER KIT | NOS | 1 | 4531.2 | 4531.2 | 1 | 4531.2 | 4531.2 | 0 | 4531.2 | 0 | 1 | 4530.99 | 4530.99 | 1 | 4530.99 | 4530.99 | 1 | 0 | 4531.2 | 0.21
4297 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Fuel Filter MICRO | NOS | 1 | 253.99 | 253.99 | 1 | 253.99 | 253.99 | 0 | 253.99 | 0 | 1 | 253.99 | 253.99 | 1 | 253.99 | 253.99 | 1 | 0 | 253.99 | 0
4298 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Fuel Filter PRE | NOS | 1 | 234.99 | 234.99 | 1 | 234.99 | 234.99 | 0 | 234.99 | 0 | 1 | 234.99 | 234.99 | 1 | 234.99 | 234.99 | 1 | 0 | 234.99 | 0
4299 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)HALF RING DN150 10004174 | PCS | 4 | 1908.06 | 7632.24 | 0 | 0 | 0 | 0 | 1908.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 7632.24 | 7632.24
4300 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)K-Oil 13 LTRS CAN | NOS | 1 | 743.4 | 743.4 | 1 | 743.4 | 743.4 | 0 | 743.4 | 0 | 1 | 746 | 746 | 1 | 746 | 746 | 1 | 0 | 743.4 | -2.6
4301 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)K-OIL 20 LITRES CAN | NOS | 1 | 6670 | 6670 | 1 | 6670 | 6670 | 0 | 6670 | 0 | 1 | 6670 | 6670 | 1 | 6670 | 6670 | 1 | 0 | 6670 | 0
4302 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)KEY SELECTOR ACTUATOR 2 POSITION TEKNIC MAKE | NOS | 1 | 920.4 | 920.4 | 0 | 0 | 0 | 0 | 920.4 | 0 | 0 | 0 | 0 | 1 | 767.47 | 767.47 | 1 | 0 | 920.4 | 152.93
4303 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Limit Switch 50 DIA ROLLER WITH ELASTOMER | NOS | 1 | 3823.2 | 3823.2 | 0 | 0 | 0 | 0 | 3823.2 | 0 | 0 | 0 | 0 | 1 | 3187.94 | 3187.94 | 1 | 0 | 3823.2 | 635.26
4304 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)MAST TO MAST CONNECTING PLAIN WASHER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 44.53 | 7124.32 | 1 | -159 | 0 | -7124.32
4305 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)MAST TO MAST CONNECTING BOLT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 526.38 | 61586.66 | 1 | -116 | 0 | -61586.66
4306 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)MAST TO MAST CONNECTING NUT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 87.12 | 6969.44 | 1 | -79 | 0 | -6969.44
4307 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)MAST TO MAST CONNECTING RING WASHER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 40.66 | 3252.4 | 1 | -79 | 0 | -3252.4
4308 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)MS FLAT WASHER 16 MM DIA | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3595 | 1.4 | 5050.25 | 1 | -3594 | 0 | -5050.25
4309 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)O-RING 160X3 NBR 70 10000478 | PCS | 4 | 56.64 | 226.56 | 0 | 0 | 0 | 0 | 56.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 226.56 | 226.56
4310 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)O-RING 220X3 NBR 70 10000630 | PCS | 4 | 28.27 | 113.08 | 0 | 0 | 0 | 0 | 28.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 113.08 | 113.08
4311 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)PENDANT - P03 | NOS | 1 | 8118.4 | 8118.4 | 0 | 0 | 0 | 0 | 8118.4 | 0 | 0 | 0 | 0 | 1 | 6764.53 | 6764.53 | 1 | 0 | 8118.4 | 1353.87
4312 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)PVC DELIVERY PIPE 1" | FT | 100 | 35.4 | 3540 | 100 | 35.4 | 3540 | 0 | 35.4 | 0 | 100 | 31.25 | 3125 | 0 | 0 | 0 | 100 | 100 | 3540 | 3540
4313 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)PVC FOOT VALVE 1" | PCS | 1 | 177 | 177 | 1 | 177 | 177 | 0 | 177 | 0 | 1 | 187.51 | 187.51 | 0 | 0 | 0 | 1 | 1 | 177 | 177
4314 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)PVC SUCTION PIPE 1.1/4" | FT | 15 | 35.4 | 531 | 15 | 35.4 | 531 | 0 | 35.4 | 0 | 15 | 31.25 | 468.75 | 0 | 0 | 0 | 15 | 15 | 531 | 531
4315 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)RACK WHEEL ROLLER ASSEMBLY | NOS | 1 | 15930 | 15930 | 0 | 0 | 0 | 0 | 15930 | 0 | 0 | 0 | 0 | 1 | 13283.07 | 13283.07 | 1 | 0 | 15930 | 2646.93
4316 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Repairing Charges for Charging Alternator | NOS | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 0 | 4130 | 0 | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 1 | 0 | 4130 | 0
4317 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Repairing Charges for Self Starter | NOS | 1 | 10266 | 10266 | 1 | 10266 | 10266 | 0 | 10266 | 0 | 1 | 10266 | 10266 | 1 | 10266 | 10266 | 1 | 0 | 10266 | 0
4318 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)RETURN VALVE SP(PART NO- 34.184.02 | NOS | 1 | 861.4 | 861.4 | 1 | 861.4 | 861.4 | 0 | 861.4 | 0 | 1 | 864.99 | 864.99 | 1 | 864.99 | 864.99 | 1 | 0 | 861.4 | -3.59
4319 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)ROLLING BRUSH | NOS | 30 | 141.6 | 4248 | 30 | 141.6 | 4248 | 0 | 141.6 | 0 | 30 | 146.13 | 4383.9 | 10 | 144.89 | 1448.89 | 30 | 20 | 4248 | 2799.11
4320 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SAFETY DEVICE ASSEMBLY | NOS | 1 | 283200 | 283200 | 0 | 0 | 0 | 0 | 283200 | 0 | 0 | 0 | 0 | 1 | 236143.49 | 236143.49 | 1 | 0 | 283200 | 47056.51
4321 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SAFETY RIBBON | ROLL | 1 | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 4 | 118 | 472 | 1 | -3 | 118 | -354
4322 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SAFETY SHOE | PAIR | 1 | 1030.4 | 1030.4 | 0 | 0 | 0 | 0 | 1030.4 | 0 | 0 | 0 | 0 | 27 | 1045.67 | 28232.96 | 1 | -26 | 1030.4 | -27202.56
4323 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SERVICE CHARGES | NOS | 1 | 1817.2 | 1817.2 | 1 | 1817.2 | 1817.2 | 0 | 1817.2 | 0 | 1 | 3540 | 3540 | 1 | 1264 | 1264 | 1 | 0 | 1817.2 | 553.2
4324 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SMPS | NOS | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 10289.6 | 10289.6 | 1 | 10217.18 | 10217.18 | 1 | 0 | 1 | -10216.18
4325 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SMPS - 120 V (S-100-24) | NOS | 1 | 9817.6 | 9817.6 | 0 | 0 | 0 | 0 | 9817.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9817.6 | 9817.6
4326 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SPACER PLATE | NOS | 1 | 23010 | 23010 | 0 | 0 | 0 | 0 | 23010 | 0 | 0 | 0 | 0 | 1 | 19186.66 | 19186.66 | 1 | 0 | 23010 | 3823.34
4327 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Spare Parts for MAP Hoist (Quot. K-60/25/24-25/0031) | LS | 1 | 439141.25 | 439141.25 | 1 | 439141.25 | 439141.25 | 0 | 439141.25 | 0 | 1 | 439141.24 | 439141.24 | 1 | 435920.88 | 435920.88 | 1 | 0 | 439141.25 | 3220.37
4328 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)Spare Parts of Hoist (Quot-KS/Q/24-25/15833) | NOS | 1 | 55696 | 55696 | 1 | 55696 | 55696 | 0 | 55696 | 0 | 1 | 56809.92 | 56809.92 | 0 | 0 | 0 | 1 | 1 | 55696 | 55696
4329 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SPARE PARTS(QUOT.-QS24101932) | LS | 1 | 11840.42 | 11840.42 | 1 | 11840.42 | 11840.42 | 0 | 11840.42 | 0 | 1 | 11840.42 | 11840.42 | 1 | 11840.42 | 11840.42 | 1 | 0 | 11840.42 | 0
4330 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SPINON FILTER | NOS | 2 | 601.8 | 1203.6 | 2 | 601.8 | 1203.6 | 0 | 601.8 | 0 | 2 | 598.99 | 1197.98 | 2 | 598.99 | 1197.98 | 2 | 0 | 1203.6 | 5.62
4331 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)SQUARE DRIVE SOCKET SET | SET | 1 | 1770 | 1770 | 1 | 1770 | 1770 | 0 | 1770 | 0 | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 1 | 0 | 1770 | -2950
4332 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)TOP & BOTTOM LIMIT SWITCH DOG ASSEMBLY | NOS | 1 | 3068 | 3068 | 0 | 0 | 0 | 0 | 3068 | 0 | 0 | 0 | 0 | 6 | 2558.22 | 15349.33 | 1 | -5 | 3068 | -12281.33
4333 | REPAIR AND MAINTENANCE - Assets Repairing Work | 0 | Started | Material | (M)WIRE BRUSH | NOS | 12 | 59 | 708 | 12 | 59 | 708 | 0 | 59 | 0 | 12 | 59 | 708 | 6 | 59 | 354 | 12 | 6 | 708 | 354
4334 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)AMC FOR SP1300D CONCRETE PUMP | LS | 1 | 64900 | 64900 | 0 | 0 | 0 | 0 | 64900 | 0 | 1 | 64900 | 64900 | 1 | 64900 | 64900 | 1 | 0 | 64900 | 0
4335 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)Repairing of Manual Drum in Mixture Machine | LS | 1 | 6650 | 6650 | 0 | 0 | 0 | 0 | 6650 | 0 | 1 | 6650 | 6650 | 1 | 6650 | 6650 | 1 | 0 | 6650 | 0
4336 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)S/C for hardfacing of Rock Valve for Conc. Pump | LS | 1 | 17700 | 17700 | 0 | 0 | 0 | 0 | 17700 | 0 | 1 | 17700 | 17700 | 1 | 17700 | 17700 | 1 | 0 | 17700 | 0
4337 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)S/C for Pumping Cyl. alignment of Concrete Pump | LS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 1 | 0 | 5900 | 0
4338 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)S/C for spare part replacement for Concrete Pump | LS | 1 | 11800 | 11800 | 0 | 0 | 0 | 0 | 11800 | 0 | 1 | 11800 | 11800 | 1 | 11800 | 11800 | 1 | 0 | 11800 | 0
4339 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)Service Charge towards replacement of failed & damaged parts | NOS | 1 | 24000 | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 1 | 28320 | 28320 | 0 | 0 | 0 | 1 | 1 | 24000 | 24000
4340 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Labour | (L)Service Charge towards rock valve shaft repairing | NOS | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | 11800 | 11800 | 0 | 0 | 0 | 1 | 1 | 10000 | 10000
4341 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)500 MM LONG PIPE | NOS | 1 | 2572.4 | 2572.4 | 0 | 0 | 0 | 0 | 2572.4 | 0 | 0 | 0 | 0 | 2 | 2504.71 | 5009.41 | 1 | -1 | 2572.4 | -2437.01
4342 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)ALLEN SCREW DIN 912 M30X140 8.8 A3C 10310091 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4343 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)BEARING BUSHING (D95/108X80) | NOS | 2 | 7080 | 14160 | 0 | 0 | 0 | 0 | 7080 | 0 | 0 | 0 | 0 | 1 | 7080 | 7080 | 2 | 1 | 14160 | 7080
4344 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)BEARING SHELL RS-100 80016249 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4345 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)BREATHER PLUG 1/4" 80009618 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4346 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)BUSHING 45X45 , 10003717 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4347 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)CUTTING RING TYPE-01 80006953 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4348 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)FEATHER KEY DIN 6885 A8X7X70 10007228 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4349 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)FEATHER KEY DIN 6885 B18X11X25 10012420 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4350 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)FLANGE DN150 | NOS | 1 | 1.18 | 1.18 | 1 | 1.18 | 1.18 | 0 | 1.18 | 0 | 1 | 6686.77 | 6686.77 | 1 | 6686.77 | 6686.77 | 1 | 0 | 1.18 | -6685.59
4351 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)FLANGE SHAFT (BEARING SIDE) 10004178 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4352 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)FLANGED SHAFT(GEAR SIDE) 80005548 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4353 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HALF RING DN150 10004174 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4354 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HAND GREASE PUMP 5 KG | NOS | 1 | 3097.5 | 3097.5 | 0 | 0 | 0 | 0 | 3097.5 | 0 | 0 | 0 | 0 | 1 | 3247.42 | 3247.42 | 1 | 0 | 3097.5 | -149.92
4355 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HEX HEAD SCREW (DIN 933 M10 X40-8.8-A2C) | NOS | 8 | 23.6 | 188.8 | 0 | 0 | 0 | 1 | 23.6 | 23.6 | 0 | 0 | 0 | 3 | 25.96 | 77.88 | 7 | 5 | 165.2 | 110.92
4356 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HEX SCREW DIN-933 M12X30-8, 8-A-C, 10001517 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4357 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HEX. HEAD BOLT DIN931 M30 X 150-8.8-A3C | NOS | 1 | 849.6 | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 0 | 0 | 0 | 2 | 849.6 | 1699.2 | 1 | -1 | 849.6 | -849.6
4358 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HP HOSE DIN 13/4X400LG 10049900 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4359 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)HYDRAULIC OIL 68 GRADE | LTR | 40 | 141.6 | 5664 | 40 | 141.6 | 5664 | 4 | 141.6 | 566.4 | 40 | 139.24 | 5569.6 | 40 | 139.24 | 5569.6 | 36 | 0 | 5097.6 | 94.4
4360 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)O - RING 195 X 3 NBR 70 | NOS | 1 | 59 | 59 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 2 | 56.64 | 113.28 | 1 | -1 | 59 | -54.28
4361 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)O - RING 214 X 5 NBR 80 | NOS | 1 | 70.8 | 70.8 | 0 | 0 | 0 | 0 | 70.8 | 0 | 0 | 0 | 0 | 2 | 67.26 | 134.52 | 1 | -1 | 70.8 | -63.72
4362 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)O- RING 70 X 8 NBR 70 | NOS | 1 | 59 | 59 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 1 | 62.54 | 62.54 | 1 | 0 | 59 | -3.54
4363 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)O- RING 95 X 8 NBR 70 | NOS | 2 | 47.2 | 94.4 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 1 | 46.02 | 46.02 | 2 | 1 | 94.4 | 48.38
4364 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)O-RING 160X3 NBR 70 10000478 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4365 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)O-RING 220X3 NBR 70 10000630 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4366 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)PIPE CLEANING BALL DN125 (SOFI) | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2667.75 | 5335.5 | 1 | -1 | 0 | -5335.5
4367 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)PIPE CLEANING GO - DEVIL CPL DN125 | PICS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3065.73 | 6131.46 | 1 | -1 | 0 | -6131.46
4368 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)PRESSURE SPRING RL | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2062.64 | 2062.64 | 0 | -1 | 0 | -2062.64
4369 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)PRESSURE SPRING RL 10308401 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4370 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)PUMPING CYLINDER PIPE DN150 10004126 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4371 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)RAM - DN150 (PART NO - 10006214) | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4372 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)RUBBER 20X 10 | NOS | 1 | 94.4 | 94.4 | 0 | 0 | 0 | 0 | 94.4 | 0 | 0 | 0 | 0 | 4 | 95.58 | 382.32 | 1 | -3 | 94.4 | -287.92
4373 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SCHNORR LOCK WASAHER S10 GT 500 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4374 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SCHNORR LOCK WASHER S 30 -GT 500 | NOS | 2 | 35.4 | 70.8 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 2 | 38.94 | 77.88 | 2 | 0 | 70.8 | -7.08
4375 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SCHWING HYDRO ULTRA 55 LITRS 80108010 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4376 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SCREW DIN 7984 M 10 X 16-8.8-A2C | NOS | 1 | 94.4 | 94.4 | 0 | 0 | 0 | 0 | 94.4 | 0 | 0 | 0 | 0 | 3 | 99.12 | 297.36 | 1 | -2 | 94.4 | -202.96
4377 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SCREW ISO 4014 M16 X 110-10.9-ZFSHI 10001279 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4378 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SCREW PLUG VS-R 1/4 WD 10006658 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4379 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SEAL RL KIDNEY | NOS | 1 | 2537 | 2537 | 0 | 0 | 0 | 0 | 2537 | 0 | 0 | 0 | 0 | 1 | 2531.1 | 2531.1 | 1 | 0 | 2537 | 5.9
4380 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SEAL RL KIDNEY 80012036 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4381 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SEALING CONE (10004928) | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4382 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SEALING COVER | NOS | 1 | 1392.4 | 1392.4 | 0 | 0 | 0 | 0 | 1392.4 | 0 | 0 | 0 | 0 | 1 | 1387.68 | 1387.68 | 1 | 0 | 1392.4 | 4.72
4383 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SHORT 90° BEND | NOS | 1 | 6372 | 6372 | 0 | 0 | 0 | 0 | 6372 | 0 | 0 | 0 | 0 | 3 | 6207.16 | 18621.47 | 1 | -2 | 6372 | -12249.47
4384 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SLEWING SHAFT RL | NOS | 1 | 65879.4 | 65879.4 | 0 | 0 | 0 | 0 | 65879.4 | 0 | 0 | 0 | 0 | 1 | 65878.22 | 65878.22 | 1 | 0 | 65879.4 | 1.18
4385 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SPARE PART(Quot.-QS24110005) | LS | 1 | 15459.88 | 15459.88 | 1 | 15459.88 | 15459.88 | 0 | 15459.88 | 0 | 1 | 15459.88 | 15459.88 | 1 | 15390.84 | 15390.84 | 1 | 0 | 15459.88 | 69.04
4386 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)Spare Parts for Co.'s Concrete Pump | LS | 1 | 519189.91 | 519189.91 | 1 | 519189.91 | 519189.91 | 0 | 519189.91 | 0 | 1 | 519189.91 | 519189.91 | 1 | 519189.91 | 519189.91 | 1 | 0 | 519189.91 | 0
4387 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SPARE PARTS FOR CONCRETE PUMP | LS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 104068.48 | 104068.48 | 2 | 1 | 0 | -104068.48
4388 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)SUPPORT BUSHING | NOS | 1 | 12213 | 12213 | 0 | 0 | 0 | 0 | 12213 | 0 | 0 | 0 | 0 | 1 | 12209.46 | 12209.46 | 1 | 0 | 12213 | 3.54
4389 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)TOP COVER RL 160 | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 560.5 | 560.5 | 1 | 0 | 1 | -559.5
4390 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)WASHER DIN 6916 17-C45--DT500 1000512 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4391 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)WEARING INSERT TYPE1 (80006952) | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4392 | REPAIR AND MAINTENANCE - Concrete Pump Repairing | 10 | Started | Material | (M)X- RING 94.62 X 5.33 | NOS | 1 | 160 | 160 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 1 | 184.08 | 184.08 | 1 | 0 | 160 | -24.08
4393 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Labour | (L)BATCHING PLANT& ACCESSORIES REPAIRING& NEW MATERIALS FIXING | NOS | 1 | 106200 | 106200 | 0 | 0 | 0 | 0 | 106200 | 0 | 1 | 106200 | 106200 | 1 | 106200 | 106200 | 1 | 0 | 106200 | 0
4394 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Labour | (L)Charges for Gas cutting & welding Mach. w/ freight ch. | LS | 1 | 3068 | 3068 | 0 | 0 | 0 | 0 | 3068 | 0 | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 1 | 0 | 3068 | 0
4395 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Labour | (L)Erection , commissioning &calibrationforbatching plant& silo | NOS | 1 | 236000 | 236000 | 0 | 0 | 0 | 0 | 236000 | 0 | 1 | 236000 | 236000 | 1 | 236000 | 236000 | 1 | 0 | 236000 | 0
4396 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Labour | (L)L/c for Gas Cutting Work & Oxygen Gas Charges | LS | 1 | 4554.8 | 4554.8 | 0 | 0 | 0 | 0 | 4554.8 | 0 | 1 | 3068 | 3068 | 1 | 3068 | 3068 | 1 | 0 | 4554.8 | 1486.8
4397 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Labour | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 33 | 885 | 29205 | 0 | 0 | 0 | 0 | 885 | 0 | 33 | 1180 | 38940 | 33 | 1180 | 38940 | 33 | 0 | 29205 | -9735
4398 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)1.5 SQMM X 7 CORE COPPER FLEXIBLE CABLE | MTR | 15 | 186.44 | 2796.6 | 15 | 186.44 | 2796.6 | 0 | 186.44 | 0 | 15 | 213.27 | 3199.05 | 15 | 209.17 | 3137.51 | 15 | 0 | 2796.6 | -340.91
4399 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)10 SQMM FLAT TYPE COPPER LUGS | NOS | 12 | 59 | 708 | 12 | 59 | 708 | 0 | 59 | 0 | 12 | 18.88 | 226.56 | 12 | 18.88 | 226.56 | 12 | 0 | 708 | 481.44
4400 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)10 Sqmm X 3 Core Flexible Copper Cable | MTR | 100 | 686.76 | 68676 | 100 | 686.76 | 68676 | 0 | 686.76 | 0 | 100 | 338.57 | 33857.24 | 100 | 338.23 | 33822.86 | 100 | 0 | 68676 | 34853.14
4401 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)10' Long Earthing Pipe | NOS | 10 | 1711 | 17110 | 10 | 1711 | 17110 | 0 | 1711 | 0 | 10 | 1736.78 | 17367.8 | 10 | 1732.73 | 17327.3 | 10 | 0 | 17110 | -217.3
4402 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)100 AMP Busbar (Copper) | NOS | 1 | 2737.6 | 2737.6 | 1 | 2737.6 | 2737.6 | 0 | 2737.6 | 0 | 1 | 2778.85 | 2778.85 | 1 | 2772.37 | 2772.37 | 1 | 0 | 2737.6 | -34.77
4403 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)150mm AL LUGS FLAT TYPE | NOS | 12 | 35.4 | 424.8 | 12 | 35.4 | 424.8 | 0 | 35.4 | 0 | 12 | 41.32 | 495.84 | 12 | 41.23 | 494.72 | 12 | 0 | 424.8 | -69.92
4404 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)150MM DOUBLE COMPRESSURE GLANDS | NOS | 4 | 849.6 | 3398.4 | 4 | 849.6 | 3398.4 | 0 | 849.6 | 0 | 4 | 864.8 | 3459.2 | 4 | 862.78 | 3451.12 | 4 | 0 | 3398.4 | -52.72
4405 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)16 SQMM FLAT TYPE COPPER LUGS | NOS | 12 | 59 | 708 | 12 | 59 | 708 | 0 | 59 | 0 | 12 | 22.42 | 269.04 | 12 | 22.42 | 269.04 | 12 | 0 | 708 | 438.96
4406 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)16 Sqmm X 3 Core Flexible Copper Cable | MTR | 100 | 1076.16 | 107616 | 100 | 1076.16 | 107616 | 0 | 1076.16 | 0 | 100 | 530.6 | 53059.56 | 100 | 530.06 | 53005.52 | 100 | 0 | 107616 | 54610.48
4407 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)16mm AL LUGS FLAT TYPE | NOS | 6 | 1.18 | 7.08 | 6 | 1.18 | 7.08 | 0 | 1.18 | 0 | 6 | 12.46 | 74.78 | 6 | 12.45 | 74.71 | 6 | 0 | 7.08 | -67.63
4408 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)200 AMP Busbar (copper) | NOS | 1 | 3339.4 | 3339.4 | 1 | 3339.4 | 3339.4 | 0 | 3339.4 | 0 | 1 | 3389.72 | 3389.72 | 1 | 3381.81 | 3381.81 | 1 | 0 | 3339.4 | -42.41
4409 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)25mm AL LUGS FLAT TYPE | NOS | 4 | 11.8 | 47.2 | 4 | 11.8 | 47.2 | 0 | 11.8 | 0 | 4 | 10.18 | 40.72 | 4 | 10.16 | 40.63 | 4 | 0 | 47.2 | 6.57
4410 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)25mm X 3mm GI Earthing Strip | MTR | 123.213 | 47.2 | 5815.65 | 123.213 | 47.2 | 5815.65 | 0 | 47.2 | 0 | 123.213 | 52.93 | 6521.0947 | 123.213 | 52.8 | 6505.78 | 123.213 | 0 | 5815.654 | -690.1264
4411 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)35mm AL LUGS FLAT TYPE | NOS | 18 | 11.8 | 212.4 | 18 | 11.8 | 212.4 | 0 | 11.8 | 0 | 18 | 11.91 | 214.44 | 18 | 11.9 | 214.11 | 18 | 0 | 212.4 | -1.71
4412 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)35MM DOUBLE COMPRESSURE GLANDS | NOS | 4 | 401.2 | 1604.8 | 4 | 401.2 | 1604.8 | 0 | 401.2 | 0 | 4 | 402.45 | 1609.8 | 4 | 401.52 | 1606.06 | 4 | 0 | 1604.8 | -1.26
4413 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)400 AMP Busbar (Copper) | NOS | 1 | 8212.8 | 8212.8 | 1 | 8212.8 | 8212.8 | 0 | 8212.8 | 0 | 1 | 8336.55 | 8336.55 | 1 | 8317.1 | 8317.1 | 1 | 0 | 8212.8 | -104.3
4414 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)50 SQMM FLAT TYPE ALUMINIUM LUGS | NOS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 2 | 15.34 | 30.68 | 2 | 15.34 | 30.68 | 2 | 0 | 118 | 87.32
4415 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)6 Hole Earthing Busbar | NOS | 2 | 1.18 | 2.36 | 2 | 1.18 | 2.36 | 0 | 1.18 | 0 | 2 | 131.76 | 263.52 | 2 | 131.45 | 262.9 | 2 | 0 | 2.36 | -260.54
4416 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)70mm AL LUGS FLAT TYPE | NOS | 4 | 23.6 | 94.4 | 4 | 23.6 | 94.4 | 0 | 23.6 | 0 | 4 | 23.36 | 93.44 | 4 | 23.3 | 93.21 | 4 | 0 | 94.4 | 1.19
4417 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)8 NO. G.I. WIRE | KG | 5 | 118 | 590 | 5 | 118 | 590 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 590 | 590
4418 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)95mm AL LUGS FLAT TYPE | NOS | 18 | 23.6 | 424.8 | 18 | 23.6 | 424.8 | 0 | 23.6 | 0 | 18 | 20.46 | 368.24 | 18 | 20.42 | 367.52 | 18 | 0 | 424.8 | 57.28
4419 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)95MM DOUBLE COMPRESSURE GLANDS | NOS | 4 | 1.18 | 4.72 | 4 | 1.18 | 4.72 | 0 | 1.18 | 0 | 4 | 630.03 | 2520.12 | 4 | 628.56 | 2514.25 | 4 | 0 | 4.72 | -2509.53
4420 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)AMPERE TAPE | NOS | 2 | 70.8 | 141.6 | 2 | 70.8 | 141.6 | 0 | 70.8 | 0 | 2 | 65.88 | 131.76 | 2 | 65.73 | 131.45 | 2 | 0 | 141.6 | 10.15
4421 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Batching Gate - DV 400F 80200330 | PCS | 1 | 31576.8 | 31576.8 | 1 | 31576.8 | 31576.8 | 0 | 31576.8 | 0 | 1 | 32524.09 | 32524.09 | 1 | 32378.85 | 32378.85 | 1 | 0 | 31576.8 | -802.05
4422 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Batching gate DV300 G assly 80200750 | PCS | 3 | 26942.94 | 80828.82 | 3 | 26942.94 | 80828.82 | 0 | 26942.94 | 0 | 3 | 27751.23 | 83253.69 | 3 | 27627.29 | 82881.87 | 3 | 0 | 80828.82 | -2053.05
4423 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Bellow for linear actuator /CP18 80201897 | PCS | 1 | 3835 | 3835 | 1 | 3835 | 3835 | 0 | 3835 | 0 | 1 | 3950.05 | 3950.05 | 1 | 3932.41 | 3932.41 | 1 | 0 | 3835 | -97.41
4424 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)BUSH FOR LINEAR ACTUATOR(PB) 80201460 | PCS | 1 | 1982.4 | 1982.4 | 1 | 1982.4 | 1982.4 | 0 | 1982.4 | 0 | 1 | 2041.87 | 2041.87 | 1 | 2032.75 | 2032.75 | 1 | 0 | 1982.4 | -50.35
4425 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)CLAMP STRAP HALF ID-488 Rev.2 80200747 | PCS | 1 | 558.14 | 558.14 | 1 | 558.14 | 558.14 | 0 | 558.14 | 0 | 1 | 574.87 | 574.87 | 1 | 572.32 | 572.32 | 1 | 0 | 558.14 | -14.18
4426 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Compressor Oil | NOS | 1 | 413 | 413 | 1 | 413 | 413 | 0 | 413 | 0 | 1 | 210.04 | 210.04 | 1 | 210.04 | 210.04 | 1 | 0 | 413 | 202.96
4427 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Counter sunk screw M 12x 65 10.9-GT500 60101636 | PCS | 5 | 289.1 | 1445.5 | 5 | 289.1 | 1445.5 | 0 | 289.1 | 0 | 5 | 297.77 | 1488.85 | 5 | 296.44 | 1482.22 | 5 | 0 | 1445.5 | -36.72
4428 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)COUNTER SUNK SCREW M12 X 45 DIN7991 80150828 | PCS | 62 | 69.62 | 4316.44 | 62 | 69.62 | 4316.44 | 0 | 69.62 | 0 | 62 | 71.71 | 4446.02 | 62 | 71.39 | 4426.08 | 62 | 0 | 4316.44 | -109.64
4429 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Disc 17 DIN 125 verz.St 60083310 | PCS | 8 | 7.08 | 56.64 | 8 | 7.08 | 56.64 | 0 | 7.08 | 0 | 8 | 7.29 | 58.32 | 8 | 7.26 | 58.08 | 8 | 0 | 56.64 | -1.44
4430 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Disc A13 DIN 125 60083319 | PCS | 67 | 7.08 | 474.36 | 67 | 7.08 | 474.36 | 0 | 7.08 | 0 | 67 | 7.29 | 488.43 | 67 | 7.26 | 486.41 | 67 | 0 | 474.36 | -12.05
4431 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)DOME NUT M16 DIN 1587 M 16-6-A2C 10001274 | PCS | 8 | 41.3 | 330.4 | 8 | 41.3 | 330.4 | 0 | 41.3 | 0 | 8 | 42.54 | 340.32 | 8 | 42.35 | 338.79 | 8 | 0 | 330.4 | -8.39
4432 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)DOUBLE HORN SHOWEL (SQ) 80200844 | PCS | 6 | 2455.58 | 14733.48 | 6 | 2455.58 | 14733.48 | 0 | 2455.58 | 0 | 6 | 2529.25 | 15175.5 | 6 | 2517.95 | 15107.71 | 6 | 0 | 14733.48 | -374.23
4433 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Field Cables only - CP18 80401026 | PCS | 1 | 91580.98 | 91580.98 | 1 | 91580.98 | 91580.98 | 0 | 91580.98 | 0 | 1 | 94328.39 | 94328.39 | 1 | 93907.14 | 93907.14 | 1 | 0 | 91580.98 | -2326.16
4434 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)GASKET SSI/SK/24 60014160 | PCS | 4 | 88.5 | 354 | 4 | 88.5 | 354 | 0 | 88.5 | 0 | 4 | 91.15 | 364.6 | 4 | 90.75 | 362.99 | 4 | 0 | 354 | -8.99
4435 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Gear Oil SP-220 | NOS | 20 | 259.6 | 5192 | 20 | 259.6 | 5192 | 0 | 259.6 | 0 | 20 | 248.98 | 4979.6 | 20 | 248.98 | 4979.6 | 20 | 0 | 5192 | 212.4
4436 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Gear Oil VG-220 | NOS | 5 | 236 | 1180 | 5 | 236 | 1180 | 0 | 236 | 0 | 5 | 261.96 | 1309.8 | 5 | 261.96 | 1309.8 | 5 | 0 | 1180 | -129.8
4437 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Gear Oil VG-320 | NOS | 5 | 236 | 1180 | 5 | 236 | 1180 | 0 | 236 | 0 | 5 | 257.24 | 1286.2 | 5 | 257.24 | 1286.2 | 5 | 0 | 1180 | -106.2
4438 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)GI Nut Bolt Washer 25mm X 6mm | NOS | 100 | 4.01 | 401 | 100 | 4.01 | 401 | 0 | 4.01 | 0 | 100 | 4.72 | 472 | 100 | 4.72 | 472 | 100 | 0 | 401 | -71
4439 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)GI Nut Bolt Washer 25mm X 8mm | NOS | 100 | 11.8 | 1180 | 100 | 11.8 | 1180 | 0 | 11.8 | 0 | 100 | 7.08 | 708 | 100 | 7.08 | 708 | 100 | 0 | 1180 | 472
4440 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hex.nut DIN 934 M 10-8-A2C 10001250 | PCS | 12 | 17.7 | 212.4 | 12 | 17.7 | 212.4 | 0 | 17.7 | 0 | 12 | 18.23 | 218.76 | 12 | 18.15 | 217.79 | 12 | 0 | 212.4 | -5.39
4441 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hex.nut DIN 934 M 12-8-A2C 10001254 | PCS | 67 | 8.11 | 543.37 | 67 | 8.11 | 543.37 | 0 | 8.11 | 0 | 67 | 8.35 | 559.2289 | 67 | 8.31 | 556.95 | 67 | 0 | 543.37 | -13.58
4442 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hex.nut DIN 934 M 16-8-A2C 10001260 | PCS | 14 | 27.14 | 379.96 | 14 | 27.14 | 379.96 | 0 | 27.14 | 0 | 14 | 27.95 | 391.3 | 14 | 27.83 | 389.61 | 14 | 0 | 379.96 | -9.65
4443 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)HEXAGONAL BUSH - 431298091 80200214 | PCS | 6 | 127.44 | 764.64 | 6 | 127.44 | 764.64 | 0 | 127.44 | 0 | 6 | 131.26 | 787.56 | 6 | 130.68 | 784.06 | 6 | 0 | 764.64 | -19.42
4444 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)HOSE CLIP DIA=260 80201023 | PCS | 2 | 475.54 | 951.08 | 2 | 475.54 | 951.08 | 0 | 475.54 | 0 | 2 | 489.8 | 979.6 | 2 | 487.62 | 975.24 | 2 | 0 | 951.08 | -24.16
4445 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hose clip f.D 213-226 60078004 | PCS | 2 | 764.64 | 1529.28 | 2 | 764.64 | 1529.28 | 0 | 764.64 | 0 | 2 | 787.57 | 1575.14 | 2 | 784.06 | 1568.12 | 2 | 0 | 1529.28 | -38.84
4446 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)HOSE CLIP ID270 60096362 | PCS | 2 | 608.88 | 1217.76 | 2 | 608.88 | 1217.76 | 0 | 608.88 | 0 | 2 | 627.14 | 1254.28 | 2 | 624.35 | 1248.69 | 2 | 0 | 1217.76 | -30.93
4447 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)HOSE CONIC 60053697 | PCS | 2 | 3894 | 7788 | 2 | 3894 | 7788 | 0 | 3894 | 0 | 2 | 4010.81 | 8021.62 | 2 | 3992.91 | 7985.82 | 2 | 0 | 7788 | -197.82
4448 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hose Piece ID=216x2-500lg. 80210019 | PCS | 2 | 2832 | 5664 | 2 | 2832 | 5664 | 0 | 2832 | 0 | 2 | 2916.96 | 5833.92 | 2 | 2903.94 | 5807.87 | 2 | 0 | 5664 | -143.87
4449 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hose piece ID=250x2x-350lg. 80210023 | PCS | 2 | 1629.58 | 3259.16 | 2 | 1629.58 | 3259.16 | 0 | 1629.58 | 0 | 2 | 1678.46 | 3356.92 | 2 | 1670.97 | 3341.94 | 2 | 0 | 3259.16 | -82.78
4450 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Hose piece ID=270x2x-200lg. 80210022 | PCS | 2 | 1274.4 | 2548.8 | 2 | 1274.4 | 2548.8 | 0 | 1274.4 | 0 | 2 | 1312.63 | 2625.26 | 2 | 1306.77 | 2613.54 | 2 | 0 | 2548.8 | -64.74
4451 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)HOSE PIECE ID=480/350 X 6 X 400 LG Rev.2 80200748 | PCS | 1 | 8496 | 8496 | 1 | 8496 | 8496 | 0 | 8496 | 0 | 1 | 8750.87 | 8750.87 | 1 | 8711.8 | 8711.8 | 1 | 0 | 8496 | -215.8
4452 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)INTERMEDIATE HANGER BEARING 219 DIA (80201242) | NOS | 2 | 11125.93 | 22251.86 | 2 | 11125.93 | 22251.86 | 0 | 11125.93 | 0 | 2 | 11459.72 | 22919.44 | 2 | 11408.53 | 22817.06 | 2 | 0 | 22251.86 | -565.2
4453 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)INTERNAL WEAR SHEET 80203440 | PCS | 2 | 10759.24 | 21518.48 | 2 | 10759.24 | 21518.48 | 0 | 10759.24 | 0 | 2 | 11082.01 | 22164.02 | 2 | 11032.53 | 22065.05 | 2 | 0 | 21518.48 | -546.57
4454 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Load Cell ( 1.5 Ton capacity) | NOS | 1 | 11210 | 11210 | 1 | 11210 | 11210 | 0 | 11210 | 0 | 1 | 9500 | 9500 | 1 | 9500 | 9500 | 1 | 0 | 11210 | 1710
4455 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Load Cell 350kg, 2mV/V, M12x1.25 80200723 | PCS | 2 | 26376.54 | 52753.08 | 2 | 26376.54 | 52753.08 | 0 | 26376.54 | 0 | 2 | 27167.83 | 54335.66 | 2 | 27046.51 | 54093.01 | 2 | 0 | 52753.08 | -1339.93
4456 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)LOAD CELL 45 KG 80200771 | PCS | 1 | 35811.82 | 35811.82 | 1 | 35811.82 | 35811.82 | 0 | 35811.82 | 0 | 1 | 36886.17 | 36886.17 | 1 | 36721.44 | 36721.44 | 1 | 0 | 35811.82 | -909.62
4457 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Lock washer S 12-zinc c., 60083300 | PCS | 75 | 22.42 | 1681.5 | 75 | 22.42 | 1681.5 | 0 | 22.42 | 0 | 75 | 23.09 | 1731.75 | 75 | 22.99 | 1724.21 | 75 | 0 | 1681.5 | -42.71
4458 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)MIXING ARM VI FOR 18M3 80200685 | PCS | 1 | 5560.16 | 5560.16 | 1 | 5560.16 | 5560.16 | 0 | 5560.16 | 0 | 1 | 5726.95 | 5726.95 | 1 | 5701.39 | 5701.39 | 1 | 0 | 5560.16 | -141.23
4459 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Nut (matl.Phospher bronze ) 80201911 | PCS | 1 | 2843.8 | 2843.8 | 1 | 2843.8 | 2843.8 | 0 | 2843.8 | 0 | 1 | 2929.11 | 2929.11 | 1 | 2916.03 | 2916.03 | 1 | 0 | 2843.8 | -72.23
4460 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PLATE FOR STRIPER ARM 60014161 | PCS | 2 | 188.8 | 377.6 | 2 | 188.8 | 377.6 | 0 | 188.8 | 0 | 2 | 194.46 | 388.92 | 2 | 193.6 | 387.19 | 2 | 0 | 377.6 | -9.59
4461 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Proxi sensor-12mm & M12 Conn-5 mtr cable 80401221 | PCS | 1 | 2474.46 | 2474.46 | 1 | 2474.46 | 2474.46 | 0 | 2474.46 | 0 | 1 | 2548.68 | 2548.68 | 1 | 2537.31 | 2537.31 | 1 | 0 | 2474.46 | -62.85
4462 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Proxi sensor-18mm 80401306 | PCS | 2 | 2120.46 | 4240.92 | 2 | 2120.46 | 4240.92 | 0 | 2120.46 | 0 | 2 | 2184.07 | 4368.14 | 2 | 2174.32 | 4348.64 | 2 | 0 | 4240.92 | -107.72
4463 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PU Tube 12 Dia 80201286 | PCS | 20 | 169.92 | 3398.4 | 20 | 169.92 | 3398.4 | 0 | 169.92 | 0 | 20 | 175.02 | 3500.4 | 20 | 174.24 | 3484.72 | 20 | 0 | 3398.4 | -86.32
4464 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PU tube dia 10 (WH00B10) 80201318 | MTR | 100 | 151.04 | 15104 | 100 | 151.04 | 15104 | 0 | 151.04 | 0 | 100 | 155.57 | 15557 | 100 | 154.88 | 15487.64 | 100 | 0 | 15104 | -383.64
4465 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PVC TAPE BLUE | NOS | 2 | 35 | 70 | 2 | 35 | 70 | 0 | 35 | 0 | 2 | 45.52 | 91.04 | 2 | 48.87 | 97.74 | 2 | 0 | 70 | -27.74
4466 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PVC TAPE GREEN | NOS | 2 | 41.3 | 82.6 | 2 | 41.3 | 82.6 | 0 | 41.3 | 0 | 2 | 45.52 | 91.04 | 2 | 46.61 | 93.21 | 2 | 0 | 82.6 | -10.61
4467 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PVC TAPE RED | NOS | 2 | 41.3 | 82.6 | 2 | 41.3 | 82.6 | 0 | 41.3 | 0 | 2 | 45.52 | 91.04 | 2 | 48.87 | 97.74 | 2 | 0 | 82.6 | -15.14
4468 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)PVC TAPE YELLOW | NOS | 2 | 41.3 | 82.6 | 2 | 41.3 | 82.6 | 0 | 41.3 | 0 | 2 | 45.52 | 91.04 | 2 | 44.22 | 88.43 | 2 | 0 | 82.6 | -5.83
4469 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Rope 12mm x 22m X43 (P825) zS 80211808 | PCS | 1 | 28692.88 | 28692.88 | 1 | 28692.88 | 28692.88 | 0 | 28692.88 | 0 | 1 | 29553.66 | 29553.66 | 1 | 29421.68 | 29421.68 | 1 | 0 | 28692.88 | -728.8
4470 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)ROTOR SEALING 60043663 | PCS | 1 | 23420.64 | 23420.64 | 1 | 23420.64 | 23420.64 | 0 | 23420.64 | 0 | 1 | 24123.25 | 24123.25 | 1 | 24015.52 | 24015.52 | 1 | 0 | 23420.64 | -594.88
4471 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)RUBBER WASHER ID-13, OD-25 80150065 | PCS | 67 | 14.16 | 948.72 | 67 | 14.16 | 948.72 | 0 | 14.16 | 0 | 67 | 14.58 | 976.86 | 67 | 14.52 | 972.82 | 67 | 0 | 948.72 | -24.1
4472 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)S Beam Load Cell 700 kg, 2.0mV/V 80208148 | PCS | 1 | 26376.54 | 26376.54 | 1 | 26376.54 | 26376.54 | 0 | 26376.54 | 0 | 1 | 27167.83 | 27167.83 | 1 | 27046.5 | 27046.5 | 1 | 0 | 26376.54 | -669.96
4473 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)SCADA Software for MCI55 | NOS | 1 | 112336 | 112336 | 1 | 112336 | 112336 | 0 | 112336 | 0 | 1 | 112336 | 112336 | 1 | 112336 | 112336 | 1 | 0 | 112336 | 0
4474 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Schnorr lock washer S 16-zinc c. 60083304 | PCS | 20 | 37.76 | 755.2 | 20 | 37.76 | 755.2 | 0 | 37.76 | 0 | 20 | 38.89 | 777.8 | 20 | 38.72 | 774.38 | 20 | 0 | 755.2 | -19.18
4475 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Screw DIN 933 M 12 x 40-8.8-zinc c. 10001526 | PCS | 12 | 35.4 | 424.8 | 12 | 35.4 | 424.8 | 0 | 35.4 | 0 | 12 | 36.46 | 437.52 | 12 | 36.3 | 435.59 | 12 | 0 | 424.8 | -10.79
4476 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Seal kit-?250mm Buterfly Valve-2099480VA 80200234 | PCS | 2 | 4415.56 | 8831.12 | 2 | 4415.56 | 8831.12 | 0 | 4415.56 | 0 | 2 | 4548.02 | 9096.04 | 2 | 4527.72 | 9055.43 | 2 | 0 | 8831.12 | -224.31
4477 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)SEALING LEDGE 80200692 | PCS | 1 | 914.5 | 914.5 | 1 | 914.5 | 914.5 | 0 | 914.5 | 0 | 1 | 941.93 | 941.93 | 1 | 937.73 | 937.73 | 1 | 0 | 914.5 | -23.23
4478 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)SEALING LEDGE 80200693 | PCS | 1 | 810.66 | 810.66 | 1 | 810.66 | 810.66 | 0 | 810.66 | 0 | 1 | 834.98 | 834.98 | 1 | 831.25 | 831.25 | 1 | 0 | 810.66 | -20.59
4479 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)SEALING LEDGE 80200694 | PCS | 1 | 851.96 | 851.96 | 1 | 851.96 | 851.96 | 0 | 851.96 | 0 | 1 | 877.51 | 877.51 | 1 | 873.6 | 873.6 | 1 | 0 | 851.96 | -21.64
4480 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Servo System 32 | NOS | 1 | 188.8 | 188.8 | 1 | 188.8 | 188.8 | 0 | 188.8 | 0 | 1 | 194.7 | 194.7 | 1 | 194.7 | 194.7 | 1 | 0 | 188.8 | -5.9
4481 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Spare Parts for Batching Plant (Att. Annex.) | LS | 1 | 185085.98 | 185085.98 | 1 | 185085.98 | 185085.98 | 0 | 185085.98 | 0 | 1 | 59188.8 | 59188.8 | 1 | 59188.8 | 59188.8 | 1 | 0 | 185085.98 | 125897.18
4482 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)SPARE PARTS FOR BATCHING PLANT (Quot- QS24057583) | LS | 1 | 33535.6 | 33535.6 | 1 | 33535.6 | 33535.6 | 0 | 33535.6 | 0 | 1 | 34536.8 | 34536.8 | 1 | 34382.56 | 34382.56 | 1 | 0 | 33535.6 | -846.96
4483 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Spare Parts for Batching Plant (Quot.-QS24046988) | LS | 1 | 79428.82 | 79428.82 | 0 | 0 | 0 | 0 | 79428.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 79428.82 | 79428.82
4484 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)SPARE PARTS FOR BATCHING PLANT(Quot-QS24051947) | LS | 1 | 93060.74 | 93060.74 | 1 | 93060.74 | 93060.74 | 0 | 93060.74 | 0 | 1 | 93060.74 | 93060.74 | 1 | 92645.14 | 92645.14 | 1 | 0 | 93060.74 | 415.6
4485 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Square CSK Screw M16x30 80150775 | PCS | 12 | 116.82 | 1401.84 | 12 | 116.82 | 1401.84 | 0 | 116.82 | 0 | 12 | 120.32 | 1443.84 | 12 | 119.79 | 1437.45 | 12 | 0 | 1401.84 | -35.61
4486 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Square Socket CSK Screw M16x55 80150774 | PCS | 8 | 120.36 | 962.88 | 8 | 120.36 | 962.88 | 0 | 120.36 | 0 | 8 | 123.97 | 991.76 | 8 | 123.42 | 987.34 | 8 | 0 | 962.88 | -24.46
4487 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)STRIPPER 80200845 | PCS | 4 | 2426.08 | 9704.32 | 4 | 2426.08 | 9704.32 | 0 | 2426.08 | 0 | 4 | 2498.86 | 9995.44 | 4 | 2487.7 | 9950.81 | 4 | 0 | 9704.32 | -246.49
4488 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)STRIPPING SUPPORT 60014151 | PCS | 1 | 3850.34 | 3850.34 | 1 | 3850.34 | 3850.34 | 0 | 3850.34 | 0 | 1 | 3965.83 | 3965.83 | 1 | 3948.14 | 3948.14 | 1 | 0 | 3850.34 | -97.8
4489 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Tension spring 11,93kp d= 1,6 StN 48 80300005 | PCS | 1 | 88.5 | 88.5 | 1 | 88.5 | 88.5 | 0 | 88.5 | 0 | 1 | 91.14 | 91.14 | 1 | 90.75 | 90.75 | 1 | 0 | 88.5 | -2.25
4490 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)Tile jacket T 350 (Composite metal) 80211760 | PCS | 1 | 94483.78 | 94483.78 | 1 | 94483.78 | 94483.78 | 0 | 94483.78 | 0 | 1 | 97318.29 | 97318.29 | 1 | 96883.67 | 96883.67 | 1 | 0 | 94483.78 | -2399.89
4491 | REPAIR AND MAINTENANCE - B. Plant and Sylo Erection | 0 | Started | Material | (M)WEARING PACKING 60073424 | PCS | 6 | 1085.6 | 6513.6 | 6 | 1085.6 | 6513.6 | 0 | 1085.6 | 0 | 6 | 1118.17 | 6709.02 | 6 | 1113.18 | 6679.05 | 6 | 0 | 6513.6 | -165.45
4492 | REPAIR AND MAINTENANCE - Cube Testing and Mixer Machine | 10 | Started | Labour | (L)CALIBRATION & MAINTANACE CUBE TESTING MACHINE | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 8500 | 8500 | 1 | 8500 | 8500 | 1 | 0 | 1 | -8499
4493 | REPAIR AND MAINTENANCE - Cube Testing and Mixer Machine | 10 | Started | Labour | (L)CALIBRATION & MAINTANACE OF DIGTAL CUBE TESTING MACHINE | NOS | 1 | 8500 | 8500 | 0 | 0 | 0 | 0 | 8500 | 0 | 1 | 8500 | 8500 | 1 | 8500 | 8500 | 1 | 0 | 8500 | 0
4494 | REPAIR AND MAINTENANCE - Cube Testing and Mixer Machine | 10 | Started | Labour | (L)QC LAB CONCRETE MIXER MACHINE SERVICE & MIXER MOTOR REPAIR | NOS | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 1 | 0 | 5900 | 900
4495 | REPAIR AND MAINTENANCE - Cube Testing and Mixer Machine | 10 | Started | Material | (M)BAR BENDING MACHINE | NOS | 1 | 194700 | 194700 | 0 | 0 | 0 | 0 | 194700 | 0 | 0 | 0 | 0 | 1 | 194700 | 194700 | 1 | 0 | 194700 | 0
4496 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Labour | (L)MIVAN SHUTTERING WORK | SQM | 4000 | 75 | 300000 | 0 | 0 | 0 | 0 | 75 | 0 | 4000 | 75 | 300003.2 | 3563 | 75 | 267227.86 | 4000 | 437 | 300000 | 32772.14
4497 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Labour | (L)Supply of Fitter-Mivan & Staging Mat. sorting | MAN/DAY | 720 | 708 | 509760 | 0 | 0 | 0 | 0 | 708 | 0 | 720 | 600 | 432000 | 328.12 | 600 | 196872 | 720 | 391.88 | 509760 | 312888
4498 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Labour | (L)Supply of Helper-Mivan & Staging Mat. sorting | MAN/DAY | 2500 | 590 | 1475000 | 0 | 0 | 0 | 0 | 590 | 0 | 2500 | 500 | 1250000 | 2063.911 | 500 | 1031955.5 | 2500 | 436.089 | 1475000 | 443044.5
4499 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)3"Twisted Wire Cup Brush (ALI-18-3) | NOS | 60 | 236 | 14160 | 60 | 236 | 14160 | 0 | 236 | 0 | 60 | 236 | 14160 | 60 | 236 | 14160 | 60 | 0 | 14160 | 0
4500 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)ALUMINIUM SHUTTERING OIL_(REEBOL MASTER FINISH202 IN). | LTR | 400 | 177 | 70800 | 400 | 177 | 70800 | 0 | 177 | 0 | 400 | 174.64 | 69856 | 400 | 174.64 | 69856 | 400 | 0 | 70800 | 944
4501 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)ANGEL GRINDER MACHINE | NOS | 4 | 4307 | 17228 | 0 | 0 | 0 | 0 | 4307 | 0 | 0 | 0 | 0 | 4 | 4406.92 | 17627.69 | 4 | 0 | 17228 | -399.69
4502 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)GLOVES | PAIR | 71 | 42 | 2982 | 30 | 42 | 1260 | 0 | 42 | 0 | 30 | 33.6 | 1008 | 83 | 38.28 | 3177.3 | 71 | -12 | 2982 | -195.3
4503 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)GRINDING WIRE BRUSH | NOS | 100 | 554.6 | 55460 | 0 | 0 | 0 | 0 | 554.6 | 0 | 0 | 0 | 0 | 99 | 202.92 | 20088.84 | 100 | 1 | 55460 | 35371.16
4504 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)MASK | NOS | 100 | 21 | 2100 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 74 | 19.95 | 1476.3 | 100 | 26 | 2100 | 623.7
4505 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)SAFETY SUNGLASS | NOS | 20 | 47.2 | 944 | 0 | 0 | 0 | 0 | 47.2 | 0 | 0 | 0 | 0 | 20 | 55.48 | 1109.62 | 20 | 0 | 944 | -165.62
4506 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)SHUTTERING GREASE | KG | 10 | 78 | 780 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 6 | 155.76 | 934.56 | 10 | 4 | 780 | -154.56
4507 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)SPLENDOR GLOVES | PAIR | 60 | 59 | 3540 | 60 | 59 | 3540 | 0 | 59 | 0 | 60 | 53.34 | 3200.4 | 68 | 52.56 | 3574.2 | 60 | -8 | 3540 | -34.2
4508 | REPAIR AND MAINTENANCE - Mivan Shuttering Cleaning | 0 | Started | Material | (M)WIRE BRUSH | NOS | 12 | 59 | 708 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 13 | 59 | 767 | 12 | -1 | 708 | -59